## Rules of Credit
Working Line No. | Prime Account Name | Item Description | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Milestone 8 | Milestone 9 | Unit of Measure Imperial | Unit of Measure Metric | Partial Progress Permitted? | Check! | Note | Comments | Cost Code of Account | Craft | S/C | Calgary SAP Labor Activity Type Craft | Calgary SAP Labor Activity Type Subcontract | CCOA Notes
| Earthwork and Civil | [15 empty] | * General comment - all final activities were changed to be a minimum of 10% as per Steve Laskowski's comment.
| Earthwork and Civil | Clear & Grub | Clear / Excavate | Remove For Disposal | Accept
00.01.01 | Earthwork and Civil | Clear & Grub | 50% | 40% | 10% | [6 empty] | ac | ha | Yes | 100% |  |  | 0005100 | Y | Y | 600210 | 3000927
| Earthwork and Civil | Excavation | Excavate | Shore | Dewater | Grade | Accept
00.02.01 | Earthwork and Civil | Mass Excavation (Above Water Line) | 75% |  |  | 15% | 10% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 0010100 | Y | Y | 600310 | 3000930
00.02.02 | Earthwork and Civil | Mass Excavation (Below Water Line) | 45% | 30% | 10% | 5% | 10% |  |  |  |  | yd3 | m3 | Yes | 100% |  | Dewatering milestone weighting increased as per CSA comments. | 0010100 | Y | Y | 600310 | 3000930
00.02.03 | Earthwork and Civil | Trench Excavation | 80% |  |  | 10% | 10% |  |  |  |  | yd3 | m3 | Yes | 100% | Includes Individual Foundations | Added Note | 0010100 | Y | Y | 600310 | 3000930
00.02.04 | Earthwork and Civil | Auger holes | 90% |  |  |  | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 0010100 | Y | Y | 600310 | 3000930
00.02.05 | Earthwork and Civil | Ditches | 80% |  |  | 10% | 10% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 0010100 | Y | Y | 600310 | 3000930
| Earthwork and Civil | MSE Wall | Prep | Place | Accept
00.03.01 | Earthwork and Civil | MSE Wall | 10% | 80% | 10% | [6 empty] | ft2 | m2 | Yes | 100% |  |  | 0025100 | Y | Y | 682500
| Earthwork and Civil | Gabion Wall | Mesh | Place | Accept
00.04.01 | Earthwork and Civil | Gabion Wall | 40% | 55% | 5% | [6 empty] | ft2 | m2 | Yes
| Earthwork and Civil | Backfill | Backfill | Grade | Achieve Compaction | Accept
00.05.01 | Earthwork and Civil | Mass Backfill | 70% | 10% | 10% | 10% | [5 empty] | yd3 | m3 | Yes | 100% |  |  | 0015100 | Y | Y | 600390 | 3000938
00.05.02 | Earthwork and Civil | Trench Backfill | 70% | 10% | 10% | 10% | [5 empty] | yd3 | m3 | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 0015100 | Y | Y | 600390 | 3000938
| Earthwork and Civil | Rough Grade | Rough Grade | Accept
00.06.01 | Earthwork and Civil | Rough Grade | 90% | 10% | [7 empty] | yd3 | m3 | Yes | 100% |  |  | 0005100 | Y | Y | 600220 | 3000927
| Earthwork and Civil | Storm Water & Drainage Infrastructure | Install | Testing & Reinstatement | Accept | [11 empty] | Comment received from Scott Hounsell regarding hydro testing these items. This comment was rejected, as these items are not typically hydro tested.
00.07.01 | Earthwork and Civil | Pipe (Concrete or Corrugated Metal Culvert) | 40% | 50% | 10% | [6 empty] | ft | m | Yes | 100% |  |  | 0030300 | Y | Y | 600555 | 5505205 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
00.07.02 | Earthwork and Civil | Concrete Inlet Boxes (Pre Cast) or Catch Basins | 40% | 50% | 10% | [6 empty] | ea | ea | Yes | 100% |  |  | 0030300 | Y | Y | 600555 | 5505205 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
00.07.03 | Earthwork and Civil | Other associated components | 40% | 50% | 10% | [6 empty] | ea | ea | Yes | 100% |  |  | 0030300 | Y | Y | 600555 | 5505205 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
| Earthwork and Civil | Piling | Pre-drill | Drive & Trim Piles | Remove & Restore area (as req) | Re Tap & Confirm compliance | Test (as required) & Accept | [9 empty] | Retap milstone included as per Gary Gardner's comment.
00.08.01 | Earthwork and Civil | Sheet Piles (Install) |  | 80% |  | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  | Trimming piles added as per Russell Lanes comments | 0035200 | Y | Y | 600970 | 3000973
00.08.02 | Earthwork and Civil | Prefabricated Structural Piles (Driven Metal) | 10% | 70% |  | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 0035300 | Y | Y | 600900 | 3000970
| Earthwork and Civil | Helical Piles | Install | Accept
00.08.03 | Earthwork and Civil | Helical Piles | 95% | 5% | [7 empty] | ea | ea | Yes | 100% |  |  | 0035300 | Y | Y | 600900 | 3000970
| Earthwork and Civil | Concrete Piles | Pre-drill | Install Rebar Cage | Pour Concrete | Accept
00.08.04 | Earthwork and Civil | Concrete Piles | 20% | 20% | 50% | 10% | [5 empty] | ea | ea | Yes | 100% |  |  | 0035300 | Y | Y | 600900 | 3000970
| Earthwork and Civil | Cut / Cap Structural Piles | Cut / Cap | Accept
00.09.01 | Earthwork and Civil | Cut / Cap Structural Piles | 90% | 10% | [7 empty] | ea | ea | Yes | 100% |  |  | 0035300 | Y | Y
| Earthwork and Civil | Permanent Roads | Place Material | Grade | Compaction | Reinforce | Place Wearing Course Material | Accept
00.10.01 | Earthwork and Civil | Base Course | 70% | 10% | 10% |  |  | 10% |  |  |  | ft2 | m2 | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 0025100 | Y | Y | 600700 | 3000964
00.10.02 | Earthwork and Civil | Wearing Course (Asphalt Paved) |  | 15% |  |  | 75% | 10% |  |  |  | ft2 | m2 | Yes | 100% |  |  | 0025100 | Y | Y | 600700 | 3000964
00.10.03 | Earthwork and Civil | Wearing Course (Concrete Paved) |  | 10% |  | 50% | 30% | 10% |  |  |  | ft2 | m2 | Yes | 100% |  |  | 0025100 | Y | Y | 600700 | 3000964
00.10.04 | Earthwork and Civil | Wearing Course (Unpaved/Gravel) | 70% | 15% | 5% |  |  | 10% |  |  |  | ft2 | m2 | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 0025100 | Y | Y | 600700 | 3000964
| Earthwork and Civil | RCC - Rolled Compacted Concrete | Material Processing - Preparation | Transport / Install | Complete Punch List & Accept
00.10.05 | Earthwork and Civil | RCC - Rolled Compacted Concrete | 60% | 30% | 10% | [6 empty] | ft2 | m2 | Yes | 100%
| Earthwork and Civil | Bollards | Place Bollard & Stabilize | Clean & Apply Coatings | Accept
00.11.01 | Earthwork and Civil | Pipe Bollards | 75% | 15% | 10% | [6 empty] | ea | ea | Yes | 100% |  |  | 0030100 | Y | Y | 600675 | 3000956
| Earthwork and Civil | Lining & Geotextiles | Place Material | Grade | Compaction | Accept
00.12.01 | Earthwork and Civil | Clay (or similar material) Lining | 50% | 25% | 15% | 10% | [5 empty] | ft2 | m2 | Yes | 100% |  |  |  | N | Y
00.12.02 | Earthwork and Civil | Geotextile Material | 90% |  |  | 10% | [5 empty] | ft2 | m2 | Yes | 100% |  |  |  | N | Y
00.12.03 | Earthwork and Civil | HDPE / Geomembrane Liner | 90% |  |  | 10% | [5 empty] | ft2 | m2 | Yes | 100%
| Earthwork and Civil | Fencing | Clear & Level Area, Layout | Place Posts, Gates, & Turnstiles | Place Wire & Tension | Accept
00.13.01 | Earthwork and Civil | Chain Link | 15% | 45% | 30% | 10% | [5 empty] | ft | m | Yes | 100% |  | Comments rejected from CSA (Civil) regarding weightings. | 0030220 | N | Y |  | 5506290 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
00.13.02 | Earthwork and Civil | Multiple Wire | 15% | 30% | 45% | 10% | [5 empty] | ft | m | Yes | 100% |  | Comments rejected from CSA (Civil) regarding weightings. | 0030220 | N | Y |  | 5506290 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
| Earthwork and Civil | Rock Anchoring - Drilling (Dam) | Stage | Drill | Install | Post Tension & Test | Accept
00.14.01 | Earthwork and Civil | Rock anchoring | 10% | 30% | 40% | 10% | 10% |  |  |  |  | ft2 | m2 | Yes | 100%
| Earthwork and Civil | Containment / Grout Curtain | Stage | Drill | Install | Test & Acceptance
00.15.01 | Earthwork and Civil | Containment / Grout Curtain | 10% | 40% | 40% | 10% | [5 empty] | ft2 | m2 | Yes | 100%
| Earthwork and Civil | Road Guards / Barricades | Stage | Install | Accept
00.16.01 | Earthwork and Civil | Road Guards / Barricades | 10% | 80% | 10% | [6 empty] | ea | ea | Yes | 100%
| Earthwork and Civil | Shotcreting (including fastening) | Stage | Place | Accept
00.17.01 | Earthwork and Civil | Shotcrete Installation | 10% | 80% | 10% | [6 empty] | yd3 | m3 | Yes | 100%
00.18.01 | Earthwork and Civil | Stonework for Roads | Stage | Install | Accept
| Earthwork and Civil | Stonework for Roads | 10% | 80% | 10% | [8 empty] | Yes | 100%
| Concrete | [15 empty] | * Rub & Finish made to be as applicable as per Gary Gardner's comments.
| Concrete | Concrete | Surface Prep / Set Forms | Install Reinforcing & Embeds | Place & Finish | Strip Formwork, Patch, Rub & Finish (if applicable) | Complete Punch List & Accept
10.01.01 | Concrete | Mud Mats (with forms) | 20% |  | 70% | 5% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  | Comments from Patrick Purser were incorporated, reducing the 10% weighted final activity to 5% and distributing the final 5% among formwork and rebar. | 1010300 | Y | Y | 610070 | 5516500 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
10.01.02 | Concrete | Mud Mats (without forms) |  |  | 100% | [6 empty] | yd3 | m3 | Yes | 100% |  |  | 1010300 | Y | Y | 610070 | 5516500 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
10.01.03 | Concrete | Drilled Piers | 25% | 40% | 30% |  | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 1025100 | Y | Y | 610130 | 3001037 | further breakout at Cost Element / SAP Detail Level
10.01.04 | Concrete | Area Paving (non structural slab) | 20% | 40% | 30% | 5% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  | Comment partially accepted from CSA regarding milestone weightings. | 1045100 | Y | Y | 610330 | 3001048 | further breakout at Cost Element / SAP Detail Level
10.01.05 | Concrete | Curbs | 30% | 30% | 15% | 20% | 5% |  |  |  |  | ft | m | Yes | 100%
10.01.06 | Concrete | Columns | 45% | 30% | 5% | 15% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1020100 | Y | Y | 610090 | 3001030 | further breakout at Cost Element / SAP Detail Level
10.01.07 | Concrete | Slabs (at grade) | 30% | 30% | 15% | 20% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1045100 | Y | Y | 610320 | 3001050 | further breakout at Cost Element / SAP Detail Level
10.01.08 | Concrete | Slabs (elevated) | 40% | 25% | 20% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1020100 | Y | Y | 610100 | 3001031 | further breakout at Cost Element / SAP Detail Level
10.01.09 | Concrete | Small Blocks (< 3 CY) (square or rectangular) | 45% | 30% | 5% | 15% | 5% |  |  |  |  | yd3 | m3 | No | 100% |  |  | 1025100 | Y | Y | 610130; 610140; 610150; 610160 | 3001035; 3001036; 3001037; 3001038 | further breakout at Cost Element / SAP Detail Level
10.01.10 | Concrete | Large Blocks (> 3 CY) (square or rectangular) | 30% | 45% | 10% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1030100 | Y | Y | 610165; 610180; 610190; 610200 | 3001039; 3001040; 3001041 | further breakout at Cost Element / SAP Detail Level
10.01.11 | Concrete | Octagonal Foundations | 45% | 35% | 5% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1025100 | Y | Y | 610150 | 3001036 | further breakout at Cost Element / SAP Detail Level
10.01.12 | Concrete | Medium Pours (<25 CY Structures) | 35% | 40% | 10% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  |  | 1030100 | Y | Y | 610190 | 3001041 | further breakout at Cost Element / SAP Detail Level
10.01.13 | Concrete | Mass Pours (>25 CY Structures) | 35% | 40% | 10% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  | Some milestone weightings adjusted, but not all as a result of conflicting comments. (CSA/S. Laskowski) | 1030100 | Y | Y | 610200 | 3001040 | further breakout at Cost Element / SAP Detail Level
10.01.14 | Concrete | Duct Bank | 30% | 20% | 35% | 10% | 5% |  |  |  |  | yd3 | m3 | Yes | 100% |  | Comments rejected from CSA (Civil) regarding weightings. | 1050100 | Y | Y |  |  | further breakout at Cost Element / SAP Detail Level
10.01.15 | Concrete | Grout | 25% |  | 50% | 20% | 5% |  |  |  |  | ft3 | m3 | Yes | 100% |  |  | 1085100 | Y | Y | 620020; 639910 | 3001052 | this is general, also available are 1085200 - Cementitious and 1085300 - Epoxy
10.01.16 | Concrete | Concrete Cap Structural Piles | 20% | 45% | 20% | 10% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 1030100 | Y | Y | 610190 | 3001041
| Concrete | Precast Concrete (manholes; catch basins; foundations; pads) | Shakeout / Stage | Install | Joining | Accept
10.02.01 | Concrete | Precast Concrete | 10% | 60% | 25% | 5% | [5 empty] | yd3 | m3 | Yes | 100% |  | NP-7-Aug-18 - corrected line no.
| Concrete | Precast Concrete Structural Members | Shakeout / Stage | Erect / Install | Bolt / Weld | Accept
10.03.01 | Concrete | Precast Columns | 10% | 60% | 25% | 5% | [5 empty] | yd3 | m3 | Yes | 100%
10.03.02 | Concrete | Precast Beams | 10% | 40% | 45% | 5% | [5 empty] | yd3 | m3 | Yes | 100%
Structural Steel
| Structural Steel | Structural Steel | Shakeout & Stage | Erect / Install | Complete Bolting / Welding | Accept
20.01.01 | Structural Steel | Structural Steel Members, individual | 10% | 40% | 45% | 5% | [5 empty] | Ton | MT | Yes | 100% |  | Preassembled steel separated & weighted differently as per CSA comments | 2010100 | Y | Y |  | 3001071; 3001073; 3001074; 3001072; 3001076; | further breakout at Cost Element / SAP Detail Level
20.01.02 | Structural Steel | Structural Steel, Miscellaneous | 10% | 60% | 25% | 5% | [5 empty] | Ton | MT | Yes | 100% | This item applies to loose miscellaneous structural steel requiring field installation. | Added Note | 2010100 | Y | Y |  | 3001071; 3001073; 3001074; 3001072; 3001076; | further breakout at Cost Element / SAP Detail Level
20.01.03 | Structural Steel | Stair Stringers | 5% | 55% | 35% | 5% | [5 empty] | Ton | MT | Yes | 100% |  |  | 2010100 | Y | Y | 620370 |  | further breakout at Cost Element / SAP Detail Level
20.01.04 | Structural Steel | Stair Treads | 10% | 85% |  | 5% | [5 empty] | Ton | MT | Yes | 100% |  |  | 2010100 | Y | Y | 620370 |  | further breakout at Cost Element / SAP Detail Level
20.01.05 | Structural Steel | Crane Rails | 5% | 55% | 35% | 5% | [5 empty] | Ton | MT | Yes | 100% |  |  | 2010100 | Y | Y | 620120 |  | further breakout at Cost Element / SAP Detail Level
20.01.06 | Structural Steel | Hand Rails (including toe Plate) | 10% | 85% |  | 5% | [5 empty] | Ton | MT | Yes | 100% |  |  | 2010100 | Y | Y | 620350; 620360 | 3001085 | further breakout at Cost Element / SAP Detail Level
20.01.07 | Structural Steel | Ladders & Platforms | 10% | 85% |  | 5% | [5 empty] | Ton | MT | Yes | 100% |  |  | 2010100 | Y | Y | 620340; 620310 | 3001086; 3001083 | further breakout at Cost Element / SAP Detail Level
20.01.08 | Structural Steel | Grating | 10% | 60% | 25% | 5% | [5 empty] | Ton | MT | Yes | 100% | This item applies to loose grating, where not in a pre fabricated platform or other application. | added Note | 2010100 | Y | Y | 620320 | 3001084 | further breakout at Cost Element / SAP Detail Level
| Structural Steel | Fabrication | Issue IWP | Cut | Fabricate | NDE | Painted or Galvanized | Delivery at Site | Installed at Yard
20.02.01 | Structural Steel | Steel Fabrication | 5% | 10% | 50% | 5% | 10% | 5% | 15% |  |  | Ton | MT | Yes
20.02.02 | Structural Steel | Handrails, Ladders and Platforms | 5% | 10% | 75% | 5% | 0% | 5% |  |  |  | Ton | MT | Yes |  | `
20.02.03 | Structural Steel | Decking/Grating Fabrication | 5% | 10% | 80% | 0% | 0% | 5% |  |  |  | Ton | MT | Yes
| Structural Steel | Removal of Shipping / Temporary Steel, Bracing, Strapping etc. | Remove Temporary Steel
20.03.01 | Structural Steel | Removal of Shipping / Temporary Steel, Bracing, Strapping etc. | 100% | [8 empty] | Lot | Lot | Yes | 100% | This item applies to loose grating, where not in a pre fabricated platform or other application. | added Note | 2080100 | Y | N | 600141 |  | further breakout at Cost Element / SAP Detail Level
| Structural Steel | Module Interconnecting Activities | Prepare & Stage | Complete | Accept
20.04.01 | Structural Steel | Structural Interconnections | 10% | 80% | 10% | [6 empty] | ea | ea | Yes | 100% |  |  | 2080100 | Y | Y | 600140 | 5501505 | highlighted green which is SAP Cost Element not SAP Labour Activity Type
Architectural and Buildings
| Architectural and Buildings | Building Exteriors | Stage Material | Layout & Begin Install | Complete Installation | Trim Work & Finishes | Inspect & Accept
30.01.01 | Architectural and Buildings | Curtain Wall System | 5% | 15% | 60% | 10% | 10% |  |  |  |  | ft2 | m2 | Yes | 100% |  |  | 3015400 | Y | Y | 632240 | 3001211
30.01.02 | Architectural and Buildings | Preinsulated Panel (Kingspan or other) | 5% | 15% | 60% | 10% | 10% |  |  |  |  | ft2 | m2 | Yes | 100% |  |  | 3015400 | Y | Y | 632240 | 3001211
30.01.03 | Architectural and Buildings | Sheet Metal Siding | 5% | 5% | 70% | 10% | 10% |  |  |  |  | ft2 | m2 | Yes | 100% |  |  | 3015400 | Y | Y | 632240 | 3001211
30.01.04 | Architectural and Buildings | Roofing | 5% | 5% | 55% | 25% | 10% |  |  |  |  | ft2 | m2 | Yes | 100% |  |  | 3015300 | Y | Y | 632240 | 3001211
| Architectural and Buildings | Building Electrical | Stage Material | Install | Punch & Accept
30.02.01 | Architectural and Buildings | Building Electrical | 5% | 90% | 5% | [6 empty] | Lot | Lot | Yes | 100% |  |  | 3015700 | Y | Y | 632240 | 3001211
| Architectural and Buildings | Interior Fixtures & Finishes | Stage Material | Install | Punch & Accept
30.03.01 | Architectural and Buildings | Interior Fixtures & Finishes | 5% | 75% | 20% | [6 empty] | Lot | Lot | Yes | 100% |  | Acceptance milestone increased in weight as per CSA comments. | 3030100 | Y | Y | 632240 | 3001211 | further breakout at Cost Element / SAP Detail Level
| Architectural and Buildings | HVAC Equipment | Stage Components | Set | Install | Complete Connections & Insulation | Inspect / Accept
30.04.01 | Architectural and Buildings | HVAC Equipment | 15% | 75% |  |  | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 3020100 | Y | Y | 630400 | 3001130
30.04.02 | Architectural and Buildings | Louvers, Registers, etc. | 5% |  | 90% |  | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 3020100 | Y | Y | 630480 | 3001138
| Architectural and Buildings | HVAC Ductwork | Stage Components | Install Hangers | Erect / Install Ductwork | Test | Ductwork Insulation | Accept
30.05.01 | Architectural and Buildings | HVAC Ductwork | 5% | 10% | 55% | 5% | 15% | 10% |  |  |  | ft | m | Yes | 100% |  | Moved from the HVAC equipment sections above (Row hidden in spreadsheet with comments) | 3020100 | Y | Y | 630480 | 3001138
| Architectural and Buildings | Other Architectural & Building Scope | Install | Accept
30.06.01 | Architectural and Buildings | Not included in the above | 90% | 10% | [7 empty] | Lot | Lot | Yes | 100% |  |  | 3000100 | N | Y | 632240 | 3001211
| Architectural and Buildings | Drywall | Install Stud Wall | Install Gypsum Board | Mud & Tape Joints & Fasteners | Paint / Caulk | Accept
30.07.01 | Architectural and Buildings | Drywall | 20% | 45% | 15% | 15% | 5% |  |  |  |  | ft2 | m2 | Yes | 100% |  |  | 3030100 | Y | Y | 632240 | 3001211 | further breakout at Cost Element / SAP Detail Level
| Architectural and Buildings | Clean Room Panel Systems | Install Ceiling Supports | Install Ceiling Panels | Install Floor Track | Install Wall Panels | Install Windows & Doors | Final Trim & Accessories | Accept
30.08.01 | Architectural and Buildings | Clean Room Panel Systems | 10% | 25% | 5% | 25% | 10% | 20% | 5% |  |  | ft2 | m2 | Yes | 100% |  |  | 3035100 | Y | Y | 632240 | 3001211
| Architectural and Buildings | Cold Rooms | Layout / Stage Components | Install Insulated Panels | Electrical Components | Install Mechanical Equipment | Test & Punch | Accept
30.09.01 | Architectural and Buildings | Cold Rooms | 5% | 45% | 15% | 20% | 10% | 5% |  |  |  | ft2 | m2 | Yes | 100% | Assumes a Cold Room System installation method, where there would be some electrical and HVAC man hours associated with this line item. | Added Note | 3030100 | Y | Y | 632240 | 3001211 | further breakout at Cost Element / SAP Detail Level
| Architectural and Buildings | Flooring | Prep & Layout | Apply 3 Coats of Epoxy | Cove | Accept
30.10.01 | Architectural and Buildings | Epoxy Flooring | 5% | 75% | 15% | 5% | [5 empty] | ft2 | m2 | Yes | 100% |  |  | 3030100 | Y | Y | 632240 | 3001211 | further breakout at Cost Element / SAP Detail Level
| Architectural and Buildings |  | Prep & Layout | Install | Accept
30.10.02 | Architectural and Buildings | Raised / Floating Flooring | 15% | 80% | 5% | [6 empty] | ft2 | m2 | Yes | 100% |  |  | 3030100 | Y | Y | 632240 | 3001211 | further breakout at Cost Element / SAP Detail Level
Machinery and Equipment
| Machinery and Equipment | Pre Fabricated Non Rotating | Stage | Set / Install & Secure | Align | Accept
40.01.01 | Machinery and Equipment | Shop Fabricated Tanks, Vessels, Reactors, etc. (With Internals) | 5% | 55% | 30% | 10% | [5 empty] | ea | ea | Yes | 100% |  |  | 4020100 - 4020400 | Y | Y | 640160 | 3001265 | By type
40.01.02 | Machinery and Equipment | Shop Fabricated Tanks, Vessels, Reactors, etc. (Without Internals) | 5% | 55% | 30% | 10% | [5 empty] | ea | ea | Yes | 100% | Refer to 40.12.01 below for internals | Added Note | 4020100 - 4020300 | Y | Y | 640160 | 3001265 | By type | Refer to 40.12.01 below for internals
| Machinery and Equipment | Field Fabricated Equipment | Stage Materials | Fit / Align | Weld | Erect | Support | Test | Punch / Accept
40.02.01 | Machinery and Equipment | Field Fabricated Tanks (cone/fixed roof) | 5% |  | 55% | 25% |  | 5% | 10% |  |  | ea | ea | Yes | 100% |  |  | 4010100 | Y | Y | 640100 | 3001262 | further breakout at Cost Element / SAP Detail Level
40.02.02 | Machinery and Equipment | Field Fabricated Tanks (floating roof) | 5% |  | 40% | 35% |  | 10% | 10% |  |  | ea | ea | Yes | 100% |  | item for floating roof tanks added as per Russell Lane's comments | 4010100 | Y | Y | 640100 | 3001263 | further breakout at Cost Element / SAP Detail Level
40.02.02 | Machinery and Equipment | Field Fabricated Vessels | 5% |  | 55% | 25% |  | 5% | 10% |  |  | ea | ea | Yes |  |  | Proposed
40.02.03 | Machinery and Equipment | Coal Silos | 5% |  | 55% | 30% |  |  | 10% |  |  | ea | ea | Yes | 100% |  |  | 4010100 | Y | Y |  | 3001263 | further breakout at Cost Element / SAP Detail Level
40.02.04 | Machinery and Equipment | Baghouse Hoppers | 5% |  | 45% | 40% |  |  | 10% |  |  | ea | ea | Yes | 100% |  |  | 4070400 | Y | Y | 641370 | 5537515 | further breakout at Cost Element / SAP Detail Level
40.02.05 | Machinery and Equipment | Baghouse Poppet Vlvs |  | 20% | 25% | 25% | 20% |  | 10% |  |  | ea | ea | Yes | 100% |  |  | 4070400 | Y | Y | 641370 | 5537515 | further breakout at Cost Element / SAP Detail Level
40.02.06 | Machinery and Equipment | Baghouse Dampers |  | 30% | 15% | 25% | 20% |  | 10% |  |  | ea | ea | Yes | 100% |  |  | 4070400 | Y | Y | 641370 | 5537515 | further breakout at Cost Element / SAP Detail Level
40.02.07 | Machinery and Equipment | Field Erected Cooling Tower | 5% |  |  | 55% | 30% |  | 10% |  |  | ea | ea | Yes |  |  | Proposed
| Machinery and Equipment | Cooling Tower | Stage | Set / Install & Secure | Hookup & Completion | Accept | [10 empty] | Proposed
40.03.01 | Machinery and Equipment | Package Cooling Tower | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No |  |  | Proposed
| Machinery and Equipment | Furnaces | Stage Materials | Install radiant walls, floor, coils, arch, dress with platforms and refractory | Install convection and transition sections, platforms, refractory | Install stack with any refractory and dress with platforms | Install burners, E&I and piping | Acceptance
40.04.01 | Machinery and Equipment | Furnace | 5% | 25% | 20% | 15% | 25% | 10% |  |  |  | ea | ea | Yes | 100% |  | Milestones may change. No Hydro, Chemical clean, pigging or purging of lines after hydro was included | ??? | Y | Y | 640660 | 5538105 | Should this be under Conveyor's Cost Account 4080500
| Machinery and Equipment | Waste Heat Recovery Unit (WHRU) | Stage material | Install support structure | Install coil bundle section up to transition and dress | Install stack and dress | Install inlet ducting support steel and ducting | Acceptance |  |  |  | ea | ea
40.05.01 | Machinery and Equipment | Waste Heat Recovery Unit (WHRU) | 5% | 10% | 40% | 15% | 20% | 10% |  |  |  | ea | ea | Yes | 100%
Additional activities & intermediate milestones added as per Robert Van Baal's suggestion on 11/2/16
| Machinery and Equipment | Air Cooled Heat Exchangers | Stage Materials | Erect Structure / Supports | Set & Align | Install Drive Components | Accept
40.06.01 | Machinery and Equipment | Air Cooled Heat Exchangers | 5% | 35% | 25% | 25% | 10% |  |  |  |  | ea | ea | No | 100% |  | Weighting Adjusted as per Russel Lane's comments | 4040100 | Y | Y | 640370 | 3001283
| Machinery and Equipment | Heat Exchangers | Stage | Set / Install & Secure | Hookup & Completion | Accept | [10 empty] | Proposed
40.07.01 | Machinery and Equipment | Shell and Tube Heat Exchangers | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No |  |  | Proposed
40.07.02 | Machinery and Equipment | Plate and Frame Heat Exchangers | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No |  |  | Proposed
40.07.03 | Machinery and Equipment | Electric Heaters | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No |  |  | Proposed
| Machinery and Equipment | Boilers | Arrival at site | Set package on foundations and dress with platforms/ladders/etc. | Install burners and secondary components, superheater/condensor/piping/etc. | Install fan, hot and cold flue gas ducting including stack | Install insulation | Acceptance | [8 empty] | Does not include potential milestones like Hydro, Chemical cleaning, purging on installing burners. Milestones based on boiler being supplied as a package boiler
40.08.01 | Machinery and Equipment | Boilers | 5% | 20% | 25% | 25% | 15% | 10% |  |  |  | ea | ea | No | 100%
| Machinery and Equipment | Flares | Stage Materials | Install Enclosure | Complete Refractory, Burner, & Pilot | Complete Header | Accept
40.09.01 | Machinery and Equipment | Flare Equipment (elevated) | 5% | 20% | 40% | 25% | 10% |  |  |  |  | ea | ea | Yes | 100% | The basis of this item is a guyed flare, for derrick flares, the derrick structure should be progressed using the appropriate structural steel rules of credit. | Added Note | 4050300 | Y | Y | 640620 | 3001304
40.09.02 | Machinery and Equipment | Flare Equipment (at grade) | 5% | 30% | 25% | 30% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4050300 | Y | Y | 640620 | 3001304
| Machinery and Equipment | Turbine Equipment | Stage / Rough Set | Install | Preliminary Alignment | Final Alignment | Accept
40.10.01 | Machinery and Equipment | Turbine Equipment | 10% | 70% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  | Additional milestones for turbines were added as per Mechanical Discipline engineering comments, to be more like the compressor milestones. | 4030200 / 4030300 | Y | Y | 640320; 640330 | 5537410; 5537415 | Steam / Gas
| Machinery and Equipment | Pumps | Stage / Rough Set | Set / Install & Secure | Preliminary Alignment | Final Alignment | Accept
40.11.01 | Machinery and Equipment | Pumps | 5% | 20% | 45% | 20% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4060100 -4060600 | Y | Y | 6400460 | 3001294 | By type
40.11.02 | Machinery and Equipment | Pumps Set in Module; Final Alignment at Site / Post Module Set |  |  |  | 90% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4060100 -4060600 | Y | Y |  |  | By type
| Machinery and Equipment | Compressors | Stage / Rough Set | Install | Preliminary Alignment | Final Alignment | Accept
40.12.01 | Machinery and Equipment | Blowers & Fans | 5% | 70% | 10% | 10% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4030500 | Y | Y | 640270; 640271 | 5537421; 5537420
40.12.02 | Machinery and Equipment | Centrifugal | 5% | 60% | 20% | 5% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4030100 | Y | Y | 640260 | 3001274 | further breakout at Cost Element / SAP Detail Level
40.12.03 | Machinery and Equipment | Reciprocating | 5% | 60% | 20% | 5% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4030100 | Y | Y | 640250 | 3001273 | further breakout at Cost Element / SAP Detail Level
40.12.04 | Machinery and Equipment | Packaged Units (centrifugal or reciprocating) | 5% | 75% |  | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4030100 | Y | Y | Above | Above | further breakout at Cost Element / SAP Detail Level
| Machinery and Equipment | Material Handling Equipment | Stage | Set / Install & Secure | Preliminary Alignment | Final Alignment | Accept
40.13.01 | Machinery and Equipment | Conveyors (Belt) | 5% | 50% | 20% | 15% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080500 | Y | Y | 640660 | 5538105 | further breakout at Cost Element / SAP Detail Level
40.13.02 | Machinery and Equipment | Conveyors (Roller) | 5% | 50% | 20% | 15% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080500 | Y | Y | 640660 | 5538105 | further breakout at Cost Element / SAP Detail Level
40.13.03 | Machinery and Equipment | Conveyors (Screw) | 5% | 50% | 20% | 15% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080500 | Y | Y | 640660 | 5538105 | further breakout at Cost Element / SAP Detail Level
40.13.04 | Machinery and Equipment | Conveyors (Bucket Elevator) | 5% | 50% | 20% | 15% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080500 | Y | Y | 640660 | 5538105 | further breakout at Cost Element / SAP Detail Level
| Machinery and Equipment | Generators/Gensets | Stage | Set / Install & Secure | Hookup & Completion | Accept | [10 empty] | Proposed
40.14.01 | Machinery and Equipment | Generators/Gensets | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No | 100% |  | Proposed
| Machinery and Equipment | Skids & Package Equipment | Stage | Set / Install & Secure | Hookup & Completion | Accept
40.15.01 | Machinery and Equipment | Skids & Package Equipment | 5% | 30% | 45% | 20% | [5 empty] | ea | ea | No | 100% |  |  | Multiple - see above | [5 empty] | Too generic, too many variables
| Machinery and Equipment | Process Equipment Internals | Stage | Remove Existing Internals | Install New Internals | Accept
40.16.01 | Machinery and Equipment | Install Internals | 5% |  | 85% | 10% | [5 empty] | ea | ea | No | 100% |  |  | 4020400 | Y | Y | 640230 | 3001270
40.16.02 | Machinery and Equipment | Remove Existing Internals & Install New | 5% | 35% | 50% | 10% | [5 empty] | ea | ea | No | 100% |  |  | 4020900 | Y | Y | 640240 | 5537230
| Machinery and Equipment | Surface Condenser | Stage | Install | Weld | Test | Accept
40.17.01 | Machinery and Equipment | Surface Condenser | 5% | 30% | 55% | 5% | 5% |  |  |  |  | ea | ea | No | 100% |  |  | 4040400 | Y | Y | 640352 | 3001287 | further breakout at Cost Element / SAP Detail Level
| Machinery and Equipment | Air heater | Erect | Fit / Weld | Final Alignment | Punch / Accept
40.18.01 | Machinery and Equipment | Air heater | 40% | 45% | 10% | 5% | [5 empty] | ea | ea | No | 100% |  |  | ???
| Machinery and Equipment | Coal Pipe | Erect | Bolt Up / Weld | Support | Punch / Accept
40.19.01 | Machinery and Equipment | Coal Pipe | 35% | 30% | 30% | 5% | [5 empty] | ea | ea | Yes | 100% |  |  | ???
| Machinery and Equipment | Ductwork | Erect | Fit / Weld | Support | Punch / Accept
40.20.01 | Machinery and Equipment | Ductwork | 25% | 55% | 15% | 5% | [5 empty] | ea | ea | Yes | 100% |  |  | 4050500 | Y | N | 640400 ???? | 5537620 ????
| Machinery and Equipment | Fans | Pre Assemble | Rough Set | Fit / Align | Final Alignment | Punch / Accept
40.21.01 | Machinery and Equipment | Fans | 15% | 20% | 40% | 15% | 10% |  |  |  |  | ea | ea | No | 100% |  |  | ??? |  |  | 630440 | 3001130 | Exhaust Fans????
| Machinery and Equipment | Pulverizers | Rough Set | Fit / Align | Final Alignment | Punch / Accept
40.22.01 | Machinery and Equipment | Pulverizers | 40% | 40% | 15% | 5% | [5 empty] | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640810 | 3001324
| Machinery and Equipment | Waterwalls | Erect | Tube Fit / Weld | Membrane Fit / Weld | Punch / Accept
40.23.01 | Machinery and Equipment | Waterwalls | 25% | 40% | 30% | 5% | [5 empty] | ea | ea | Yes | 100% |  |  | ???
| Machinery and Equipment | Cranes & Hoists | Stage | Preliminary Alignment | Final Alignment | Load Test | Punch / Accept
40.24.01 | Machinery and Equipment | Cranes & Hoists | 30% | 25% | 25% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  | Milestone for testing was added as per Scott Hounsell's comment | 4080600 | Y | Y | 640670 | 3001315
| Machinery and Equipment | Other Processing Equipment | Stage | Set / Install & Secure | Preliminary Alignment | Final Alignment | Punch / Accept
40.25.01 | Machinery and Equipment | Agitators (Top Entry) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 | Y | Y | 640580 | 3001300
40.25.02 | Machinery and Equipment | Agitators (Side Entry) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 | Y | Y | 640580 | 3001300
40.25.03 | Machinery and Equipment | Agitators (Bottom Entry) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 | Y | Y | 640580 | 3001300
40.25.04 | Machinery and Equipment | Centrifuge (Batch) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 | Y | Y | 641520 ???? | 5537865???
40.25.05 | Machinery and Equipment | Centrifuge (High Speed) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 | Y | Y | 641520 ???? | 5537865???
40.25.06 | Machinery and Equipment | Centrifuge (Conveyor) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 | Y | Y | 641520 ???? | 5537865???
40.25.07 | Machinery and Equipment | Centrifuge (Bowl) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 | Y | Y | 641520 ???? | 5537865???
40.25.08 | Machinery and Equipment | Crystalizer (Batch Vacuum) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080300 | Y | Y | 641640 ??? | 5527839 ???
40.25.09 | Machinery and Equipment | Crystalizer (Mechanical, Scraped Surface) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080300 | Y | Y | 641640 ??? | 5527839 ???
40.25.10 | Machinery and Equipment | Dryer (Drum) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070600 / 4080300 | Y | Y | 641640 | 5527839 | Liquids / Solids
40.25.11 | Machinery and Equipment | Dryer (Rotary) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070600 / 4080300 | Y | Y | 641640 | 5527839 | Liquids / Solids
40.25.12 | Machinery and Equipment | Dryer (Tray) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070600 / 4080300 | Y | Y | 641640 | 5527839 | Liquids / Solids
40.25.13 | Machinery and Equipment | Dryer (Spray) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070600 / 4080300 | Y | Y | 641640 | 5527839 | Liquids / Solids
40.25.14 | Machinery and Equipment | Dust Collector (Mechanical) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080100 | Y | Y | 641610 | 5537836? | further breakout at Cost Element / SAP Detail Level
40.25.15 | Machinery and Equipment | Dust Collector (Spray) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080100 | Y | Y | 641610 | 5537836? | further breakout at Cost Element / SAP Detail Level
40.25.16 | Machinery and Equipment | Dust Collector (Cloth Bay) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080100 | Y | Y | 641610 | 5537836? | further breakout at Cost Element / SAP Detail Level
40.25.17 | Machinery and Equipment | Dust Collector (Precipitator) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4080100 | Y | Y | 641610 | 5537836? | further breakout at Cost Element / SAP Detail Level
40.25.18 | Machinery and Equipment | Extractor | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070400 / 4080100 | Y | Y |  |  | Liquids / Solids
40.25.19 | Machinery and Equipment | Filter (Plate & Frame) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.20 | Machinery and Equipment | Filter (Pressure Leaf) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.21 | Machinery and Equipment | Filter (Rotary) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.22 | Machinery and Equipment | Filter (Sewage) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.23 | Machinery and Equipment | Filter (Sparkler) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.24 | Machinery and Equipment | Filter (Vibrating Screens) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.25 | Machinery and Equipment | Filter (Flotation) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070100 / 4070500 | Y | Y | 641510 | 5537865? | further breakout at Cost Element / SAP Detail Level
40.25.26 | Machinery and Equipment | Mixer (Propeller) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 / 4080200 | Y | Y | 641522 | 5537821 | Liquids / Solids
40.25.27 | Machinery and Equipment | Mixer (Blender) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 / 4080200 | Y | Y | 641522 | 5537821 | Liquids / Solids
40.25.28 | Machinery and Equipment | Mixer (Batch) | 5% | 60% | 15% | 10% | 10% |  |  |  |  | ea | ea | Yes | 100% |  |  | 4070200 / 4080200 | Y | Y | 641522 | 5537821 | Liquids / Solids
| Machinery and Equipment | Size Reduction Equipment | Stage | Install | Preliminary Alignment | Final Alignment | Punch / Accept
40.26.01 | Machinery and Equipment | Crushers (Rotary) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.02 | Machinery and Equipment | Crushers (Sawtooth) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.03 | Machinery and Equipment | Crushers (Swing Hammer) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.04 | Machinery and Equipment | Crushers (Swing Jaw) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.05 | Machinery and Equipment | Crushers (Single Roll) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.06 | Machinery and Equipment | Crushers (Gyratory) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640820 | 3001326 | further breakout at Cost Element / SAP Detail Level
40.26.07 | Machinery and Equipment | Mills (Attrition) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y |  |  | further breakout at Cost Element / SAP Detail Level
40.26.08 | Machinery and Equipment | Mills (Micro Pulverizer) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y |  |  | further breakout at Cost Element / SAP Detail Level
40.26.09 | Machinery and Equipment | Mills (Roller) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y |  |  | further breakout at Cost Element / SAP Detail Level
40.26.10 | Machinery and Equipment | Mills (Ball) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y | 640830 | 3001325 | further breakout at Cost Element / SAP Detail Level
40.26.11 | Machinery and Equipment | Size Reduction Cutter (Rotary Knife) | 5% | 75% | 10% | 5% | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 480400 | Y | Y |  |  | further breakout at Cost Element / SAP Detail Level
| Machinery and Equipment | Ladders & Platforms for Vessels & Equipment | Shakeout & Stage | Erect / Install | Accept
40.27.01 | Machinery and Equipment | Install Ladders & Platforms for Vessels & Equipment | 10% | 80% | 10% | [6 empty] | ea | ea | Yes | 100% |  | Added as per comment from Scott Hounsell | 2010100 | Y | Y | 620340; 620370
| Machinery and Equipment | "Other" Equipment Not Covered in the Types Above | Stage | Set / Install | Alignment | Punch / Accept
40.28.01 | Machinery and Equipment | "Other Equipment" (Static) | 5% | 85% |  | 10% | [5 empty] | ea | ea | Yes | 100% |  |  | ??? |  |  |  |  | lots of CCOAs by equipment type
40.28.02 | Machinery and Equipment | "Other Equipment" (Rotating, Reciprocating, etc.) | 5% | 60% | 25% | 10% | [5 empty] | ea | ea | Yes | 100% |  |  | ??? |  |  |  |  | lots of CCOAs by equipment type
| Piping | [15 empty] | Milestone weightings for piping adjusted as per Scott Housell's comment regarding the weighting of testing-reinstatement activities. (Typical for Metallic piping)
| Piping |  | Stage | Erect / Install | Complete Bolted Joints / Welds | Complete Supports & Trim | Punch & Accept
| Piping | Small Bore Piping, Pipe Rack | [14 empty] | Staging for all piping was raised to 10% weighting as per Gary Gardner's comment.
50.01.01 | Piping | Carbon Steel | 10% | 25% | 40% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  | Added Note | 5010200 | Y | Y | 650090 | 5545102 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports
50.01.02 | Piping | Stainless Steel & Alloy | 10% | 25% | 40% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  | The final activity weighting for all items was increased to 25% based on comments by Patrick Purser | 5010300 | Y | Y | 650170 | 5545103 | Assumes all shop fab; where are ROC for field fab?
| Piping | Large Bore Piping, Pipe Rack
50.02.01 | Piping | Carbon Steel | 10% | 30% | 35% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010200 | Y | Y | 650100 | 5545102 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports
50.02.02 | Piping | Stainless Steel & Alloy | 10% | 25% | 40% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010300 | Y | Y | 650180 | 5545103 | Assumes all shop fab; where are ROC for field fab?
0%
| Piping | Small Bore Piping, Process Area | [12 empty] | 0%
50.03.01 | Piping | Carbon Steel | 10% | 20% | 45% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010200 | Y | Y | 650090 | 5545102 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports
50.03.02 | Piping | Stainless Steel & Alloy | 10% | 20% | 45% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010300 | Y | Y | 650170 | 5545103 | Assumes all shop fab; where are ROC for field fab?
| Piping | Large Bore Piping, Process Area
50.04.01 | Piping | Carbon Steel | 10% | 30% | 35% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010200 | Y | Y | 650100 | 5545102 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports
50.04.02 | Piping | Stainless Steel & Alloy | 10% | 25% | 40% | 20% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010300 | Y | Y | 650180 | 5545103 | Assumes all shop fab; where are ROC for field fab?
| Piping | Other Piping
50.05.01 | Piping | Fiberglass Piping | 10% | 25% | 35% | 25% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010400 | Y | Y | 601441; 601442 | 5545125 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports; AG only
50.05.02 | Piping | Poly Vinyl Chloride (PVC) Piping | 10% | 10% | 20% | 55% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010400 | Y | Y | 601441; 601442 | 5545125 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports; AG only
50.05.03 | Piping | Polypropylene Piping | 10% | 10% | 20% | 55% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5010400 | Y | Y | 601441; 601442 | 5545125 | Assumes all shop fab; where are ROC for field fab? Separate CCOA for Supports; AG only
50.05.04 | Piping | Copper Pipe | 10% | 25% | 35% | 25% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | ??? |  |  | 650692; 650694 | 5545105
50.05.05 | Piping | Deluge / Fire Water Piping | 10% | 40% | 40% | 5% | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 5070100 | Y | Y | 601360; 632000 | 3001190; 3001191
50.05.06 | Piping | Steam Tracing | 10% | 80% |  | 5% | 5% |  |  |  |  | ft | m | Yes | 100% |  | Weighting added for supporting Steam Tracing as per Gary Gardner's comments | 5065100 | Y | Y | 650470 | 3001403
50.05.07 | Piping | Steam Tracing, hard piped | 10% | 35% | 45% | 5% | 5% |  |  |  |  | ft | m | Yes | 100% |  | This line added for hard-piped steam tracing, as per Ronnie Westerhoven's comments. | 5065100 | Y | Y | 650470 | 3001403
50.05.08 | Piping | HDPE Piping | 10% | 30% | 50% | 5% | 5% |  |  |  |  | ft | m | Yes | 100% |  | This line added for hard-piped steam tracing, as per Ronnie Westerhoven's comments. | 5065100 | Y | Y | 632000 | 3001191
| Piping | Hygienic Piping | Stage | Install Hangers | Install Pipe | Weld | Slope Check
50.06.01 | Piping | Hygienic Piping (any metallurgy) | 5% | 25% | 30% | 30% | 10% |  |  |  |  | ft | m | Yes | 100% |  | Added as per LS&AM input (see Fred Pearson Comments) | 3015600 | Y | Y | 630700 | 3001145
| Piping | Fabrication | Issue IWP | Cut/Bevel | Fabricate | Hydrostatic Test | NDE | Delivery at Site | Installed at Yard
50.07.01 | Piping | Piping | 5% | 15% | 40% | 10% | 5% | 5% | 20% |  |  | ft | m | Yes
50.07.02 | Piping | Piping Supports | 5% | 20% | 65% | 5% | 5% |  |  |  |  | ft | m | Yes
| Piping | Test & Reinstate | Prep for Test | Test | Reinstate | Punch / Accept
50.08.01 | Piping | Test & Reinstate | 35% | 20% | 40% | 5% | [5 empty] | ft | m | Yes | 100% |  |  | 5090100 | Y | N | 650670 | 5545100?
| Piping | Hot Taps & Tie-ins | Prep | Complete Welded / Bolted Joint | Punch / Accept
50.09.01 | Piping | Hot Taps & Tie-ins | 10% | 80% | 10% | [6 empty] | ea | ea | No | 100% |  |  | 5080200 | Y | N | 601400 | 3001404
| Piping | Valve Handling (except Control Valves; see 70.6) | Stage | Remove Temp Spool / Pup Piece | Install | Punch / Accept
50.10.01 | Piping | Valve Handling (except Control Valves; see 70.6) | 10% | 15% | 70% | 5% | [5 empty] | ea | ea | No | 100% |  |  | 5030900 | Y | N | 650500 | 5545160?
| Piping | Module Interconnecting Activities | Prepare & Stage | Complete | Punch / Accept
50.11.01 | Piping | Piping Interconnections | 10% | 80% | 10% | [6 empty] | ea | ea | Yes | 100% |  |  | 5085100 | Y | Y | 600136 | 5505510
| Piping | Eye Wash Stations | Stage | Set / Install & Secure | Hookup & Completion | Accept
50.12.01 | Piping | Eye Wash Stations | 5% | 30% | 55% | 10% | [5 empty] | ea | ea | No | 100% | [5 empty] | 650410 | 554500
Pipelines
| Pipelines | Onshore Pipeline | String and Bend | Weld | Coat | Tie-in | Lower
55.01.01 | Pipelines | Lay Pipeline | 15% | 25% | 10% | 25% | 25% |  |  |  |  | ft | m | Yes | 100% | See 00 for Civil work (clear, grade, ditch, backfill) |  | 5520200 | Y | Y | 602370 | 3001726 | further breakout at Cost Element / SAP Detail Level
| Pipelines | Horizontal Directional Drilling (HDD) | Pilot | Ream | Pullback
55.02.01 | Pipelines | Horizontal Directional Drilling (HDD) | 20% | 20% | 60% | [6 empty] | ft | m | Yes | 100% |  |  | 5520200 | Y | Y | 602370 | 3001726 | further breakout at Cost Element / SAP Detail Level
| Pipelines | Road Bore | Install
55.03.01 | Pipelines | Road Bore | 100% | [8 empty] | ft | m | Yes | 100% |  |  | 5520200 | Y | Y | 602370 | 3001726 | further breakout at Cost Element / SAP Detail Level
| Electrical | [15 empty] | Electrical section was modified as per electrical engineering discipline comments., line items were renamed and testing descriptions added. Some weightings were changed)
| Electrical | Cable Tray | Stage | Install Supports / Hangers | Installation at Yard | Gland / Terminate | Inspect, Test, Torque & Accept
60.01.01 | Electrical | Cable Tray | 5% | 50% | 40% |  | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 6060100 | Y | Y | 660300 | 3001447
60.01.02 | Electrical | Channel Tray | 5% | 50% | 40% |  | 5% |  |  |  |  | ft | m | Yes | 100% | [5 empty] | 660300 | 3001447
60.01.03 | Electrical | Install Tray Covers | 5% |  | 90% |  | 5% |  |  |  |  | ea | ea | Yes | 100% | [5 empty] | 660300 | 3001447
60.01.04 | Electrical | Conduit | 5% | 20% | 70% |  | 5% |  |  |  |  | ft | m | Yes | 100% |  |  | 6025200 | Y | Y | 660230 | 3001429 | AG only
60.01.05 | Electrical | Lighting (Light Fixtures, including bulbs, Light Pole/Stanchion) / Receptacles | 20% | 10% | 65% |  | 5% |  |  |  |  | ea | ea | Yes | 100% | Layout & begin installation includes any preparation & preassembly. |  | 6035200 / 6035210 | Y | Y | 660130; 660135 | 5547205; 5546260 | Separate CCOA for Lighting Poles
60.01.06 | Electrical | Cable Bus | 5% | 25% | 30% | 30% | 10% |  |  |  |  | ft | m | Yes | 100% | Testing includes continuity tests, insulation resistance
60.01.07 | Electrical | Bus Duct | 5% | 25% | 40% |  | 30% |  |  |  |  | ft | m | Yes | 100% |  |  | 6020240 |  |  | 660060 | 3001410
60.01.08 | Electrical | Electrical Equipment (Transformers, EDG, Switch Gear, EHT Controllers, MCC, UPS, VFD, Panels, etc.) | 10% |  | 80% |  | 10% |  |  |  |  | ea | ea | Yes | 100%
60.01.09 | Electrical | Grounding | 5% |  | 90% |  | 5% |  |  |  |  | ft | m | Yes | 100% | Testing includes ground resistance tests, ground grid integrit tests, and connection |  | 6045100 |  |  | 660330 | 3001451
60.01.10 | Electrical | Lightning Protection | 5% |  | 90% |  | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 6045300 |  |  | 660340 | 3001456
60.01.11 | Electrical | Junction Boxes & Push / Pull Stations |  | 10% | 85% |  | 5% |  |  |  |  | ea | ea | Yes | 100% |  |  | 7035100 |  |  | 670240 | 3001506
| Electrical | Cable Pull | Stage / Install Tugger & Rollers | Pull | Secure / Tie-Wrap/Cleanup
60.02.01 | Electrical | Cable & Wire (Medium/High Voltage) - Above Ground | 20% | 70% | 10% | [6 empty] | ft | m | No | 100% |  |  | 6030100 | Y | Y | 660260 | 3001442 | further breakout at Cost Element / SAP Detail Level
60.02.02 | Electrical | Cable & Wire (Low Voltage, Instrument Cable) - Above Ground | 15% | 75% | 10% | [6 empty] | ft | m | No | 100% |  |  | 6030100 | Y | Y | 660270 | 3001444 | further breakout at Cost Element / SAP Detail Level
60.02.03 | Electrical | Cable & Wire (Medium/High Voltage) - Below Ground | 15% | 75% | 10% | [6 empty] | ft | m | No | 100% |  | Buried cable items added as per Russell Lane's comments | 6030100 | Y | Y | 680020? | 3001527? | further breakout at Cost Element / SAP Detail Level
60.02.04 | Electrical | Cable & Wire (Low Voltage, Instrument Cable) - Below Ground | 10% | 80% | 10% | [6 empty] | ft | m | No | 100% |  | Buried cable items added as per Russell Lane's comments | 6030100 | Y | Y | 680020? | 3001527? | further breakout at Cost Element / SAP Detail Level
| Electrical | Cable Terminations | Gland | Terminate / Wire Tags | Cable Tag | Test / Torque & Accept
60.03.01 | Electrical | Terminations (individual) | 40% | 40% | 5% | 15% | [5 empty] | ea | ea | No | 100% | Meggar testing & continuity testing |  | 6030100 | Y | Y | 660255 |  | further breakout at Cost Element / SAP Detail Level
| Electrical | Cathodic Protection | Stage | Intall Anode Pile | Install Undergrounds | Install Rectifiers / JB's | Inspect, Energize, and Accept | [10 empty] | 6045200 | Y | Y
60.04.01 | Electrical | Impressed Current Cathodic Protection | 5% | 20% | 30% | 40% | 5% |  |  |  |  | ea | ea | Yes | 100% | Testing includes electrode function tests |  | 6045200 |  |  | 660350 | 3001454
60.04.02 | Electrical | Sacrificial Anode | 5% |  | 90% |  | 5% |  |  |  |  | ea | ea | No | 100% |  |  | 6045200 |  |  | 660350 | 3001454
| Electrical | Specialty Test | Setup | Bump / Run / Test | Accept
60.05.01 | Electrical | Motor Bump / Run Test | 25% | 65% | 10% | [6 empty] | ea | ea | No | 100% |  |  | 6090100 |  |  | 660360 | 3001459
60.05.02 | Electrical | Testing of Electrical Equipment (Switchgear/Transformers/etc.) | 10% | 85% | 5% | [6 empty] | ea | ea | Yes | 100% |  |  | 6090100 |  |  | 660360 | 3001459
60.05.03 | Electrical | Cable Hipot Test | 10% | 85% | 5% | [6 empty] | ea | ea | No | 100%
| Electrical | Electric Heat Tracing (EHT) | Delivery at Yard | Install & Test Yard | Test (Post Insulation) at Yard | Accept | [10 empty] | New Line item added, EHT moved from Line 60.9 & new milestones added as per Scott Hounsell's comments.
60.06.01 | Electrical | Electric Heat Tracing (EHT) | 10% | 75% | 10% | 5% | [5 empty] | ft | m | Yes | 100% |  |  | 6040100 | Y | Y | 660400 | 5548600? | further breakout at Cost Element / SAP Detail Level; testing with DFL is a separate activity type
| Electrical | Pole Lines/Switchyards/Substations | Stage | Assemble | Set | Anchor | Guy Wires | String / Set | Splice / Sag / Test | Accept | [6 empty] | New Line item added, EHT moved from Line 60.9 & new milestones added as per Scott Hounsell's comments.
60.07.01 | Electrical | Mono Steel Power Poles/Supports (for powerline or bus supports) | 10% | 50% | 35% |  |  |  |  | 5% |  | ea | ea | Yes | 100% |  |  | 6050100 |  |  | 660310 | 3001449
60.07.02 | Electrical | Wood Power Poles | 10% | 40% | 25% | 12% | 8% |  |  | 5% |  | ea | ea | Yes | 100% |  |  | 6050100 |  |  | 660310 | 3001449
60.07.03 | Electrical | Power Pole Frames | 10% | 50% | 15% | 20% |  |  |  | 5% |  | ea | ea | Yes | 100% |  |  | 6050100 |  |  | 660310 | 3001449
60.07.04 | Electrical | Powerline | [5 empty] | 85% | 10% | 5% |  | ft | m | Yes | 100% |  |  | 6050100 |  |  | 660310 | 3001449
60.07.05 | Electrical | Switchyard/Outdoor Substation overhead bus | [5 empty] | 90% |  | 10% |  | ft | m | Yes | 100%
| Electrical | Prefabricated Substations (excluding system interconnection work) | Receive & Offload from Transport | Transport to Installation site | Set in Place & Secure | Accept | [8 empty] | 0%
60.08.01 | Electrical | Crane Set of Prefabricated Substation | 20% | 30% | 40% | 10% | [5 empty] | ea | ea | No | 100%
60.08.02 | Electrical | SPMT of Prefabricated Substation | 20% | 50% | 20% | 10% | [5 empty] | ea | ea | No | 100%
| Electrical | Module Interconnecting Activities | Stage / Prep / Test | Install | Support/Tie-wrap | Gland / Terminate / Label | Cable Tag | Test / Torque & Accept | [6 empty] | 0%
60.09.01 | Electrical | Cable Tray | 30% | 65% |  |  |  | 5% |  |  |  | ea | ea | Yes | 100% |  |  | 6070100 / 7070100 | Y | Y | 600137 | 5501515? | Electrical / Instrumentation separate CCOAs
60.09.02 | Electrical | Uncoil Cable (Electrical/Instrumentation) |  | 45% | 10% | 30% | 5% | 10% |  |  |  | ft | m | Yes | 100% |  |  | 6070100 / 7070100 | Y | Y | 600137 | 5501515? | Electrical / Instrumentation separate CCOAs
| Electrical | Module EHT Interconnecting Activities | Install & Test | Test (Post Insulation) | Accept | [9 empty] | 0%
60.10.01 | Electrical | EHT Interconnect (excludes removal/install of insulation) | 90% | 5% | 5% | [6 empty] | ea | ea | Yes | 100% |  |  | 6070100 / 7070100 | Y | Y | 600137 | 5501515? | Electrical / Instrumentation separate CCOAs
0%
| Control Systems | [13 empty] | 0%
| Control Systems |  | Stage | Install | Support | Connect Tubing | Test | Accept | [6 empty] | 0%
70.01.01 | Control Systems | Tubing | 5% | 45% | 35% |  | 10% | 5% |  |  |  | ft | m | No | 100% |  |  | 7040100 | Y | Y | 670270 | 3001511 | further breakout at Cost Element / SAP Detail Level
70.01.02 | Control Systems | Tubing Tray | 5% | 40% | 50% |  |  | 5% |  |  |  | ft | m | No | 100% |  |  | 7040100 | Y | Y | 670270 | 3001511 | further breakout at Cost Element / SAP Detail Level
70.01.03 | Control Systems | Gauges & Indicators | 5% | 85% |  |  |  | 10% |  |  |  | ea | ea | No | 100% |  |  | 7010100 | Y | Y | 6700200 | 3001470 | General Instrument installation; Separate CCOA for testing / calibration
70.01.04 | Control Systems | Transmitters | 5% | 30% |  | 45% | 10% | 10% |  |  |  | ea | ea | No | 100% |  |  | 7010100 | Y | Y | 6700200 | 3001470 | General Instrument installation; Separate CCOA for testing / calibration
70.01.05 | Control Systems | Control Valves | 5% | 55% |  | 20% | 10% | 10% |  |  |  | ea | ea | No | 100% |  |  | 7010220 | Y | Y | 670080 | 3001466 | Separate CCOA for testing / calibration
70.01.06 | Control Systems | Switches | 5% | 85% |  |  |  | 10% |  |  |  | ea | ea | No | 100% |  |  | 7010300 | Y | Y | 670110 | 3001473
70.01.07 | Control Systems | Distributed Control System, Emergency Shut Down System, Fire & Gas Detection System component Installation | 10% | 55% |  |  | 25% | 10% |  |  |  | ea | ea | Yes | 100% |  |  | 7025100 | Y | Y | 670130 | 3001483 | see detail at SAP Detail Level
70.01.08 | Control Systems | Marshalling Cabinets | 5% | 75% | 10% |  |  | 10% |  |  |  | ea | ea | Yes | 100% |  |  | 7814310 | Y | Y | 670250 | 3001509 | see detail at SAP Detail Level
70.01.09 | Control Systems | Instrument Calibration |  |  |  |  | 90% | 10% |  |  |  | ea | ea | No | 100% |  |  | 7090100 |  |  | 670360 | 3001524
70.01.10 | Control Systems | Loop Check |  |  |  |  | 90% | 10% |  |  |  | ea | ea | No | 100% |  |  | 7090100 |  |  | 670370 | 3001525
70.01.11 | Control Systems | Thermowells | 5% |  | 80% |  |  | 15% |  |  |  | ea | ea | No | 100%
70.01.12 | Control Systems | Relief Devices | 5% | 20% | 70% |  |  | 5% |  |  |  | ea | ea | No | 100%
70.01.13 | Control Systems | I/P Devices | 5% | 10% | 70% |  |  | 15% |  |  |  | ea | ea | No | 100%
| Control Systems | Prefabricated Instrument/Control Buildings | Receive & Offload from Transport | Transport to Installation site | Set in Place & Secure | Accept | [10 empty] | NP7-Aug-18 - updated to remove working line from title.
70.02.01 | Control Systems | Prefabricated Instrument/Control Buildings | 20% | 30% | 40% | 10% | [5 empty] | ea | ea | No | 100% |  | NP7-Aug-18 - updated to correct working line . | 7050100 |  |  | 632210 | 3001208
| Control Systems | Module Interconnecting Activities | Prepare & Stage | Complete | Test | Accept | [10 empty] | NP7-Aug-18 - updated to correct working line .
70.03.01 | Control Systems | Instrumentation Interconnections | 10% | 60% | 20% | 10% | [5 empty] | lot | lot | Yes | 100% |  | NP7-Aug-18 - updated to correct working line . | 6070100 / 7070100 | Y | Y | 600138 | 5501520? | Electrical / Instrumentation separate CCOAs
Communications and Security
| Communications and Security | Equipment | Stage | Install Equipment | Program / Test | Accept
75.01.01 | Communications and Security | WAN (Antennas, Dishes, Transmission Equipment) | 5% | 80% | 10% | 5% | [5 empty] | ea | ea | Yes | 100% |  |  | 7510100 |  |  | 680380; 680600 | 3001580; 3001609
75.01.02 | Communications and Security | LAN | 5% | 85% | 5% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7510110 |  |  | 660200 | 3001418
75.01.03 | Communications and Security | Telephone Systems | 5% | 70% | 20% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7510120 | 1 |  | 5001760? | 3001526 |  |  | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
75.01.04 | Communications and Security | Radio Frequency Systems | 5% | 70% | 20% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7510120 | 1 |  | 5001760? | 3001526 |  |  | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
75.01.05 | Communications and Security | Weather Monitoring Systems | 5% | 75% | 15% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7510170 | 1 |  | 680586 | 5551020? |  |  | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
75.01.06 | Communications and Security | Entertainment Systems | 5% | 85% | 5% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7510180 | 1 |  | 681005 | 5551025? |  |  | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
75.01.07 | Communications and Security | Security Alarm / CCTV / Access | 5% | 75% | 15% | 5% | [5 empty] | lot | lot | Yes | 100% |  |  | 7520100 | 1 |  | 660160 | 3001422 |  |  | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
| Communications and Security | Cable Pull | Stage / Test | Pull | Test | Gland / Terminate / Cable Tags / Markers | Test | Accept | [9 empty] | No | 0 | [5 empty] | Y | Y | General Instrument installation; Separate CCOA for testing / calibration
75.02.01 | Communications and Security | Fiber Optic | 5% | 30% | 5% | 50% | 5% | 5% |  |  |  | ft | m | Yes | 100% |  |  | 6030100 |  |  | 680210
75.02.02 | Communications and Security | CAT 5 / 6 | 5% | 40% |  | 45% | 5% | 5% |  |  |  | ft | m | Yes | 100%
Painting and Coatings
| Painting and Coatings |  | Blast / Surface Prep | Prime | Final Coat | Accept
81.01.01 | Painting and Coatings | Primer Coat Only | 40% | 50% |  | 10% | [5 empty] | ft2 | m2 | Yes | 100% |  | Note relocated | 8110100 | Y | Y | 690010 | 3001664 | further breakout at Cost Element / SAP Detail Level
81.01.02 | Painting and Coatings | Prime & Paint | 20% | 30% | 40% | 10% | [5 empty] | ft2 | m2 | Yes | 100% | Final coat milestone includes touch up, as required. |  | 8110100 | Y | Y | 690010 | 3001664 | further breakout at Cost Element / SAP Detail Level
81.01.03 | Painting and Coatings | Thermal Spray Aluminum or Zinc (TSA/TSZn) Coating | 50% |  | 40% | 10% | [5 empty] | ft2 | m2 | Yes | 100% | Final coat milestone includes touch up, as required. |  | 8110100 | Y | Y | 690010 | 3001664 | further breakout at Cost Element / SAP Detail Level
81.01.04 | Painting and Coatings | Intumescent Fireproofing | 20% | 20% | 50% | 10% | [5 empty] | ft2 | m2 | Yes | 100% | Final coat milestone includes touch up, as required. |  | 8130100 | Y | Y | 690300 | 3001676 | further breakout at Cost Element / SAP Detail Level
81.01.05 | Painting and Coatings | Galvanizing |  |  |  | 100% | [5 empty] | ft2 | m2 | Yes | 100% | Vendor performed scope |  | 8130100 | Y | Y | 690300 | 3001676 | further breakout at Cost Element / SAP Detail Level
| Painting and Coatings | Structural Fireproofing (cementitious type) | Set Forms | Install Reinforcing & Embeds | Place & Finish | Strip Formwork, Patch, Rub & Finish (if applicable) | Complete Punch List & Accept | [9 empty] | * Rub & Finish made to be as applicable as per Gary Gardner's comments.
81.02.01 | Painting and Coatings | Structural Fireproofing (cementitious type) | 30% | 35% | 10% | 20% | 5% |  |  |  |  | ft2 | m2 | Yes | 100% | This item assumes fireproofing is broken into individual piece marks or small packages for progressing, not the entire scope of fireproofing on a project. | Added Note | 8130100 | Y | Y | 690300 | 3001676 | further breakout at Cost Element / SAP Detail Level
| Painting and Coatings | Module Interconnecting Activities | Complete | Accept
81.03.01 | Painting and Coatings | Paint Touch Up & Punch Items | 90% | 10% | [7 empty] | lot | lot | Yes | 100% |  |  | 8110100 | Y | Y | 690010 | 3001664 | further breakout at Cost Element / SAP Detail Level
81.03.02 | Painting and Coatings | Fireproofing Interconnections | 90% | 10% | [7 empty] | lot | lot | Yes | 100% |  | The Description for milestones using the word "receive" was modified to only use the word "stage" for the avoidance of confusion with initial receipt of materials. - change made based on comments from Patrick Purser | 8130100 | Y | Y | 690300 | 3001676 | see SAP Activity for Patch Joints
Insulation/Refractory
| Insulation/Refractory |  | Place Insulation System | Install Jacketing | Accept
82.01.01 | Insulation/Refractory | Pipe Insulation (mineral wool, cellular glass) | 45% | 45% | 10% | [6 empty] | ft2 | m2 | Yes | 100% |  |  | 8210200 | Y | Y | 690110 | 5562110?
82.01.02 | Insulation/Refractory | Equipment Insulation | 50% | 40% | 10% | [6 empty] | ft2 | m2 | Yes | 100% |  |  | 8210400 | Y | Y | 690130 | 5562120?
82.01.03 | Insulation/Refractory | Cryogenic Insulation (Piping) | 75% | 15% | 10% | [6 empty] | ft2 | m2 | Yes | 100% |  | Cryogenic Insulation added as per Gary Gardner's comments | 8210200 | Y | Y | 690110 | 5562110?
82.01.04 | Insulation/Refractory | Multiple Layer Insulation (Piping) | 65% | 25% | 10% | [6 empty] | ft2 | m2 | Yes | 100% |  | Multi Layer Insulation added as per Gary Gardner's comments | 8210200 | Y | Y | 690110 | 5562110?
82.01.05 | Insulation/Refractory | Insulated valve boxes | 95% |  | 5% | [6 empty] | ea | ea | Yes | 100% |  |  | 8210200 | Y | Y | 690110 | 5562110?
| Insulation/Refractory | Module Interconnecting Activities | Complete | Accept
82.02.01 | Insulation/Refractory | Insulation Completion | 90% | 10% | [7 empty] | lot | lot | Yes | 100% |  |  | 8210200 | Y | Y
Modularization
| Modularization | Module Setting (excluding system interconnection work) | Receive & Offload from Transport | Transport to Installation site | Set in Place & Secure | Accept
83.01.01 | Modularization | Crane Set Module | 20% | 30% | 40% | 10% | [5 empty] | ea | ea | No | 100% |  |  | 8310100 | Y | Y | 600134 | 5501525?
83.01.02 | Modularization | SPMT Set Module | 20% | 50% | 20% | 10% | [5 empty] | lot | lot | No | 100% |  |  | 8310100 | Y | Y |  | 5505130?
| Modularization | Packing & Loadout | Fabricate | Delivery | Installation at Site | [12 empty] | 8705100 |  |  | 690200 | 3001675
83.02.01 | Modularization | Ship Loose Material | 60% | 10% | 30% | [8 empty] | No | 100%
| Demolition | [15 empty] | * General comment - all final activities were changed to be a minimum of 10% as per Steve Laskowski's comment.
| Demolition | Demolition | Excavate | Demolish | Remove for Disposal | Grade | Achieve Compaction | Clear | Accept
84.01.01 | Demolition | Under Ground Concrete Demolition | 10% | 30% | 20% | 10% | 10% | 10% | 10% |  |  | lot | lot | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 8410100 | Y | Y | 600200 | 3000924
84.01.02 | Demolition | Above Ground Concrete Demolition |  | 55% | 25% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 8410100 | Y | Y | 600200 | 3000924
84.01.03 | Demolition | Area Paving (concrete) Demolition |  | 45% | 20% | 15% |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 8410100 | Y | Y | 600200 | 3000924
84.01.04 | Demolition | Structural Steel Demolition |  | 60% | 20% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  |  | 8410100 | Y | Y | 600200 | 3000924
84.01.05 | Demolition | Asphalt Road Demolition (Wearing course only) |  | 40% | 25% | 15% |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  |  | 8410100 | Y | Y | 600200 | 3000924
84.01.06 | Demolition | Road Base Demolition (Base portion only) | 45% |  | 20% | 15% |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 8410100 | Y | Y | 600200 | 3000924
84.01.07 | Demolition | Underground Pipe Demolition | 25% | 45% | 10% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  | Weightings adjusted as per CSA (Civil) comments. | 8410100 | Y | Y | 600200 | 3000924
84.01.08 | Demolition | Above Ground Pipe Demolition |  | 65% | 15% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100% |  |  | 8410100 | Y | Y | 600200 | 3000924
84.01.09 | Demolition | All Piles (Remove) |  | 100% | [7 empty] | lot | lot | Yes | 100% |  |  | 8410100 | Y | Y | 600200 | 3000924
84.01.10 | Demolition | Underground Electrical Demolition | 25% | 45% | 10% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100%
84.01.11 | Demolition | Above Ground Electrical Demolition |  | 65% | 15% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100%
84.01.12 | Demolition | Instrument Demolition |  | 70% | 10% |  |  | 10% | 10% |  |  | lot | lot | Yes | 100%
General Requirements
| General Requirements | Scaffolding | Erect | Maintenance | Dismantle | [12 empty] | 8705100 |  |  | 690200 | 3001675
87.01.01 | General Requirements | Scaffolding | 40% | 20% | 40% | [8 empty] | Yes | 100% | Hours to be distributed as per milestones, but do not include in the project progress calculation
| General Requirements | Material Purchase | RFP/MTO | PO | Material Delivery | [12 empty] | 8705100 |  |  | 690200 | 3001675
87.02.01 | General Requirements | Bulk Material Purchase | 10% | 30% | 60% | [8 empty] | No | 100%
The Description for milestones using the word "receive" was modified to only use the word "stage" for the avoidance of confusion with initial receipt of materials. - change made based on comments from Patrick Purser
| Startup and Commissioning | Pre-Commissioning
| Startup and Commissioning | Pre-Commissioning | Walkdown | Complete Task | Walkdown | [12 empty] | 8810100 |  |  | 690400 | 5565000
88.01.01 | Startup and Commissioning | Pre-commissioning | 5% | 90% | 5% | [8 empty] | Yes | 100%
88.01.02 | Startup and Commissioning | [15 empty] | The Description for milestones using the word "receive" was modified to only use the word "stage" for the avoidance of confusion with initial receipt of materials. - change made based on comments from Patrick Purser
| Startup and Commissioning | Commissioning
Startup and Commissioning
88.02.01 | Startup and Commissioning | [13 empty] | 0% | Milestones and weightings will be dependant on the specific scope of work. A separate progress baseline will be established. |  | 8820100 |  |  | 690500 | 5566100
88.02.02 | Startup and Commissioning | [13 empty] | 0% |  | The Description for milestones using the word "receive" was modified to only use the word "stage" for the avoidance of confusion with initial receipt of materials. - change made based on comments from Patrick Purser
| Startup and Commissioning | Start-up
Startup and Commissioning
88.03.01 | Startup and Commissioning | [13 empty] | 0% | Milestones and weightings will be dependant on the specific scope of work. A separate progress baseline will be established. |  | 8830100 |  |  | 690600 | 5567100
88.03.02 | Startup and Commissioning | [13 empty] | 0% |  | The Description for milestones using the word "receive" was modified to only use the word "stage" for the avoidance of confusion with initial receipt of materials. - change made based on comments from Patrick Purser
Note on C168: Richard Burwell: Can these be consolidated into 1 line as RoC are the same?
Note on C219: Richard Burwell: Can these be consolidated into 1 line as RoC are the same?
Note on F388: Microsoft: Cable tags often get delayed due to being missing/misplaced and tracked as a punch item. Might be better to break them out as a milestone for progressing purposes
Note on F414: Microsoft: Is this tie wrap? Maybe we can rename this to show that instead of adding as a separate milestone
Note on H414: Microsoft: Same comment as above on cable tags

## Extra Work & Delays
Progress Item ID | WBS | ROC Set |  |  | Description | WEEK ENDING DATE(S) | ORIG QTYS | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | APPROVED CHANGES | CONTROL BASE HRS | ML01 | ML02 | ML03 | ML04 | ML05 | ML06 | TOTAL PROGRESS | EARN HOURS | ACTUAL HOURS | COMMENT / NOTE
Progress Item ID | WBS | ROC Set | Module | IWP | Description | [5 empty] | #VALUE! | #VALUE! | #VALUE! | [7 empty] | #VALUE! | 27641
[5 empty] | Extra Work / Delays | [5 empty] | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 27641
K214-CUB-IC-0021 | CUB | 40.28.01 |  |  | EXTRA WORK - ASSIST MAMMOET WITH MODULE INSTALLATION | 06.15.2025 | [15 empty] | 227 | Removed from Actual MH "Setting / Stacking"
| CUB |  |  |  | EXTRA WORK - REMOVING BACKING PLATES | 06.15.2025 06.22.2025 | [15 empty] | 415 | Removed from Actual MH "Ship Loose / Ext. Module Struct. Steel Installation"
| CUB |  |  |  | DELAY - WAITING ON FIREPROOF REMOVAL FROM COLUMNS | 07.13.2025 | [15 empty] | 40 | Removed from Actual MH "Ship Loose / Ext. Module Struct. Steel Installation"
| CUB |  |  |  | EXTRA WORK - FABBING FOR RFI B1LG-K214-RFI-000067-0001 | 07.20.2025 07.27.2025 08.24.2025 | [15 empty] | 293 | Removed from Actual MH "Ship Loose / Ext. Module Struct. Steel Installation"
| CUB |  |  |  | EXTRA WORK - SUPPORT LABOR FOR MATERIAL RELOCATION | 07.20.2025 7.27.2025 08.03.2025 08.10.2025 | [15 empty] | 224.5 | Removed from Actual MH "Ship Loose / Ext. Module Struct. Steel Installation"
| CUB |  |  |  | DELAY - WEATHER (CUB) | 07.27.2025 08.24.2025 09.28.2025 | [15 empty] | 207 | Remove 27MH from Actual MH "Single Weld - PIPE" and 50MH from "Ship Loose / Ext. Module Struct. Steel Installation"
| TFS |  |  |  | DELAY - WEATHER (TFS) | 07.27.2025 | [15 empty] | 52.5 | Remove from Actual MH "Main Steel"
[5 empty] | DELAY - WAITING ON SCAFFOLD | 08.10.2025 08.24.2025 | [15 empty] | 9 | Remove from Actual MH "Single Weld - PIPE"
| TFS |  |  |  | TT109 UNABLE TO BOLT UP BEAMS TO SUPPORTING COLUMNS DUE TO BOLT HOLES NOT LINING UP. | 08.17.2025 | [15 empty] | 47.5
| TFS |  |  |  | TT109 UNABLE TO BOLT UP BEAMS TO SUPPORTING COLUMNS DUE TO BOLT HOLES NOT LINING UP. | 8.21.2025 | [15 empty] | 21.5 | moving beams around per Lilly request.
| TFS |  |  |  | WAREHOUSE | 02.15.2026 02.22.2026 03.01.2026 03.08.2026 03.15.2026 03.20.2026 03.27.2026 | [15 empty] | 4855 | 728.5 hrs WE 03.27.2026
| TFS |  |  |  | OPERATORS | 02.15.2026 02.22.2026 03.01.2026 03.08.2026 03.15.2026 03.20.2026 03.27.2026 | [15 empty] | 2076.5 | 398.75 hrs WE 03.27.2026
| TFS |  |  |  | ORIENTATION | 02.15.2026 02.22.2026 03.01.2026 03.08.2026 03.15.2026 03.20.2026 03.27.2026 | [15 empty] | 1399 | 184 hrs WE 03.27.2026
| TFS |  |  |  | EXTRA WORK | 02.15.2026 02.22.2026 03.01.2026 03.08.2025 03.15.2026 03.20.2026 03.27.2026 | [15 empty] | 3963.5 | 709.75 hrs WE 03.27.2026
| TFS |  |  |  | TOTAL INDIRECTS | 02.22.2026 03.01.2026 03.08.2026 03.15.2026 03.20.2026 03.27.2026 | [15 empty] | 10766 | 1992.25 hrs for WE 03.27.2026
| TFS |  |  |  | STANDBY/WEATHER | 02.22.2026 03.01.2026 03.08.2026 03.15.2026 03.20.2026 | [15 empty] | 2838.5 | 0 WE 03.27.2026 (STDB due to others and weather out)
[5 empty] | PP1 DESCOPE | 03.01.2026 | [15 empty] | 93 | Locating and gathering PP1 material to turn over
| TFS |  |  |  | IFC REVISION | 03.15.2026 03.20.2026 | [15 empty] | 112.5 | 15 WE 03.20.2026
| TFS |  |  |  | SRU Scope | 03.08.2026 | [15 empty] | 566 | Support + Conduit Installed, Rework of EHT, Installed Equipment
| TFS |  |  |  | CHANGE ORDER FOR STEEL SUPPORTS ON TT RACK | 03.08.2026 |  |  | 80 | [12 empty] | 113
| TFS |  |  |  | DELAY - WEATHER (TFS) | 03.08.2026 | [15 empty] | 116
| TFS |  |  |  | SRU scope | 03.15.2026 |  |  | 60' RMC | [12 empty] | 60 | 60' RMC, 24' Strut support installed.
| TFS |  |  |  | WINDOUT - WEATHER (TFS) | 03.16.2026 | [15 empty] | 84
| TFS |  |  |  | OVERHEAD CRANE WORK CAUSED REDIRECT OF WORK | 03.18.2026 | [15 empty] | 9
| TFS |  |  |  | SCAFFOLD MODS IN AREA AND EQUIPMENT (FROM OTHERS) IN THE WAY | 03.19.2026 | [15 empty] | 14
| TFS |  |  |  | SRU CONDUIT, KNOCKOUTS, SUPPORTS | 03.17.2026 |  |  | 40' RMC | [12 empty] | 52
| TFS |  |  |  | SRU CONDUIT, KNOCKOUTS, SUPPORTS | 03.18.2026 |  |  | 60' RMC | [12 empty] | 80
| TFS |  |  |  | SRU LIGHTING CONDUIT, KNOCKOUTS, SUPPORTS | 03.19.2026 |  |  | 75' RMC | [12 empty] | 80
| TFS |  |  |  | SRU LIGHTING CONDUIT, KNOCKOUTS, SUPPORTS | 03.20.2026 |  |  | 60' RMC | [12 empty] | 40
| TFS |  |  |  | SCAFFOLD MODS IN AREA AND EQUIPMENT (FROM OTHERS) IN THE WAY | 03.19.2026 | [15 empty] | 14
| TFS |  |  |  | SRU Scope | 03.29.2026 |  |  | 40' | [12 empty] | 30 | 3/4'' RMC Installed
| TFS |  |  |  | SRU Scope | 03.29.2026 |  |  | 40' | [12 empty] | 20 | 1'' RMC Installed
| TFS |  |  |  | SRU Scope | 03.29.2026 |  |  | 90' | [12 empty] | 80 | 2'' RMC Installed
| TFS |  |  |  | SRU Scope | 03.29.2026 |  |  | 14 | [12 empty] | 57 | Strut Supports for RMC
| TFS |  |  |  | TB Rack Interconnect Plate Swap | 03.29.2026 |  |  | 11 | [12 empty] | 130 | Expansion Plate swap on TB Interconnects
| TFS |  |  |  | TA Work to Go trays | 03.29.2026 |  |  | 130' | [12 empty] | 282 | Installed trays that were designated (Work to go) from mod yard.

## TFS Progress Sheets
K214 - Structural Steel | [26 empty] | PROGRESS PERIOD DATE: 2026-03-27
Progress Item ID | WBS | ROC Set | [6 empty] | Description | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS |  | MILESTONES |  |  |  |  | TOTAL PROGRESS | EARN HOURS | Actual HOURS |  |  | COMMENT / NOTE
[20 empty] | ML01 | ML02 | ML03 | ML04 | ML05
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [5 empty] | 125938.6617 |  | 0 | 183811.6783 |  | Shakeout & Stage | Erect / Install | Complete Bolting / Welding | Accept | Release | 56.33% | 103538.6813 | 74744
Indirects
| TFS | N/A | Weather impact |  |  |  | N/A |  | Indirect hours | - |  | - | - | - | 0 |  | #REF! | #REF! |  | - | - | - | - | - |  | #REF! | #REF!
| TFS | N/A | Ceremonial steel |  |  |  | N/A |  | Indirect hours | - |  | - | - | - | 0 |  | 350 | 350 |  | - | - | - | - | - |  | 350 | #REF!
| TFS | N/A | Remob |  |  |  | N/A |  | Indirect hours | - |  | - | - | - | 0 |  | 837 | 837 |  | - | - | - | - | - |  | 837 | #REF!
[9 empty] | Ship Loose / Ext. Module Struct. Steel Installation | 63030.5153 | -403.1463 | 28213.869 | #DIV/0! |  | 61616.8117 | 1071.5 | 0 | 69825.9523 |  | 10% | 40% | 45% | 5% | 0% | 70.79% | 43621.2482 | 30710.25
K214-TFS-0001 | TFS | 20.01.01 | TFS00A104MM | N.A. | TFS00A104MMCS | K214 | IP-TFS00A104MMCS-K214-030 | 30.TA104-M.F | A-LVL STEEL INSTALLATION ON TA104 | 23 | 0 | 23 | 23 | TN | 437 |  | 0 | 437 |  | 100% | 100% | 100% | 100% | 0% | 100% | 437 | 0
K214-TFS-0002 | TFS | 20.01.01 | TFS00A105MM | N.A. | TFS00A105MMCS | K214 | IP-TFS00A105MMCS-K214-030 | 30.TA105-M.F | A-LVL STEEL INSTALLATION ON TA105 | 37.3 | 0 | 37.3 | 37.3 | TN | 671 |  | 0 | 671 |  | 100% | 100% | 100% | 100% | 0% | 100% | 671 | 0
K214-TFS-0003 | TFS | 20.01.01 | TFS00A106MM | N.A. | TFS00A106MMCS | K214 | IP-TFS00A106MMCS-K214-030 | 30.TA106-M.F | A-LVL STEEL INSTALLATION ON TA106 | 43 | 0 | 43 | 43 | TN | 693 |  | 0 | 693 |  | 100% | 100% | 100% | 100% | 0% | 100% | 693 | 0
K214-TFS-0004 | TFS | 20.01.01 | TFS00A107MM | N.A. | TFS00A107MMCS | K214 | IP-TFS00A107MMCS-K214-030 | 30.TA107-M.F | A-LVL STEEL INSTALLATION ON TA107 | 23.6 | 0 | 23.6 | 23.6 | TN | 459 |  | 0 | 459 |  | 100% | 100% | 100% | 100% | 0% | 100% | 459 | 0
K214-TFS-0005 | TFS | 20.01.01 | TFS00A108MM | N.A. | TFS00A108MMCS | K214 | IP-TFS00A108MMCS-K214-030 | 30.TA108-M.F | A-LVL STEEL INSTALLATION ON TA108 | 42.7 | 0 | 42.7 | 42.7 | TN | 786 |  | 0 | 786 |  | 100% | 100% | 100% | 100% | 0% | 100% | 786 | 0
K214-TFS-0006 | TFS | 20.01.01 | TFS00A109MM | N.A. | TFS00A109MMCS | K214 | IP-TFS00A109MMCS-K214-030 | 30.TA109-M.F | A-LVL STEEL INSTALLATION ON TA109 | 29.69 | 0 | 29.69 | 29.69 | TN | 598 |  | 0 | 598 |  | 100% | 100% | 100% | 100% | 0% | 100% | 598 | 0
K214-TFS-0007 | TFS | 20.01.01 | TFS00A110MM | N.A. | TFS00A110MMCS | K214 | IP-TFS00A110MMCS-K214-030 | 30.TA110-M.F | A-LVL STEEL INSTALLATION ON TA110 | 31.29 | 0 | 31.29 | 31.29 | TN | 590 |  | 0 | 590 |  | 100% | 100% | 100% | 100% | 0% | 100% | 590 | 0
K214-TFS-0008 | TFS | 20.01.01 | TFS00A111MM | N.A. | TFS00A111MMCS | K214 | IP-TFS00A111MMCS-K214-030 | 30.TA111-M.F | A-LVL STEEL INSTALLATION ON TA111 | 29.71 | 0 | 29.71 | 29.71 | TN | 556.33 |  | 0 | 556.33 |  | 100% | 100% | 100% | 100% | 0% | 100% | 556.33 | 0
K214-TFS-0009 | TFS | 20.01.01 | TFS00A112MM | N.A. | TFS00A112MMCS | K214 | IP-TFS00A112MMCS-K214-030 | 30.TA112-M.F | A-LVL STEEL INSTALLATION ON TA112 | 28 | 0 | 28 | 0 | TN | 518 |  | 0 | 518 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0010 | TFS | 20.01.01 | TFS00A101MM | N.A. | TFS00A101MMCS | K214 | IP-TFS00A101MMCS-K214-030 | 30.TA101-M.F | A-LVL STEEL INSTALLATION ON TA101 | 18.48 | 0 | 18.48 | 18.48 | TN | 365 |  | 0 | 365 |  | 100% | 100% | 100% | 100% | 0% | 100% | 365 | 0
K214-TFS-0011 | TFS | 20.01.01 | TFS00A102MM | N.A. | TFS00A102MMCS | K214 | IP-TFS00A102MMCS-K214-030 | 30.TA102-M.F | A-LVL STEEL INSTALLATION ON TA102 | 42.4 | 0 | 42.4 | 42.4 | TN | 849 |  | 0 | 849 |  | 100% | 100% | 100% | 100% | 0% | 100% | 849 | 0
K214-TFS-0012 | TFS | 20.01.01 | TFS00A103MM | N.A. | TFS00A103MMCS | K214 | IP-TFS00A103MMCS-K214-030 | 30.TA103-M.F | A-LVL STEEL INSTALLATION ON TA103 | 39.832 | 0 | 39.832 | 39.832 | TN | 770 |  | 0 | 770 |  | 100% | 100% | 100% | 100% | 0% | 100% | 770 | 0
K214-TFS-0024 | TFS | 20.01.01 | TFS00B101MM | N.A. | TFS00B101MMCS | K214 | IP-TFS00B101MMCS-K214-030 | 30.TB101-M.F | A-LVL STEEL INSTALLATION ON TB101 | 42.492 | 0 | 42.492 | 42.492 | TN | 774.358 |  | 0 | 774.358 |  | 100% | 100% | 100% | 100% | 0% | 100% | 774.358 | 0
K214-TFS-0025 | TFS | 20.01.01 | TFS00B102MM | N.A. | TFS00B102MMCS | K214 | IP-TFS00B102MMCS-K214-030 | 30.TB102-M.F | A-LVL STEEL INSTALLATION ON TB102 | 37.2578 | 0 | 37.2578 | 37.2578 | TN | 708.958 |  | 0 | 708.958 |  | 100% | 100% | 100% | 100% | 0% | 100% | 708.958 | 0
K214-TFS-0026 | TFS | 20.01.01 | TFS00B103MM | N.A. | TFS00B103MMCS | K214 | IP-TFS00B103MMCS-K214-030 | 30.TB103-M.F | A-LVL STEEL INSTALLATION ON TB103 | 36.1093 | 0 | 36.1093 | 36.1093 | TN | 623.578 |  | 0 | 623.578 |  | 100% | 100% | 100% | 100% | 0% | 100% | 623.578 | 0
K214-TFS-0027 | TFS | 20.01.01 | TFS00B104MM | N.A. | TFS00B104MMCS | K214 | IP-TFS00B104MMCS-K214-030 | 30.TB104-M.F | A-LVL STEEL INSTALLATION ON TB104 | 27.6693 | 0 | 27.6693 | 27.6693 | TN | 499.586 |  | 0 | 499.586 |  | 100% | 100% | 100% | 100% | 0% | 100% | 499.586 | 0
K214-TFS-0028 | TFS | 20.01.01 | TFS00B105MM | N.A. | TFS00B105MMCS | K214 | IP-TFS00B105MMCS-K214-030 | 30.TB105-M.F | A-LVL STEEL INSTALLATION ON TB105 | 28.6395 | 0 | 28.6395 | 28.6395 | TN | 487.822 |  | 0 | 487.822 |  | 100% | 100% | 100% | 100% | 0% | 100% | 487.822 | 0
K214-TFS-0029 | TFS | 20.01.01 | TFS00B106MM | N.A. | TFS00B106MMCS | K214 | IP-TFS00B106MMCS-K214-030 | 30.TB106-M.F | A-LVL STEEL INSTALLATION ON TB106 | 42.7913 | 0 | 42.7913 | 42.7913 | TN | 760.622 |  | 0 | 760.622 |  | 100% | 100% | 100% | 100% | 0% | 100% | 760.622 | 0
K214-TFS-0030 | TFS | 20.01.01 | TFS00B107MM | N.A. | TFS00B107MMCS | K214 | IP-TFS00B107MMCS-K214-030 | 30.TB107-M.F | A-LVL STEEL INSTALLATION ON TB107 | 19.8403 | 0 | 19.8403 | 19.8403 | TN | 356.202 |  | 0 | 356.202 |  | 100% | 100% | 100% | 100% | 0% | 100% | 356.202 | 0
K214-TFS-0031 | TFS | 20.01.01 | TFS00B108MM | N.A. | TFS00B108MMCS | K214 | IP-TFS00B108MMCS-K214-030 | 30.TB108-M.F | A-LVL STEEL INSTALLATION ON TB108 | 30.1954 | 0 | 30.1954 | 30.1954 | TN | 566.979 |  | 0 | 566.979 |  | 100% | 100% | 100% | 100% | 0% | 100% | 566.979 | 0
K214-TFS-0032 | TFS | 20.01.01 | TFS00B109MM | N.A. | TFS00B109MMCS | K214 | IP-TFS00B109MMCS-K214-030 | 30.TB109-M.F | A-LVL STEEL INSTALLATION ON TB109 | 26.1127 | 0 | 26.1127 | 26.1127 | TN | 480.206 |  | 0 | 480.206 |  | 100% | 100% | 100% | 100% | 0% | 100% | 480.206 | 0
K214-TFS-0033 | TFS | 20.01.01 | TFS00T101MM | N.A. | TFS00T101MMCS | K210 | IP-TFS00T101MMCS-K214-030 | 30.TT101-M.F | A-LVL STEEL INSTALLATION ON TT101 | 0 | 4.28 | 4.28 | 0 | TN | 143.1073 |  | 0 | 143.1073 |  | 100% | 100% | 100% | 100% | 0% | 100% | 143.1073
K214-TFS-0067 | TFS | 20.01.01 | TFS00T102MM | N.A. | TFS00T102MMCS | K214 | IP-TFS00T102MMCS-K214-030 | 30.TT102-M.F | A-LVL STEEL INSTALLATION ON TT102 | 17 |  | 17 | 17 | TN |  |  |  | 338 |  | 100% | 100% | 100% | 100% | 0% | 100% | 338
K214-TFS-0034 | TFS | 20.01.01 | TFS00T103MM | N.A. | TFS00T103MMCS | K210 | IP-TFS00T103MMCS-K214-030 | 30.TT103-M.F | A-LVL STEEL INSTALLATION ON TT103 | 0 | 11.752 | 11.752 | 0 | TN | 350.3114 | 30 | 0 | 350.3114 |  | 100% | 100% | 100% | 100% | 0% | 100% | 350.3114 | 56
K214-TFS-0035 | TFS | 20.01.01 | TFS00T104MM | N.A. | TFS00T104MMCS | K210 | IP-TFS00T104MMCS-K214-030 | 30.TT104-M.F | A-LVL STEEL INSTALLATION ON TT104 | 0 | 2.706 | 2.706 | 0 | TN | 68.8614 |  | 0 | 68.8614 |  | 100% | 100% | 100% | 100% | 0% | 100% | 68.8614 | 25
K214-TFS-0036 | TFS | 20.01.01 | TFS00T105MM | N.A. | TFS00T105MMCS | K210 | IP-TFS00T105MMCS-K214-030 | 30.TT105-M.F | A-LVL STEEL INSTALLATION ON TT105 | 0 | 11.804 | 11.804 | 0 | TN | 353.0812 |  | 0 | 353.0812 |  | 100% | 100% | 100% | 100% | 0% | 100% | 353.0812 | 0
K214-TFS-0037 | TFS | 20.01.01 | TFS00T106MM | N.A. | TFS00T106MMCS | K210 | IP-TFS00T106MMCS-K214-030 | 30.TT106-M.F | A-LVL STEEL INSTALLATION ON TT106 | 0 | 2.706 | 2.706 | 0 | TN | 68.8614 |  | 0 | 68.8614 |  | 100% | 100% | 100% | 100% | 0% | 100% | 68.8614 | 0
K214-TFS-0038 | TFS | 20.01.01 | TFS00T107MM | N.A. | TFS00T107MMCS | K214 | IP-TFS00T107MMCS-K214-030 | 30.TT107-M.F | A-LVL STEEL INSTALLATION ON TT107 | 16 |  | 16 | 15.95 | TN |  |  | 0 | 320 |  | 100% | 100% | 100% | 100% | 0% | 100% | 320 | 0
K214-TFS-0039 | TFS | 20.01.01 | TFS00T108MM | N.A. | TFS00T108MMCS | K210 | IP-TFS00T108MMCS-K214-030 | 30.TT108-M.F | A-LVL STEEL INSTALLATION ON TT108 | 0 | 4.28 | 4.28 | 0 | TN | 131.1468 | 37.25 | 0 | 168.3968 |  | 100% | 100% | 100% | 100% | 0% | 100% | 168.3968 | 73.5
K214-TFS-0040 | TFS | 20.01.01 | TFS00T109MM | N.A. | TFS00T109MMCS | K210 | IP-TFS00T109MMCS-K214-030 | 30.TT109-M.F | A-LVL STEEL INSTALLATION ON TT109 | 0 | 13.8 | 13.8 | 0 | TN | 411.6225 | 129 | 0 | 540.6225 |  | 100% | 100% | 100% | 100% | 0% | 100% | 540.6225 | 48
K214-TFS-0041 | TFS | 20.01.01 | TFS00T110MM | N.A. | TFS00T110MMCS | K210 | IP-TFS00T110MMCS-K214-030 | 30.TT110-M.F | A-LVL STEEL INSTALLATION ON TT110 | 0 |  | 0 | 0 | TN | 0 |  | 0 | 0 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  |  | TT110 HAS NO A LEVEL STEEL IT'S A LEVEL IS TT108
K214-TFS-0043 | TFS | 20.01.01 | TFS00E141MM | N.A. | TFS00E141MSCS | K210 | IP-TFS00E141MSCS-K214-030 | 30.TE141-M.F | Assembly of A level Steel for Module TE141 | 0 | 16.6267 | 16.6267 | 0 | TN | 660.31 |  | 0 | 660.31 |  | 100% | 100% | 100% | 0% | 0% | 95% | 627.2945 | 0 |  |  | Piers became available and module was set (should have been claimed out previously but got missed)
K214-TFS-0044 | TFS | 20.01.01 | TFS00E142MM | N.A. | TFS00E142MSCS | K210 | IP-TFS00E142MSCS-K214-030 | 30.TE142-M.F | MS STEEL ON TE142 | 0 | 11.5009 | 11.5009 | 0 | TN | 469.55 |  | 0 | 469.55 |  | 100% | 60% | 30% | 0% | 0% | 47.5% | 223.0362 | 0
K214-TFS-0045 | TFS | 20.01.01 | TFS00E143MM | N.A. | TFS00E143MSCS | K210 | IP-TFS00E143MSCS-K214-030 | 30.TE143-M.F | MS STEEL ON TE143 | 0 | 7.3981 | 7.3981 | 0 | TN | 323.05 |  | 0 | 323.05 |  | 100% | 60% | 30% | 0% | 0% | 47.5% | 153.4487 | 0
K214-TFS-0046 | TFS | 20.01.01 | TFS00K101MM | N.A. | TFS00K101MMCS | K210 | IP-TFS00K101MMCS-K214-030 | 30.TK101-M.F | A-LVL STEEL INSTALLATION ON TK101 | 15.829 | 0 | 15.829 | 15.829 | TN | 526.907 |  | 0 | 526.907 |  | 100% | 100% | 100% | 100% | 0% | 100% | 526.907 | 0
K214-TFS-0047 | TFS | 20.01.01 | TFS00K102MM | N.A. | TFS00K102MMCS | K214 | IP-TFS00K102MMCS-K214-030 | 30.TK102-M.F | A-LVL STEEL INSTALLATION ON TK102 | 14 | 0 | 14 | 14 | TN | 227.66 |  | 0 | 227.66 |  | 100% | 100% | 100% | 100% | 0% | 100% | 227.66 | 0
K214-TFS-0048 | TFS | 20.01.01 | TFS00K103MM | N.A. | TFS00K103MMCS | K210 | IP-TFS00K103MMCS-K214-030 | 30.TK103-M.F | A-LVL STEEL INSTALLATION ON TK103 | 2.762 | 0 | 2.762 | 2.762 | TN | 71.7251 |  | 0 | 71.7251 |  | 100% | 100% | 100% | 100% | 0% | 100% | 71.7251 | 0
K214-TFS-0049 | TFS | 20.01.01 | TFS00K104MM | N.A. | TFS00K104MMCS | K210 | IP-TFS00K104MMCS-K214-030 | 30.TK104-M.F | A-LVL STEEL INSTALLATION ON TK104 | 11.275 | 0 | 11.275 | 11.275 | TN | 333.5698 |  | 0 | 333.5698 |  | 100% | 100% | 100% | 100% | 0% | 100% | 333.5698 | 0
K214-TFS-0050 | TFS | 20.01.01 | TFS00K105MM | N.A. | TFS00K105MMCS | K210 | IP-TFS00K105MMCS-K214-030 | 30.TK105-M.F | A-LVL STEEL INSTALLATION ON TK105 | 2.816 | 0 | 2.816 | 2.816 | TN | 77.1844 |  | 0 | 77.1844 |  | 100% | 100% | 100% | 100% | 0% | 100% | 77.1844 | 0
K214-TFS-0051 | TFS | 20.01.01 | TFS00K106MM | N.A. | TFS00K106MMCS | K210 | IP-TFS00K106MMCS-K214-030 | 30.TK106-M.F | A-LVL STEEL INSTALLATION ON TK106 | 11.265 | 0 | 11.265 | 11.265 | TN | 332.957 |  | 0 | 332.957 |  | 100% | 100% | 100% | 100% | 0% | 100% | 332.957 | 0
K214-TFS-0052 | TFS | 20.01.01 | TFS00K107MM | N.A. | TFS00K107MMCS | K210 | IP-TFS00K107MMCS-K214-030 | 30.TK107-M.F | A-LVL STEEL INSTALLATION ON TK107 | 5.794 | 0 | 5.794 | 5.794 | TN | 158.718 |  | 0 | 158.718 |  | 100% | 100% | 100% | 100% | 0% | 100% | 158.718 | 0
K214-TFS-0053 | TFS | 20.01.01 | TFS00K108MM | N.A. | TFS00K108MMCS | K214 | IP-TFS00K108MMCS-K214-030 | 30.TK108-M.F | A-LVL STEEL INSTALLATION ON TK108 | 14 | 0 | 14 | 14 | TN | 205.3 |  | 0 | 205.3 |  | 100% | 100% | 100% | 100% | 0% | 100% | 205.3 | 0
K214-TFS-0054 | TFS | 20.01.01 | TFS00K109MM | N.A. | TFS00K109MMCS | K210 | IP-TFS00K109MMCS-K214-030 | 30.TK109-M.F | A-LVL STEEL INSTALLATION ON TK109 | 2.89 | 0 | 2.89 | 2.89 | TN | 77.0615 |  | 0 | 77.0615 |  | 100% | 100% | 100% | 100% | 0% | 100% | 77.0615 | 0
K214-TFS-0055 | TFS | 20.01.01 | TFS00K110MM | N.A. | TFS00K110MMCS | K210 | IP-TFS00K110MMCS-K214-030 | 30.TK110-M.F | A-LVL STEEL INSTALLATION ON TK110 | 17.382 | 0 | 17.382 | 17.382 | TN | 577.3807 |  | 0 | 577.3807 |  | 100% | 100% | 100% | 100% | 0% | 100% | 577.3807 | 0
K214-TFS-0056 | TFS | 20.01.01 | TFS00V101MM | N.A. | TFS00V101MMCS | K210 | IP-TFS00V101MMCS-K214-030 | 30.TV101-M.F | A-LVL STEEL INSTALLATION ON TV101 | 11.216 | 0 | 11.216 | 11.216 | TN | 330.2208 |  | 0 | 330.2208 |  | 100% | 100% | 100% | 100% | 0% | 100% | 330.2208 | 0
K214-TFS-0057 | TFS | 20.01.01 | TFS00V102MM | N.A. | TFS00V102MMCS | K210 | IP-TFS00V102MMCS-K214-030 | 30.TV102-M.F | A-LVL STEEL INSTALLATION ON TV102 | 5.232 | 0 | 5.232 | 5.232 | TN | 133.2499 |  | 0 | 133.2499 |  | 100% | 100% | 100% | 100% | 0% | 100% | 133.2499 | 0
K214-TFS-0058 | TFS | 20.01.01 | TFS00V103MM | N.A. | TFS00V103MMCS | K210 | IP-TFS00V103MMCS-K214-030 | 30.TV103-M.F | A-LVL STEEL INSTALLATION ON TV103 | 9.396 | 0 | 9.396 | 9.396 | TN | 263.274 |  | 0 | 263.274 |  | 100% | 100% | 100% | 100% | 0% | 100% | 263.274 | 0
K214-TFS-0059 | TFS | 20.01.01 | TFS00W101MM | N.A. | TFS00W101MMCS | K210 | IP-TFS00W101MMCS-K214-030 | 30.TW101-M.F | A-LVL STEEL INSTALLATION ON TW101 | 14.705 | 0 | 14.705 | 14.705 | TN | 448.665 |  | 0 | 448.665 |  | 100% | 100% | 100% | 100% | 0% | 100% | 448.665 | 0
K214-TFS-0060 | TFS | 20.01.01 | TFS00W102MM | N.A. | TFS00W102MMCS | K210 | IP-TFS00W102MMCS-K214-030 | 30.TW102-M.F | A-LVL STEEL INSTALLATION ON TW102 | 11.369 | 0 | 11.369 | 11.369 | TN | 352.13 |  | 0 | 352.13 |  | 100% | 100% | 100% | 100% | 0% | 100% | 352.13 | 0
K214-TFS-0061 | TFS | 20.01.01 | TFS00W103MM | N.A. | TFS00W103MMCS | K210 | IP-TFS00W103MMCS-K214-030 | 30.TW103-M.F | A-LVL STEEL INSTALLATION ON TW103 | 16.917 | 0 | 16.917 | 16.917 | TN | 569.8662 |  | 0 | 569.8662 |  | 100% | 100% | 100% | 100% | 0% | 100% | 569.8662 | 0
K214-TFS-0062 | TFS | 20.01.01 | TFS00W104MM | N.A. | TFS00W104MMCS | K214 | IP-TFS00W104MMCS-K214-030 | 30.TW104-M.F | A-LVL STEEL INSTALLATION ON TW104 | 48.6975 | 0 | 48.6975 | 0 | TN | 0 |  | 0 | 0 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-0063 | TFS | 20.01.01 | TFS00W105MM | N.A. | TFS00W105MMCS | K214 | IP-TFS00W105MMCS-K214-030 | 30.TW105-M.F | A-LVL STEEL INSTALLATION ON TW105 | 37.6462 | 0 | 37.6462 | 0 | TN | 0 |  | 0 | 0 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-0064 | TFS | 20.01.01 | TFS00W106MM | N.A. | TFS00W106MMCS | K210 | IP-TFS00W106MMCS-K214-030 | 30.TW106-M.F | A-LVL STEEL INSTALLATION ON TW106 | 2.6 | 0 | 2.6 | 2.6 | TN | 101.6979 |  | 0 | 101.6979 |  | 100% | 100% | 100% | 100% | 0% | 100% | 101.6979 | 0
K214-TFS-0068 | TFS | 20.01.01 | TFS00S101MM | N.A. | TFS00S101MMCS | K214 | IP-TFS00S101MMCS-K214-030 | 30.TS101-M.F | A-LVL STEEL INSTALLATION ON TS101 | 26.16 | 0 | 26.16 | 24.852 | TN |  |  |  | 502 |  | 100% | 100% | 100% | 0% | 0% | 95% | 476.9 | 0
K214-TFS-0069 | TFS | 20.01.01 | TFS00D101MM | N.A. | TFS00D101MSCS |  | IP-TFS00D101MSCS-K214-030 | 30.TD101-M.F | Assembly of A Level Steel for Module TD101 | 3.8714 | 0 | 3.8714 | 3.8714 | TN | 148.2298 |  | 0 | 148.2298 |  | 100% | 100% | 100% | 100% | 0% | 100% | 148.2298 | 0
K214-TFS-0070 | TFS | 20.01.01 | TFS00D102MM | N.A. | TFS00D102MSCS | K210 | IP-TFS00D102MSCS-K214-030 | 30.TD102-M.F | MS STEEL ON TD102 | 6.4026 | 0 | 6.4026 | 2.0648 | TN | 274.1846 |  | 0 | 274.1846 |  | 50% | 40% | 25% | 0% | 0% | 32.25% | 88.4245 | 0
K214-TFS-0071 | TFS | 20.01.01 | TFS00D103MM | N.A. | TFS00D103MSCS | K210 | IP-TFS00D103MSCS-K214-030 | 30.TD103-M.F | Assembly of A Level Steel for Module TD103 | 4.6945 | 0 | 4.6945 |  | TN | 180.1327 |  | 0 | 180.1327 |  | 100% | 100% | 100% | 100% | 0% | 100% | 180.1327 | 0
K214-TFS-0072 | TFS | 20.01.01 | TFS00D104MM | N.A. | TFS00D104MSCS | K210 | IP-TFS00D104MSCS-K214-030 | 30.TD104-M.F | MS STEEL ON TD104 | 4.0553 | 0 | 4.0553 |  | TN | 163.9425 |  | 0 | 163.9425 |  | 50% | 40% | 25% | 0% | 0% | 32.25% | 52.8714 | 0
K214-TFS-1369 | TFS | 20.01.01 | TFS00D105MM | N.A. |  |  |  |  | Assembly of A Level Steel for Module TD105 | 2.088 | 0 | 2.088 |  | TN | 60.762 |  |  | 60.762 |  | 100% | 100% | 100% | 100% | 0% | 100% | 60.762 | 0 |  |  | Split A-LVL into separate record
K214-TFS-0073 | TFS | 20.01.01 | TFS00D105MM | N.A. | TFS00D105MSCS | K210 | IP-TFS00D105MSCS-K214-030 | 30.TD105-M.F | MS STEEL ON TD105 | 1.701 | 0 | 1.701 |  | TN | 100.762 |  | 0 | 100.762 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 |  |  | Split A-LVL into separate record
K214-TFS-0074 | TFS | 20.01.01 | TFS00D106MM | N.A. | TFS00D106MSCS | K210 | IP-TFS00D106MSCS-K214-030 | 30.TD106-M.F | MS STEEL ON TD106 | 8.3352 | 0 | 8.3352 |  | TN | 382.7438 |  | 0 | 382.7438 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0075 | TFS | 20.01.01 | TFS00D107MM | N.A. | TFS00D107MSCS | K210 | IP-TFS00D107MSCS-K214-030 | 30.TD107-M.F | Assembly of A Level Steel for Module TD107 | 2.871 | 0 | 2.871 |  | TN | 104.7809 |  | 0 | 104.7809 |  | 100% | 100% | 100% | 100% | 0% | 100% | 104.7809 | 0
K214-TFS-0076 | TFS | 20.01.01 | TFS00D108MM | N.A. | TFS00D108MSCS | K210 | IP-TFS00D108MSCS-K214-030 | 30.TD108-M.F | MS STEEL ON TD108 | 3.1565 | 0 | 3.1565 |  | TN | 137.9167 |  | 0 | 137.9167 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0077 | TFS | 20.01.01 | TFS00D109MM | N.A. | TFS00D109MSCS | K210 | IP-TFS00D109MSCS-K214-030 | 30.TD109-M.F | MS STEEL ON TD109 | 3.2203 | 0 | 3.2203 |  | TN | 116.1025 |  | 0 | 116.1025 |  | 80% | 65% | 65% | 0% | 0% | 63.25% | 73.4348 | 0
K214-TFS-0078 | TFS | 20.01.01 | TFS00D110MM | N.A. | TFS00D110MSCS | K210 | IP-TFS00D110MSCS-K214-030 | 30.TD110-M.F | MS STEEL ON TD110 | 0.44089 | 0 | 0.44089 |  | TN | 20.1895 |  | 0 | 20.1895 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0079 | TFS | 20.01.01 | TFS00D113MM | N.A. | TFS00D113MSCS | K214 | IP-TFS00D113MSCS-K214-030 | 30.TD113-M.F | MS STEEL ON TD113 | 16.3846 | 0 | 16.3846 |  | TN | 678.9668 |  | 0 | 678.9668 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0080 | TFS | 20.01.01 | TFS00D114MM | N.A. | TFS00D114MSCS | K210 | IP-TFS00D114MSCS-K214-030 | 30.TD114-M.F | MS STEEL ON TD114 | 4.097 | 0 | 4.097 |  | TN | 156.5442 |  | 0 | 156.5442 |  | 100% | 80% | 50% | 0% | 0% | 64.5% | 100.971 | 0
K214-TFS-0081 | TFS | 20.01.01 | TFS00D115MM | N.A. | TFS00D115MSCS | K210 | IP-TFS00D115MSCS-K214-030 | 30.TD115-M.F | MS STEEL ON TD115 | 0.826 | 0 | 0.826 |  | TN | 38.3644 |  | 0 | 38.3644 |  | 100% | 80% | 50% | 0% | 0% | 64.5% | 24.7451 | 0
K214-TFS-0082 | TFS | 20.01.01 | TFS00D116MM | N.A. | TFS00D116MSCS | K210 | IP-TFS00D116MSCS-K214-030 | 30.TD116-M.F | MS STEEL ON TD116 | 2.591 | 0 | 2.591 |  | TN | 86.3757 |  | 0 | 86.3757 |  | 100% | 80% | 50% | 0% | 0% | 64.5% | 55.7123 | 0
K214-TFS-0083 | TFS | 20.01.01 | TFS00D117MM | N.A. | TFS00D117MSCS | K210 | IP-TFS00D117MSCS-K214-030 | 30.TD117-M.F | MS STEEL ON TD117 | 0.88 | 0 | 0.88 |  | TN | 41.1259 |  | 0 | 41.1259 |  | 100% | 80% | 100% | 0% | 0% | 87% | 35.7795 | 0
K214-TFS-0084 | TFS | 20.01.01 | TFS00D118MM | N.A. | TFS00D118MSCS | K214 | IP-TFS00D118MSCS-K214-030 | 30.TD118-M.F | MS STEEL ON TD118 | 17.3539 | 0 | 17.3539 |  | TN | 721.9771 |  | 0 | 721.9771 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0085 | TFS | 20.01.01 | TFS00D119MM | N.A. | TFS00D119MSCS | K210 | IP-TFS00D119MSCS-K214-030 | 30.TD119-M.F | MS STEEL ON TD119 | 7.2168 | 0 | 7.2168 |  | TN | 295.4963 |  | 0 | 295.4963 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0086 | TFS | 20.01.01 | TFS00D120MM | N.A. | TFS00D120MSCS | K210 | IP-TFS00D120MSCS-K214-030 | 30.TD120-M.F | MS STEEL ON TD120 | 6.501 | 0 | 6.501 |  | TN | 274.1439 |  | 0 | 274.1439 |  | 50% | 30% | 20% | 0% | 0% | 26% | 71.2774 | 0
K214-TFS-0087 | TFS | 20.01.01 | TFS00D121MM | N.A. | TFS00D121MSCS | K210 | IP-TFS00D121MSCS-K214-030 | 30.TD121-M.F | MS STEEL ON TD121 | 3.807 | 0 | 3.807 |  | TN | 174.5742 |  | 0 | 174.5742 |  | 50% | 30% | 20% | 0% | 0% | 26% | 45.3893 | 0
K214-TFS-0088 | TFS | 20.01.01 | TFS00D122MM | N.A. | TFS00D122MSCS | K210 | IP-TFS00D122MSCS-K214-030 | 30.TD122-M.F | MS STEEL ON TD122 | 3.527 | 0 | 3.527 |  | TN | 150.9918 |  | 0 | 150.9918 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0089 | TFS | 20.01.01 | TFS00E103MM | N.A. | TFS00E103MSCS | K210 | IP-TFS00E103MSCS-K214-030 | 30.TE103-M.F | MS STEEL ON TE103 | 4.3977 | 0 | 4.3977 |  | TN | 158.9578 |  | 0 | 158.9578 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0090 | TFS | 20.01.01 | TFS00E104MM | N.A. | TFS00E104MSCS | K210 | IP-TFS00E104MSCS-K214-030 | 30.TE104-M.F | MS STEEL ON TE104 | 1.4727 | 0 | 1.4727 |  | TN | 69.1408 |  | 0 | 69.1408 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0091 | TFS | 20.01.01 | TFS00E105MM | N.A. | TFS00E105MSCS | K210 | IP-TFS00E105MSCS-K214-030 | 30.TE105-M.F | MS STEEL ON TE105 | 2.0607 | 0 | 2.0607 |  | TN | 72.4071 |  | 0 | 72.4071 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0092 | TFS | 20.01.01 | TFS00E106MM | N.A. | TFS00E106MSCS | K210 | IP-TFS00E106MSCS-K214-030 | 30.TE106-M.F | MS STEEL ON TE106 | 0.27153 | 0 | 0.27153 |  | TN | 12.0063 |  | 0 | 12.0063 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0093 | TFS | 20.01.01 | TFS00E107MM | N.A. | TFS00E107MSCS | K210 | IP-TFS00E107MSCS-K214-030 | 30.TE107-M.F | MS STEEL ON TE107 | 3.6743 | 0 | 3.6743 |  | TN | 137.0675 |  | 0 | 137.0675 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0094 | TFS | 20.01.01 | TFS00E108MM | N.A. | TFS00E108MSCS | K210 | IP-TFS00E108MSCS-K214-030 | 30.TE108-M.F | MS STEEL ON TE108 | 0.71403 | 0 | 0.71403 |  | TN | 33.0886 |  | 0 | 33.0886 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0095 | TFS | 20.01.01 | TFS00E109MM | N.A. | TFS00E109MSCS | K210 | IP-TFS00E109MSCS-K214-030 | 30.TE109-M.F | MS STEEL ON TE109 | 3.1185 | 0 | 3.1185 |  | TN | 109.7577 |  | 0 | 335 |  | 100% | 95% | 95% | 30% | 0% | 92.25% | 309.0375 | 0
K214-TFS-0096 | TFS | 20.01.01 | TFS00E110MM | N.A. | TFS00E110MSCS | K210 | IP-TFS00E110MSCS-K214-030 | 30.TE110-M.F | MS STEEL ON TE110 | 0.20605 | 0 | 0.20605 |  | TN | 9.1108 |  | 0 | 175.781 |  | 100% | 65% | 60% | 15% | 0% | 63.75% | 112.0604 | 0 |  |  | Original hrs not accuate for all the ship loose steel
K214-TFS-0097 | TFS | 20.01.01 | TFS00E111MM | N.A. | TFS00E111MSCS | K210 | IP-TFS00E111MSCS-K214-030 | 30.TE111-M.F | MS STEEL ON TE111 | 3.0155 | 0 | 3.0155 |  | TN | 96.1788 |  | 0 | 96.1788 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0098 | TFS | 20.01.01 | TFS00E112MM | N.A. | TFS00E112MSCS | K210 | IP-TFS00E112MSCS-K214-030 | 30.TE112-M.F | MS STEEL ON TE112 | 2.3849 | 0 | 2.3849 |  | TN | 111.4177 |  | 0 | 111.4177 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0099 | TFS | 20.01.01 | TFS00E113MM | N.A. | TFS00E113MSCS | K210 | IP-TFS00E113MSCS-K214-030 | 30.TE113-M.F | MS STEEL ON TE113 | 3.4847 | 0 | 3.4847 |  | TN | 127.6843 |  | 0 | 127.6843 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0100 | TFS | 20.01.01 | TFS00E114MM | N.A. | TFS00E114MSCS | K210 | IP-TFS00E114MSCS-K214-030 | 30.TE114-M.F | MS STEEL ON TE114 | 2.0659 | 0 | 2.0659 |  | TN | 97.968 |  | 0 | 97.968 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0101 | TFS | 20.01.01 | TFS00E115MM | N.A. | TFS00E115MSCS | K210 | IP-TFS00E115MSCS-K214-030 | 30.TE115-M.F | MS STEEL ON TE115 | 3.3348 | 0 | 3.3348 |  | TN | 111.6957 |  | 0 | 111.6957 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0102 | TFS | 20.01.01 | TFS00E116MM | N.A. | TFS00E116MSCS | K210 | IP-TFS00E116MSCS-K214-030 | 30.TE116-M.F | MS STEEL ON TE116 | 0.62988 | 0 | 0.62988 |  | TN | 29.0798 |  | 0 | 29.0798 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0103 | TFS | 20.01.01 | TFS00E117MM | N.A. | TFS00E117MSCS | K210 | IP-TFS00E117MSCS-K214-030 | 30.TE117-M.F | MS STEEL ON TE117 | 3.2618 | 0 | 3.2618 |  | TN | 117.3504 |  | 0 | 117.3504 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0104 | TFS | 20.01.01 | TFS00E118MM | N.A. | TFS00E118MSCS | K210 | IP-TFS00E118MSCS-K214-030 | 30.TE118-M.F | MS STEEL ON TE118 | 0.41516 | 0 | 0.41516 |  | TN | 19.4409 |  | 0 | 19.4409 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0105 | TFS | 20.01.01 | TFS00E119MM | N.A. | TFS00E119MSCS | K210 | IP-TFS00E119MSCS-K214-030 | 30.TE119-M.F | MS STEEL ON TE119 | 2.6467 | 0 | 2.6467 |  | TN | 89.4046 |  | 0 | 89.4046 |  | 100% | 100% | 100% | 100% | 0% | 100% | 89.4046 | 0
K214-TFS-0106 | TFS | 20.01.01 | TFS00E120MM | N.A. | TFS00E120MSCS | K210 | IP-TFS00E120MSCS-K214-030 | 30.TE120-M.F | MS STEEL ON TE120 | 0.19871 | 0 | 0.19871 |  | TN | 10.2071 |  | 0 | 10.2071 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0107 | TFS | 20.01.01 | TFS00E123MM | N.A. | TFS00E123MSCS | K214 | IP-TFS00E123MSCS-K214-030 | 30.TE123-M.F | MS STEEL ON TE123 | 18.029 | 0 | 18.029 |  | TN | 729.4702 |  | 0 | 729.4702 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0108 | TFS | 20.01.01 | TFS00E126MM | N.A. | TFS00E126MSCS | K210 | IP-TFS00E126MSCS-K214-030 | 30.TE126-M.F | MS STEEL ON TE126 | 6.2151 | 0 | 6.2151 |  | TN | 267.1904 |  | 0 | 267.1904 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0109 | TFS | 20.01.01 | TFS00E128MM | N.A. | TFS00E128MSCS | K210 | IP-TFS00E128MSCS-K214-030 | 30.TE128-M.F | MS STEEL ON TE128 | 0.98784 | 0 | 0.98784 |  | TN | 47.2487 |  | 0 | 47.2487 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0110 | TFS | 20.01.01 | TFS00E129MM | N.A. | TFS00E129MSCS | K210 | IP-TFS00E129MSCS-K214-030 | 30.TE129-M.F | MS STEEL ON TE129 | 0.38258 | 0 | 0.38258 |  | TN | 16.9165 |  | 0 | 225 |  | 100% | 85% | 80% | 15% | 0% | 80.75% | 181.6875 | 0 |  |  | Original hrs not accuate for all the ship loose steel
K214-TFS-0111 | TFS | 20.01.01 | TFS00E130MM | N.A. | TFS00E130MSCS | K210 | IP-TFS00E130MSCS-K214-030 | 30.TE130-M.F | MS STEEL ON TE130 | 2.193 | 0 | 2.193 |  | TN | 106.864 |  | 0 | 106.864 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0112 | TFS | 20.01.01 | TFS00E131MM | N.A. | TFS00E131MSCS | K210 | IP-TFS00E131MSCS-K214-030 | 30.TE131-M.F | MS STEEL ON TE131 | 3.0212 | 0 | 3.0212 |  | TN | 138.6551 |  | 0 | 138.6551 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0113 | TFS | 20.01.01 | TFS00E132MM | N.A. | TFS00E132MSCS | K210 | IP-TFS00E132MSCS-K214-030 | 30.TE132-M.F | MS STEEL ON TE132 | 12.0883 | 0 | 12.0883 |  | TN | 461.4496 |  | 0 | 461.4496 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0114 | TFS | 20.01.01 | TFS00E133MM | N.A. | TFS00E133MSCS | K210 | IP-TFS00E133MSCS-K214-030 | 30.TE133-M.F | MS STEEL ON TE133 | 0.4905 | 0 | 0.4905 |  | TN | 23.8884 |  | 0 | 23.8884 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0115 | TFS | 20.01.01 | TFS00E134MM | N.A. | TFS00E134MSCS | K210 | IP-TFS00E134MSCS-K214-030 | 30.TE134-M.F | MS STEEL ON TE134 | 2.9262 | 0 | 2.9262 |  | TN | 126.7098 |  | 0 | 126.7098 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0116 | TFS | 20.01.01 | TFS00E136MM | N.A. | TFS00E136MSCS | K214 | IP-TFS00E136MSCS-K214-030 | 30.TE136-M.F | MS STEEL ON TE136 | 18.33 | 0 | 18.33 |  | TN | 742.127 |  | 0 | 742.127 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0117 | TFS | 20.01.01 | TFS00E137MM | N.A. | TFS00E137MSCS | K210 | IP-TFS00E137MSCS-K214-030 | 30.TE137-M.F | MS STEEL ON TE137 | 8.6268 | 0 | 8.6268 |  | TN | 359.5391 |  | 0 | 359.5391 |  | 100% | 90% | 80% | 0% | 0% | 82% | 294.8221 | 0
K214-TFS-0118 | TFS | 20.01.01 | TFS00E138MM | N.A. | TFS00E138MSCS | K210 | IP-TFS00E138MSCS-K214-030 | 30.TE138-M.F | MS STEEL ON TE138 | 3.7871 | 0 | 3.7871 |  | TN | 141.7838 |  | 0 | 141.7838 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0119 | TFS | 20.01.01 | TFS00E139MM | N.A. | TFS00E139MSCS | K210 | IP-TFS00E139MSCS-K214-030 | 30.TE139-M.F | MS STEEL ON TE139 | 0.27153 | 0 | 0.27153 |  | TN | 12.0063 |  | 0 | 12.0063 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0120 | TFS | 20.01.01 | TFS00E140MM | N.A. | TFS00E140MSCS | K210 | IP-TFS00E140MSCS-K214-030 | 30.TE140-M.F | MS STEEL ON TE140 | 0.3363 | 0 | 0.3363 |  | TN | 15.8652 |  | 0 | 15.8652 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0121 | TFS | 20.01.01 | TFS00E144MM | N.A. | TFS00E144MSCS | K210 | IP-TFS00E144MSCS-K214-030 | 30.TE144-M.F | MS STEEL ON TE144 | 0.33383 | 0 | 0.33383 |  | TN | 16.3819 |  | 0 | 16.3819 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0122 | TFS | 20.01.01 | TFS00E145MM | N.A. | TFS00E145MSCS | K210 | IP-TFS00E145MSCS-K214-030 | 30.TE145-M.F | MS STEEL ON TE145 | 1.7567 | 0 | 1.7567 |  | TN | 70.649 |  | 0 | 70.649 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0123 | TFS | 20.01.01 | TFS00F101MM | N.A. | TFS00F101MMCS | K214 | IP-TFS00F101MMCS-K214-030 | 30.TF101-M.F | A-LVL STEEL INSTALLATION ON TF101 | 16.9 | 0 | 16.9 |  | TN | 4302.0864 |  | 0 | 185.85 |  | 100% | 100% | 100% | 100% | 0% | 100% | 185.85 | 0
K214-TFS-0124 | TFS | 20.01.01 | TFS00F102MM | N.A. | TFS00F102MMCS | K214 | IP-TFS00F102MMCS-K214-030 | 30.TF102-M.F | A-LVL STEEL INSTALLATION ON TF102 | 4.67 | 0 | 4.67 |  | TN | 3948.4821 |  | 0 | 69.74 |  | 100% | 100% | 100% | 100% | 0% | 100% | 69.74 | 0
K214-TFS-0125 | TFS | 20.01.01 | TFS00G101MM | N.A. | TFS00G101MMCS | K214 | IP-TFS00G101MMCS-K214-030 | 30.TG101-M.F | INSTALLATION OF SHIPLOOSE STEEL ON TG101 | 113.1573 | 0 | 113.1573 |  | TN | 3958.7412 |  | 0 | 507 |  | 100% | 85% | 80% | 0% | 0% | 80% | 405.6 | 0
K214-TFS-0126 | TFS | 20.01.01 | TFS00H101MM | N.A. | TFS00H101MMCS | K214 | IP-TFS00H101MMCS-K214-030 | 30.TH101-M.F | A-LVL STEEL INSTALLATION ON TH101 | 18.064 | 0 | 18.064 |  | TN | 3445.0557 |  | 0 | 221.58 |  | 100% | 100% | 100% | 100% | 0% | 100% | 221.58 | 0
K214-TFS-0127 | TFS | 20.01.01 | TFS00I101MM | N.A. | TFS00I101MSCS | K210 | IP-TFS00I101MSCS-K214-030 | 30.TI101-M.F | MS STEEL ON TI101 | 3.706 | 0 | 3.706 |  | TN | 128.4704 |  | 0 | 128.4704 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0128 | TFS | 20.01.01 | TFS00I102MM | N.A. | TFS00I102MSCS | K210 | IP-TFS00I102MSCS-K214-030 | 30.TI102-M.F | MS STEEL ON TI102 | 1.3 | 0 | 1.3 |  | TN | 59.6557 |  | 0 | 59.6557 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0129 | TFS | 20.01.01 | TFS00I103MM | N.A. | TFS00I103MSCS | K210 | IP-TFS00I103MSCS-K214-030 | 30.TI103-M.F | MS STEEL ON TI103 | 4.752 | 0 | 4.752 |  | TN | 177.3262 |  | 0 | 177.3262 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0130 | TFS | 20.01.01 | TFS00I104MM | N.A. | TFS00I104MSCS | K210 | IP-TFS00I104MSCS-K214-030 | 30.TI104-M.F | MS STEEL ON TI104 | 0.467 | 0 | 0.467 |  | TN | 21.7983 |  | 0 | 21.7983 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0131 | TFS | 20.01.01 | TFS00I105MM | N.A. | TFS00I105MSCS | K210 | IP-TFS00I105MSCS-K214-030 | 30.TI105-M.F | MS STEEL ON TI105 | 3.214 | 0 | 3.214 |  | TN | 104.9794 |  | 0 | 104.9794 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0132 | TFS | 20.01.01 | TFS00I106MM | N.A. | TFS00I106MSCS | K210 | IP-TFS00I106MSCS-K214-030 | 30.TI106-M.F | MS STEEL ON TI106 | 1.211 | 0 | 1.211 |  | TN | 56.8707 |  | 0 | 56.8707 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0133 | TFS | 20.01.01 | TFS00I107MM | N.A. | TFS00I107MSCS | K214 | IP-TFS00I107MSCS-K214-030 | 30.TI107-M.F | MS STEEL ON TI107 | 17.8273 | 0 | 17.8273 |  | TN | 720.0897 |  | 0 | 720.0897 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0134 | TFS | 20.01.01 | TFS00I108MM | N.A. | TFS00I108MSCS | K214 | IP-TFS00I108MSCS-K214-030 | 30.TI108-M.F | MS STEEL ON TI108 | 17.816 | 0 | 17.816 |  | TN | 719.5839 |  | 0 | 719.5839 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0135 | TFS | 20.01.01 | TFS00I109MM | N.A. | TFS00I109MSCS | K210 | IP-TFS00I109MSCS-K214-030 | 30.TI109-M.F | MS STEEL ON TI109 | 1.47 | 0 | 1.47 |  | TN | 63.3152 |  | 0 | 63.3152 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0136 | TFS | 20.01.01 | TFS00I110MM | N.A. | TFS00I110MSCS | K210 | IP-TFS00I110MSCS-K214-030 | 30.TI110-M.F | MS STEEL ON TI110 | 6.765 | 0 | 6.765 |  | TN | 270.6622 |  | 0 | 270.6622 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0137 | TFS | 20.01.01 | TFS00I111MM | N.A. | TFS00I111MSCS | K210 | IP-TFS00I111MSCS-K214-030 | 30.TI111-M.F | MS STEEL ON TI111 | 4.131 | 0 | 4.131 |  | TN | 170.3958 |  | 0 | 170.3958 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0138 | TFS | 20.01.01 | TFS00J101MM | N.A. | TFS00J101MSCS | K214 | IP-TFS00J101MSCS-K214-030 | 30.TJ101-M.F | MS STEEL ON TJ101 | 131.2229 | 0 | 131.2229 |  | TN | 3854.9627 |  | 0 | 3854.9627 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1358 | TFS | 20.01.01 | TFS00K110MM | [5 empty] | MS STEEL ON TK110 |  | 0 |  |  | TN | 130 |  | 0 | 130.25 |  | 100% | 80% | 75% | 0% | 0% | 75.75% | 98.6644 | 0
K214-TFS-0139 | TFS | 20.01.01 | TFS00-EH-43 | N.A. | TFS00M006YSCS | K214 | IP-TFS00M006YSCS-K214-030 | 30.EH43-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #43 |  | 0 | 0 |  |  | 300 |  | 0 | 300 |  | 100% | 100% | 100% | 0% | 0% | 95% | 285 | 204
K214-TFS-0140 | TFS | 20.01.01 | TFS00-EH-44 | N.A. | TFS00M008YSCS | K214 | IP-TFS00M008YSCS-K214-030 | 30.EH44-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #44 |  | 0 | 0 |  |  | 300 |  | 0 | 300 |  | 100% | 100% | 100% | 0% | 0% | 95% | 285 | 264
K214-TFS-0350 | TFS | 20.01.01 | TFS00-EH-40 | N.A. | TFS00M002YSCS | K214 | IP-TFS00M002YSCS-K214-030 | 30.EH40-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #40 |  | 0 | 0 |  |  | 600 |  | 0 | 600 |  | 100% | 100% | 50% | 0% | 0% | 72.5% | 435 | 292.625
K214-TFS-0351 | TFS | 20.01.01 | TFS00SRUOM7 | N.A. | TFS00SRUH06CS | K209 | IP-TFS00SRUH06CS-K214-045 |  | A-LVL STEEL INSTALLATION ON SRU-OM7 |  | 0 | 0 |  |  | 250 |  | 0 | 250 |  | 100% | 100% | 100% | 100% | 0% | 100% | 250 | 189.5
K214-TFS-0352 | TFS | 20.01.01 | TFS00-EH-41 | N.A. | TFS00M003YSCS | K214 | IP-TFS00M003YSCS-K214-030 | 30.EH41-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #41 |  | 0 | 0 |  |  | 800 |  | 0 | 400 |  | 100% | 100% | 100% | 0% | 0% | 95% | 380 | 175.25
K214-TFS-1056 | TFS | 20.01.01 | TFS00-EH-42 | N.A. | TFS00M005YSCS | K214 | IP-TFS00M005YSCS-K214-030 | 30.EH42-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #42 |  | 0 | 0 |  |  | 300 |  | 0 | 300 |  | 100% | 95% | 93% | 0% | 0% | 89.85% | 269.55 | 0
K214-TFS-1059 | TFS | 20.01.01 | TFS00-EH-45 | N.A. | TFS00M011YSCS | K214 | IP-TFS00M011YSCS-K214-030 | 30.EH45-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #45 |  | 0 | 0 |  |  |  |  | 0 | 300 |  | 100% | 75% | 50% | 0% | 0% | 62.5% | 187.5 | 0
K214-TFS-1060 | TFS | 20.01.01 | TFS00-EH-46 | N.A. | TFS00M012YSCS | K214 | IP-TFS00M012YSCS-K214-030 | 30.EH46-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #46 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1061 | TFS | 20.01.01 | TFS00-EH-47 | N.A. | TFS00E047MMCS | K214 | IP-TFS00E047MMCS-K214-030 | 30.EH47-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #47 |  | 0 | 0 |  |  |  |  | 0 | 0 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1062 | TFS | 20.01.01 | TFS00-EH-48 | N.A. | TFS00M001YSCS | K214 | IP-TFS00M001YSCS-K214-030 | 30.EH48-M.F | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #48 |  | 0 | 0 |  |  |  |  | 0 | 300 |  | 100% | 100% | 95% | 0% | 0% | 92.75% | 278.25 | 0
K214-TFS-1184 | TFS | 20.01.01 | TFS00A101MM | N.A. |  |  |  | 30.TA101-M.F | INSTALLATION OF SHIP LOOSE STEEL ON TA101 | 14.26 | 0 | 14.26 | 6.8305 | TN | 354.5 |  | 0 | 354.5 |  | 67% | 57% | 50% | 21% | 0% | 47.9% | 188.0622 | 0
K214-TFS-1185 | TFS | 20.01.01 | TFS00A107MM | N.A. |  |  |  | 30.TA107-M.F | INSTALLATION OF SHIP LOOSE STEEL ON TA107 | 70.2 | 0 | 70.2 | 69.5331 | TN | 3778 |  | 0 | 3778 |  | 100% | 100% | 99% | 90% | 0% | 99.05% | 3742.109 | 0
K214-TFS-1186 | TFS | 20.01.01 | TFS00A108MM | N.A. |  |  |  | 30.TA108-M.F | INSTALLATION OF SHIP LOOSE STEEL ON TA108 | 2.63 | 0 | 2.63 | 2.3801 | TN | 1100 |  | 0 | 1100 |  | 100% | 100% | 90% | 0% | 0% | 90.5% | 995.5 | 0
K214-TFS-1187 | TFS | 20.01.01 | TFS00A104MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA104 | 46.55 | 0 | 46.55 | 39.102 | TN | 1772.71 |  | 0 | 1772.71 |  | 100% | 95% | 80% | 0% | 0% | 84% | 1489.0764 | 0
K214-TFS-1188 | TFS | 20.01.01 | TFS00A105MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA105 | 20.53 | 0 | 20.53 | 19.5035 | TN | 614 |  | 0 | 614 |  | 100% | 100% | 100% | 0% | 0% | 95% | 583.3 | 0
K214-TFS-1261 | TFS | 20.01.01 | TFS00F101MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TF101 | 8.38 | 0 | 8.38 | 6.704 | TN | 415.15 |  | 0 | 415.15 |  | 100% | 85% | 80% | 0% | 0% | 80% | 332.12 | 0
K214-TFS-1335 | TFS | 20.01.01 | TFS00F102MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TF102 | 92 | 0 | 92 | 73.6 | TN | 658.66 |  | 0 | 658.66 |  | 100% | 85% | 80% | 0% | 0% | 80% | 526.928 | 0
K214-TFS-1262 | TFS | 20.01.01 | TFS00H101MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TH101 | 11.1 | 0 | 11.1 | 9.102 | TN | 414.42 |  | 0 | 414.42 |  | 100% | 90% | 80% | 0% | 0% | 82% | 339.8244 | 0
K214-TFS-1263 | TFS | 20.01.01 | TFS00A102MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA102 | 37.5 | 0 | 37.5 | 30 | TN | 1689.44 |  | 0 | 1689.44 |  | 100% | 85% | 80% | 0% | 0% | 80% | 1351.552 | 0
K214-TFS-1313 | TFS | 20.01.01 | TFS00A109MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA109 | 57.93 | 0 | 57.93 | 38.8131 | TN | 2991 |  | 0 | 2991 |  | 100% | 75% | 60% | 0% | 0% | 67% | 2003.97 | 0
K214-TFS-1336 | TFS | 20.01.01 | TFS00A110MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA110 | 43 | 0 | 43 | 19.565 | TN | 2847 |  | 0 | 2847 |  | 100% | 55% | 30% | 0% | 0% | 45.5% | 1295.385 | 0
K214-TFS-1337 | TFS | 20.01.01 | TFS00A111MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA111 | 42 | 0 | 42 | 7.98 | TN | 1453.84 |  | 0 | 1453.84 |  | 85% | 15% | 10% | 0% | 0% | 19% | 276.2296 | 0
K214-TFS-1338 | TFS | 20.01.01 | TFS00A103MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TA103 | 37.77 | 0 | 214.4 | 31.8212 | TN | 1469.13 |  | 0 | 1469.13 |  | 100% | 90% | 85% | 0% | 0% | 84.25% | 1237.742 | 0
| TFS | 20.01.01 | TFS00B101MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB101 | 1 | 0 | [5 empty] | 0 | 17.16 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1339 | TFS | 20.01.01 | TFS00B102MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB102 | 38 | 0 |  |  | TN | 1270.33 |  | 0 | 1270.33 |  | 20% | 20% | 20% | 0% | 0% | 19% | 241.3627 | 0
| TFS | 20.01.01 | TFS00B103MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB103 | 5.7 | 0 |  |  | TN |  |  | 0 | 166.65 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B104MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB104 |  | 0 | [5 empty] | 0 | 314.12 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B105MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB105 |  | 0 | [5 empty] | 0 | 169.16 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B106MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB106 |  | 0 | [5 empty] | 0 | 620.25 |  | 25% | 15% | 10% | 0% | 0% | 13% | 80.6325 | 0
| TFS | 20.01.01 | TFS00B107MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB107 |  | 0 | [5 empty] | 0 | 598.37 |  | 25% | 10% | 5% | 0% | 0% | 8.75% | 52.3574 | 0
| TFS | 20.01.01 | TFS00B108MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB108 |  | 0 | [5 empty] | 0 | 1957.91 |  | 10% | 5% | 5% | 0% | 0% | 5.25% | 102.7903 | 0
| TFS | 20.01.01 | TFS00B109MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TB109 |  | 0 | [5 empty] | 0 | 624.53 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00D101MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TD101 | 3 | 0 | [5 empty] | 0 | 150.45 |  | 50% | 40% | 25% | 0% | 0% | 32.25% | 48.5201
| TFS | 20.01.01 | TFS00D103MM | N.A. |  |  |  |  | INSTALLATION OF SHIP LOOSE STEEL ON TD103 | 0.922 | 0 | [5 empty] | 0 | 125.27 |  | 50% | 40% | 25% | 0% | 0% | 32.25% | 40.3996
K214-TFS-1231 | TFS | 20.01.01 | TFS00SRU | N.A. |  |  |  |  | INSTALLATION OF STEEL FOR SRU GRATING |  | 0 | [5 empty] | 0 | 1400 |  | 100% | 100% | 100% | 0% | 0% | 95% | 1330 | 0
K214-TFS-1264 | TFS | 20.01.01 | TFS00SRU | N.A. |  |  |  |  | INSTALLATION OF STEEL FOR SRU GIRTS AND SAG RODS |  | 0 | [5 empty] | 0 | 1400 |  | 100% | 100% | 100% | 0% | 0% | 95% | 1330 | 0
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description SETTING | [10 empty] | Stage | Set / Install |  | %
[9 empty] | Setting / Stacking | 184 | 0 | 179 | 24.56 |  | 17741.85 | 247 | 0 | 18180.74 |  | 5% | 85% | 0% | 10% | 0% |  | 13731.7832 | 11506.75
K214-TFS-0013 | TFS | 40.28.01 | TFS00T101MM | N.A. | TFS00T101MMCS | K210 | IP-TFS00T101MMCS-K214-045 | 30.TT101-M.F | INSTALLATION OF MODULE TT101 | 1 | 0 | 1 | 1 | EA | 64.27 | 237 | 0 | 301.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 301.27 | 301
K214-TFS-1063 | TFS | 40.28.02 | TFS00T102MM | N.A. | TFS00T102MMCS | K214 | IP-TFS00T102MMCS-K214-045 | 30.TT102-M.F | INSTALLATION OF SHOEBOX TT102-B | 1 | 0 | 1 | 1 | EA | 193 |  |  | 192.81 |  | 100% | 100% | 0% | 100% | 0% | 100% | 192.81 | 0
K214-TFS-0042 | TFS | 40.28.01 | TFS00T103MM | N.A. | TFS00T103MMCS | K210 | IP-TFS00T103MMCS-K214-045 | 30.TT103-M.F | INSTALLATION OF MODULE TT103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0014 | TFS | 40.28.01 | TFS00T104MM | N.A. | TFS00T104MMCS | K210 | IP-TFS00T104MMCS-K214-045 | 30.TT104-M.F | INSTALLATION OF MODULE TT104 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0015 | TFS | 40.28.01 | TFS00T105MM | N.A. | TFS00T105MMCS | K210 | IP-TFS00T105MMCS-K214-045 | 30.TT105-M.F | INSTALLATION OF MODULE TT105 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0016 | TFS | 40.28.01 | TFS00T106MM | N.A. | TFS00T106MMCS | K210 | IP-TFS00T106MMCS-K214-045 | 30.TT106-M.F | INSTALLATION OF MODULE TT106 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0017 | TFS | 40.28.01 | TFS00T107MM | N.A. | TFS00T107MMCS | K214 | IP-TFS00T107MMCS-K214-045 | 30.TT107-M.F | INSTALLATION OF MODULE TT107 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0018 | TFS | 40.28.01 | TFS00T108MM | N.A. | TFS00T108MMCS | K210 | IP-TFS00T108MMCS-K214-045 | 30.TT108-M.F | INSTALLATION OF MODULE TT108 | 1 | 0 | 1 | 1 | EA | 64.27 | 10 | 0 | 74.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 74.27 | 161
K214-TFS-0019 | TFS | 40.28.01 | TFS00T109MM | N.A. | TFS00T109MMCS | K210 | IP-TFS00T109MMCS-K214-045 | 30.TT109-M.F | INSTALLATION OF MODULE TT109 | 1 | 0 | 1 | 0 | EA | 87 |  | 0 | 87 |  | 100% | 100% | 0% | 100% | 0% | 100% | 87 | 87
K214-TFS-0020 | TFS | 40.28.01 | TFS00T110MM | N.A. | TFS00T110MMCS | K210 | IP-TFS00T110MMCS-K214-045 | 30.TT110-M.F | INSTALLATION OF MODULE TT110 | 1 | 0 | 1 | 1 | EA | 87 |  | 0 | 87 |  | 100% | 100% | 0% | 100% | 0% | 100% | 87 | 87
K214-TFS-0021 | TFS | 40.28.01 | TFS00-EH-40 | N.A. | TFS00M002YSCS | K214 | IP-TFS00M002YSCS-K214-045 | 30.T-EH40M.F | INSTALLATION OF E-HOUSE #40 | 1 | 0 | 1 | 1 | EA | 98.25 |  | 0 | 98.25 |  | 100% | 100% | 0% | 100% | 0% | 100% | 98.25 | 98.25
K214-TFS-0065 | TFS | 40.28.01 | TFS00-EH-41 | N.A. | TFS00M003YSCS | K214 | IP-TFS00M003YSCS-K214-045 | 30.T-EH41M.F | INSTALLATION OF E-HOUSE #41 | 1 | 0 | 1 | 1 | EA | 216 |  | 0 | 216 |  | 100% | 100% | 0% | 100% | 0% | 100% | 216 | 216
K214-TFS-0066 | TFS | 40.28.01 | TFS00-EH-42 | N.A. | TFS00M005YSCS | K214 | IP-TFS00M005YSCS-K214-045 | 30.T-EH42M.F | INSTALLATION OF E-HOUSE #42 | 1 | 0 | 1 | 1 | EA | 180 |  | 0 | 180 |  | 100% | 100% | 0% | 100% | 0% | 100% | 180 | 180
K214-TFS-0022 | TFS | 40.28.01 | TFS00-EH-43 | N.A. | TFS00M006YSCS | K214 | IP-TFS00M006YSCS-K214-045 | 30.T-EH43M.F | INSTALLATION OF E-HOUSE #43 | 1 | 0 | 1 | 1 | EA | 167 |  | 0 | 167 |  | 100% | 100% | 0% | 100% | 0% | 100% | 167 | 167
K214-TFS-0023 | TFS | 40.28.01 | TFS00-EH-44 | N.A. | TFS00M008YSCS | K214 | IP-TFS00M008YSCS-K214-045 | 30.T-EH44M.F | INSTALLATION OF E-HOUSE #44 | 1 | 0 | 1 | 1 | EA | 106 |  | 0 | 106 |  | 100% | 100% | 0% | 100% | 0% | 100% | 106 | 106
K214-TFS-1064 | TFS | 40.28.01 | TFS00-EH-45 | N.A. | TFS00M011YSCS | K214 | IP-TFS00M011YSCS-K214-045 | 30.T-EH45M.F | INSTALLATION OF E-HOUSE #45 | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 350 |  | 100% | 100% | 0% | 100% | 0% | 100% | 350 | 0
K214-TFS-1065 | TFS | 40.28.01 | TFS00-EH-46 | N.A. | TFS00M012YSCS | K214 | IP-TFS00M012YSCS-K214-045 | 30.T-EH46M.F | INSTALLATION OF E-HOUSE #46 | 1 | 0 | 1 | 0.56 | EA | 200 |  | 0 | 350 |  | 100% | 60% | 40% |  | 0% | 56% | 196 | 0
K214-TFS-1066 | TFS | 40.28.01 | TFS00-EH-47 | N.A. | TFS00-EH-47CS | K214 | IP-TFS00-EH-47CS-K214-045 | 30.T-EH47M.F | INSTALLATION OF E-HOUSE #47 | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 0 |  |  |  | 0% |  | 0% | 0% | 0 | 0
K214-TFS-1067 | TFS | 40.28.01 | TFS00-EH-48 | N.A. | TFS00M001YSCS | K214 | IP-TFS00M001YSCS-K214-045 | 30.T-EH48M.F | INSTALLATION OF E-HOUSE #48 | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0141 | TFS | 40.28.01 | TFS00A108MM | N.A. | TFS00A108MMCS | K214 | IP-TFS00A108MMCS-K214-045 | 30.TA108-M.F | INSTALLATION OF SHOEBOX TA108-B | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0142 | TFS | 40.28.01 | TFS00A108MM | N.A. | TFS00A108MMCS | K214 | IP-TFS00A108MMCS-K214-045 | 30.TA108-M.F | INSTALLATION OF SHOEBOX TA108-C | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0143 | TFS | 40.28.01 | TFS00A108MM | N.A. | TFS00A108MMCS | K214 | IP-TFS00A108MMCS-K214-045 | 30.TA108-M.F | INSTALLATION OF SHOEBOX TA108-D | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0144 | TFS | 40.28.01 | TFS00W101MM | N.A. | TFS00W101MMCS | K210 | IP-TFS00W101MMCS-K214-045 | 30.TW101-M.F | INSTALLATION OF MODULE TW101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0145 | TFS | 40.28.01 | TFS00W102MM | N.A. | TFS00W102MMCS | K210 | IP-TFS00W102MMCS-K214-045 | 30.TW102-M.F | INSTALLATION OF MODULE TW102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0148 | TFS | 40.28.01 | TFS00W103MM | N.A. | TFS00W103MMCS | K210 | IP-TFS00W103MMCS-K214-045 | 30.TW103-M.F | INSTALLATION OF MODULE TW103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0190 | TFS | 40.28.01 | TFS00K101MM | N.A. | TFS00K101MMCS | K210 | IP-TFS00K101MMCS-K214-045 | 30.TK101-M.F | INSTALLATION OF MODULE TK101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0147 | TFS | 40.28.01 | TFS00K103MM | N.A. | TFS00K103MMCS | K210 | IP-TFS00K103MMCS-K214-045 | 30.TK103-M.F | INSTALLATION OF MODULE TK103 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0146 | TFS | 40.28.01 | TFS00K106MM | N.A. | TFS00K106MMCS | K210 | IP-TFS00K106MMCS-K214-045 | 30.TK106-M.F | INSTALLATION OF MODULE TK106 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0152 | TFS | 40.28.01 | TFS00K105MM | N.A. | TFS00K105MMCS | K210 | IP-TFS00K105MMCS-K214-045 | 30.TK105-M.F | INSTALLATION OF MODULE TK105 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0153 | TFS | 40.28.01 | TFS00K107MM | N.A. | TFS00K107MMCS | K210 | IP-TFS00K107MMCS-K214-045 | 30.TK107-M.F | INSTALLATION OF MODULE TK107 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0154 | TFS | 40.28.01 | TFS00K109MM | N.A. | TFS00K109MMCS | K210 | IP-TFS00K109MMCS-K214-045 | 30.TK109-M.F | INSTALLATION OF MODULE TK109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0155 | TFS | 40.28.01 | TFS00D114MM | N.A. | TFS00D114MMCS | K210 | IP-TFS00D114MMCS-K214-045 | 30.TD114-M.F | INSTALLATION OF MODULE TD114 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0156 | TFS | 40.28.01 | TFS00D115MM | N.A. | TFS00D115MMCS | K210 | IP-TFS00D115MMCS-K214-045 | 30.TD115-M.F | INSTALLATION OF MODULE TD115 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0157 | TFS | 40.28.01 | TFS00D121MM | N.A. | TFS00D121MMCS | K210 | IP-TFS00D121MMCS-K214-045 | 30.TD121-M.F | INSTALLATION OF MODULE TD121 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0158 | TFS | 40.28.01 | TFS00D116MM | N.A. | TFS00D116MMCS | K210 | IP-TFS00D116MMCS-K214-045 | 30.TD116-M.F | INSTALLATION OF MODULE TD116 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0159 | TFS | 40.28.01 | TFS00D117MM | N.A. | TFS00D117MMCS | K210 | IP-TFS00D117MMCS-K214-045 | 30.TD117-M.F | INSTALLATION OF MODULE TD117 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0160 | TFS | 40.28.01 | TFS00D122MM | N.A. | TFS00D122MMCS | K210 | IP-TFS00D122MMCS-K214-045 | 30.TD122-M.F | INSTALLATION OF MODULE TD122 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0161 | TFS | 40.28.01 | TFS00W106MM | N.A. | TFS00W106MMCS | K210 | IP-TFS00W106MMCS-K214-045 | 30.TW106-M.F | INSTALLATION OF MODULE TW106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0162 | TFS | 40.28.01 | TFS00V101MM | N.A. | TFS00V101MMCS | K210 | IP-TFS00V101MMCS-K214-045 | 30.TV101-M.F | INSTALLATION OF MODULE TV101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0163 | TFS | 40.28.01 | TFS00V102MM | N.A. | TFS00V102MMCS | K210 | IP-TFS00V102MMCS-K214-045 | 30.TV102-M.F | INSTALLATION OF MODULE TV102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0164 | TFS | 40.28.01 | TFS00D109MM | N.A. | TFS00D109MMCS | K210 | IP-TFS00D109MMCS-K214-045 | 30.TD109-M.F | INSTALLATION OF MODULE TD109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0165 | TFS | 40.28.01 | TFS00V103MM | N.A. | TFS00V103MMCS | K210 | IP-TFS00V103MMCS-K214-045 | 30.TV103-M.F | INSTALLATION OF MODULE TV103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0166 | TFS | 40.28.01 | TFS00D110MM | N.A. | TFS00D110MMCS | K210 | IP-TFS00D110MMCS-K214-045 | 30.TD110-M.F | INSTALLATION OF MODULE TD110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0167 | TFS | 40.28.01 | TFS00D119MM | N.A. | TFS00D119MMCS | K210 | IP-TFS00D119MMCS-K214-045 | 30.TD119-M.F | INSTALLATION OF MODULE TD119 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0168 | TFS | 40.28.01 | TFS00K110MM | N.A. | TFS00K110MMCS | K210 | IP-TFS00K110MMCS-K214-045 | 30.TK110-M.F | INSTALLATION OF MODULE TK110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0169 | TFS | 40.28.01 | TFS00I101MM | N.A. | TFS00I101MMCS | K210 | IP-TFS00I101MMCS-K214-045 | 30.TI101-M.F | INSTALLATION OF MODULE TI101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0170 | TFS | 40.28.01 | TFS00I102MM | N.A. | TFS00I102MMCS | K210 | IP-TFS00I102MMCS-K214-045 | 30.TI102-M.F | INSTALLATION OF MODULE TI102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0171 | TFS | 40.28.01 | TFS00I109MM | N.A. | TFS00I109MMCS | K210 | IP-TFS00I109MMCS-K214-045 | 30.TI109-M.F | INSTALLATION OF MODULE TI109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0172 | TFS | 40.28.01 | TFS00D101MM | N.A. | TFS00D101MMCS | K210 | IP-TFS00D101MMCS-K214-045 | 30.TD101-M.F | INSTALLATION OF MODULE TD101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0173 | TFS | 40.28.01 | TFS00D102MM | N.A. | TFS00D102MMCS | K210 | IP-TFS00D102MMCS-K214-045 | 30.TD102-M.F | INSTALLATION OF MODULE TD102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0174 | TFS | 40.28.01 | TFS00D103MM | N.A. | TFS00D103MMCS | K210 | IP-TFS00D103MMCS-K214-045 | 30.TD103-M.F | INSTALLATION OF MODULE TD103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0175 | TFS | 40.28.01 | TFS00D104MM | N.A. | TFS00D104MMCS | K210 | IP-TFS00D104MMCS-K214-045 | 30.TD104-M.F | INSTALLATION OF MODULE TD104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0176 | TFS | 40.28.01 | TFS00E107MM | N.A. | TFS00E107MMCS | K210 | IP-TFS00E107MMCS-K214-045 | 30.TE107-M.F | INSTALLATION OF MODULE TE107 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0177 | TFS | 40.28.01 | TFS00E108MM | N.A. | TFS00E108MMCS | K210 | IP-TFS00E108MMCS-K214-045 | 30.TE108-M.F | INSTALLATION OF MODULE TE108 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0178 | TFS | 40.28.01 | TFS00E128MM | N.A. | TFS00E128MMCS | K210 | IP-TFS00E128MMCS-K214-045 | 30.TE128-M.F | INSTALLATION OF MODULE TE128 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0179 | TFS | 40.28.01 | TFS00E144MM | N.A. | TFS00E144MMCS | K210 | IP-TFS00E144MMCS-K214-045 | 30.TE144-M.F | INSTALLATION OF MODULE TE144 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0180 | TFS | 40.28.01 | TFS00E138MM | N.A. | TFS00E138MMCS | K210 | IP-TFS00E138MMCS-K214-045 | 30.TE138-M.F | INSTALLATION OF MODULE TE138 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0181 | TFS | 40.28.01 | TFS00E111MM | N.A. | TFS00E111MMCS | K210 | IP-TFS00E111MMCS-K214-045 | 30.TE111-M.F | INSTALLATION OF MODULE TE111 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0182 | TFS | 40.28.01 | TFS00E112MM | N.A. | TFS00E112MMCS | K210 | IP-TFS00E112MMCS-K214-045 | 30.TE112-M.F | INSTALLATION OF MODULE TE112 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0183 | TFS | 40.28.01 | TFS00E130MM | N.A. | TFS00E130MMCS | K210 | IP-TFS00E130MMCS-K214-045 | 30.TE130-M.F | INSTALLATION OF MODULE TE130 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0184 | TFS | 40.28.01 | TFS00E113MM | N.A. | TFS00E113MMCS | K210 | IP-TFS00E113MMCS-K214-045 | 30.TE113-M.F | INSTALLATION OF MODULE TE113 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0185 | TFS | 40.28.01 | TFS00E114MM | N.A. | TFS00E114MMCS | K210 | IP-TFS00E114MMCS-K214-045 | 30.TE114-M.F | INSTALLATION OF MODULE TE114 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0186 | TFS | 40.28.01 | TFS00E131MM | N.A. | TFS00E131MMCS | K210 | IP-TFS00E131MMCS-K214-045 | 30.TE131-M.F | INSTALLATION OF MODULE TE131 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0187 | TFS | 40.28.01 | TFS00E139MM | N.A. | TFS00E139MMCS | K210 | IP-TFS00E139MMCS-K214-045 | 30.TE139-M.F | INSTALLATION OF MODULE TE139 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0188 | TFS | 40.28.01 | TFS00E140MM | N.A. | TFS00E140MMCS | K210 | IP-TFS00E140MMCS-K214-045 | 30.TE140-M.F | INSTALLATION OF MODULE TE140 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0149 | TFS | 40.28.01 | TFS00E141MM | N.A. | TFS00E141MMCS | K210 | IP-TFS00E141MMCS-K214-045 | 30.TE141-M.F | INSTALLATION OF MODULE TE141 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0150 | TFS | 40.28.01 | TFS00E142MM | N.A. | TFS00E142MMCS | K210 | IP-TFS00E142MMCS-K214-045 | 30.TE142-M.F | INSTALLATION OF MODULE TE142 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0151 | TFS | 40.28.01 | TFS00E143MM | N.A. | TFS00E143MMCS | K210 | IP-TFS00E143MMCS-K214-045 | 30.TE143-M.F | INSTALLATION OF MODULE TE143 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0189 | TFS | 40.28.01 | TFS00E145MM | N.A. | TFS00E145MMCS | K210 | IP-TFS00E145MMCS-K214-045 | 30.TE145-M.F | INSTALLATION OF MODULE TE145 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0191 | TFS | 40.28.01 | TFS00E109MM | N.A. | TFS00E109MMCS | K210 | IP-TFS00E109MMCS-K214-045 | 30.TE109-M.F | INSTALLATION OF MODULE TE109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0192 | TFS | 40.28.01 | TFS00E103MM | N.A. | TFS00E103MMCS | K210 | IP-TFS00E103MMCS-K214-045 | 30.TE103-M.F | INSTALLATION OF MODULE TE103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0193 | TFS | 40.28.01 | TFS00E104MM | N.A. | TFS00E104MMCS | K210 | IP-TFS00E104MMCS-K214-045 | 30.TE104-M.F | INSTALLATION OF MODULE TE104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0194 | TFS | 40.28.01 | TFS00E119MM | N.A. | TFS00E119MMCS | K210 | IP-TFS00E119MMCS-K214-045 | 30.TE119-M.F | INSTALLATION OF MODULE TE119 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0195 | TFS | 40.28.01 | TFS00E120MM | N.A. | TFS00E120MMCS | K210 | IP-TFS00E120MMCS-K214-045 | 30.TE120-M.F | INSTALLATION OF MODULE TE120 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0196 | TFS | 40.28.01 | TFS00E134MM | N.A. | TFS00E134MMCS | K210 | IP-TFS00E134MMCS-K214-045 | 30.TE134-M.F | INSTALLATION OF MODULE TE134 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 60% | 0% | 0% | 0% | 56% | 35.9912 | 0
K214-TFS-0197 | TFS | 40.28.01 | TFS00E110MM | N.A. | TFS00E110MMCS | K210 | IP-TFS00E110MMCS-K214-045 | 30.TE110-M.F | INSTALLATION OF MODULE TE110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0198 | TFS | 40.28.01 | TFS00E129MM | N.A. | TFS00E129MMCS | K210 | IP-TFS00E129MMCS-K214-045 | 30.TE129-M.F | INSTALLATION OF MODULE TE129 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0199 | TFS | 40.28.01 | TFS00E126MM | N.A. | TFS00E126MMCS | K210 | IP-TFS00E126MMCS-K214-045 | 30.TE126-M.F | INSTALLATION OF MODULE TE126 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0200 | TFS | 40.28.01 | TFS00E105MM | N.A. | TFS00E105MMCS | K210 | IP-TFS00E105MMCS-K214-045 | 30.TE105-M.F | INSTALLATION OF MODULE TE105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0201 | TFS | 40.28.01 | TFS00E106MM | N.A. | TFS00E106MMCS | K210 | IP-TFS00E106MMCS-K214-045 | 30.TE106-M.F | INSTALLATION OF MODULE TE106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0202 | TFS | 40.28.01 | TFS00E115MM | N.A. | TFS00E115MMCS | K210 | IP-TFS00E115MMCS-K214-045 | 30.TE115-M.F | INSTALLATION OF MODULE TE115 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0203 | TFS | 40.28.01 | TFS00E127MM | N.A. | TFS00E127MMCS | K210 | IP-TFS00E127MMCS-K214-045 | 30.TE127-M.F | INSTALLATION OF MODULE TE127 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0204 | TFS | 40.28.01 | TFS00I103MM | N.A. | TFS00I103MMCS | K210 | IP-TFS00I103MMCS-K214-045 | 30.TI103-M.F | INSTALLATION OF MODULE TI103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0205 | TFS | 40.28.01 | TFS00I104MM | N.A. | TFS00I104MMCS | K210 | IP-TFS00I104MMCS-K214-045 | 30.TI104-M.F | INSTALLATION OF MODULE TI104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0206 | TFS | 40.28.01 | TFS00I110MM | N.A. | TFS00I110MMCS | K210 | IP-TFS00I110MMCS-K214-045 | 30.TI110-M.F | INSTALLATION OF MODULE TI110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0207 | TFS | 40.28.01 | TFS00I105MM | N.A. | TFS00I105MMCS | K210 | IP-TFS00I105MMCS-K214-045 | 30.TI105-M.F | INSTALLATION OF MODULE TI105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0208 | TFS | 40.28.01 | TFS00I106MM | N.A. | TFS00I106MMCS | K210 | IP-TFS00I106MMCS-K214-045 | 30.TI106-M.F | INSTALLATION OF MODULE TI106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0209 | TFS | 40.28.01 | TFS00I111MM | N.A. | TFS00I111MMCS | K210 | IP-TFS00I111MMCS-K214-045 | 30.TI111-M.F | INSTALLATION OF MODULE TI111 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0210 | TFS | 40.28.01 | TFS00E116MM | N.A. | TFS00E116MMCS | K210 | IP-TFS00E116MMCS-K214-045 | 30.TE116-M.F | INSTALLATION OF MODULE TE116 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0211 | TFS | 40.28.01 | TFS00E132MM | N.A. | TFS00E132MMCS | K210 | IP-TFS00E132MMCS-K214-045 | 30.TE132-M.F | INSTALLATION OF MODULE TE132 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0212 | TFS | 40.28.01 | TFS00E117MM | N.A. | TFS00E117MMCS | K210 | IP-TFS00E117MMCS-K214-045 | 30.TE117-M.F | INSTALLATION OF MODULE TE117 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0213 | TFS | 40.28.01 | TFS00E118MM | N.A. | TFS00E118MMCS | K210 | IP-TFS00E118MMCS-K214-045 | 30.TE118-M.F | INSTALLATION OF MODULE TE118 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0214 | TFS | 40.28.01 | TFS00E133MM | N.A. | TFS00E133MMCS | K210 | IP-TFS00E133MMCS-K214-045 | 30.TE133-M.F | INSTALLATION OF MODULE TE133 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0215 | TFS | 40.28.01 | TFS00E137MM | N.A. | TFS00E137MMCS | K210 | IP-TFS00E137MMCS-K214-045 | 30.TE137-M.F | INSTALLATION OF MODULE TE137 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0216 | TFS | 40.28.01 | TFS00D105MM | N.A. | TFS00D105MMCS | K210 | IP-TFS00D105MMCS-K214-045 | 30.TD105-M.F | INSTALLATION OF MODULE TD105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0217 | TFS | 40.28.01 | TFS00D106MM | N.A. | TFS00D106MMCS | K210 | IP-TFS00D106MMCS-K214-045 | 30.TD106-M.F | INSTALLATION OF MODULE TD106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0218 | TFS | 40.28.01 | TFS00D107MM | N.A. | TFS00D107MMCS | K210 | IP-TFS00D107MMCS-K214-045 | 30.TD107-M.F | INSTALLATION OF MODULE TD107 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0219 | TFS | 40.28.01 | TFS00D108MM | N.A. | TFS00D108MMCS | K210 | IP-TFS00D108MMCS-K214-045 | 30.TD108-M.F | INSTALLATION OF MODULE TD108 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0220 | TFS | 40.28.01 | TFS00D120MM | N.A. | TFS00D120MMCS | K210 | IP-TFS00D120MMCS-K214-045 | 30.TD120-M.F | INSTALLATION OF MODULE TD120 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0221 | TFS | 40.28.01 | TFS00A101MM | N.A. | TFS00A101MMCS | K214 | IP-TFS00A101MMCS-K214-045 | 30.TA101-M.F | INSTALLATION OF SHOEBOX TA101-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0222 | TFS | 40.28.01 | TFS00A101MM | N.A. | TFS00A101MMCS | K214 | IP-TFS00A101MMCS-K214-045 | 30.TA101-M.F | INSTALLATION OF SHOEBOX TA101-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0223 | TFS | 40.28.01 | TFS00A101MM | N.A. | TFS00A101MMCS | K214 | IP-TFS00A101MMCS-K214-045 | 30.TA101-M.F | INSTALLATION OF SHOEBOX TA101-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0224 | TFS | 40.28.01 | TFS00A102MM | N.A. | TFS00A102MMCS | K214 | IP-TFS00A102MMCS-K214-045 | 30.TA102-M.F | INSTALLATION OF SHOEBOX TA102-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0225 | TFS | 40.28.01 | TFS00A102MM | N.A. | TFS00A102MMCS | K214 | IP-TFS00A102MMCS-K214-045 | 30.TA102-M.F | INSTALLATION OF SHOEBOX TA102-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0226 | TFS | 40.28.01 | TFS00A102MM | N.A. | TFS00A102MMCS | K214 | IP-TFS00A102MMCS-K214-045 | 30.TA102-M.F | INSTALLATION OF SHOEBOX TA102-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0227 | TFS | 40.28.01 | TFS00A103MM | N.A. | TFS00A103MMCS | K214 | IP-TFS00A103MMCS-K214-045 | 30.TA103-M.F | INSTALLATION OF SHOEBOX TA103-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0228 | TFS | 40.28.01 | TFS00A103MM | N.A. | TFS00A103MMCS | K214 | IP-TFS00A103MMCS-K214-045 | 30.TA103-M.F | INSTALLATION OF SHOEBOX TA103-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0229 | TFS | 40.28.01 | TFS00A103MM | N.A. | TFS00A103MMCS | K214 | IP-TFS00A103MMCS-K214-045 | 30.TA103-M.F | INSTALLATION OF SHOEBOX TA103-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0230 | TFS | 40.28.01 | TFS00A104MM | N.A. | TFS00A104MMCS | K214 | IP-TFS00A104MMCS-K214-045 | 30.TA104-M.F | INSTALLATION OF SHOEBOX TA104-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0231 | TFS | 40.28.01 | TFS00A104MM | N.A. | TFS00A104MMCS | K214 | IP-TFS00A104MMCS-K214-045 | 30.TA104-M.F | INSTALLATION OF SHOEBOX TA104-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0232 | TFS | 40.28.01 | TFS00A104MM | N.A. | TFS00A104MMCS | K214 | IP-TFS00A104MMCS-K214-045 | 30.TA104-M.F | INSTALLATION OF SHOEBOX TA104-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0233 | TFS | 40.28.01 | TFS00A105MM | N.A. | TFS00A105MMCS | K214 | IP-TFS00A105MMCS-K214-045 | 30.TA105-M.F | INSTALLATION OF SHOEBOX TA105-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0234 | TFS | 40.28.01 | TFS00A105MM | N.A. | TFS00A105MMCS | K214 | IP-TFS00A105MMCS-K214-045 | 30.TA105-M.F | INSTALLATION OF SHOEBOX TA105-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0235 | TFS | 40.28.01 | TFS00A105MM | N.A. | TFS00A105MMCS | K214 | IP-TFS00A105MMCS-K214-045 | 30.TA105-M.F | INSTALLATION OF SHOEBOX TA105-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0236 | TFS | 40.28.01 | TFS00A106MM | N.A. | TFS00A106MMCS | K214 | IP-TFS00A106MMCS-K214-045 | 30.TA106-M.F | INSTALLATION OF SHOEBOX TA106-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0237 | TFS | 40.28.01 | TFS00A106MM | N.A. | TFS00A106MMCS | K214 | IP-TFS00A106MMCS-K214-045 | 30.TA106-M.F | INSTALLATION OF SHOEBOX TA106-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0238 | TFS | 40.28.01 | TFS00A106MM | N.A. | TFS00A106MMCS | K214 | IP-TFS00A106MMCS-K214-045 | 30.TA106-M.F | INSTALLATION OF SHOEBOX TA106-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0239 | TFS | 40.28.01 | TFS00A107MM | N.A. | TFS00A107MMCS | K214 | IP-TFS00A107MMCS-K214-045 | 30.TA107-M.F | INSTALLATION OF SHOEBOX TA107-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0240 | TFS | 40.28.01 | TFS00A107MM | N.A. | TFS00A107MMCS | K214 | IP-TFS00A107MMCS-K214-045 | 30.TA107-M.F | INSTALLATION OF SHOEBOX TA107-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0241 | TFS | 40.28.01 | TFS00A107MM | N.A. | TFS00A107MMCS | K214 | IP-TFS00A107MMCS-K214-045 | 30.TA107-M.F | INSTALLATION OF SHOEBOX TA107-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 |  | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0242 | TFS | 40.28.01 | TFS00A109MM | N.A. | TFS00A109MMCS | K214 | IP-TFS00A109MMCS-K214-045 | 30.TA109-M.F | INSTALLATION OF SHOEBOX TA109-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0243 | TFS | 40.28.01 | TFS00A109MM | N.A. | TFS00A109MMCS | K214 | IP-TFS00A109MMCS-K214-045 | 30.TA109-M.F | INSTALLATION OF SHOEBOX TA109-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0244 | TFS | 40.28.01 | TFS00A109MM | N.A. | TFS00A109MMCS | K214 | IP-TFS00A109MMCS-K214-045 | 30.TA109-M.F | INSTALLATION OF SHOEBOX TA109-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0245 | TFS | 40.28.01 | TFS00A110MM | N.A. | TFS00A110MMCS | K214 | IP-TFS00A110MMCS-K214-045 | 30.TA110-M.F | INSTALLATION OF SHOEBOX TA110-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0246 | TFS | 40.28.01 | TFS00A110MM | N.A. | TFS00A110MMCS | K214 | IP-TFS00A110MMCS-K214-045 | 30.TA110-M.F | INSTALLATION OF SHOEBOX TA110-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0247 | TFS | 40.28.01 | TFS00A110MM | N.A. | TFS00A110MMCS | K214 | IP-TFS00A110MMCS-K214-045 | 30.TA110-M.F | INSTALLATION OF SHOEBOX TA110-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0248 | TFS | 40.28.01 | TFS00A111MM | N.A. | TFS00A111MMCS | K214 | IP-TFS00A111MMCS-K214-045 | 30.TA111-M.F | INSTALLATION OF SHOEBOX TA111-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0249 | TFS | 40.28.01 | TFS00A111MM | N.A. | TFS00A111MMCS | K214 | IP-TFS00A111MMCS-K214-045 | 30.TA111-M.F | INSTALLATION OF SHOEBOX TA111-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0250 | TFS | 40.28.01 | TFS00A111MM | N.A. | TFS00A111MMCS | K214 | IP-TFS00A111MMCS-K214-045 | 30.TA111-M.F | INSTALLATION OF SHOEBOX TA111-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0251 | TFS | 40.28.01 | TFS00A112MM | N.A. | TFS00A112MMCS | K214 | IP-TFS00A112MMCS-K214-045 | 30.TA112-M.F | INSTALLATION OF SHOEBOX TA112-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0252 | TFS | 40.28.01 | TFS00A112MM | N.A. | TFS00A112MMCS | K214 | IP-TFS00A112MMCS-K214-045 | 30.TA112-M.F | INSTALLATION OF SHOEBOX TA112-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0253 | TFS | 40.28.01 | TFS00B101MM | N.A. | TFS00B101MMCS | K214 | IP-TFS00B101MMCS-K214-045 | 30.TB101-M.F | INSTALLATION OF SHOEBOX TB101-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0254 | TFS | 40.28.01 | TFS00B101MM | N.A. | TFS00B101MMCS | K214 | IP-TFS00B101MMCS-K214-045 | 30.TB101-M.F | INSTALLATION OF SHOEBOX TB101-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0255 | TFS | 40.28.01 | TFS00B101MM | N.A. | TFS00B101MMCS | K214 | IP-TFS00B101MMCS-K214-045 | 30.TB101-M.F | INSTALLATION OF SHOEBOX TB101-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0256 | TFS | 40.28.01 | TFS00B102MM | N.A. | TFS00B102MMCS | K214 | IP-TFS00B102MMCS-K214-045 | 30.TB102-M.F | INSTALLATION OF SHOEBOX TB102-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0257 | TFS | 40.28.01 | TFS00B102MM | N.A. | TFS00B102MMCS | K214 | IP-TFS00B102MMCS-K214-045 | 30.TB102-M.F | INSTALLATION OF SHOEBOX TB102-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 100 |  | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0258 | TFS | 40.28.01 | TFS00B102MM | N.A. | TFS00B102MMCS | K214 | IP-TFS00B102MMCS-K214-045 | 30.TB102-M.F | INSTALLATION OF SHOEBOX TB102-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0259 | TFS | 40.28.01 | TFS00B103MM | N.A. | TFS00B103MMCS | K214 | IP-TFS00B103MMCS-K214-045 | 30.TB103-M.F | INSTALLATION OF SHOEBOX TB103-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0260 | TFS | 40.28.01 | TFS00B103MM | N.A. | TFS00B103MMCS | K214 | IP-TFS00B103MMCS-K214-045 | 30.TB103-M.F | INSTALLATION OF SHOEBOX TB103-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0261 | TFS | 40.28.01 | TFS00B103MM | N.A. | TFS00B103MMCS | K214 | IP-TFS00B103MMCS-K214-045 | 30.TB103-M.F | INSTALLATION OF SHOEBOX TB103-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0262 | TFS | 40.28.01 | TFS00B104MM | N.A. | TFS00B104MMCS | K214 | IP-TFS00B104MMCS-K214-045 | 30.TB104-M.F | INSTALLATION OF SHOEBOX TB104-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0263 | TFS | 40.28.01 | TFS00B104MM | N.A. | TFS00B104MMCS | K214 | IP-TFS00B104MMCS-K214-045 | 30.TB104-M.F | INSTALLATION OF SHOEBOX TB104-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0264 | TFS | 40.28.01 | TFS00B104MM | N.A. | TFS00B104MMCS | K214 | IP-TFS00B104MMCS-K214-045 | 30.TB104-M.F | INSTALLATION OF SHOEBOX TB104-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0265 | TFS | 40.28.01 | TFS00B105MM | N.A. | TFS00B105MMCS | K214 | IP-TFS00B105MMCS-K214-045 | 30.TB105-M.F | INSTALLATION OF SHOEBOX TB105-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0266 | TFS | 40.28.01 | TFS00B105MM | N.A. | TFS00B105MMCS | K214 | IP-TFS00B105MMCS-K214-045 | 30.TB105-M.F | INSTALLATION OF SHOEBOX TB105-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0267 | TFS | 40.28.01 | TFS00B105MM | N.A. | TFS00B105MMCS | K214 | IP-TFS00B105MMCS-K214-045 | 30.TB105-M.F | INSTALLATION OF SHOEBOX TB105-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0268 | TFS | 40.28.01 | TFS00B106MM | N.A. | TFS00B106MMCS | K214 | IP-TFS00B106MMCS-K214-045 | 30.TB106-M.F | INSTALLATION OF SHOEBOX TB106-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0269 | TFS | 40.28.01 | TFS00B106MM | N.A. | TFS00B106MMCS | K214 | IP-TFS00B106MMCS-K214-045 | 30.TB106-M.F | INSTALLATION OF SHOEBOX TB106-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0270 | TFS | 40.28.01 | TFS00B106MM | N.A. | TFS00B106MMCS | K214 | IP-TFS00B106MMCS-K214-045 | 30.TB106-M.F | INSTALLATION OF SHOEBOX TB106-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0271 | TFS | 40.28.01 | TFS00B107MM | N.A. | TFS00B107MMCS | K214 | IP-TFS00B107MMCS-K214-045 | 30.TB107-M.F | INSTALLATION OF SHOEBOX TB107-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0272 | TFS | 40.28.01 | TFS00B107MM | N.A. | TFS00B107MMCS | K214 | IP-TFS00B107MMCS-K214-045 | 30.TB107-M.F | INSTALLATION OF SHOEBOX TB107-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0273 | TFS | 40.28.01 | TFS00B107MM | N.A. | TFS00B107MMCS | K214 | IP-TFS00B107MMCS-K214-045 | 30.TB107-M.F | INSTALLATION OF SHOEBOX TB107-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0274 | TFS | 40.28.01 | TFS00B108MM | N.A. | TFS00B108MMCS | K214 | IP-TFS00B108MMCS-K214-045 | 30.TB108-M.F | INSTALLATION OF SHOEBOX TB108-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0275 | TFS | 40.28.01 | TFS00B108MM | N.A. | TFS00B108MMCS | K214 | IP-TFS00B108MMCS-K214-045 | 30.TB108-M.F | INSTALLATION OF SHOEBOX TB108-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0276 | TFS | 40.28.01 | TFS00B108MM | N.A. | TFS00B108MMCS | K214 | IP-TFS00B108MMCS-K214-045 | 30.TB108-M.F | INSTALLATION OF SHOEBOX TB108-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0277 | TFS | 40.28.01 | TFS00B109MM | N.A. | TFS00B109MMCS | K214 | IP-TFS00B109MMCS-K214-045 | 30.TB109-M.F | INSTALLATION OF SHOEBOX TB109-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0278 | TFS | 40.28.01 | TFS00B109MM | N.A. | TFS00B109MMCS | K214 | IP-TFS00B109MMCS-K214-045 | 30.TB109-M.F | INSTALLATION OF SHOEBOX TB109-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0279 | TFS | 40.28.01 | TFS00B109MM | N.A. | TFS00B109MMCS | K214 | IP-TFS00B109MMCS-K214-045 | 30.TB109-M.F | INSTALLATION OF SHOEBOX TB109-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0280 | TFS | 40.28.01 | TFS00F101MM | N.A. | TFS00F101MMCS | K214 | IP-TFS00F101MMCS-K214-045 | 30.TF101-M.F | INSTALLATION OF SHOEBOX TF101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0281 | TFS | 40.28.01 | TFS00F101MM | N.A. | TFS00F101MMCS | K214 | IP-TFS00F101MMCS-K214-045 | 30.TF101-M.F | INSTALLATION OF SHOEBOX TF101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0282 | TFS | 40.28.01 | TFS00F102MM | N.A. | TFS00F102MMCS | K214 | IP-TFS00F102MMCS-K214-045 | 30.TF102-M.F | INSTALLATION OF SHOEBOX TF102-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0283 | TFS | 40.28.01 | TFS00F102MM | N.A. | TFS00F102MMCS | K214 | IP-TFS00F102MMCS-K214-045 | 30.TF102-M.F | INSTALLATION OF SHOEBOX TF102-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0284 | TFS | 40.28.01 | TFS00G101MM | N.A. | TFS00G101MMCS | K214 | IP-TFS00G101MMCS-K214-045 | 30.TG101-M.F | INSTALLATION OF SHOEBOX TG101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0285 | TFS | 40.28.01 | TFS00G101MM | N.A. | TFS00G101MMCS | K214 | IP-TFS00G101MMCS-K214-045 | 30.TG101-M.F | INSTALLATION OF SHOEBOX TG101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0286 | TFS | 40.28.01 | TFS00H101MM | N.A. | TFS00H101MMCS | K214 | IP-TFS00H101MMCS-K214-045 | 30.TH101-M.F | INSTALLATION OF SHOEBOX TH101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0287 | TFS | 40.28.01 | TFS00H101MM | N.A. | TFS00H101MMCS | K214 | IP-TFS00H101MMCS-K214-045 | 30.TH101-M.F | INSTALLATION OF SHOEBOX TH101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0288 | TFS | 40.28.01 | TFS00J101MM | N.A. | TFS00J101MMCS | K214 | IP-TFS00J101MMCS-K214-045 | 30.TJ101-M.F | INSTALLATION OF SHOEBOX TJ101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0289 | TFS | 40.28.01 | TFS00J101MM | N.A. | TFS00J101MMCS | K214 | IP-TFS00J101MMCS-K214-045 | 30.TJ101-M.F | INSTALLATION OF SHOEBOX TJ101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0290 | TFS | 40.28.01 | TFS00K102MM | N.A. | TFS00K102MMCS | K214 | IP-TFS00K102MMCS-K214-045 | 30.TK102-M.F | INSTALLATION OF SHOEBOX TK102-B | 1 | 0 | 1 | 0 | EA | 192 |  | 0 | 192 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0292 | TFS | 40.28.01 | TFS00K108MM | N.A. | TFS00K108MMCS | K214 | IP-TFS00K108MMCS-K214-045 | 30.TK108-M.F | INSTALLATION OF SHOEBOX TK108-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 192 |  | 100% | 100% | 0% | 100% | 0% | 100% | 192 | 0
K214-TFS-0293 | TFS | 40.28.01 | TFS00L101MM | N.A. | TFS00L101MMCS | K214 | IP-TFS00L101MMCS-K214-045 | 30.TL101-M.F | INSTALLATION OF SHOEBOX TL101-B | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0294 | TFS | 40.28.01 | TFS00L101MM | N.A. | TFS00L101MMCS | K214 | IP-TFS00L101MMCS-K214-045 | 30.TL101-M.F | INSTALLATION OF SHOEBOX TL101-C | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0295 | TFS | 40.28.01 | TFS00L102MM | N.A. | TFS00L102MMCS | K214 | IP-TFS00L102MMCS-K214-045 | 30.TL102-M.F | INSTALLATION OF SHOEBOX TL102-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0296 | TFS | 40.28.01 | TFS00S101MM | N.A. | TFS00S101MMCS | K214 | IP-TFS00S101MMCS-K214-045 | 30.TS101-M.F | INSTALLATION OF SHOEBOX TS101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0297 | TFS | 40.28.01 | TFS00S101MM | N.A. | TFS00S101MMCS | K214 | IP-TFS00S101MMCS-K214-045 | 30.TS101-M.F | INSTALLATION OF SHOEBOX TS101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 |  | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0298 | TFS | 40.28.01 | TFS00W104MM | N.A. | TFS00W104MMCS | K214 | IP-TFS00W104MMCS-K214-045 | 30.TW104-M.F | INSTALLATION OF SHOEBOX TW104-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 |  | 100% | 100% | 0% | 100% | 0% | 100% | 128.54 | 0
K214-TFS-0299 | TFS | 40.28.01 | TFS00W105MM | N.A. | TFS00W105MMCS | K214 | IP-TFS00W105MMCS-K214-045 | 30.TW105-M.F | INSTALLATION OF SHOEBOX TW105-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 |  | 100% | 100% | 0% | 100% | 0% | 100% | 128.54 | 0
K214-TFS-0353 | TFS | 40.28.01 | TFS00K104MM | N.A. | TFS00K104MMCS | K210 | IP-TFS00K104MMCS-K214-045 | 30.TK104-M.F | INSTALLATION OF MODULE TK104 | 1 | 0 | 1 | 0 | EA | 90 |  | 0 | 90 |  | 100% | 100% | 0% | 100% | 0% | 100% | 90 | 0
K214-TFS-0363 | TFS | 40.28.01 | TFS00SRUH06 | N.A. | TFS00SRUH06CS | K209 | IP-TFS00SRUH06CS-K214-045 | 30.SRUH06-M.F | INSTALLATION OF SRU-H06 | 1 | 1 | 1 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1068 | TFS | 40.28.01 | TFS00SRUS01 | N.A. | TFS00SRUS01CS | K209 | IP-TFS00SRUS01CS-K214-045 | 30.SRUS01-M.F | INSTALLATION OF SRU-S01 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1069 | TFS | 40.28.01 | TFS00SRUV02 | N.A. | TFS00SRUV02CS | K209 | IP-TFS00SRUV02CS-K214-045 | 30.SRUV02-M.F | INSTALLATION OF SRU-V02 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1070 | TFS | 40.28.01 | TFS00SRUV03 | N.A. | TFS00SRUV03CS | K209 | IP-TFS00SRUV03CS-K214-045 | 30.SRUV03-M.F | INSTALLATION OF SRU-V03 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1071 | TFS | 40.28.01 | TFS00SRUV04 | N.A. | TFS00SRUV04CS | K209 | IP-TFS00SRUV04CS-K214-045 | 30.SRUV04-M.F | INSTALLATION OF SRU-V04 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1072 | TFS | 40.28.01 | TFS00SRUV05 | N.A. | TFS00SRUV05CS | K209 | IP-TFS00SRUV05CS-K214-045 | 30.SRUV05-M.F | INSTALLATION OF SRU-V05 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 |  | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
[10 empty] | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS | MILESTONES | [5 empty] | TOTAL PROGRESS | EARN HOURS | Actual HOURS |  |  | COMMENT / NOTE
[20 empty] | ML01 | ML02 | ML03 | ML04 | ML05
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Drawing Number (ISO) | [5 empty] | #REF! |  | 0 |  |  | Prepare & Stage | Complete | Punch / Accept |  |  | 59.09% | 28335.6498 | 19596
[9 empty] | Weld - PIPE | 8850.579 | 9 | 8421.325 | #DIV/0! |  |  |  | 0 | 47954.986 |  | 10% | 80% | 10%
K214-TFS-0364 | TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-05 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | (DWH) | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 23.6 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0365 | TFS | 50.11.01 | TFS00F101MM | LP1Y-S(130)-018051-03 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 100% | 63.454 | 0
K214-TFS-0366 | TFS | 50.11.01 | TFS00A110MM | LP1Y-APL(100)-019072-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0367 | TFS | 50.11.01 | TFS00A111MM | LP1Y-APL(100)-019072-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0368 | TFS | 50.11.01 | TFS00B101MM | LP1Y-APL(100)-019072-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 100% | 18.768 | 0
K214-TFS-0369 | TFS | 50.11.01 | TFS00B102MM | LP1Y-APL(100)-019072-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0370 | TFS | 50.11.01 | TFS00A112MM | LP1Y-APL(100)-019072-14 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0371 | TFS | 50.11.01 | TFS00L101MM | LP1Y-APL(100)-019072-16 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0372 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AWNP-037002-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0373 | TFS | 50.11.01 | TFS00J101MM | LP1Y-AWNP-037002-04 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 21.345 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0374 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AWNP-037002-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0375 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AWNP-037002-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0376 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AWNP-037002-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0377 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AWNP-037002-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0378 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AWNP-037002-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0379 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AWNP-037002-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0380 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AWNP-037002-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 43.453 |  | 100% | 100% | 100% |  |  | 100% | 43.453 | 0
K214-TFS-0381 | TFS | 50.11.01 | TFS00B109MM | LP1Y-AWNP-037002-13 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0382 | TFS | 50.11.01 | TFS00S101MM | LP1Y-AWNP-037004-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.317 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0383 | TFS | 50.11.01 | TFS00W105MM | LP1Y-AWNP-037004-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.16 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0384 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AWNP-037006-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0385 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AWNP-037006-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0386 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AWNP-037006-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0387 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AWNP-037006-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0388 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AWNP-037006-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0389 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AWNP-037006-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0390 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AWNP-037007-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0391 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AWNP-037007-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0392 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-101309-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.475 |  | 100% | 100% | 100% |  |  | 100% | 58.475 | 0
K214-TFS-0393 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-168101-03 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0394 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-168101-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0395 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-168101-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.5 |  | 100% | 100% | 100% |  |  | 100% | 37.5 | 0
K214-TFS-0396 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-168101-06 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0397 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-802111-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0398 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-802111-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 100% | 44.719 | 0
K214-TFS-0399 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-802111-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 89.4 |  | 100% | 100% | 100% |  |  | 100% | 89.4 | 0
K214-TFS-0400 | TFS | 50.11.01 | TFS00F101MM | LP1Y-AWNP-802111-04 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 45.944 |  | 100% | 100% | 100% |  |  | 100% | 45.944 | 0
K214-TFS-0401 | TFS | 50.11.01 | TFS00A107MM | LP1Y-AWNP-850001-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 75.012 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0402 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AWNP-850001-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 4 | 0 | 4 | 4 | EA | 0 |  | 0 | 75.012 |  | 100% | 100% | 100% |  |  | 100% | 75.012 | 0
K214-TFS-0403 | TFS | 50.11.01 | TFS00A109MM | LP1Y-AWNP-850001-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0404 | TFS | 50.11.01 | TFS00H101MM | LP1Y-BS-016012-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.085 |  | 100% | 100% | 100% |  |  | 100% | 2.085 | 0
K214-TFS-0405 | TFS | 50.11.01 | TFS00A104MM | LP1Y-APL(100)-019072-19 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0406 | TFS | 50.11.01 | TFS00L102MM | LP1Y-APL(100)-019072-20 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0407 | TFS | 50.11.01 | TFS00B108MM | LP1Y-APL(100)-034026-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0408 | TFS | 50.11.01 | TFS00B109MM | LP1Y-APL(100)-034026-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0409 | TFS | 50.11.01 | TFS00B103MM | LP1Y-APL(100)-034026-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0410 | TFS | 50.11.01 | TFS00B104MM | LP1Y-APL(100)-034026-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0411 | TFS | 50.11.01 | TFS00B105MM | LP1Y-APL(100)-034026-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0412 | TFS | 50.11.01 | TFS00B106MM | LP1Y-APL(100)-034026-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0413 | TFS | 50.11.01 | TFS00B107MM | LP1Y-APL(100)-034026-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0414 | TFS | 50.11.01 | TFS00J101MM | LP1Y-APL(100)-034032-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.074 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0415 | TFS | 50.11.01 | TFS00B108MM | LP1Y-APL(100)-034033-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0416 | TFS | 50.11.01 | TFS00S101MM | LP1Y-APL(100)-034033-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.618 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0417 | TFS | 50.11.01 | TFS00B102MM | LP1Y-APL(100)-034033-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0418 | TFS | 50.11.01 | TFS00B103MM | LP1Y-APL(100)-034033-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0419 | TFS | 50.11.01 | TFS00B104MM | LP1Y-APL(100)-034033-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0420 | TFS | 50.11.01 | TFS00B105MM | LP1Y-APL(100)-034033-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0421 | TFS | 50.11.01 | TFS00B106MM | LP1Y-APL(100)-034033-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0422 | TFS | 50.11.01 | TFS00B107MM | LP1Y-APL(100)-034033-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0423 | TFS | 50.11.01 | TFS00W105MM | LP1Y-APL(100)-034040-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0424 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AWNP-015001-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0425 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-015001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0426 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-015001-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0427 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-015001-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 DWHU Connection | 2 |  | 2 | 2 | EA | 0 |  | 0 | 81.71 |  | 100% | 100% | 100% |  |  | 100% | 81.71 | 0
K214-TFS-1314 | TFS | 50.11.01 | TFS00A101MM | LP1Y-AWNP-015001-07 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA101 TO TA102 DWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  |  | 44.7 |  | 100% | 100% | 100% |  |  | 100% | 44.7 | 0
K214-TFS-0428 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-015003-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0429 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-015003-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0430 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-015003-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0431 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-015003-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0432 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AWNP-015003-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 100% | 37.506 | 0
K214-TFS-1370 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AWNP-015003-08 |  |  |  |  | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753
K214-TFS-0433 | TFS | 50.11.01 | TFS00A110MM | LP1Y-AWNP-015003-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0434 | TFS | 50.11.01 | TFS00A111MM | LP1Y-AWNP-015003-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0435 | TFS | 50.11.01 | TFS00G101MM | LP1Y-AWNP-015004-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 100% | 4.205 | 0
K214-TFS-0436 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACN-010018-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0437 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACN-010018-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 52 |  | 0 | 52 |  | 100% | 100% | 100% |  |  | 100% | 52 | 0
K214-TFS-0438 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACN-010018-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0439 | TFS | 50.11.01 | TFS00A106MM | LP1Y-ACN-010018-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0440 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACN-010018-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0441 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACN-010018-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0442 | TFS | 50.11.01 | TFS00A109MM | LP1Y-ACN-010018-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0443 | TFS | 50.11.01 | TFS00A110MM | LP1Y-ACN-010018-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0444 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACN-011008-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 26.602 |  | 100% | 100% | 100% |  |  | 100% | 26.602 | 0
K214-TFS-0445 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACN-011008-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 10% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0446 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACN-011008-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 100% | 25.85 | 0
K214-TFS-0447 | TFS | 50.11.01 | TFS00A112MM | LP1Y-ACN-064102-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0448 | TFS | 50.11.01 | TFS00L101MM | LP1Y-ACN-064102-04 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0449 | TFS | 50.11.01 | TFS00L102MM | LP1Y-ACN-064102-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0450 | TFS | 50.11.01 | TFS00A111MM | LP1Y-ACN-177302-06 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0451 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACN-850013-02 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.383 |  | 100% | 100% | 100% |  |  | 100% | 19.383 | 0
K214-TFS-0452 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACN-850013-03 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.782 |  | 100% | 100% | 100% |  |  | 100% | 18.782 | 0
K214-TFS-0453 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACNDMSO-010008-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.6 |  | 100% | 100% | 100% |  |  | 100% | 37.6 | 0
K214-TFS-0454 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACNDMSO-010008-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0455 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACNDMSO-010008-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0456 | TFS | 50.11.01 | TFS00A106MM | LP1Y-ACNDMSO-010008-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0457 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACNDMSO-010008-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0458 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACNDMSO-010008-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.766 |  | 100% | 100% | 100% |  |  | 100% | 38.766 | 0
K214-TFS-0459 | TFS | 50.11.01 | TFS00A109MM | LP1Y-ACNDMSO-010008-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | -1 | 1 | 2 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 100% | 25.912 | 0 |  |  | Not a DWHU
K214-TFS-0460 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACNDMSO-010032-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 100% | 18.813 | 0
K214-TFS-0461 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACNDMSO-010032-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0462 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACNDMSO-010032-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0463 | TFS | 50.11.01 | TFS00A110MM | LP1Y-ACNDMSO-010032-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 51.824 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1315 | TFS | 50.11.01 | TFS00A101MM | LP1Y-AI(100)-019009-02 |  |  |  |  | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0464 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AI(100)-019009-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0465 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AI(100)-019009-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0466 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AI(100)-019009-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0467 | TFS | 50.11.01 | TFS00A107MM | LP1Y-AI(100)-019009-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0468 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AI(100)-019009-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0469 | TFS | 50.11.01 | TFS00A109MM | LP1Y-AI(100)-019009-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0470 | TFS | 50.11.01 | TFS00A110MM | LP1Y-AI(100)-019009-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0471 | TFS | 50.11.01 | TFS00A111MM | LP1Y-AI(100)-019009-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0472 | TFS | 50.11.01 | TFS00A112MM | LP1Y-AI(100)-019009-12 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0473 | TFS | 50.11.01 | TFS00L101MM | LP1Y-AI(100)-019009-13 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0474 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AI(100)-019009-14 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 100% | 18.768 | 0
K214-TFS-0475 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AI(100)-019009-15 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0476 | TFS | 50.11.01 | TFS00L102MM | LP1Y-AI(100)-019009-20 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0477 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AI(100)-034028-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0478 | TFS | 50.11.01 | TFS00B109MM | LP1Y-AI(100)-034028-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0479 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AI(100)-034028-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0480 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AI(100)-034028-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0481 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AI(100)-034028-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0482 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AI(100)-034028-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0483 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AI(100)-034028-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0484 | TFS | 50.11.01 | TFS00F101MM | LP1Y-APL(100)-019001-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 45.844 |  | 100% | 100% | 100% |  |  | 100% | 45.844 | 0
K214-TFS-0485 | TFS | 50.11.01 | TFS00H101MM | LP1Y-APL(100)-019053-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.006 |  | 100% | 100% | 100% |  |  | 100% | 33.006 | 0
K214-TFS-0486 | TFS | 50.11.01 | TFS00A104MM | LP1Y-APL(100)-019053-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.96 |  | 100% | 100% | 100% |  |  | 100% | 33.96 | 0
K214-TFS-0487 | TFS | 50.11.01 | TFS00A105MM | LP1Y-APL(100)-019053-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.59 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0488 | TFS | 50.11.01 | TFS00A106MM | LP1Y-APL(100)-019053-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.59 |  | 100% | 100% | 100% |  |  | 100% | 44.59 | 0
K214-TFS-0489 | TFS | 50.11.01 | TFS00A107MM | LP1Y-APL(100)-019053-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.96 |  | 100% | 100% | 100% |  |  | 100% | 33.96 | 0
K214-TFS-0490 | TFS | 50.11.01 | TFS00A108MM | LP1Y-APL(100)-019053-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.939 |  | 100% | 100% | 100% |  |  | 100% | 33.939 | 0
K214-TFS-0491 | TFS | 50.11.01 | TFS00A102MM | LP1Y-APL(100)-019072-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0492 | TFS | 50.11.01 | TFS00A103MM | LP1Y-APL(100)-019072-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38 |  | 100% | 100% | 100% |  |  | 100% | 38 | 0
K214-TFS-0493 | TFS | 50.11.01 | TFS00A105MM | LP1Y-APL(100)-019072-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0494 | TFS | 50.11.01 | TFS00A106MM | LP1Y-APL(100)-019072-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0495 | TFS | 50.11.01 | TFS00A107MM | LP1Y-APL(100)-019072-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0496 | TFS | 50.11.01 | TFS00A108MM | LP1Y-APL(100)-019072-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0497 | TFS | 50.11.01 | TFS00A109MM | LP1Y-APL(100)-019072-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 DWHU Connection | 1 | 1 | 2 | 1 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 100% | 37.506 | 0
K214-TFS-0498 | TFS | 50.11.01 | TFS00A102MM | LP1Y-BS-100104-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0499 | TFS | 50.11.01 | TFS00A103MM | LP1Y-BS-100104-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0500 | TFS | 50.11.01 | TFS00A104MM | LP1Y-BS-100104-07 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.079 |  | 100% | 100% | 100% |  |  | 100% | 2.079 | 0
K214-TFS-0501 | TFS | 50.11.01 | TFS00A105MM | LP1Y-BS-100104-08 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0502 | TFS | 50.11.01 | TFS00A106MM | LP1Y-BS-100104-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.079 |  | 100% | 100% | 100% |  |  | 100% | 2.079 | 0
K214-TFS-0503 | TFS | 50.11.01 | TFS00B101MM | LP1Y-BS-100104-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.086 |  | 100% | 100% | 100% |  |  | 100% | 2.086 | 0
K214-TFS-0504 | TFS | 50.11.01 | TFS00B102MM | LP1Y-BS-100104-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0505 | TFS | 50.11.01 | TFS00F101MM | LP1Y-CHWR-017024-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 79.427 |  | 100% | 100% | 100% |  |  | 100% | 79.427 | 0
K214-TFS-0506 | TFS | 50.11.01 | TFS00G101MM | LP1Y-CHWR-017059-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 100% | 63.454 | 0
K214-TFS-0507 | TFS | 50.11.01 | TFS00A103MM | LP1Y-CHWR-017059-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0508 | TFS | 50.11.01 | TFS00A104MM | LP1Y-CHWR-017059-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0509 | TFS | 50.11.01 | TFS00A105MM | LP1Y-CHWR-017059-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0510 | TFS | 50.11.01 | TFS00A106MM | LP1Y-CHWR-017059-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 130.284 |  | 100% | 100% | 100% |  |  | 100% | 130.284 | 0
K214-TFS-0511 | TFS | 50.11.01 | TFS00A107MM | LP1Y-CHWR-017059-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0512 | TFS | 50.11.01 | TFS00A108MM | LP1Y-CHWR-017070-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0513 | TFS | 50.11.01 | TFS00A109MM | LP1Y-CHWR-017070-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0514 | TFS | 50.11.01 | TFS00A110MM | LP1Y-CHWR-017070-04 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0515 | TFS | 50.11.01 | TFS00W105MM | LP1Y-CHWR-033041-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 100% | 42.463 | 0
K214-TFS-0516 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWR-033044-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0517 | TFS | 50.11.01 | TFS00S101MM | LP1Y-CHWR-033044-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.697 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0518 | TFS | 50.11.01 | TFS00B102MM | LP1Y-CHWR-033044-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 67.596 |  | 100% | 100% | 100% |  |  | 100% | 67.596 | 0
K214-TFS-0519 | TFS | 50.11.01 | TFS00B103MM | LP1Y-CHWR-033044-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0520 | TFS | 50.11.01 | TFS00B104MM | LP1Y-CHWR-033044-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0521 | TFS | 50.11.01 | TFS00B105MM | LP1Y-CHWR-033044-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0522 | TFS | 50.11.01 | TFS00B106MM | LP1Y-CHWR-033044-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0523 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWR-033044-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0524 | TFS | 50.11.01 | TFS00J101MM | LP1Y-CHWR-033047-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 59.233 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0525 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWR-033068-02 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0526 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWR-033068-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0527 | TFS | 50.11.01 | TFS00B109MM | LP1Y-CHWR-033068-04 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0528 | TFS | 50.11.01 | TFS00G101MM | LP1Y-CHWS-017022-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 100% | 63.454 | 0
K214-TFS-0529 | TFS | 50.11.01 | TFS00A103MM | LP1Y-CHWS-017022-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0530 | TFS | 50.11.01 | TFS00A104MM | LP1Y-CHWS-017022-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 63.524 |  | 100% | 100% | 100% |  |  | 100% | 63.524 | 0
K214-TFS-0531 | TFS | 50.11.01 | TFS00A105MM | LP1Y-CHWS-017022-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0532 | TFS | 50.11.01 | TFS00A106MM | LP1Y-CHWS-017022-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0533 | TFS | 50.11.01 | TFS00A107MM | LP1Y-CHWS-017022-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 100% | 65.142 | 0
K214-TFS-0534 | TFS | 50.11.01 | TFS00A108MM | LP1Y-CHWS-017069-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0535 | TFS | 50.11.01 | TFS00A109MM | LP1Y-CHWS-017069-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0536 | TFS | 50.11.01 | TFS00A110MM | LP1Y-CHWS-017069-04 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 100% | 10.792 | 0
K214-TFS-0537 | TFS | 50.11.01 | TFS00F101MM | LP1Y-CHWS-017111-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 79.427 |  | 100% | 100% | 100% |  |  | 100% | 79.427 | 0
K214-TFS-0538 | TFS | 50.11.01 | TFS00J101MM | LP1Y-CHWS-033023-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 59.233 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0539 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWS-033032-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0540 | TFS | 50.11.01 | TFS00S101MM | LP1Y-CHWS-033032-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 65.697 |  | 100% | 100% | 100% |  |  | 100% | 65.697 | 0
K214-TFS-0541 | TFS | 50.11.01 | TFS00B102MM | LP1Y-CHWS-033032-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 67.596 |  | 100% | 100% | 100% |  |  | 100% | 67.596 | 0
K214-TFS-0542 | TFS | 50.11.01 | TFS00B103MM | LP1Y-CHWS-033032-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0543 | TFS | 50.11.01 | TFS00B104MM | LP1Y-CHWS-033032-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0544 | TFS | 50.11.01 | TFS00B105MM | LP1Y-CHWS-033032-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0545 | TFS | 50.11.01 | TFS00B106MM | LP1Y-CHWS-033032-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0546 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWS-033032-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0547 | TFS | 50.11.01 | TFS00W105MM | LP1Y-CHWS-033038-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 100% | 42.463 | 0
K214-TFS-0548 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWS-033067-02 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0549 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWS-033067-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0550 | TFS | 50.11.01 | TFS00B109MM | LP1Y-CHWS-033067-04 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0551 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DCM-010017-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0552 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DCM-010017-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.75 |  | 100% | 100% | 100% |  |  | 100% | 38.75 | 0
K214-TFS-0553 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DCM-010017-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0554 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DCM-010017-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0555 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DCM-010017-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0556 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DCM-010017-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0557 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DCM-010017-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0558 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DCM-010017-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0559 | TFS | 50.11.01 | TFS00A111MM | LP1Y-DCM-177202-06 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0560 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMF-010036-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0561 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMF-010036-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0562 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMF-010036-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0563 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMF-065102-02 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 100% | 27.354 | 0
K214-TFS-0564 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DMF-065102-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 54.708 |  | 100% | 100% | 100% |  |  | 100% | 54.708 | 0
K214-TFS-0565 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DMF-065102-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 54.692 |  | 100% | 100% | 100% |  |  | 100% | 54.692 | 0
K214-TFS-0566 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMF-065102-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 54.708 |  | 100% | 100% | 100% |  |  | 100% | 54.708 | 0
K214-TFS-0567 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DMF-065102-06 (SUPERSEDED) | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | -1 | 0 | #DIV/0! | EA | 0 |  | 0 | 0 |  | 0% | 0% | 0% |  |  | #DIV/0! | 0 | 0 |  |  | Drawing Superseded
K214-TFS-1371 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMF-062302-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 100% | 27.354
K214-TFS-0568 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DMF-062302-06 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 100% | 27.354 | 0
K214-TFS-0569 | TFS | 50.11.01 | TFS00A111MM | LP1Y-DMF-065102-08 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0570 | TFS | 50.11.01 | TFS00A112MM | LP1Y-DMF-065102-09 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0571 | TFS | 50.11.01 | TFS00L101MM | LP1Y-DMF-065102-10 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.602 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0572 | TFS | 50.11.01 | TFS00L102MM | LP1Y-DMF-065102-11 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.602 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0573 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMSO-010012-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0574 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMSO-010012-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.75 |  | 100% | 100% | 100% |  |  | 100% | 38.75 | 0
K214-TFS-0575 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMSO-010012-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0576 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DMSO-010012-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-1372 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMSO-010012-07 |  |  |  |  | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.92 |  | 100% | 100% | 100% |  |  | 100% | 25.92
K214-TFS-0577 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DMSO-010012-08 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 26 |  | 100% | 100% | 100% |  |  | 100% | 26 | 0
K214-TFS-0578 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMSO-010033-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 39.88 |  | 100% | 100% | 100% |  |  | 100% | 39.88 | 0
K214-TFS-0579 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMSO-010033-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0580 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMSO-010033-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0581 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DMSO-010033-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0582 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMSO-010033-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0583 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DMSO-010033-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 51.84 |  | 100% | 100% | 100% |  |  | 100% | 51.84 | 0
K214-TFS-0584 | TFS | 50.11.01 | TFS00L102MM | LP1Y-H2SO4-013011-01 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0585 | TFS | 50.11.01 | TFS00L101MM | LP1Y-H2SO4-013011-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0586 | TFS | 50.11.01 | TFS00A112MM | LP1Y-H2SO4-013011-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0587 | TFS | 50.11.01 | TFS00A111MM | LP1Y-H2SO4-013011-04 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0588 | TFS | 50.11.01 | TFS00A110MM | LP1Y-H2SO4-013011-05 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0589 | TFS | 50.11.01 | TFS00A109MM | LP1Y-H2SO4-013011-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0590 | TFS | 50.11.01 | TFS00A108MM | LP1Y-H2SO4-013011-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0591 | TFS | 50.11.01 | TFS00A107MM | LP1Y-H2SO4-013011-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 100% | 32.151 | 0
K214-TFS-0592 | TFS | 50.11.01 | TFS00A106MM | LP1Y-H2SO4-013011-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0593 | TFS | 50.11.01 | TFS00A105MM | LP1Y-H2SO4-013011-10 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0594 | TFS | 50.11.01 | TFS00A104MM | LP1Y-H2SO4-013011-11 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0595 | TFS | 50.11.01 | TFS00A103MM | LP1Y-H2SO4-013011-12 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0596 | TFS | 50.11.01 | TFS00A102MM | LP1Y-H2SO4-013011-13 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0597 | TFS | 50.11.01 | TFS00B101MM | LP1Y-H2SO4-013011-15 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.218 |  | 100% | 100% | 100% |  |  | 100% | 31.218 | 0
K214-TFS-0598 | TFS | 50.11.01 | TFS00B102MM | LP1Y-H2SO4-013011-16 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0599 | TFS | 50.11.01 | TFS00B108MM | LP1Y-H2SO4-032003-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0600 | TFS | 50.11.01 | TFS00A102MM | LP1Y-H2SO4-032003-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0601 | TFS | 50.11.01 | TFS00A103MM | LP1Y-H2SO4-032003-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0602 | TFS | 50.11.01 | TFS00A104MM | LP1Y-H2SO4-032003-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0603 | TFS | 50.11.01 | TFS00A105MM | LP1Y-H2SO4-032003-06 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0604 | TFS | 50.11.01 | TFS00A106MM | LP1Y-H2SO4-032003-07 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.424 |  | 100% | 100% | 100% |  |  | 100% | 27.424 | 0
K214-TFS-0605 | TFS | 50.11.01 | TFS00B101MM | LP1Y-H2SO4-032003-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 28.169 |  | 100% | 100% | 100% |  |  | 100% | 28.169 | 0
K214-TFS-0606 | TFS | 50.11.01 | TFS00B102MM | LP1Y-H2SO4-032003-12 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 56.338 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0607 | TFS | 50.11.01 | TFS00B104MM | LP1Y-H2SO4-032003-14 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0608 | TFS | 50.11.01 | TFS00B105MM | LP1Y-H2SO4-032003-15 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0609 | TFS | 50.11.01 | TFS00B106MM | LP1Y-H2SO4-032003-16 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0610 | TFS | 50.11.01 | TFS00B107MM | LP1Y-H2SO4-032003-17 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0611 | TFS | 50.11.01 | TFS00B109MM | LP1Y-H2SO4-032003-18 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0612 | TFS | 50.11.01 | TFS00J101MM | LP1Y-H2SO4-032018-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 21.345 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0613 | TFS | 50.11.01 | TFS00H101MM | LP1Y-IPA-010016-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0614 | TFS | 50.11.01 | TFS00A104MM | LP1Y-IPA-010016-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 51.7 |  | 100% | 100% | 100% |  |  | 100% | 51.7 | 0
K214-TFS-0615 | TFS | 50.11.01 | TFS00A105MM | LP1Y-IPA-010016-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 100% | 25.85 | 0
K214-TFS-0616 | TFS | 50.11.01 | TFS00A106MM | LP1Y-IPA-010016-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 100% | 25.85 | 0
K214-TFS-0617 | TFS | 50.11.01 | TFS00A107MM | LP1Y-IPA-010016-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 100% | 25.851 | 0
K214-TFS-0618 | TFS | 50.11.01 | TFS00A108MM | LP1Y-IPA-010016-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 100% | 25.851 | 0
K214-TFS-0619 | TFS | 50.11.01 | TFS00A109MM | LP1Y-IPA-010016-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 100% | 25.851 | 0
K214-TFS-0620 | TFS | 50.11.01 | TFS00A110MM | LP1Y-IPA-010016-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.851 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0621 | TFS | 50.11.01 | TFS00A111MM | LP1Y-IPA-177102-07 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0622 | TFS | 50.11.01 | TFS00H101MM | LP1Y-MTBE-010019-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0623 | TFS | 50.11.01 | TFS00A104MM | LP1Y-MTBE-010019-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0624 | TFS | 50.11.01 | TFS00A105MM | LP1Y-MTBE-010019-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0625 | TFS | 50.11.01 | TFS00A106MM | LP1Y-MTBE-010019-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0626 | TFS | 50.11.01 | TFS00A107MM | LP1Y-MTBE-010019-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0627 | TFS | 50.11.01 | TFS00A108MM | LP1Y-MTBE-010019-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0628 | TFS | 50.11.01 | TFS00A109MM | LP1Y-MTBE-010019-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0629 | TFS | 50.11.01 | TFS00A110MM | LP1Y-MTBE-010019-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0630 | TFS | 50.11.01 | TFS00A111MM | LP1Y-MTBE-010019-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0631 | TFS | 50.11.01 | TFS00A112MM | LP1Y-MTBE-063102-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0632 | TFS | 50.11.01 | TFS00L101MM | LP1Y-MTBE-063102-04 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0633 | TFS | 50.11.01 | TFS00L102MM | LP1Y-MTBE-063102-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0634 | TFS | 50.11.01 | TFS00A102MM | LP1Y-N2(100)-018010-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0635 | TFS | 50.11.01 | TFS00A103MM | LP1Y-N2(100)-018010-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0636 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2(100)-018010-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0637 | TFS | 50.11.01 | TFS00A105MM | LP1Y-N2(100)-018010-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0638 | TFS | 50.11.01 | TFS00A106MM | LP1Y-N2(100)-018010-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0639 | TFS | 50.11.01 | TFS00A107MM | LP1Y-N2(100)-018010-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 62 |  | 100% | 100% | 100% |  |  | 100% | 62 | 0
K214-TFS-0640 | TFS | 50.11.01 | TFS00A108MM | LP1Y-N2(100)-018010-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0641 | TFS | 50.11.01 | TFS00A109MM | LP1Y-N2(100)-018010-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 DWHU Connection | 1 | 1 | 2 | 1 | EA | 0 |  | 0 | 62.192 |  | 100% | 100% | 100% |  |  | 100% | 62.192 | 0
K214-TFS-0642 | TFS | 50.11.01 | TFS00A110MM | LP1Y-N2(100)-018010-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0643 | TFS | 50.11.01 | TFS00A111MM | LP1Y-N2(100)-018010-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0644 | TFS | 50.11.01 | TFS00B102MM | LP1Y-N2(100)-018010-12 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.536 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0645 | TFS | 50.11.01 | TFS00A112MM | LP1Y-N2(100)-018010-13 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.073 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0646 | TFS | 50.11.01 | TFS00B101MM | LP1Y-N2(100)-018010-18 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 100% | 18.768 | 0
K214-TFS-0647 | TFS | 50.11.01 | TFS00L101MM | LP1Y-N2(100)-018058-03 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0648 | TFS | 50.11.01 | TFS00L102MM | LP1Y-N2(100)-018058-04 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0649 | TFS | 50.11.01 | TFS00H101MM | LP1Y-N2(100)-018075-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.006 |  | 100% | 100% | 100% |  |  | 100% | 33.006 | 0
K214-TFS-0650 | TFS | 50.11.01 | TFS00A103MM | LP1Y-N2(100)-018075-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0651 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2(100)-018075-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 84.426 |  | 100% | 100% | 100% |  |  | 100% | 84.426 | 0
K214-TFS-0652 | TFS | 50.11.01 | TFS00A105MM | LP1Y-N2(100)-018075-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0653 | TFS | 50.11.01 | TFS00A106MM | LP1Y-N2(100)-018075-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0654 | TFS | 50.11.01 | TFS00A107MM | LP1Y-N2(100)-018075-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0655 | TFS | 50.11.01 | TFS00A108MM | LP1Y-N2(100)-018075-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0656 | TFS | 50.11.01 | TFS00B101MM | LP1Y-N2(100)-018075-08 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.143 |  | 100% | 100% | 100% |  |  | 100% | 31.143 | 0
K214-TFS-0657 | TFS | 50.11.01 | TFS00B102MM | LP1Y-N2(100)-018075-09 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0658 | TFS | 50.11.01 | TFS00B103MM | LP1Y-N2(100)-018075-10 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.138 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0659 | TFS | 50.11.01 | TFS00B104MM | LP1Y-N2(100)-018075-11 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0660 | TFS | 50.11.01 | TFS00B105MM | LP1Y-N2(100)-018075-12 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0661 | TFS | 50.11.01 | TFS00B106MM | LP1Y-N2(100)-018075-13 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0662 | TFS | 50.11.01 | TFS00B107MM | LP1Y-N2(100)-018075-14 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0663 | TFS | 50.11.01 | TFS00A102MM | LP1Y-N2(100)-018075-15 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 100% | 42.165 | 0
K214-TFS-0664 | TFS | 50.11.01 | TFS00B108MM | LP1Y-N2(100)-018075-17 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0665 | TFS | 50.11.01 | TFS00B109MM | LP1Y-N2(100)-018075-18 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0666 | TFS | 50.11.01 | TFS00B108MM | LP1Y-N2(100)-034025-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0667 | TFS | 50.11.01 | TFS00B109MM | LP1Y-N2(100)-034025-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0668 | TFS | 50.11.01 | TFS00B103MM | LP1Y-N2(100)-034025-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0669 | TFS | 50.11.01 | TFS00B104MM | LP1Y-N2(100)-034025-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0670 | TFS | 50.11.01 | TFS00B105MM | LP1Y-N2(100)-034025-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0671 | TFS | 50.11.01 | TFS00B106MM | LP1Y-N2(100)-034025-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0672 | TFS | 50.11.01 | TFS00B107MM | LP1Y-N2(100)-034025-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0673 | TFS | 50.11.01 | TFS00J101MM | LP1Y-N2(100)-034029-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.94 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0674 | TFS | 50.11.01 | TFS00S101MM | LP1Y-N2(100)-034037-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 20.455 |  | 100% | 100% | 100% |  |  | 100% | 20.455 | 0
K214-TFS-0675 | TFS | 50.11.01 | TFS00W105MM | LP1Y-N2(100)-034037-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.766 |  | 100% | 100% | 100% |  |  | 100% | 18.766 | 0
K214-TFS-0676 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2-180029-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0677 | TFS | 50.11.01 | TFS00L101MM | LP1Y-NAOH50-013012-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0678 | TFS | 50.11.01 | TFS00A112MM | LP1Y-NAOH50-013012-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0679 | TFS | 50.11.01 | TFS00A111MM | LP1Y-NAOH50-013012-04 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0680 | TFS | 50.11.01 | TFS00A110MM | LP1Y-NAOH50-013012-05 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0681 | TFS | 50.11.01 | TFS00A109MM | LP1Y-NAOH50-013012-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0682 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-013012-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0683 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NAOH50-013012-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0684 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NAOH50-013012-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0685 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NAOH50-013012-10 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0686 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NAOH50-013012-11 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0687 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NAOH50-013012-12 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0688 | TFS | 50.11.01 | TFS00A102MM | LP1Y-NAOH50-013012-13 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 100% | 34.017 | 0
K214-TFS-0689 | TFS | 50.11.01 | TFS00B101MM | LP1Y-NAOH50-013012-15 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.218 |  | 100% | 100% | 100% |  |  | 100% | 31.218 | 0
K214-TFS-0690 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NAOH50-013012-16 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0691 | TFS | 50.11.01 | TFS00G101MM | LP1Y-NAOH50-016011-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 100% | 18.813 | 0
K214-TFS-0692 | TFS | 50.11.01 | TFS00A109MM | LP1Y-NAOH50-016020-01 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0693 | TFS | 50.11.01 | TFS00B108MM | LP1Y-NAOH50-032002-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0694 | TFS | 50.11.01 | TFS00A102MM | LP1Y-NAOH50-032002-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.424 |  | 100% | 100% | 100% |  |  | 100% | 27.424 | 0
K214-TFS-0695 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NAOH50-032002-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-0696 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NAOH50-032002-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-0697 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NAOH50-032002-06 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0698 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NAOH50-032002-07 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0699 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NAOH50-032002-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0700 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-032002-09 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-1373 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-032002-10 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 1 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 100% | 27.354
K214-TFS-0701 | TFS | 50.11.01 | TFS00B109MM | LP1Y-NAOH50-032002-11 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0702 | TFS | 50.11.01 | TFS00B101MM | LP1Y-NAOH50-032002-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 28.169 |  | 100% | 100% | 100% |  |  | 100% | 28.169 | 0
K214-TFS-0703 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NAOH50-032002-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0704 | TFS | 50.11.01 | TFS00B103MM | LP1Y-NAOH50-032002-14 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0705 | TFS | 50.11.01 | TFS00B104MM | LP1Y-NAOH50-032002-15 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0706 | TFS | 50.11.01 | TFS00B105MM | LP1Y-NAOH50-032002-16 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0707 | TFS | 50.11.01 | TFS00B106MM | LP1Y-NAOH50-032002-17 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0708 | TFS | 50.11.01 | TFS00B107MM | LP1Y-NAOH50-032002-18 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0709 | TFS | 50.11.01 | TFS00J101MM | LP1Y-NAOH50-032017-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.545 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0710 | TFS | 50.11.01 | TFS00G101MM | LP1Y-NG-018007-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.777 |  | 100% | 100% | 100% |  |  | 100% | 13.777 | 0
K214-TFS-0711 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NG-018007-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 100% | 13.409 | 0
K214-TFS-0712 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NG-018007-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 100% | 13.409 | 0
K214-TFS-0713 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NG-018007-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.405 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0714 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NG-018007-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 100% | 13.409 | 0
K214-TFS-0715 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NG-018007-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 100% | 13.409 | 0
K214-TFS-0716 | TFS | 50.11.01 | TFS00F101MM | LP1Y-NG-018012-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.777 |  | 100% | 100% | 100% |  |  | 100% | 13.777 | 0
K214-TFS-0717 | TFS | 50.11.01 | TFS00J101MM | LP1Y-NG-034031-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.207 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0718 | TFS | 50.11.01 | TFS00B108MM | LP1Y-NG-034034-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0719 | TFS | 50.11.01 | TFS00S101MM | LP1Y-NG-034034-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 100% | 13.409 | 0
K214-TFS-0720 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NG-034034-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 12.303 |  | 100% | 100% | 100% |  |  | 100% | 12.303 | 0
K214-TFS-0721 | TFS | 50.11.01 | TFS00B103MM | LP1Y-NG-034034-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0722 | TFS | 50.11.01 | TFS00B104MM | LP1Y-NG-034034-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0723 | TFS | 50.11.01 | TFS00B105MM | LP1Y-NG-034034-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0724 | TFS | 50.11.01 | TFS00B106MM | LP1Y-NG-034034-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0725 | TFS | 50.11.01 | TFS00B107MM | LP1Y-NG-034034-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0726 | TFS | 50.11.01 | TFS00B109MM | LP1Y-NG-034034-10 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.081 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0727 | TFS | 50.11.01 | TFS00W105MM | LP1Y-NG-034039-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 9.365 |  | 100% | 100% | 100% |  |  | 100% | 9.365 | 0
K214-TFS-0728 | TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 16.542 |  | 100% | 100% | 100% |  |  | 100% | 16.542 | 0
K214-TFS-0729 | TFS | 50.11.01 | TFS00G101MM | LP1Y-PSC-017031-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.071 |  | 100% | 100% | 100% |  |  | 100% | 13.071 | 0
K214-TFS-0730 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PSC-017031-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.228 |  | 100% | 100% | 100% |  |  | 100% | 42.228 | 0
K214-TFS-0731 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PSC-017031-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 12.702 |  | 100% | 100% | 100% |  |  | 100% | 12.702 | 0
K214-TFS-0732 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PSC-017031-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 12.706 |  | 100% | 100% | 100% |  |  | 100% | 12.706 | 0
K214-TFS-0733 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PSC-017031-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.075 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0734 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PSC-017031-11 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 100% | 16.075 | 0
K214-TFS-0735 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PSC-017031-13 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 100% | 16.075 | 0
K214-TFS-0736 | TFS | 50.11.01 | TFS00W105MM | LP1Y-PSC-033040-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 100% | 15.609 | 0
K214-TFS-0737 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PSC-033042-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0738 | TFS | 50.11.01 | TFS00S101MM | LP1Y-PSC-033042-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 100% | 16.075 | 0
K214-TFS-0739 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PSC-033042-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 100% | 15.609 | 0
K214-TFS-0740 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PSC-033042-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0741 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PSC-033042-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0742 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PSC-033042-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0743 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PSC-033042-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0744 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PSC-033042-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0745 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PSC-033042-10 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0746 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PSC-033049-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.702 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0747 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PV-013001-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 41.875 |  | 100% | 100% | 100% |  |  | 100% | 41.875 | 0
K214-TFS-0748 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PV-013001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.066 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0749 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PV-013001-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.29 |  | 100% | 100% | 100% |  |  | 100% | 42.29 | 0
K214-TFS-0750 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PV-013001-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.29 |  | 100% | 100% | 100% |  |  | 100% | 42.29 | 0
K214-TFS-0751 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PV-013001-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.449 |  | 100% | 100% | 100% |  |  | 100% | 42.449 | 0
K214-TFS-0752 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PV-013001-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.877 |  | 100% | 100% | 100% |  |  | 100% | 42.877 | 0
K214-TFS-0753 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PV-013001-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.877 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0754 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PV-013001-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0755 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PV-300064-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.194 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0756 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PV-300064-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.106 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0757 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PV-300065-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.154 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0758 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PVP-013004-02 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0759 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PVP-013004-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0760 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PVP-013004-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection (VOIDED) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0761 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PVP-013004-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection *DWG VOIDED* | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0762 | TFS | 50.11.01 | TFS00L102MM | LP1Y-PVP-013022-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 103.4 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0763 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PVP-102109-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 100% | 25.098 | 0
K214-TFS-0764 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PVP-110218-02 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0765 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PVP-112109-01 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0766 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PVP-300308-04 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 6 | 0 | 6 | 0 | EA | 0 |  | 0 | 126.384 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0767 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PVP-300308-06 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 42.128 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0768 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014002-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0769 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014002-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0770 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014003-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0771 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014003-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0772 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PWP-014003-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 100% | 37.506 | 0
K214-TFS-0773 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PWP-014003-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0774 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PWP-014003-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0775 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PWP-014003-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0776 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PWP-014003-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0777 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014007-02 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0778 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014007-03 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 100% | 44.719 | 0
K214-TFS-0779 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PWP-014007-04 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 89.438 |  | 100% | 100% | 100% |  |  | 100% | 89.438 | 0
K214-TFS-0780 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PWP-014007-05 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 89.438 |  | 100% | 100% | 100% |  |  | 100% | 89.438 | 0
K214-TFS-0781 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PWP-014007-06 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 100% | 44.719 | 0
K214-TFS-0782 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PWP-014007-07 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 100% | 44.719 | 0
K214-TFS-0783 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PWP-014007-08 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 100% | 44.719 | 0
K214-TFS-0784 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PWP-014007-09 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0785 | TFS | 50.11.01 | TFS00A112MM | LP1Y-PWP-014007-10 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0786 | TFS | 50.11.01 | TFS00L101MM | LP1Y-PWP-014007-11 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.493 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0787 | TFS | 50.11.01 | TFS00L102MM | LP1Y-PWP-014007-12 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.493 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0788 | TFS | 50.11.01 | TFS00G101MM | LP1Y-PWP-014009-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 100% | 4.205 | 0
K214-TFS-0789 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PWP-014009-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0790 | TFS | 50.11.01 | TFS00S101MM | LP1Y-PWP-036002-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.182 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0791 | TFS | 50.11.01 | TFS00W105MM | LP1Y-PWP-036003-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.813 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0792 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PWP-036047-01 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0793 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PWP-036047-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0794 | TFS | 50.11.01 | TFS00A102MM | LP1Y-PWP-036047-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0795 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PWP-036047-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0796 | TFS | 50.11.01 | TFS00B101MM | LP1Y-PWP-036047-07 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0797 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PWP-036047-08 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0798 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PWP-036047-10 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0799 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PWP-036047-11 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0800 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PWP-036047-12 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0801 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PWP-036047-13 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0802 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PWP-036049-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0803 | TFS | 50.11.01 | TFS00A102MM | LP1Y-PWP-036049-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 100% | 32.151 | 0
K214-TFS-0804 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PWP-036049-06 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 20.501 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0805 | TFS | 50.11.01 | TFS00B101MM | LP1Y-PWP-036049-07 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.084 |  | 100% | 100% | 100% |  |  | 100% | 33.084 | 0
K214-TFS-0806 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PWP-036049-08 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 26.664 |  | 100% | 100% | 100% |  |  | 100% | 26.664 | 0
K214-TFS-0807 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PWP-036049-09 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0808 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PWP-036049-10 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0809 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PWP-036049-11 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0810 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PWP-036049-12 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0811 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PWP-036049-14 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0812 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-850051-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0813 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-850051-08 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0814 | TFS | 50.11.01 | TFS00F101MM | LP1Y-S(130)-018051-01 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 60.077 |  | 100% | 100% | 100% |  |  | 100% | 60.077 | 0
K214-TFS-0815 | TFS | 50.11.01 | TFS00G101MM | LP1Y-S(130)-018062-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 29.852 |  | 100% | 100% | 100% |  |  | 100% | 29.852 | 0
K214-TFS-0816 | TFS | 50.11.01 | TFS00A103MM | LP1Y-S(130)-018062-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 29.011 |  | 100% | 100% | 100% |  |  | 100% | 29.011 | 0
K214-TFS-0817 | TFS | 50.11.01 | TFS00A102MM | LP1Y-S(130)-018062-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.938 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0818 | TFS | 50.11.01 | TFS00A104MM | LP1Y-S(130)-018062-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 58.15 |  | 100% | 100% | 100% |  |  | 100% | 58.15 | 0
K214-TFS-0819 | TFS | 50.11.01 | TFS00A105MM | LP1Y-S(130)-018062-09 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 100% | 58.389 | 0
K214-TFS-0820 | TFS | 50.11.01 | TFS00A106MM | LP1Y-S(130)-018062-12 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 100% | 58.389 | 0
K214-TFS-0821 | TFS | 50.11.01 | TFS00A107MM | LP1Y-S(130)-018062-13 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 100% | 58.389 | 0
K214-TFS-0822 | TFS | 50.11.01 | TFS00A108MM | LP1Y-S(130)-018062-15 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 100% | 58.389 | 0
K214-TFS-0823 | TFS | 50.11.01 | TFS00A109MM | LP1Y-S(130)-018062-18 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0824 | TFS | 50.11.01 | TFS00A110MM | LP1Y-S(130)-018062-19 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 100% | 58.389 | 0
K214-TFS-0825 | TFS | 50.11.01 | TFS00A111MM | LP1Y-S(130)-018062-20 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1316 | TFS | 50.11.01 | TFS00A102MM | LP1Y-S(130)-018079-01 |  |  |  |  | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 9.938 |  | 100% | 100% | 100% |  |  | 100% | 9.938 | 0
K214-TFS-0826 | TFS | 50.11.01 | TFS00B101MM | LP1Y-S(130)-018079-03 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 9.376 |  | 100% | 100% | 100% |  |  | 100% | 9.376 | 0
K214-TFS-0827 | TFS | 50.11.01 | TFS00B102MM | LP1Y-S(130)-018079-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 9.376 |  | 100% | 100% | 100% |  |  | 100% | 9.376 | 0
K214-TFS-0828 | TFS | 50.11.01 | TFS00A112MM | LP1Y-S(130)-018091-02 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0829 | TFS | 50.11.01 | TFS00L101MM | LP1Y-S(130)-018091-03 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0830 | TFS | 50.11.01 | TFS00L102MM | LP1Y-S(130)-018091-04 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0831 | TFS | 50.11.01 | TFS00J101MM | LP1Y-S(130)-034030-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 29.011 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0832 | TFS | 50.11.01 | TFS00B109MM | LP1Y-S(130)-034035-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0833 | TFS | 50.11.01 | TFS00B102MM | LP1Y-S(130)-034035-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 100% | 42.463 | 0
K214-TFS-0834 | TFS | 50.11.01 | TFS00B103MM | LP1Y-S(130)-034035-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0835 | TFS | 50.11.01 | TFS00B104MM | LP1Y-S(130)-034035-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0836 | TFS | 50.11.01 | TFS00B105MM | LP1Y-S(130)-034035-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0837 | TFS | 50.11.01 | TFS00B106MM | LP1Y-S(130)-034035-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0838 | TFS | 50.11.01 | TFS00B107MM | LP1Y-S(130)-034035-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0839 | TFS | 50.11.01 | TFS00B108MM | LP1Y-S(130)-034035-18 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0840 | TFS | 50.11.01 | TFS00S101MM | LP1Y-S(130)-034035-20 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.729 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0841 | TFS | 50.11.01 | TFS00W105MM | LP1Y-S(130)-034038-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 100% | 15.609 | 0
K214-TFS-0842 | TFS | 50.11.01 | TFS00B108MM | LP1Y-S(130)-034077-04 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.358 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0843 | TFS | 50.11.01 | TFS00B103MM | LP1Y-S(130)-034109-01 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0844 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SOLV-300404-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 9 | 0 | 9 | 0 | EA | 0 |  | 0 | 253.521 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0845 | TFS | 50.11.01 | TFS00B109MM | LP1Y-SOLV-300404-06 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 10 | 0 | 10 | 0 | EA | 0 |  | 0 | 255.857 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0846 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SOLV-300404-08 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 10 | 0 | 10 | 0 | EA | 0 |  | 0 | 285.45 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0847 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SOLV-300404-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 112.676 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0848 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SOLV-322202-06 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.626 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0849 | TFS | 50.11.01 | TFS00G101MM | LP1Y-SRACNP-011001-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.16 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0850 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SRACNP-011001-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 100% | 25.912 | 0
K214-TFS-0851 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SRACNP-011001-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 51.82 |  | 100% | 100% | 100% |  |  | 100% | 51.82 | 0
K214-TFS-0852 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SRACNP-011001-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 100% | 25.912 | 0
K214-TFS-0853 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SRACNP-011001-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 100% | 25.912 | 0
K214-TFS-0854 | TFS | 50.11.01 | TFS00A107MM | LP1Y-SRACNP-011001-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.92 |  | 100% | 100% | 100% |  |  | 100% | 25.92 | 0
K214-TFS-0855 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SRACNP-011001-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 100% | 32.151 | 0
K214-TFS-0856 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SRACNP-108104-03 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0857 | TFS | 50.11.01 | TFS00B101MM | LP1Y-STORMP-015002-13 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0858 | TFS | 50.11.01 | TFS00A102MM | LP1Y-STORMP-015002-15 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0859 | TFS | 50.11.01 | TFS00A104MM | LP1Y-STORMP-015002-17 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0860 | TFS | 50.11.01 | TFS00A105MM | LP1Y-STORMP-015002-18 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0861 | TFS | 50.11.01 | TFS00A106MM | LP1Y-STORMP-015002-19 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0862 | TFS | 50.11.01 | TFS00A107MM | LP1Y-STORMP-015002-20 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0863 | TFS | 50.11.01 | TFS00A108MM | LP1Y-STORMP-015002-21 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0864 | TFS | 50.11.01 | TFS00A109MM | LP1Y-STORMP-015002-22 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-0865 | TFS | 50.11.01 | TFS00A110MM | LP1Y-STORMP-015002-23 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0866 | TFS | 50.11.01 | TFS00A111MM | LP1Y-STORMP-015002-24 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0867 | TFS | 50.11.01 | TFS00B108MM | LP1Y-STORMP-037007-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0868 | TFS | 50.11.01 | TFS00B109MM | LP1Y-STORMP-037007-05 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0869 | TFS | 50.11.01 | TFS00B102MM | LP1Y-STORMP-037007-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0870 | TFS | 50.11.01 | TFS00B103MM | LP1Y-STORMP-037007-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0871 | TFS | 50.11.01 | TFS00B107MM | LP1Y-STORMP-037007-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0872 | TFS | 50.11.01 | TFS00B104MM | LP1Y-STORMP-037007-14 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0873 | TFS | 50.11.01 | TFS00B105MM | LP1Y-STORMP-037007-15 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0874 | TFS | 50.11.01 | TFS00B106MM | LP1Y-STORMP-037007-16 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0875 | TFS | 50.11.01 | TFS00J101MM | LP1Y-STORMP-037009-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 20.501 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0876 | TFS | 50.11.01 | TFS00A103MM | LP1Y-STORMP-165334-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.105 |  | 100% | 100% | 100% |  |  | 100% | 25.105 | 0
K214-TFS-0877 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SWP-014001-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0878 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0879 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014001-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 100% | 40.855 | 0
K214-TFS-0880 | TFS | 50.11.01 | TFS00A111MM | LP1Y-SWP-014004-01 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0881 | TFS | 50.11.01 | TFS00A110MM | LP1Y-SWP-014004-02 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0882 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014004-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0883 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014004-08 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.51 |  | 100% | 100% | 100% |  |  | 100% | 37.51 | 0
K214-TFS-0884 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014005-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0885 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014005-08 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 37.51 |  | 100% | 100% | 100% |  |  | 100% | 37.51 | 0
K214-TFS-0886 | TFS | 50.11.01 | TFS00G101MM | LP1Y-SWP-014010-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 41.042 |  | 100% | 100% | 100% |  |  | 100% | 41.042 | 0
K214-TFS-0887 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-014010-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 100% | 31.096 | 0
K214-TFS-0888 | TFS | 50.11.01 | TFS00H101MM | LP1Y-SWP-014015-02 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 100% | 18.813 | 0
K214-TFS-0889 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SWP-036045-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0890 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036045-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0891 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036045-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0892 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036045-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0893 | TFS | 50.11.01 | TFS00B102MM | LP1Y-SWP-036045-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0894 | TFS | 50.11.01 | TFS00B104MM | LP1Y-SWP-036045-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0895 | TFS | 50.11.01 | TFS00B106MM | LP1Y-SWP-036045-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0896 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SWP-036045-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0897 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036046-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0898 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036046-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0899 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036046-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 100% | 19.939 | 0
K214-TFS-0900 | TFS | 50.11.01 | TFS00B105MM | LP1Y-SWP-036046-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0901 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036048-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 100% | 32.151 | 0
K214-TFS-0902 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036048-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 42.24 |  | 100% | 100% | 100% |  |  | 100% | 42.24 | 0
K214-TFS-0903 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SWP-036048-05 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 46.124 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0904 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036048-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 33.084 |  | 100% | 100% | 100% |  |  | 100% | 33.084 | 0
K214-TFS-0905 | TFS | 50.11.01 | TFS00B102MM | LP1Y-SWP-036048-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0906 | TFS | 50.11.01 | TFS00B103MM | LP1Y-SWP-036048-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0907 | TFS | 50.11.01 | TFS00B104MM | LP1Y-SWP-036048-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0908 | TFS | 50.11.01 | TFS00B105MM | LP1Y-SWP-036048-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0909 | TFS | 50.11.01 | TFS00B106MM | LP1Y-SWP-036048-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0910 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SWP-036048-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0911 | TFS | 50.11.01 | TFS00B109MM | LP1Y-SWP-036048-14 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 59.817 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0912 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SWP-036048-15 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0913 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SWP-036052-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 41.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0914 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-100404-02 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 26.664 |  | 100% | 100% | 100% |  |  | 100% | 26.664 | 0
K214-TFS-0915 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-100404-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 100% | 25.912 | 0
K214-TFS-0916 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-100404-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0917 | TFS | 50.11.01 | TFS00A109MM | LP1Y-SWP-109022-01 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 3 | 0 | 3 | 3 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 100% | 56.259 | 0
K214-TFS-0918 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SWP-109022-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 3 | 0 | 3 | 3 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 100% | 56.259 | 0
K214-TFS-0919 | TFS | 50.11.01 | TFS00A107MM | LP1Y-SWP-109022-03 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 3 | 0 | 3 | 3 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 100% | 56.259 | 0
K214-TFS-0920 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SWP-109022-04 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 4 | 0 | 4 | 4 | EA | 0 |  | 0 | 75.012 |  | 100% | 100% | 100% |  |  | 100% | 75.012 | 0
K214-TFS-0921 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-109022-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 100% | 18.753 | 0
K214-TFS-0922 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-109022-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38 |  | 100% | 100% | 100% |  |  | 100% | 38 | 0
K214-TFS-0923 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-850004-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 100% | 19.376 | 0
K214-TFS-0924 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-850004-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 100% | 38.752 | 0
K214-TFS-0925 | TFS | 50.11.01 | TFS00H101MM | LP1Y-TFA-010004-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.471 |  | 100% | 100% | 100% |  |  | 100% | 19.471 | 0
K214-TFS-0926 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TFA-010004-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.82 |  | 100% | 100% | 100% |  |  | 100% | 38.82 | 0
K214-TFS-0927 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TFA-010004-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 100% | 19.408 | 0
K214-TFS-0928 | TFS | 50.11.01 | TFS00H101MM | LP1Y-TFA-010031-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.471 |  | 100% | 100% | 100% |  |  | 100% | 19.471 | 0
K214-TFS-0929 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TFA-010031-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 100% | 19.408 | 0
K214-TFS-0930 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TFA-010031-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 100% | 19.408 | 0
K214-TFS-0931 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TFA-010031-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 100% | 38.816 | 0
K214-TFS-0932 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TFA-010031-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 100% | 38.816 | 0
K214-TFS-0933 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TFA-010031-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 100% | 38.816 | 0
K214-TFS-0934 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TFA-010031-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 100% | 38.816 | 0
K214-TFS-1374 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TFA-010004-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 |  | EA | 0 |  | 0 | 19 |  | 100% | 100% | 100% |  |  | 100% | 19
K214-TFS-0935 | TFS | 50.11.01 | TFS00F101MM | LP1Y-TWRP-017021-01 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 118.822 |  | 100% | 100% | 100% |  |  | 100% | 118.822 | 0
K214-TFS-0936 | TFS | 50.11.01 | TFS00G101MM | LP1Y-TWRP-017063-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 75.205 |  | 100% | 100% | 100% |  |  | 100% | 75.205 | 0
K214-TFS-0937 | TFS | 50.11.01 | TFS00A103MM | LP1Y-TWRP-017063-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 100% | 77.316 | 0
K214-TFS-0938 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TWRP-017063-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 100% | 121.925 | 0
K214-TFS-0939 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TWRP-017063-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 DWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 243.851 |  | 100% | 100% | 100% |  |  | 100% | 243.851 | 0
K214-TFS-0940 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TWRP-017063-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 121.718 |  | 100% | 100% | 100% |  |  | 100% | 121.718 | 0
K214-TFS-0941 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWRP-017063-10 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 100% | 77.316 | 0
K214-TFS-0942 | TFS | 50.11.01 | TFS00B108MM | LP1Y-TWRP-033045-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0943 | TFS | 50.11.01 | TFS00B109MM | LP1Y-TWRP-033045-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.833 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0944 | TFS | 50.11.01 | TFS00B106MM | LP1Y-TWRP-033045-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0945 | TFS | 50.11.01 | TFS00B107MM | LP1Y-TWRP-033045-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0946 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TWRP-109313-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 100% | 13.44 | 0
K214-TFS-0947 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TWRP-109313-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 100% | 13.44 | 0
K214-TFS-0948 | TFS | 50.11.01 | TFS00F101MM | LP1Y-TWSP-017016-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 118.822 |  | 100% | 100% | 100% |  |  | 100% | 118.822 | 0
K214-TFS-0949 | TFS | 50.11.01 | TFS00G101MM | LP1Y-TWSP-017017-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 75.205 |  | 100% | 100% | 100% |  |  | 100% | 75.205 | 0
K214-TFS-0950 | TFS | 50.11.01 | TFS00A103MM | LP1Y-TWSP-017017-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102 TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 100% | 77.316 | 0
K214-TFS-0951 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWSP-017017-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 77 |  | 100% | 100% | 100% |  |  | 100% | 77 | 0
K214-TFS-0952 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TWSP-017017-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 100% | 121.925 | 0
K214-TFS-0953 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TWSP-017017-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 100% | 121.925 | 0
K214-TFS-0954 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TWSP-017017-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 121.718 |  | 100% | 100% | 100% |  |  | 100% | 121.718 | 0
K214-TFS-0955 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TWSP-017020-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 100% | 13.44 | 0
K214-TFS-0956 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TWSP-017020-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 100% | 13.44 | 0
K214-TFS-0957 | TFS | 50.11.01 | TFS00J101MM | LP1Y-TWSP-033021-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 46.26 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0958 | TFS | 50.11.01 | TFS00B108MM | LP1Y-TWSP-033034-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0959 | TFS | 50.11.01 | TFS00B109MM | LP1Y-TWSP-033034-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.833 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0960 | TFS | 50.11.01 | TFS00B106MM | LP1Y-TWSP-033034-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0961 | TFS | 50.11.01 | TFS00B107MM | LP1Y-TWSP-033034-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0962 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WFO-017007-70 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0963 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WFO-017007-71 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0964 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WI-037001-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0965 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WI-037001-04 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0966 | TFS | 50.11.01 | TFS00A102MM | LP1Y-WNP-017007-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.149 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0967 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WNP-017007-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 100% | 2.062 | 0
K214-TFS-0968 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WNP-017007-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0969 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WNP-017007-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0970 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WNP-017007-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0971 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WNP-017007-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0972 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WNP-017007-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 100% | 2.062 | 0
K214-TFS-0973 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WFO-017007-50 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 100% | 2.062 | 0
K214-TFS-0974 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WNP-017007-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0975 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WNP-017007-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.061 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0976 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WNP-017007-16 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0977 | TFS | 50.11.01 | TFS00A101MM | LP1Y-WFO-017060-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.21 |  | 100% | 100% | 100% |  |  | 100% | 2.21 | 0
K214-TFS-0978 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WNP-017007-40 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.21 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0979 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WNP-033018-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0980 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WNP-033018-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0981 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WNP-033018-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0982 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WNP-033018-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0983 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WNP-033018-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0984 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WNP-033018-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0985 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WNP-033056-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.08 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0986 | TFS | 50.11.01 | TFS00G101MM | LP1Y-WPC-017015-02 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 100% | 2.122 | 0
K214-TFS-0987 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WPC-017056-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0988 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WPC-017056-03 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0989 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WPC-017061-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.085 |  | 100% | 100% | 100% |  |  | 100% | 2.085 | 0
K214-TFS-0990 | TFS | 50.11.01 | TFS00A102MM | LP1Y-WPC-017062-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0991 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WPC-017062-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 100% | 1.994 | 0
K214-TFS-0992 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WPC-017062-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0993 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WPC-017062-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0994 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WPC-017062-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 100% | 1.994 | 0
K214-TFS-0995 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WPC-017062-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 100% | 2.122 | 0
K214-TFS-0996 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WPC-017062-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 100% | 1.994 | 0
K214-TFS-0997 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WPC-017062-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 100% | 1.994 | 0
K214-TFS-0998 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WPC-017062-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0999 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WPC-017062-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1000 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WPC-017062-12 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1001 | TFS | 50.11.01 | TFS00F101MM | LP1Y-WPC-017064-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 100% | 2.122 | 0
K214-TFS-1002 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WPC-033020-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.273 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1003 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WPC-033035-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1004 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WPC-033035-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1005 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WPC-033035-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1006 | TFS | 50.11.01 | TFS00B103MM | LP1Y-WPC-033035-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1007 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WPC-033035-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1008 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WPC-033035-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1009 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WPC-033035-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1010 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WPC-033035-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1011 | TFS | 50.11.01 | TFS00S101MM | LP1Y-WPC-033039-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.449 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1012 | TFS | 50.11.01 | TFS00W105MM | LP1Y-WPC-033039-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1013 | TFS | 50.11.01 | TFS00F101MM | LP1Y-WS-017025-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.456 |  | 100% | 100% | 100% |  |  | 100% | 4.456 | 0
K214-TFS-1014 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WS-017025-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1015 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WS-017025-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 100% | 8.66 | 0
K214-TFS-1016 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WS-017025-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 100% | 8.66 | 0
K214-TFS-1017 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WS-017030-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 100% | 4.205 | 0
K214-TFS-1018 | TFS | 50.11.01 | TFS00B101MM | LP1Y-WS-017030-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.455 |  | 100% | 100% | 100% |  |  | 100% | 4.455 | 0
K214-TFS-1019 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WS-017034-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 100% | 4.205 | 0
K214-TFS-1020 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WS-017034-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.33 |  | 100% | 100% | 100% |  |  | 100% | 4.33 | 0
K214-TFS-1021 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WS-017034-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.33 |  | 100% | 100% | 100% |  |  | 100% | 4.33 | 0
K214-TFS-1022 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WS-017034-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1023 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WS-017034-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 100% | 8.66 | 0
K214-TFS-1024 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WS-033030-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1025 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WS-033030-03 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1026 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WS-033030-05 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1027 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WS-033031-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1028 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WS-033043-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1029 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WS-033043-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 8.66 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1030 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WS-033043-04 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1031 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WS-033043-05 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1032 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WS-033052-01 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1033 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WS-033052-03 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 100% | 4.205 | 0
K214-TFS-1034 | TFS | 50.11.01 | TFS00B103MM | LP1Y-WS-033052-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1035 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WS-033052-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1036 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WTFAP-014011-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.16 |  | 100% | 100% | 100% |  |  | 100% | 25.16 | 0
K214-TFS-1037 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WTFAP-014011-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-1038 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WTFAP-014011-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-1039 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WTFAP-014011-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-1040 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WTFAP-014011-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-1041 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WTFAP-014011-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 100% | 25.07 | 0
K214-TFS-1042 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WTFAP-014011-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.167 |  | 100% | 100% | 100% |  |  | 100% | 31.167 | 0
K214-TFS-1043 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WV-061046-18 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1044 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WV-061046-19 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1045 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WV-061046-20 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1046 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WV-061046-21 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1047 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WV-061046-22 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1048 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WV-061046-23 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1049 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WV-061046-24 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1050 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WV-061046-25 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1051 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WV-061046-26 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1052 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WV-061046-27 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1053 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WV-061046-28 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 100% | 27.417 | 0
K214-TFS-1054 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WV-321011-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1189 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWSP-017063-04 |  |  |  |  | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 120 |  | 100% | 100% | 100% |  |  | 100% | 120 | 1
K214-TFS-1190 | TFS | 50.11.01 | TFA00A103MM | LP1Y-PV-013001-02 |  |  |  |  | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 44 |  | 100% | 100% | 100% |  |  | 100% | 44 | 2
K214-TFS-1265 | TFS | 50.11.01 | TFS00F102MM | LP1Y-APL(100)-019001-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 21.62 |  | 100% | 100% | 100% |  |  | 100% | 21.62 | 0
K214-TFS-1266 | TFS | 50.11.01 | TFS00F102MM | LP1Y-CHWR-017024-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 77.3 |  | 100% | 100% | 100% |  |  | 100% | 77.3 | 0
K214-TFS-1267 | TFS | 50.11.01 | TFS00F102MM | LP1Y-CHWS-017111-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 77.3 |  | 100% | 100% | 100% |  |  | 100% | 77.3 | 0
K214-TFS-1268 | TFS | 50.11.01 | TFS00F102MM | LP1Y-NG-018012-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 13.41 |  | 100% | 100% | 100% |  |  | 100% | 13.41 | 0
| TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-05 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 100% | 15.609
K214-TFS-1359 | TFS | 50.11.01 | TFS00F102MM | LP1Y-TWRP-017021-02 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 118.82 |  | 100% | 100% | 100% |  |  | 100% | 118.82
K214-TFS-1375 | TFS | 50.11.01 | TFS00F102MM | LP1Y-TWSP-017016-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 118.82 |  | 100% | 100% | 100% |  |  | 100% | 118.82
K214-TFS-1128 | TFS | 50.11.01 | TFS00A101MS |  | TFS00A101MSPP | K214 | IP-TFS00A101MSPP-K214-050 | 50.TA101-M.F | Assembly of Ship Loose Pipe for Module TA101 | 557.715 | 0 | 557.715 | 72.503 | LF | 1698.6 |  | 0 | 1698.6 |  | 13% | 13% | 13% |  |  | 13% | 220.818 | 0
K214-TFS-1317 | TFS | 50.11.01 | TFS00A102MS | [5 empty] | Assembly of Ship Loose Pipe for Module TA102 | 68.923 | 0 | 68.923 | 45.7649 | LF | 1101.7 |  | 0 | 1101.7 |  | 100% | 63% | 60% |  |  | 66.4% | 731.5288 | 0
K214-TFS-1232 | TFS | 50.11.01 | TFS00A103MS | [5 empty] | Assembly of Ship Loose Pipe for Module TA103 | 438.254 | 0 | 0 | 238.8484 | LF | 1552 |  | 0 | 1552 |  | 100% | 50% | 45% |  |  | 54.5% | 845.84 | 1
K214-TFS-1137 | TFS | 50.11.01 | TFS00A104MS |  | TFS00A104MSPP | K214 | IP-TFS00A104MSPP-K214-050 | 50.TA104-M.F | Assembly of Ship Loose Pipe for Module TA104 | 874.01 | 0 | 874.01 | 201.0223 | LF | 1119.188 |  | 0 | 1119.188 |  | 100% | 15% | 10% |  |  | 23% | 257.4132 | 0
K214-TFS-1129 | TFS | 50.11.01 | TFS00A105MS |  | TFS00A105MSPP | K214 | IP-TFS00A105MSPP-K214-050 | 50.TA105-M.F | Assembly of Ship Loose Pipe for Module TA105 | 638.73 | 0 | 638.73 | 424.1167 | LF | 2191.107 |  | 0 | 2191.107 |  | 100% | 63% | 60% |  |  | 66.4% | 1454.895 | 0
K214-TFS-1130 | TFS | 50.11.01 | TFS00A106MS |  | TFS00A106MSPP | K214 | IP-TFS00A106MSPP-K214-050 | 50.TA106-M.F | Assembly of Ship Loose Pipe for Module TA106 | 882.922 | 0 | 882.922 | 644.5331 | LF | 3348.979 |  | 0 | 3348.979 |  | 100% | 70% | 70% |  |  | 73% | 2444.7547 | 0
K214-TFS-1131 | TFS | 50.11.01 | TFS00A107MS |  | TFS00A107MSPP | K214 | IP-TFS00A107MSPP-K214-050 | 50.TA107-M.F | Assembly of Ship Loose Pipe for Module TA107 | 502.36 | 0 | 502.36 | 366.7228 | LF | 1035.622 |  | 0 | 1035.622 |  | 100% | 70% | 70% |  |  | 73% | 756.0041 | 0
K214-TFS-1132 | TFS | 50.11.01 | TFS00A108MS |  | TFS00A108MSPP | K214 | IP-TFS00A108MSPP-K214-050 | 50.TA108-M.F | Assembly of Ship Loose Pipe for Module TA108 | 797.27 | 0 | 797.27 | 510.2528 | LF | 1902.8 |  | 0 | 1902.8 |  | 100% | 60% | 60% |  |  | 64% | 1217.792 | 0
K214-TFS-1138 | TFS | 50.11.01 | TFS00A109MS |  | TFS00A109MSPP | K214 | IP-TFS00A109MSPP-K214-050 | 50.TA109-M.F | Assembly of Ship Loose Pipe for Module TA109 | 726.55 | 0 | 726.55 | 32.6948 | LF | 2615 |  | 0 | 2615 |  | 45% | 0% | 0% |  |  | 4.5% | 117.675 | 0
[9 empty] | Assembly of Ship Loose Pipe for Module TA110 | 1140.791 | 0 | 1140.791 |  | LF | 5801.339
[9 empty] | Assembly of Ship Loose Pipe for Module TA111 | 481.994 | 0 | 481.994 |  | LF | 3597.944
[9 empty] | Assembly of Ship Loose Pipe for Module TA112 | 429.06 | 0 | 429.06 |  | LF | 2361.245
K214-TFS-1133 | TFS | 50.11.01 | TFS00F101MS |  | TFS00F101MSPP | K214 | IP-TFS00F101MSPP-K214-050 | 50.TF101-M.F | Assembly of Ship Loose Pipe for Module TF101 | 176 | 0 | 176 | 96.8 | LF | 1292 |  | 0 | 1292 |  | 100% | 50% | 50% |  |  | 55% | 710.6 | 0
K214-TFS-1134 | TFS | 50.11.01 | TFS00F102MS |  | TFS00F102MSPP | K214 | IP-TFS00F102MSPP-K214-050 | 50.TF102-M.F | Assembly of Ship Loose Pipe for Module TF102 | 39 | 0 | 39 | 14.43 | LF | 529 |  | 0 | 529 |  | 100% | 30% | 30% |  |  | 37% | 195.73 | 0
K214-TFS-1135 | TFS | 50.11.01 | TFS00H101MS |  | TFS00H101MSPP | K214 | IP-TFS00H101MSPP-K214-050 | 50.TH101-M.F | Assembly of Ship Loose Pipe for Module TH101 | 15 | 0 | 15 | 15 | EA | 334 |  | 0 | 334 |  | 100% | 100% | 100% |  |  | 100% | 334 | 0
K214-TFS-1136 | TFS | 50.11.01 | TFS00K102MS |  | TFS00K102MSPP | K214 | IP-TFS00K102MSPP-K214-050 | 50.TK102-M.F | Assembly of Ship Loose Pipe for Module TK102 | 3 | 0 | 3 | 3 | EA | 52.31 |  | 0 | 52 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1191 | TFS | 50.11.01 | TFS00K103MM | [5 empty] | Assembly of Ship Loose Pipe for Module TK103 | 2 | 0 | 2 | 2 | EA | 127.392 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 100% | 127.392 | 0
K214-TFS-1192 | TFS | 50.11.01 | TFS00K105MM | [5 empty] | Assembly of Ship Loose Pipe for Module TK105 | 2 | 0 | 2 | 2 | EA | 127.392 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 100% | 127.392 | 0
K214-TFS-1153 | TFS | 50.11.01 | TFS00K103MM | LP1Y-WPC-033024-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 32 |  | 0 | 32 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1154 | TFS | 50.11.01 | TFS00K103MM | LP1Y-CHWR-033050-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1155 | TFS | 50.11.01 | TFS00K103MM | LP1Y-CHWS-033013-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1156 | TFS | 50.11.01 | TFS00K103MM | LP1Y-APL(100)-034012-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1157 | TFS | 50.11.01 | TFS00K103MM | LP1Y-NG-034009-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1158 | TFS | 50.11.01 | TFS00K103MM | LP1Y-N2(100)-034041-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1159 | TFS | 50.11.01 | TFS00K103MM | LP1Y-SWP-036050-05 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1160 | TFS | 50.11.01 | TFS00K103MM | LP1Y-PSC-033051-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1161 | TFS | 50.11.01 | TFS00K103MM | LP1Y-S(130)-034010-06 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696 | 0
K214-TFS-1162 | TFS | 50.11.01 | TFS00K104MM | LP1Y-WPC-033024-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1163 | TFS | 50.11.01 | TFS00K104MM | LP1Y-CHWR-033050-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1164 | TFS | 50.11.01 | TFS00K104MM | LP1Y-CHWS-033013-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.554 |  | 0 | 95.554 |  | 100% | 100% | 100% |  |  | 100% | 95.554 | 0
K214-TFS-1165 | TFS | 50.11.01 | TFS00K104MM | LP1Y-NG-034009-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1166 | TFS | 50.11.01 | TFS00K104MM | LP1Y-N2(100)-034041-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1167 | TFS | 50.11.01 | TFS00K104MM | LP1Y-SWP-036050-06 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1168 | TFS | 50.11.01 | TFS00K104MM | LP1Y-PSC-033051-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1169 | TFS | 50.11.01 | TFS00K104MM | LP1Y-APL(100)-034012-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1170 | TFS | 50.11.01 | TFS00K104MM | LP1Y-S(130)-034010-07 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696 | 0
K214-TFS-1171 | TFS | 50.11.01 | TFS00K105MM | LP1Y-WPC-033024-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1172 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWR-033050-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1173 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWS-033013-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1174 | TFS | 50.11.01 | TFS00K105MM | LP1Y-NG-034009-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1175 | TFS | 50.11.01 | TFS00K105MM | LP1Y-N2(100)-034041-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1176 | TFS | 50.11.01 | TFS00K105MM | LP1Y-SWP-036050-07 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1177 | TFS | 50.11.01 | TFS00K105MM | LP1Y-PSC-033051-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1178 | TFS | 50.11.01 | TFS00K105MM | LP1Y-APL(100)-034012-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1179 | TFS | 50.11.01 | TFS00K105MM | LP1Y-S(130)-034010-10 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696 | 0
K214-TFS-1180 | TFS | 50.11.01 | TFS00K106MM | LP1Y-CHWS-033013-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1181 | TFS | 50.11.01 | TFS00K106MM | LP1Y-NG-034009-07 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1182 | TFS | 50.11.01 | TFS00K106MM | LP1Y-PSC-033051-07 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1183 | TFS | 50.11.01 | TFS00K106MM | LP1Y-S(130)-034010-11 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696 | 0
K214-TFS-1193 | TFS | 50.11.01 | TFS00K105MM | LP1Y-WPC-033024-06 | LP1Y-WPC-033024-06 |  |  |  | TK105 TO TK106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
'K214-TFS-1194 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWR-033050-06 |  |  |  |  | TK105 TO TK106 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1195 | TFS | 50.11.01 | TFS00K106MM | LP1Y-N2(100)-034041-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1196 | TFS | 50.11.01 | TFS00K106MM | LP1Y-SWP-036050-08 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1197 | TFS | 50.11.01 | TFS00K106MM | LP1Y-APL(100)-034012-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1198 | TFS | 50.11.01 | TFS00K106MM | LP1Y-WPC-033024-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1199 | TFS | 50.11.01 | TFS00K106MM | LP1Y-CHWR-033050-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1200 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWS-033013-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1360 | TFS | 50.11.01 | TFS00K108MM | LP1Y-S(130)-034010-13 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696
K214-TFS-1361 | TFS | 50.11.01 | TFS00K108MM | LP1Y-PSC-033051-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
K214-TFS-1362 | TFS | 50.11.01 | TFS00K108MM | LP1Y-NG-034009-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886
K214-TFS-1363 | TFS | 50.11.01 | TFS00K108MM | LP1Y-SWP-036050-10 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
K214-TFS-1364 | TFS | 50.11.01 | TFS00K108MM | LP1Y-N2(100)-034041-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
K214-TFS-1365 | TFS | 50.11.01 | TFS00K108MM | LP1Y-APL(100)-034012-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544
| TFS | 50.11.01 | TFS00K108MM | LP1Y-APL(100)-034012-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 47.772 |  |  | 47.772 |  | 100% | 100% | 100% |  |  | 100% | 47.772
| TFS | 50.11.01 | TFS00K108MM | LP1Y-WPC-033024-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 63.696 |  |  | 63.696 |  | 100% | 100% | 100% |  |  | 100% | 63.696
| TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWR-033050-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 191.088 |  |  | 191.088 |  | 100% | 100% | 100% |  |  | 100% | 191.088
| TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWS-033013-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 191.088 |  |  | 191.088 |  | 100% | 100% | 100% |  |  | 100% | 191.088
| TFS | 50.11.01 | TFS00K108MM | LP1Y-N2(100)-034041-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848
| TFS | 50.11.01 | TFS00K108MM | LP1Y-SWP-036050-11 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848
K214-TFS-1376 | TFS | 50.11.01 | TFS00K108MM | LP1Y-PSC-033051-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 31.48 |  | 0 | 31.48 |  | 100% | 100% | 100% |  |  | 100% | 31.48
K214-TFS-1377 | TFS | 50.11.01 | TFS00K108MM | LP1Y-NG-034009-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 47.72 |  | 0 | 47.72 |  | 100% | 100% | 100% |  |  | 100% | 47.72
K214-TFS-1378 | TFS | 50.11.01 | TFS00K108MM | LP1Y-S(130)-034010-13 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 1 | EA | 0 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 100% | 127.392
K214-TFS-1379 | TFS | 50.11.01 | TFS00K110MM | LP1Y-SWP-036050-12 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% | 0% | 0% | 100% | 23.886 | 0
K214-TFS-1380 | TFS | 50.11.01 | TFS00K110MM | LP1Y-N2(100)-034041-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% | 0% | 0% | 100% | 23.886 | 0
K214-TFS-1381 | TFS | 50.11.01 | TFS00K110MM | LP1Y-PSC-033051-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% | 0% | 0% | 100% | 31.848 | 0
K214-TFS-1382 | TFS | 50.11.01 | TFS00K110MM | LP1Y-S(130)-034010-17 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% | 0% | 0% | 100% | 63.696 | 0
K214-TFS-1383 | TFS | 50.11.01 | TFS00K110MM | LP1Y-APL(100)-034012-10 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% | 0% | 0% | 100% | 95.544 | 0
K214-TFS-1384 | TFS | 50.11.01 | TFS00K110MM | LP1Y-NG-034009-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% | 0% | 0% | 100% | 95.544 | 0
K214-TFS-1385 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWR-033050-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% | 0% | 0% | 100% | 15.924 | 0
K214-TFS-1386 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWS-033013-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% | 0% | 0% | 100% | 15.924 | 0
K214-TFS-1366 | TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWR-033050-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.5 |  | 0 | 95.54 |  | 100% | 100% | 100% | 0% | 0% | 100% | 95.54 | 0
K214-TFS-1367 | TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWS-033013-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.5 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 100% | 95.54
K214-TFS-1201 | TFS | 50.11.01 | TFS00W101MM | LP1Y-PSC-033040-03 |  |  |  |  | TW101 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1202 | TFS | 50.11.01 | TFS00W102MM | LP1Y-NG-034039-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1203 | TFS | 50.11.01 | TFS00W102MM | LP1Y-S(130)-034038-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1204 | TFS | 50.11.01 | TFS00W102MM | LP1Y-CHWS-033038-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1205 | TFS | 50.11.01 | TFS00D116MM | LP1Y-AI(100)-019009-19 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1206 | TFS | 50.11.01 | TFS00D116MM | LP1Y-H2SO4-178102-02 |  |  |  |  | TD116 VERTICAL SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.84 |  | 0 | 31.84 |  | 100% | 100% | 100% |  |  | 100% | 31.84 | 0
K214-TFS-1207 | TFS | 50.11.01 | TFS00W103MM | LP1Y-S(130)-034038-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.84 |  | 0 | 31.84 |  | 100% | 100% | 100% |  |  | 100% | 31.84 | 0
K214-TFS-1208 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWS-033038-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 100% | 95.54 | 0
K214-TFS-1209 | TFS | 50.11.01 | TFS00D116MM | LP1Y-N2(100)-180087-03 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1210 | TFS | 50.11.01 | TFS00D116MM | LP1Y-APL(100)019072-18 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
'K214-TFS-1211 | TFS | 50.11.01 | TFS00W103MM | LP1Y-NG-034039-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1212 | TFS | 50.11.01 | TFS00W102MM | LP1Y-APL(100)-034040-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1213 | TFS | 50.11.01 | TFS00W102MM | LP1Y-AWNP-037004-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1215 | TFS | 50.11.01 | TFS00W102MM | LP1Y-CHWR-033041-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1216 | TFS | 50.11.01 | TFS00W102MM | LP1Y-N2(100)-034037-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1217 | TFS | 50.11.01 | TFS00W102MM | LP1Y-PWP-036003-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1218 | TFS | 50.11.01 | TFS00W102MM | LP1Y-WPC-033039-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 100% | 47.772 | 0
K214-TFS-1219 | TFS | 50.11.01 | TFS00W103MM | LP1Y-APL(100)-034040-04 |  |  |  |  | TW103 TO TW102 DWHU CONNECTION | 2 | 0 | 2 | 2 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 100% | 47.772 | 0
K214-TFS-1220 | TFS | 50.11.01 | TFS00W103MM | LP1Y-AWNP-037004-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1221 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWR-033041-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544 | 0
K214-TFS-1222 | TFS | 50.11.01 | TFS00W103MM | LP1Y-N2(100)-034037-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1223 | TFS | 50.11.01 | TFS00W103MM | LP1Y-PWP-036003-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1224 | TFS | 50.11.01 | TFS00W103MM | LP1Y-WPC-033039-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 100% | 47.772 | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-AWNP-037004-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 23.886 |  |  | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886
| TFS | 50.11.01 | TFS00W103MM | LP1Y-APL(100)-034040-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 23.886 |  |  | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886
| TFS | 50.11.01 | TFS00W103MM | LP1Y-S(130)-034038-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848
| TFS | 50.11.01 | TFS00W103MM | LP1Y-WPC-033039-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 47.772 |  |  | 47.772 |  | 100% | 100% | 100% |  |  | 100% | 47.772
| TFS | 50.11.01 | TFS00W103MM | LP1Y-NG-034039-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
| TFS | 50.11.01 | TFS00W103MM | LP1Y-PWP-036003-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
| TFS | 50.11.01 | TFS00W103MM | LP1Y-N2(100)-034037-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
K214-TFS-1387 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWR-033041-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 100% | 95.54
K214-TFS-1388 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWS-033038-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 100% | 95.54
K214-TFS-1389 | TFS | 50.11.01 | TFS00W103MM | LP1Y-PSC-033040-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 1 | EA | 0 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848
K214-TFS-1225 | TFS | 50.11.01 | TFS00D116MM | LP1Y-S(130)-018131-03 |  |  |  |  | TD116 TO TD114 DWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 100% | 31.848 | 0
K214-TFS-1226 | TFS | 50.11.01 | TFS00D116MM | LP1Y-WFO-017060-19 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1227 | TFS | 50.11.01 | TFS00D116MM | LP1Y-WPC-017061-07 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1228 | TFS | 50.11.01 | TFS00D117MM | LP1Y-H2SO4-100303-03 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886 | 0
K214-TFS-1229 | TFS | 50.11.01 | TFS00D117MM | LP1Y-STORMP-165114-04 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1230 | TFS | 50.11.01 | TFS00D117MM | LP1Y-SWP-165113-04 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1233 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AI(100)-019013-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1234 | TFS | 50.11.01 | TFS00D103MM | LP1Y-APL(100)-198104-01 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1235 | TFS | 50.11.01 | TFS00D103MM | LP1Y-NAHOH50-101304-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1236 | TFS | 50.11.01 | TFS00D103MM | LP1Y-H2SO4-101303-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1237 | TFS | 50.11.01 | TFS00D103MM | LP1Y-S(130)-018078-03 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1238 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AWNP-101302-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 47.773 |  | 0 | 47.773 |  | 100% | 100% | 100% |  |  | 100% | 47.773 | 0
K214-TFS-1239 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AWNP-101309-06 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 47.773 |  | 0 | 47.773 |  | 100% | 100% | 100% |  |  | 100% | 47.773 | 0
K214-TFS-1240 | TFS | 50.11.01 | TFS00D101MM | LP1Y-H2SO4-016001-01 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1241 | TFS | 50.11.01 | TFS00D101MM | LP1Y-NAOH50-016002-02 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1269 | TFS | 50.11.01 | TFS00D103MM | LP1Y-WFO-017007-61 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1270 | TFS | 50.11.01 | TFS00D101MM | LP1Y-APL(100)-019074-03 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1271 | TFS | 50.11.01 | TFS00D101MM | LP1Y-AI(100)-019013-03 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924 | 0
K214-TFS-1272 | TFS | 50.11.01 | TFS00D101MM | LP1Y-AWNP-101309-10 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 47.77 |  | 100% | 100% | 100% |  |  | 100% | 47.77 | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-AWNP-037004-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-APL(100)-034040-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 100% | 23.886
| TFS | 50.11.01 | TFS00W101MM | LP1Y-S(130)-034038-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-PSC-033040-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-CHWS-033038-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544
| TFS | 50.11.01 | TFS00W101MM | LP1Y-CHWR-033041-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 100% | 95.544
| TFS | 50.11.01 | TFS00S101MM | LP1Y-WPC-033039-01 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 47.772 |  | 0 | 47.772 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-PWP-036003-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-NG-034039-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-N2(100)-034037-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 1 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 100% | 15.924
K214-TFS-1273 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 100% | 7.4 | 0
K214-TFS-1274 | TFS | 50.11.01 | TFS00SRU | AWNP(315)(108)852004-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 100% | 7.4 | 0
K214-TFS-1275 | TFS | 50.11.01 | TFS00SRU | PWP(315)(108)854014-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 100% | 7.4 | 0
K214-TFS-1276 | TFS | 50.11.01 | TFS00SRU | SRACNP(315)P(108)852001-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 100% | 7.4 | 0
K214-TFS-1318 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)854019-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1319 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)854018-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1277 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860010-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1320 | TFS | 50.11.01 | TFS00SRU | PSC(002)(101)862003-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1278 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)860001-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1279 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1321 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)859007-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1322 | TFS | 50.11.01 | TFS00SRU | SWP(315)(108)859011-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1323 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)856017-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1280 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)859010-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1324 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)856016-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1325 | TFS | 50.11.01 | TFS00SRU | TWSP-(006)(108)859009-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1281 | TFS | 50.11.01 | TFS00SRU | WPC(036)(108)861023-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1326 | TFS | 50.11.01 | TFS00SRU | ACN(315)P(108)857003-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1327 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)857012-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1282 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)858020-02 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 8 |  | 0 | 8 |  | 100% | 100% | 100% |  |  | 100% | 8 | 0
K214-TFS-1283 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)858019-02 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1328 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)857011-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 8 |  | 0 | 8 |  | 100% | 100% | 100% |  |  | 100% | 8 | 0
K214-TFS-1284 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1285 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860011-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1286 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860012-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1287 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1288 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)853002-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1289 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)855002-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1290 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)854017-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1291 | TFS | 50.11.01 | TFS00SRU | S(002)(103)853006-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1292 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)853004-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1293 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)853025-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1294 | TFS | 50.11.01 | TFS00SRU | SC(002)(101)862005-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1295 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1296 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1297 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)855009-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1298 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)856013-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1299 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)858016-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1300 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)854017-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1301 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)860001-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1302 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)857007-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1303 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)859003-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1304 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1305 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1306 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)856012-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1307 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)858016-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1308 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)858018-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1309 | TFS | 50.11.01 | TFS00SRU | S(002)(103)857008-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1310 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)857006-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 2 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 100% | 7.3 | 0
K214-TFS-1311 | TFS | 50.11.01 | TFS00SRU | TWSP-858019-02 |  |  |  |  | H06V05 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 25.47 |  | 0 | 25.47 |  | 100% | 100% | 100% |  |  | 100% | 25.47 | 0
K214-TFS-1312 | TFS | 50.11.01 | TFS00SRU | TWSP-858020-02 |  |  |  |  | H06V05 SWHU CONNECTION | 1 | 0 | 1 | 1 | EA | 25.47 |  | 0 | 25.47 |  | 100% | 100% | 100% |  |  | 100% | 25.47 | 0
K214-TFS-1329 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V02) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-1330 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V03) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-1331 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V04) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-1332 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V05) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-1333 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (H06) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
[10 empty] | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS | MILESTONES | [5 empty] | TOTAL PROGRESS | EARN HOURS | ACTUAL HOURS |  |  | COMMENT / NOTE
[19 empty] | ML01 | ML02 | ML03 | ML04 | ML05 | ML06
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | 33654 |  |  |  |  | 46580 |  | 0 | 47850 | Stage / Prep / Test | Install | Support/Tie-wrap | Gland / Terminate / Label | Cable Tag | Test / Torque & Accept |  | 17850 | 12931
[9 empty] | MM Interconnects - ELEC (Cable Tray) | 5810 | -509 | 5301 | 3588 |  | 7306 | 528 | 0 | 8729 | 30% | 65% | 0% | 0% | 0% | 5% | 67.68% | 5908 | 5325
K214-TFS-0300 | TFS | 60.01.01 | TFS00T101MM | N.A. | TFS00T101MSEN | K210 | IP-TFS00T101MSEN-K214-060 | 60.TT101-M.F | CABLE TRAY INTERCONNECTS ON TT101 | 240 |  | 240 | 210 | LF | 316 | 30 | 0 | 346 | 100% | 75% |  |  |  | 75% | 82.5% | 286 | 219 |  |  | REDESIGN
K214-TFS-0301 | TFS | 60.01.01 | TFS00T102MM | N.A. | TFS00T102MSEN | K214 | IP-TFS00T102MSEN-K214-060 | 60.TT102-M.F | CABLE TRAY INTERCONNECTS ON TT102 | 110 |  | 110 | 110 | LF | 145 | 30 | 0 | 175 | 100% | 100% |  |  |  | 80% | 99% | 173 | 160 |  |  | REDESIGN
K214-TFS-0302 | TFS | 60.01.01 | TFS00T103MM | N.A. | TFS00T103MSEN | K210 | IP-TFS00T103MSEN-K214-060 | 60.TT103-M.F | CABLE TRAY INTERCONNECTS ON TT103 | 110 |  | 110 | 110 | LF | 145 | 40 | 0 | 185 | 100% | 100% |  |  |  | 80% | 99% | 183 | 141 |  |  | REDESIGN
K214-TFS-0303 | TFS | 60.01.01 | TFS00T104MM | N.A. | TFS00T104MSEN | K210 | IP-TFS00T104MSEN-K214-060 | 60.TT104-M.F | CABLE TRAY INTERCONNECTS ON TT104 | 110 |  | 110 | 110 | LF | 193 | 40 | 0 | 233 | 100% | 100% |  |  |  | 80% | 99% | 230 | 167 |  |  | REDESIGN
K214-TFS-0304 | TFS | 60.01.01 | TFS00T105MM | N.A. | TFS00T105MSEN | K210 | IP-TFS00T105MSEN-K214-060 | 60.TT105-M.F | CABLE TRAY INTERCONNECTS ON TT105 | 110 |  | 110 | 110 | LF | 193 | 38 | 0 | 231 | 100% | 100% |  |  |  | 80% | 99% | 228 | 119 |  |  | REDESIGN
K214-TFS-0305 | TFS | 60.01.01 | TFS00T106MM | N.A. | TFS00T106MSEN | K210 | IP-TFS00T106MSEN-K214-060 | 60.TT106-M.F | CABLE TRAY INTERCONNECTS ON TT106 | 110 |  | 110 | 110 | LF | 341 | 25 | 0 | 366 | 100% | 100% |  |  |  | 80% | 99% | 362 | 325 |  |  | REDESIGN
K214-TFS-0306 | TFS | 60.01.01 | TFS00T107MM | N.A. | TFS00T107MSEN | K214 | IP-TFS00T107MSEN-K214-060 | 60.TT107-M.F | CABLE TRAY INTERCONNECTS ON TT107 | 120 |  | 120 | 120 | LF | 158 | 65 | 0 | 223 | 100% | 97% |  |  |  | 0% | 93.1% | 208 | 170 |  |  | REDESIGN
K214-TFS-0307 | TFS | 60.01.01 | TFS00T108MM | N.A. | TFS00T108MSEN | K210 | IP-TFS00T108MSEN-K214-060 | 60.TT108-M.F | CABLE TRAY INTERCONNECTS ON TT108 | 220 |  | 220 | 220 | LF | 290 | 50 | 0 | 340 | 100% | 41% |  |  |  | 0% | 56.7% | 193 | 150 |  |  | REDESIGN
K214-TFS-0308 | TFS | 60.01.01 | TFS00T109MM | N.A. | TFS00T109MSEN | K210 | IP-TFS00T109MSEN-K214-060 | 60.TT109-M.F | CABLE TRAY INTERCONNECTS ON TT109 | 40 |  | 40 | 40 | LF | 80 | 40 | 0 | 120 | 100% | 100% |  |  |  | 80% | 99% | 119 | 104 |  |  | REDESIGN
K214-TFS-0309 | TFS | 60.01.01 | TFS00T110MM | N.A. | TFS00T110MSEN | K210 | IP-TFS00T110MSEN-K214-060 | 60.TT110-M.F | CABLE TRAY INTERCONNECTS ON TT110 | 110 |  | 110 | 110 | LF | 145 | 50 | 0 | 195 | 100% | 34% |  |  |  | 0% | 52.1% | 102 | 72 |  |  | REDESIGN
K214-TFS-1073 | TFS | 60.09.01 | TFS00A101MM | N.A. | TFS00A101MSEN | K214 | IP-TFS00A101MSEN-K214-060 | 60.TA101-M.F | CABLE TRAY INTERCONNECTS ON TA101 | 220 |  | 220 | 20 | LF | 290 |  | 0 | 290 | 100% | 32% |  |  |  | 20% | 51.8% | 150 | 133
K214-TFS-1075 | TFS | 60.09.01 | TFS00A102MM | N.A. | TFS00A102MSEN | K214 | IP-TFS00A102MSEN-K214-060 | 60.TA102-M.F | CABLE TRAY INTERCONNECTS ON TA102 | 200 |  | 200 | 180 | LF | 264 |  | 0 | 342 | 100% | 100% |  |  |  | 80% | 99% | 339 | 233
K214-TFS-1076 | TFS | 60.09.01 | TFS00A103MM | N.A. | TFS00A103MSEN | K214 | IP-TFS00A103MSEN-K214-060 | 60.TA103-M.F | CABLE TRAY INTERCONNECTS ON TA103 | 180 |  | 180 | 160 | LF | 237 |  | 0 | 305 | 100% | 100% |  |  |  | 80% | 99% | 302 | 304
K214-TFS-1077 | TFS | 60.09.01 | TFS00A104MM | N.A. | TFS00A104MSEN | K214 | IP-TFS00A104MSEN-K214-060 | 60.TA104-M.F | CABLE TRAY INTERCONNECTS ON TA104 | 200 |  | 200 | 200 | LF | 264 |  | 0 | 343 | 100% | 100% |  |  |  | 90% | 99.5% | 341 | 305
K214-TFS-1078 | TFS | 60.09.01 | TFS00A105MM | N.A. | TFS00A105MSEN | K214 | IP-TFS00A105MSEN-K214-060 | 60.TA105-M.F | CABLE TRAY INTERCONNECTS ON TA105 | 200 |  | 200 | 190 | LF | 264 |  | 0 | 342 | 100% | 100% |  |  |  | 90% | 99.5% | 340 | 373
K214-TFS-1079 | TFS | 60.09.01 | TFS00A106MM | N.A. | TFS00A106MSEN | K214 | IP-TFS00A106MSEN-K214-060 | 60.TA106-M.F | CABLE TRAY INTERCONNECTS ON TA106 | 200 |  | 200 | 180 | LF | 264 |  | 0 | 329 | 100% | 100% |  |  |  | 80% | 99% | 326 | 275 |  |  | Hangers Installed
K214-TFS-1080 | TFS | 60.09.01 | TFS00A107MM | N.A. | TFS00A107MSEN | K214 | IP-TFS00A107MSEN-K214-060 | 60.TA107-M.F | CABLE TRAY INTERCONNECTS ON TA107 | 660 |  | 660 | 630 | LF | 870 |  | 0 | 870 | 100% | 90% |  |  |  | 90% | 93% | 809 | 800
K214-TFS-1081 | TFS | 60.09.01 | TFS00A108MM | N.A. | TFS00A108MSEN | K214 | IP-TFS00A108MSEN-K214-060 | 60.TA108-M.F | CABLE TRAY INTERCONNECTS ON TA108 | 130 |  | 130 | 60 | LF | 171 |  | 0 | 171 | 50% | 50% |  |  |  | 50% | 50% | 86 | 86
K214-TFS-0354 | TFS | 60.09.01 | TFS00B101MM | N.A. | TFS00B101MSEN | K214 | IP-TFS00B101MSEN-K214-060 | 60.TB101-M.F | CABLE TRAY INTERCONNECTS ON TB101 | 130 |  | 130 | 0 | LF | 171 |  | 0 | 171 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0355 | TFS | 60.09.01 | TFS00B102MM | N.A. | TFS00B102MSEN | K214 | IP-TFS00B102MSEN-K214-060 | 60.TB102-M.F | CABLE TRAY INTERCONNECTS ON TB102 | 130 |  | 130 | 0 | LF | 171 |  | 0 | 171 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0356 | TFS | 60.09.01 | TFS00B103MM | N.A. | TFS00B103MSEN | K214 | IP-TFS00B103MSEN-K214-060 | 60.TB103-M.F | CABLE TRAY INTERCONNECTS ON TB103 | 110 |  | 110 | 0 | LF | 145 |  | 0 | 145 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0357 | TFS | 60.09.01 | TFS00B104MM | N.A. | TFS00B104MSEN | K214 | IP-TFS00B104MSEN-K214-060 | 60.TB104-M.F | CABLE TRAY INTERCONNECTS ON TB104 | 110 |  | 110 | 0 | LF | 145 |  | 0 | 145 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0358 | TFS | 60.09.01 | TFS00B105MM | N.A. | TFS00B105MSEN | K214 | IP-TFS00B105MSEN-K214-060 | 60.TB105-M.F | CABLE TRAY INTERCONNECTS ON TB105 | 110 |  | 110 | 0 | LF | 145 |  | 0 | 145 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0359 | TFS | 60.09.01 | TFS00B106MM | N.A. | TFS00B106MSEN | K214 | IP-TFS00B106MSEN-K214-060 | 60.TB106-M.F | CABLE TRAY INTERCONNECTS ON TB106 | 220 |  | 220 | 0 | LF | 290 |  | 0 | 290 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0360 | TFS | 60.09.01 | TFS00B107MM | N.A. | TFS00B107MSEN | K214 | IP-TFS00B107MSEN-K214-060 | 60.TB107-M.F | CABLE TRAY INTERCONNECTS ON TB107 | 100 |  | 100 | 0 | LF | 132 |  | 0 | 132 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0361 | TFS | 60.09.01 | TFS00B108MM | N.A. | TFS00B108MSEN | K214 | IP-TFS00B108MSEN-K214-060 | 60.TB108-M.F | CABLE TRAY INTERCONNECTS ON TB108 | 230 |  | 230 | 0 | LF | 303 |  | 0 | 303 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-0362 | TFS | 60.09.01 | TFS00B109MM | N.A. | TFS00B109MSEN | K214 | IP-TFS00B109MSEN-K214-060 | 60.TB109-M.F | CABLE TRAY INTERCONNECTS ON TB109 | 0 |  | 0 | 0 | LF | 0 |  | 0 | 0 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00K102 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK102 | 120 | -60 | 60 | 0 | LF | 79 |  | 0 | 79 | 100% | 0% |  |  |  | 0% | 30% | 24 | 0
| TFS | 60.09.01 | TFS00K103 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK103 | 120 | -60 | 60 | 60 | LF | 79 |  | 0 | 79 | 100% | 100% |  |  |  | 80% | 99% | 78 | 148 |  |  | REDESIGN
| TFS | 60.09.01 | TFS00K104 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK104 | 120 | -60 | 60 | 60 | LF | 79 |  | 0 | 79 | 100% | 100% |  |  |  | 80% | 99% | 78 | 90
| TFS | 60.09.01 | TFS00K105 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK105 | 120 | -60 | 60 | 60 | LF | 79 |  | 0 | 79 | 100% | 100% |  |  |  | 80% | 99% | 78 | 70
| TFS | 60.09.01 | TFS00K106 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK106 | 120 | -60 | 60 | 60 | LF | 79 |  | 0 | 79 | 100% | 100% |  |  |  | 80% | 99% | 78 | 72
| TFS | 60.09.01 | TFS00K107 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTSON TK107 | 200 | -117 | 83 | 60 | LF | 109 |  | 0 | 109 | 100% | 100% |  |  |  | 50% | 97.5% | 107 | 150
| TFS | 60.09.01 | TFS00K108 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TK108 | 80 | -40 | 40 |  | LF | 53 |  | 0 | 580 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00V101 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TV101 | 80 | -20 | 60 | 60 | LF | 79 | 20 | 0 | 99 | 100% | 100% |  |  |  | 80% | 99% | 98 | 114 |  |  | REDESIGN
[9 empty] | CABLE TRAY INTERCONNECTS ON TV102 | 80 | -32 | 48 | 48 | LF | 63 | 50 |  | 113 | 100% | 100% |  |  |  | 80% | 99% | 112 | 126 |  |  | REDESIGN
| TFS | 60.09.01 | TFS00V102 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TV103 | 80 | 70 | 150 | 150 | LF | 198 | 20 | 0 | 218 | 100% | 100% |  |  |  | 0% | 95% | 207 | 105 |  |  | REDESIGN
| TFS | 60.09.01 | TFS00W101 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TW101 | 140 | 0 | 140 | 90 | LF | 185 |  | 0 | 185 | 100% | 100% |  |  |  | 0% | 95% | 175 | 159
| TFS | 60.09.01 | TFS00W102 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TW102 | 140 | -70 | 70 | 70 | LF | 92 | 30 | 0 | 122 | 100% | 70% |  |  |  | 60% | 78.5% | 96 | 155 |  |  | REDESIGN
| TFS | 60.09.01 | TFS00W103 | N.A. |  |  |  |  | CABLE TRAY INTERCONNECTS ON TW103 | 0 |  | 0 | 0 | LF | 0 |  | 0 | 0
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [9 empty] | Stage | Install Supports / Hangers | Installation at Yard | Gland / Terminate | Test / Torque & Accept
[9 empty] | MS Ship Loose / Off Module Cable Tray Installation | 6650 | 0 | 6650 | 0 |  | 8762 | 0 | 0 | 8609 | 5% | 50% | 40% |  | 5% | 0% | 0% | 0 | 1241
K214-TFS-1082 | TFS | 60.09.01 | TFS00A101MM | N.A. | TFS00A101MSEN | K214 | IP-TFS00A101MSEN-K214-060 | 60.TA101-M.F | OFF-MODULE TRAY - TFS00A101 | 46 |  | 46 | 0 | LF | 61 |  | 0 | 61 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 33 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1083 | TFS | 60.09.01 | TFS00A102MM | N.A. | TFS00A102MSEN | K214 | IP-TFS00A102MSEN-K214-060 | 60.TA102-M.F | OFF-MODULE TRAY - TFS00A102 | 243 |  | 243 | 0 | LF | 320 |  | 0 | 320 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 233 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1084 | TFS | 60.09.01 | TFS00A103MM | N.A. | TFS00A103MSEN | K214 | IP-TFS00A103MSEN-K214-060 | 60.TA103-M.F | OFF-MODULE TRAY - TFS00A103 | 262 |  | 262 | 0 | LF | 345 |  | 0 | 345 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 304 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1085 | TFS | 60.09.01 | TFS00A104MM | N.A. | TFS00A104MSEN | K214 | IP-TFS00A104MSEN-K214-060 | 60.TA104-M.F | OFF-MODULE TRAY - TFS00A104 | 285 |  | 285 | 0 | LF | 376 |  | 0 | 376 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 305 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1086 | TFS | 60.09.01 | TFS00A105MM | N.A. | TFS00A105MSEN | K214 | IP-TFS00A105MSEN-K214-060 | 60.TA105-M.F | OFF-MODULE TRAY - TFS00A105 | 319 |  | 319 | 0 | LF | 420 |  | 0 | 420 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 240 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1087 | TFS | 60.09.01 | TFS00A106MM | N.A. | TFS00A106MSEN | K214 | IP-TFS00A106MSEN-K214-060 | 60.TA106-M.F | OFF-MODULE TRAY - TFS00A106 | 331 |  | 331 | 0 | LF | 436 |  | 0 | 436 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 126 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00A107MM | N.A. | TFS00A107MSEN | K214 | IP-TFS00A107MSEN-K214-060 | 60.TA107-M.F | OFF-MODULE TRAY - TFS00A107 | 228 |  | 228 | 0 | LF | 301 |  | 0 | 301 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1089 | TFS | 60.09.01 | TFS00A108MM | N.A. | TFS00A108MSEN | K214 | IP-TFS00A108MSEN-K214-060 | 60.TA108-M.F | OFF-MODULE TRAY - TFS00A108 | 359 |  | 359 | 0 | LF | 473 |  | 0 | 473 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00A109MM | N.A. | TFS00A109MSEN | K214 | IP-TFS00A109MSEN-K214-060 | 60.TA109-M.F | OFF-MODULE TRAY - TFS00A109 | 469 |  | 469 | 0 | LF | 618 |  | 0 | 618 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00A110MM | N.A. | TFS00A110MSEN | K214 | IP-TFS00A110MSEN-K214-060 | 60.TA110-M.F | OFF-MODULE TRAY - TFS00A110 | 725 |  | 725 | 0 | LF | 956 |  | 0 | 956 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00A111MM | N.A. | TFS00A111MSEN | K214 | IP-TFS00A111MSEN-K214-060 | 60.TA111-M.F | OFF-MODULE TRAY - TFS00A111 | 325 |  | 325 | 0 | LF | 428 |  | 0 | 428 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00A112MM | N.A. | TFS00A112MSEN | K214 | IP-TFS00A112MSEN-K214-060 | 60.TA112-M.F | OFF-MODULE TRAY - TFS00A112 | 69 |  | 69 | 0 | LF | 91 |  | 0 | 91 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1090 | TFS | 60.09.01 | TFS00B101MM | N.A. | TFS00B101MSEN | K214 | IP-TFS00B101MSEN-K214-060 | 60.TB101-M.F | OFF-MODULE TRAY - TFS00B101 | 256 |  | 256 | 0 | LF | 337 |  | 0 | 337 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1091 | TFS | 60.09.01 | TFS00B102MM | N.A. | TFS00B102MSEN | K214 | IP-TFS00B102MSEN-K214-060 | 60.TB102-M.F | OFF-MODULE TRAY - TFS00B102 | 287 |  | 287 | 0 | LF | 378 |  | 0 | 378 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1092 | TFS | 60.09.01 | TFS00B103MM | N.A. | TFS00B103MSEN | K214 | IP-TFS00B103MSEN-K214-060 | 60.TB103-M.F | OFF-MODULE TRAY - TFS00B103 | 38 |  | 38 | 0 | LF | 50 |  | 0 | 50 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1093 | TFS | 60.09.01 | TFS00B104MM | N.A. | TFS00B104MSEN | K214 | IP-TFS00B104MSEN-K214-060 | 60.TB104-M.F | OFF-MODULE TRAY - TFS00B104 | 38 |  | 38 | 0 | LF | 50 |  | 0 | 50 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1094 | TFS | 60.09.01 | TFS00B105MM | N.A. | TFS00B105MSEN | K214 | IP-TFS00B105MSEN-K214-060 | 60.TB105-M.F | OFF-MODULE TRAY - TFS00B105 | 76 |  | 76 | 0 | LF | 100 |  | 0 | 100 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1095 | TFS | 60.09.01 | TFS00B106MM | N.A. | TFS00B106MSEN | K214 | IP-TFS00B106MSEN-K214-060 | 60.TB106-M.F | OFF-MODULE TRAY - TFS00B106 | 327 |  | 327 | 0 | LF | 431 |  | 0 | 431 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1096 | TFS | 60.09.01 | TFS00B107MM | N.A. | TFS00B107MSEN | K214 | IP-TFS00B107MSEN-K214-060 | 60.TB107-M.F | OFF-MODULE TRAY - TFS00B107 | 168 |  | 168 | 0 | LF | 221 |  | 0 | 221 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1097 | TFS | 60.09.01 | TFS00B108MM | N.A. | TFS00B108MSEN | K214 | IP-TFS00B108MSEN-K214-060 | 60.TB108-M.F | OFF-MODULE TRAY - TFS00B108 | 290 |  | 290 | 0 | LF | 382 |  | 0 | 382 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
K214-TFS-1098 | TFS | 60.09.01 | TFS00B109MM | N.A. | TFS00B109MSEN | K214 | IP-TFS00B109MSEN-K214-060 | 60.TB109-M.F | OFF-MODULE TRAY - TFS00B109 | 286 |  | 286 | 0 | LF | 377 |  | 0 | 377 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00F101MM | N.A. | TFS00F101MSEN | K214 | IP-TFS00F101MSEN-K214-060 | 60.TF101-M.F | OFF-MODULE TRAY - TFS00F101 | 117 |  | 117 | 0 | LF | 154 |  | 0 | 154 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00F102MM | N.A. | TFS00F102MSEN | K214 | IP-TFS00F102MSEN-K214-060 | 60.TF102-M.F | OFF-MODULE TRAY - TFS00F102 | 52 |  | 52 | 0 | LF | 69 |  | 0 | 0 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00G101MM | N.A. | TFS00G101MSEN | K214 | IP-TFS00G101MSEN-K214-060 | 60.TG101-M.F | OFF-MODULE TRAY - TFS00G101 | 104 |  | 104 | 0 | LF | 137 |  | 0 | 137 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00J101MM | N.A. | TFS00J101MSEN | K214 | IP-TFS00J101MSEN-K214-060 | 60.TJ101-M.F | OFF-MODULE TRAY - TFS00J101 | 64 |  | 64 | 0 | LF | 84 |  | 0 | 0 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K101MM | N.A. | TFS00K101MSEN | K214 | IP-TFS00K101MSEN-K214-060 | 60.TK101-M.F | OFF-MODULE TRAY - TFS00K101 | 127 |  | 127 | 0 | LF | 167 |  | 0 | 167 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K103MM | N.A. | TFS00K103MSEN | K214 | IP-TFS00K103MSEN-K214-060 | 60.TK103-M.F | OFF-MODULE TRAY - TFS00K103 | 98 |  | 98 | 0 | LF | 129 |  | 0 | 129 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K105MM | N.A. | TFS00K105MSEN | K214 | IP-TFS00K105MSEN-K214-060 | 60.TK105-M.F | OFF-MODULE TRAY - TFS00K105 | 94 |  | 94 | 0 | LF | 124 |  | 0 | 124 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K106MM | N.A. | TFS00K106MSEN | K214 | IP-TFS00K106MSEN-K214-060 | 60.TK106-M.F | OFF-MODULE TRAY - TFS00K106 | 51 |  | 51 | 0 | LF | 67 |  | 0 | 67 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K107MM | N.A. | TFS00K107MSEN | K214 | IP-TFS00K107MSEN-K214-060 | 60.TK107-M.F | OFF-MODULE TRAY - TFS00K107 | 41 |  | 41 | 0 | LF | 54 |  | 0 | 54 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K108MM | N.A. | TFS00K108MSEN | K214 | IP-TFS00K108MSEN-K214-060 | 60.TK108-M.F | OFF-MODULE TRAY - TFS00K108 | 46 |  | 46 | 0 | LF | 61 |  | 0 | 61 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K109MM | N.A. | TFS00K109MSEN | K214 | IP-TFS00K109MSEN-K214-060 | 60.TK109-M.F | OFF-MODULE TRAY - TFS00K109 | 42 |  | 42 | 0 | LF | 55 |  | 0 | 55 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00K110MM | N.A. | TFS00K110MSEN | K214 | IP-TFS00K110MSEN-K214-060 | 60.TK110-M.F | OFF-MODULE TRAY - TFS00K110 | 92 |  | 92 | 0 | LF | 121 |  | 0 | 121 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00S101MM | N.A. | TFS00S101MSEN | K214 | IP-TFS00S101MSEN-K214-060 | 60.TS101-M.F | OFF-MODULE TRAY - TFS00S101 | 64 |  | 64 | 0 | LF | 84 |  | 0 | 84 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00W101MM | N.A. | TFS00W101MSEN | K214 | IP-TFS00W101MSEN-K214-060 | 60.TW101-M.F | OFF-MODULE TRAY - TFS00W101 | 49 |  | 49 | 0 | LF | 65 |  | 0 | 65 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00W102MM | N.A. | TFS00W102MSEN | K214 | IP-TFS00W102MSEN-K214-060 | 60.TW102-M.F | OFF-MODULE TRAY - TFS00W102 | 40 |  | 40 | 0 | LF | 53 |  | 0 | 53 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00W103MM | N.A. | TFS00W103MSEN | K214 | IP-TFS00W103MSEN-K214-060 | 60.TW103-M.F | OFF-MODULE TRAY - TFS00W103 | 40 |  | 40 | 0 | LF | 53 |  | 0 | 53 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00W104MM | N.A. | TFS00W104MSEN | K214 | IP-TFS00W104MSEN-K214-060 | 60.TW104-M.F | OFF-MODULE TRAY - TFS00W104 | 64 |  | 64 | 0 | LF | 84 |  | 0 | 84 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
| TFS | 60.09.01 | TFS00W106MM | N.A. | TFS00W106MSEN | K214 | IP-TFS00W106MSEN-K214-060 | 60.TW106-M.F | OFF-MODULE TRAY - TFS00W106 | 38 |  | 38 | 0 | LF | 50 |  | 0 | 50 | 0% | 0% | 0% |  | 0% |  | 0% | 0 | 0 |  |  | OFF MOD TRAY ESTIMATE
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [9 empty] | Install & Test |  | Accept
[9 empty] | A Level Cable Tray Installation | 5245 | 0 | 5245 | 3033 |  | 6911 | 0 | 0 | 8462 | 95% |  | 5% | 0% | 0% | 0% | 55.89% | 4729 | 3617
K214-TFS-0354 | TFS | 60.09.01 | TFS00B101MM | N.A. | TFS00B101MMEN | K214 | IP-TFS00B101MMEN-K214-160 | 60.TB101-M.F | A LEVEL CABLE TRAY ON TB101 | 410 |  | 410 | 380 | LF | 540 |  |  | 500 | 100% | 89% |  |  |  | 0% | 87.9% | 439 | 312
K214-TFS-0355 | TFS | 60.09.01 | TFS00B102MM | N.A. | TFS00B102MMEN | K214 | IP-TFS00B102MMEN-K214-160 | 60.TB102-M.F | A LEVEL CABLE TRAY ON TB102 | 410 |  | 410 | 380 | LF | 540 |  |  | 625 | 100% | 90% |  |  |  | 0% | 88.5% | 553 | 329
K214-TFS-0356 | TFS | 60.09.01 | TFS00B103MM | N.A. | TFS00B103MMEN | K214 | IP-TFS00B103MMEN-K214-160 | 60.TB103-M.F | A LEVEL CABLE TRAY ON TB103 | 305 |  | 305 | 248 | LF | 402 |  |  | 300 | 100% | 73% |  |  |  | 0% | 77.5% | 232 | 201
K214-TFS-0357 | TFS | 60.09.01 | TFS00B104MM | N.A. | TFS00B104MMEN | K214 | IP-TFS00B104MMEN-K214-160 | 60.TB104-M.F | A LEVEL CABLE TRAY ON TB104 | 240 |  | 240 | 185 | LF | 316 |  |  | 300 | 100% | 66% |  |  |  | 0% | 72.9% | 219 | 180
K214-TFS-0358 | TFS | 60.09.01 | TFS00B105MM | N.A. | TFS00B105MMEN | K214 | IP-TFS00B105MMEN-K214-160 | 60.TB105-M.F | A LEVEL CABLE TRAY ON TB105 | 240 |  | 240 | 185 | LF | 316 |  |  | 125 | 100% | 66% |  |  |  | 0% | 72.9% | 91 | 67
K214-TFS-0359 | TFS | 60.09.01 | TFS00B106MM | N.A. | TFS00B106MMEN | K214 | IP-TFS00B106MMEN-K214-160 | 60.TB106-M.F | A LEVEL CABLE TRAY ON TB106 | 280 |  | 280 | 215 | LF | 369 |  |  | 350 | 100% | 66% |  |  |  | 0% | 72.9% | 255 | 101
K214-TFS-0360 | TFS | 60.09.01 | TFS00B107MM | N.A. | TFS00B107MMEN | K214 | IP-TFS00B107MMEN-K214-160 | 60.TB107-M.F | A LEVEL CABLE TRAY ON TB107 | 200 |  | 200 | 155 | LF | 264 |  |  | 275 | 100% | 67% |  |  |  | 0% | 73.6% | 202 | 104
K214-TFS-0361 | TFS | 60.09.01 | TFS00B108MM | N.A. | TFS00B108MMEN | K214 | IP-TFS00B108MMEN-K214-160 | 60.TB108-M.F | A LEVEL CABLE TRAY ON TB108 | 240 |  | 240 | 185 | LF | 316 |  |  | 275 | 100% | 66% |  |  |  | 0% | 72.9% | 200 | 96
K214-TFS-0362 | TFS | 60.09.01 | TFS00B109MM | N.A. | TFS00B109MMEN | K214 | IP-TFS00B109MMEN-K214-160 | 60.TB109-M.F | A LEVEL CABLE TRAY ON TB109 | 160 |  | 160 | 118 | LF | 211 |  |  | 200 | 100% | 60% |  |  |  | 20% | 70% | 140 | 83
K214-TFS-1073 | TFS | 60.09.01 | TFS00A101MM | N.A. | TFS00A101MMEN | K214 | IP-TFS00A101MMEN-K214-160 | 60.TA101-M.F | A LEVEL CABLE TRAY ON TA101 | 180 |  | 180 |  | LF | 237 |  |  | 237 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
K214-TFS-1075 | TFS | 60.09.01 | TFS00A102MM | N.A. | TFS00A102MMEN | K214 | IP-TFS00A102MMEN-K214-160 | 60.TA102-M.F | A LEVEL CABLE TRAY ON TA102 | 280 |  | 280 | 202 | LF | 369 |  |  | 780 | 100% | 65% |  |  |  | 20% | 73.3% | 571 | 563
K214-TFS-1076 | TFS | 60.09.01 | TFS00A103MM | N.A. | TFS00A103MMEN | K214 | IP-TFS00A103MMEN-K214-160 | 60.TA103-M.F | A LEVEL CABLE TRAY ON TA103 | 240 |  | 240 | 185 | LF | 316 |  |  | 780 | 100% | 80% |  |  |  | 75% | 85.8% | 669 | 503
K214-TFS-1077 | TFS | 60.09.01 | TFS00A104MM | N.A. | TFS00A104MMEN | K214 | IP-TFS00A104MMEN-K214-160 | 60.TA104-M.F | A LEVEL CABLE TRAY ON TA104 | 200 |  | 200 | 146 | LF | 264 |  |  | 780 | 100% | 60% |  |  |  | 0% | 69% | 538 | 464
K214-TFS-1078 | TFS | 60.09.01 | TFS00A105MM | N.A. | TFS00A105MMEN | K214 | IP-TFS00A105MMEN-K214-160 | 60.TA105-M.F | A LEVEL CABLE TRAY ON TA105 | 240 |  | 240 | 185 | LF | 316 |  |  | 275 | 100% | 70% |  |  |  | 40% | 77.5% | 213 | 212
K214-TFS-1079 | TFS | 60.09.01 | TFS00A106MM | N.A. | TFS00A106MMEN | K214 | IP-TFS00A106MMEN-K214-160 | 60.TA106-M.F | A LEVEL CABLE TRAY ON TA106 | 280 |  | 280 | 163 | LF | 369 |  |  | 250 | 100% | 55% |  |  |  | 0% | 65.8% | 164 | 162
K214-TFS-1080 | TFS | 60.09.01 | TFS00A107MM | N.A. | TFS00A107MMEN | K214 | IP-TFS00A107MMEN-K214-160 | 60.TA107-M.F | A LEVEL CABLE TRAY ON TA107 | 200 |  | 200 | 101 | LF | 264 |  |  | 510 | 100% | 27% |  |  |  | 0% | 47.6% | 243 | 240
K214-TFS-1081 | TFS | 60.09.01 | TFS00A108MM | N.A. | TFS00A108MMEN | K214 | IP-TFS00A108MMEN-K214-160 | 60.TA108-M.F | A LEVEL CABLE TRAY ON TA108 | 290 |  | 290 | 0 | LF | 382 |  |  | 780 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00A109MM | N.A. | TFS00A109MMEN | K214 | IP-TFS00A109MMEN-K214-160 | 60.TA109-M.F | A LEVEL CABLE TRAY ON TA109 | 240 |  | 240 | 0 | LF | 316 |  |  | 316 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00A110MM | N.A. | TFS00A110MMEN | K214 | IP-TFS00A110MMEN-K214-160 | 60.TA110-M.F | A LEVEL CABLE TRAY ON TA110 | 280 |  | 280 | 0 | LF | 369 |  |  | 369 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00A111MM | N.A. | TFS00A111MMEN | K214 | IP-TFS00A111MMEN-K214-160 | 60.TA111-M.F | A LEVEL CABLE TRAY ON TA111 | 280 |  | 280 | 0 | LF | 369 |  |  | 369 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
| TFS | 60.09.01 | TFS00A112MM | N.A. | TFS00A112MMEN | K214 | IP-TFS00A112MMEN-K214-160 | 60.TA112-M.F | A LEVEL CABLE TRAY ON TA112 | 50 |  | 50 | 0 | LF | 66 |  |  | 66 | 0% | 0% |  |  |  | 0% | 0% | 0 | 0
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [9 empty] | Install & Test | Test (Post Insulation) | Accept
[9 empty] | EHT | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 90% | 5% | 5% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0320 | TFS | 60.06.01 | TFS00T101MM | N.A. | TFS00T101MMET | K210 | IP-TFS00T101MMET-K214-061 | 61.TT101-M.F | EHT INSTALLATION ON TT101 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0321 | TFS | 60.06.01 | TFS00T102MM | N.A. | TFS00T102MMET | K214 | IP-TFS00T102MMET-K214-061 | 61.TT102-M.F | EHT INSTALLATION ON TT102 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0322 | TFS | 60.06.01 | TFS00T103MM | N.A. | TFS00T103MMET | K210 | IP-TFS00T103MMET-K214-061 | 61.TT103-M.F | EHT INSTALLATION ON TT103 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0323 | TFS | 60.06.01 | TFS00T104MM | N.A. | TFS00T104MMET | K210 | IP-TFS00T104MMET-K214-061 | 61.TT104-M.F | EHT INSTALLATION ON TT104 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0324 | TFS | 60.06.01 | TFS00T105MM | N.A. | TFS00T105MMET | K210 | IP-TFS00T105MMET-K214-061 | 61.TT105-M.F | EHT INSTALLATION ON TT105 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0325 | TFS | 60.06.01 | TFS00T106MM | N.A. | TFS00T106MMET | K210 | IP-TFS00T106MMET-K214-061 | 61.TT106-M.F | EHT INSTALLATION ON TT106 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0326 | TFS | 60.06.01 | TFS00T107MM | N.A. | TFS00T107MMET | K214 | IP-TFS00T107MMET-K214-061 | 61.TT107-M.F | EHT INSTALLATION ON TT107 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0327 | TFS | 60.06.01 | TFS00T108MM | N.A. | TFS00T108MMET | K210 | IP-TFS00T108MMET-K214-061 | 61.TT108-M.F | EHT INSTALLATION ON TT108 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0328 | TFS | 60.06.01 | TFS00T109MM | N.A. | TFS00T109MMET | K210 | IP-TFS00T109MMET-K214-061 | 61.TT109-M.F | EHT INSTALLATION ON TT109 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0329 | TFS | 60.06.01 | TFS00T110MM | N.A. | TFS00T110MMET | K210 | IP-TFS00T110MMET-K214-061 | 61.TT110-M.F | EHT INSTALLATION ON TT110 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [9 empty] | Stage |  | Install Supports / Hangers | Gland / Terminate | Inspect, Test, Torque & Accept
[9 empty] | Grounding & Bonding | 21194 |  | 23151 | 4610 |  | 30512 | 0 | 0 | 30512 | 5% | 0% | 90% | 0% | 5% | 0% | 23.64% | 7213 | 2748
K214-TFS-0330 | TFS | 60.01.09 | TFS00T101MM | N.A. | TFS00T101MMEN | K210 | IP-TFS00T101MMEN-K214-062 | 62.TT101-M.F | GROUNDING INSTALLATION ON TT101 | 92 | 0 | 92 | 0 | LF | 121 |  | 0 | 121 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-0331 | TFS | 60.01.09 | TFS00T102MM | N.A. | TFS00T102MMEN | K214 | IP-TFS00T102MMEN-K214-062 | 62.TT102-M.F | GROUNDING INSTALLATION ON TT102 | 343 | 0 | 343 | 243 | LF | 452 |  | 0 | 452 | 100% |  | 69% |  | 0% |  | 67.1% | 303 | 250
K214-TFS-0332 | TFS | 60.01.09 | TFS00T103MM | N.A. | TFS00T103MMEN | K210 | IP-TFS00T103MMEN-K214-062 | 62.TT103-M.F | GROUNDING INSTALLATION ON TT103 | 92 | 0 | 92 | 92 | LF | 121 |  | 0 | 121 | 100% |  | 100% |  | 0% |  | 95% | 115 | 46
K214-TFS-0333 | TFS | 60.01.09 | TFS00T104MM | N.A. | TFS00T104MMEN | K210 | IP-TFS00T104MMEN-K214-062 | 62.TT104-M.F | GROUNDING INSTALLATION ON TT104 | 92 | 0 | 92 | 92 | LF | 121 |  | 0 | 121 | 100% |  | 100% |  | 0% |  | 95% | 115 | 46
K214-TFS-0334 | TFS | 60.01.09 | TFS00T105MM | N.A. | TFS00T105MMEN | K210 | IP-TFS00T105MMEN-K214-062 | 62.TT105-M.F | GROUNDING INSTALLATION ON TT105 | 92 | 0 | 92 | 0 | LF | 121 |  | 0 | 121 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-0335 | TFS | 60.01.09 | TFS00T106MM | N.A. | TFS00T106MMEN | K210 | IP-TFS00T106MMEN-K214-062 | 62.TT106-M.F | GROUNDING INSTALLATION ON TT106 | 92 | 0 | 92 | 85 | LF | 121 |  | 0 | 121 | 100% |  | 84% |  | 0% |  | 80.6% | 98 | 38
K214-TFS-0336 | TFS | 60.01.09 | TFS00T107MM | N.A. | TFS00T107MMEN | K214 | IP-TFS00T107MMEN-K214-062 | 62.TT107-M.F | GROUNDING INSTALLATION ON TT107 | 343 | 0 | 343 | 310 | LF | 452 |  | 0 | 452 | 100% |  | 81% |  | 0% |  | 77.9% | 352 | 283
K214-TFS-0337 | TFS | 60.01.09 | TFS00T108MM | N.A. | TFS00T108MMEN | K210 | IP-TFS00T108MMEN-K214-062 | 62.TT108-M.F | GROUNDING INSTALLATION ON TT108 | 46 | 0 | 46 | 46 | LF | 61 |  | 0 | 61 | 100% |  | 90% |  | 0% |  | 86% | 52 | 40
K214-TFS-0338 | TFS | 60.01.09 | TFS00T109MM | N.A. | TFS00T109MMEN | K210 | IP-TFS00T109MMEN-K214-062 | 62.TT109-M.F | GROUNDING INSTALLATION ON TT109 | 92 | 0 | 92 | 92 | LF | 121 |  | 0 | 121 | 100% |  | 90% |  | 0% |  | 86% | 104 | 98
K214-TFS-0339 | TFS | 60.01.09 | TFS00T110MM | N.A. | TFS00T110MMEN | K210 | IP-TFS00T110MMEN-K214-062 | 62.TT110-M.F | GROUNDING INSTALLATION ON TT110 | 46 | 0 | 46 | 46 | LF | 61 |  | 0 | 61 | 100% |  | 90% |  | 0% |  | 86% | 52 | 47
K214-TFS-1082 | TFS | 60.09.01 | TFS00A101MM | N.A. | TFS00A101MSEN | K214 | IP-TFS00A101MSEN-K214-060 | 60.TA101-M.F | GROUNDING INSTALLATION ON TA101 | 521 | 0 | 521 | 249 | LF | 687 |  | 0 | 687 | 100% |  | 43% |  | 0% |  | 43.7% | 300 | 250
K214-TFS-1083 | TFS | 60.09.01 | TFS00A102MM | N.A. | TFS00A102MSEN | K214 | IP-TFS00A102MSEN-K214-060 | 60.TA102-M.F | GROUNDING INSTALLATION ON TA102 | 991 | 0 | 991 | 0 | LF | 1306 |  | 0 | 1306 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1084 | TFS | 60.09.01 | TFS00A103MM | N.A. | TFS00A103MSEN | K214 | IP-TFS00A103MSEN-K214-060 | 60.TA103-M.F | GROUNDING INSTALLATION ON TA103 | 967 | 0 | 967 | 0 | LF | 1275 |  | 0 | 1275 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1085 | TFS | 60.09.01 | TFS00A104MM | N.A. | TFS00A104MSEN | K214 | IP-TFS00A104MSEN-K214-060 | 60.TA104-M.F | GROUNDING INSTALLATION ON TA104 | 981 | 0 | 981 | 0 | LF | 1293 |  | 0 | 1293 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1086 | TFS | 60.09.01 | TFS00A105MM | N.A. | TFS00A105MSEN | K214 | IP-TFS00A105MSEN-K214-060 | 60.TA105-M.F | GROUNDING INSTALLATION ON TA105 | 1094 | 0 | 1094 | 0 | LF | 1442 |  | 0 | 1442 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1087 | TFS | 60.09.01 | TFS00A106MM | N.A. | TFS00A106MSEN | K214 | IP-TFS00A106MSEN-K214-060 | 60.TA106-M.F | GROUNDING INSTALLATION ON TA106 | 1099 | 0 | 1099 | 0 | LF | 1448 |  | 0 | 1448 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1088 | TFS | 60.09.01 | TFS00A107MM | N.A. | TFS00A107MSEN | K214 | IP-TFS00A107MSEN-K214-060 | 60.TA107-M.F | GROUNDING INSTALLATION ON TA107 | 750 | 0 | 750 | 0 | LF | 989 |  | 0 | 989 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1089 | TFS | 60.09.01 | TFS00A108MM | N.A. | TFS00A108MSEN | K214 | IP-TFS00A108MSEN-K214-060 | 60.TA108-M.F | GROUNDING INSTALLATION ON TA108 | 1188 | 0 | 1188 | 0 | LF | 1566 |  | 0 | 1566 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00A109MSEN | N.A. | TFS00A109MSEN | K214 |  |  | GROUNDING INSTALLATION ON TA109 | 720 | 392 | 1112 | 200 | LF | 1466 |  | 0 | 1466 | 100% |  | 60% |  | 0% |  | 59% | 865 | 197
| TFS | 60.09.01 | TFS00A110MSEN | N.A. | TFS00A110MSEN | K214 |  |  | GROUNDING INSTALLATION ON TA110 | 720 | 623 | 1343 | 190 | LF | 1770 |  | 0 | 1770 | 100% |  | 35% |  | 0% |  | 36.5% | 646 | 133
| TFS | 60.09.01 | TFS00A111MSEN | N.A. | TFS00A111MSEN | K214 |  |  | GROUNDING INSTALLATION ON TA111 | 720 | 180 | 900 | 180 | LF | 1186 |  | 0 | 1186 | 100% |  | 20% |  | 0% |  | 23% | 273 | 88
| TFS | 60.09.01 | TFSA00112MSEN | N.A. | TFSA00112MSEN | K214 |  |  | GROUNDING INSTALLATION ON TA112 | 720 | -156 | 564 | 380 | LF | 743 |  | 0 | 743 | 100% |  | 50% |  | 0% |  | 50% | 372 | 137
K214-TFS-1090 | TFS | 60.09.01 | TFS00B101MM | N.A. | TFS00B101MSEN | K214 | IP-TFS00B101MSEN-K214-060 | 60.TB101-M.F | GROUNDING INSATALLATION ON TB101 | 1051 | 0 | 1051 | 0 | LF | 1385 |  | 0 | 1385 | 100% |  | 0% |  | 0% |  | 5% | 69 | 0
K214-TFS-1091 | TFS | 60.09.01 | TFS00B102MM | N.A. | TFS00B102MSEN | K214 | IP-TFS00B102MSEN-K214-060 | 60.TB102-M.F | GROUNDING INSATALLATION ON TB102 | 932 | 0 | 932 | 140 | LF | 1228 |  | 0 | 1228 | 100% |  | 14% |  | 0% |  | 17.6% | 216 | 95
K214-TFS-1092 | TFS | 60.09.01 | TFS00B103MM | N.A. | TFS00B103MSEN | K214 | IP-TFS00B103MSEN-K214-060 | 60.TB103-M.F | GROUNDING INSATALLATION ON TB103 | 691 | 0 | 691 | 140 | LF | 911 |  | 0 | 911 | 100% |  | 18% |  | 0% |  | 21.2% | 193 | 80
K214-TFS-1093 | TFS | 60.09.01 | TFS00B104MM | N.A. | TFS00B104MSEN | K214 | IP-TFS00B104MSEN-K214-060 | 60.TB104-M.F | GROUNDING INSATALLATION ON TB104 | 689 | 0 | 689 | 140 | LF | 908 |  | 0 | 908 | 100% |  | 18% |  | 0% |  | 21.2% | 193 | 110
K214-TFS-1094 | TFS | 60.09.01 | TFS00B105MM | N.A. | TFS00B105MSEN | K214 | IP-TFS00B105MSEN-K214-060 | 60.TB105-M.F | GROUNDING INSATALLATION ON TB105 | 738 | 0 | 738 | 140 | LF | 973 |  | 0 | 973 | 100% |  | 17% |  | 0% |  | 20.3% | 197 | 80
K214-TFS-1095 | TFS | 60.09.01 | TFS00B106MM | N.A. | TFS00B106MSEN | K214 | IP-TFS00B106MSEN-K214-060 | 60.TB106-M.F | GROUNDING INSATALLATION ON TB106 | 980 | 0 | 980 | 0 | LF | 1292 |  | 0 | 1292 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
K214-TFS-1096 | TFS | 60.09.01 | TFS00B107MM | N.A. | TFS00B107MSEN | K214 | IP-TFS00B107MSEN-K214-060 | 60.TB107-M.F | GROUNDING INSATALLATION ON TB107 | 651 | 0 | 651 | 105 | LF | 858 |  | 0 | 858 | 100% |  | 15% |  | 0% |  | 18.5% | 159 | 112
K214-TFS-1097 | TFS | 60.09.01 | TFS00B108MM | N.A. | TFS00B108MSEN | K214 | IP-TFS00B108MSEN-K214-060 | 60.TB108-M.F | GROUNDING INSATALLATION ON TB108 | 916 | 0 | 916 | 140 | LF | 1207 |  | 0 | 1207 | 100% |  | 10% |  | 0% |  | 14% | 169 | 60
K214-TFS-1098 | TFS | 60.09.01 | TFS00B109MM | N.A. | TFS00B109MSEN | K214 | IP-TFS00B109MSEN-K214-060 | 60.TB109-M.F | GROUNDING INSATALLATION ON TB109 | 795 | 0 | 795 | 105 | LF | 1048 |  | 0 | 1048 | 100% |  | 12% |  | 0% |  | 15.8% | 166 | 60
| TFS | 60.09.01 | TFS00K102 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK102 | 200 | 87 | 200 | 140 | LF | 264 |  | 0 | 264 | 100% |  | 65% |  | 0% |  | 63.5% | 167 | 39
| TFS | 60.09.01 | TFS00K103 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK103 | 120 | 91 | 211 | 75 | LF | 278 |  | 0 | 278 | 70% |  | 70% |  | 0% |  | 66.5% | 185 | 89
| TFS | 60.09.01 | TFS00K104 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK104 | 120 | -28 | 92 | 75 | LF | 121 |  | 0 | 121 | 70% |  | 70% |  | 0% |  | 66.5% | 81 | 89
| TFS | 60.09.01 | TFS00K105 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK105 | 120 | 91 | 211 | 150 | LF | 278 |  | 0 | 278 | 100% |  | 100% |  | 0% |  | 95% | 264 | 55
| TFS | 60.09.01 | TFS00K106 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK106 | 120 | 31 | 151 | 80 | LF | 199 |  | 0 | 199 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00K107 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK107 | 120 | 15 | 135 | 70 | LF | 178 |  | 0 | 178 | 100% |  | 70% |  | 0% |  | 68% | 121 | 64
| TFS | 60.09.01 | TFS00K108 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TK108 | 120 | 217 | 337 | 100 | LF | 444 |  | 0 | 444 | 100% |  | 80% |  | 0% |  | 77% | 342 | 60
| TFS | 60.09.01 | TFS00V101 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TV101 | 120 | -28 | 92 | 80 | LF | 121 |  | 0 | 121 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00V102 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TV102 | 120 | -28 | 92 | 80 | LF | 121 |  | 0 | 121 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00W101 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TW101 | 120 | 37 | 157 | 80 | LF | 207 |  | 0 | 207 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00W102 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TW102 | 120 | 21 | 141 | 80 | LF | 186 |  | 0 | 186 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00W103 | N.A. |  |  |  |  | GROUNDING INSATALLATION ON TW103 | 120 | 16 | 136 | 80 | LF | 179 |  | 0 | 179 | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
| TFS | 60.09.01 | TFS00W104 | N.A. |  |  |  |  | GROUNDING INSTALLATION ON TW104 | 280 | -22 | 258 | 280 | LF | 340 |  | 0 | 340 | 100% |  | 100% |  | 0% |  | 95% | 323 | 70
| TFS | 60.09.01 | TFS00W105 | N.A. |  |  |  |  | GROUNDING INSTALLTION ON TW105 | 75 | 165 | 240 | 50 | LF | 316 |  | 0 | 316 | 100% |  | 65% |  | 0% |  | 63.5% | 201 | 17
| TFS | 60.09.01 | TFS00S101 | N.A. |  |  |  |  | GROUNDING INSTALLTION ON TS101 | 75 | 340 | 415 | 75 | LF | 547 |  | 0 | 547 | 100% |  | 100% |  | 0% |  | 95% | 520 | 15
[19 empty] | 0% |  | 0% |  | 0% |  | 0% | 0 | 0
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Description | [9 empty] | Stage / Install Tugger & Rollers | Pull | Secure / Tie-Wrap/ Cleanup/ Terminate
[9 empty] | Control Cable Installation & Terminations | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10% | 80% | 10% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0340 | TFS |  | TFS00T101MM | N.A. | TFS00T101MMEN | K210 | IP-TFS00T101MMEN-K214-063 | 63.TT101-M.F | LV CONTROL CABLE INSTALLATION ON TT101 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0341 | TFS |  | TFS00T102MM | N.A. | TFS00T102MMEN | K214 | IP-TFS00T102MMEN-K214-063 | 63.TT102-M.F | LV CONTROL CABLE INSTALLATION ON TT102 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0342 | TFS |  | TFS00T103MM | N.A. | TFS00T103MMEN | K210 | IP-TFS00T103MMEN-K214-063 | 63.TT103-M.F | LV CONTROL CABLE INSTALLATION ON TT103 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0343 | TFS |  | TFS00T104MM | N.A. | TFS00T104MMEN | K210 | IP-TFS00T104MMEN-K214-063 | 63.TT104-M.F | LV CONTROL CABLE INSTALLATION ON TT104 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0344 | TFS |  | TFS00T105MM | N.A. | TFS00T105MMEN | K210 | IP-TFS00T105MMEN-K214-063 | 63.TT105-M.F | LV CONTROL CABLE INSTALLATION ON TT105 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0345 | TFS |  | TFS00T106MM | N.A. | TFS00T106MMEN | K210 | IP-TFS00T106MMEN-K214-063 | 63.TT106-M.F | LV CONTROL CABLE INSTALLATION ON TT106 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0346 | TFS |  | TFS00T107MM | N.A. | TFS00T107MMEN | K214 | IP-TFS00T107MMEN-K214-063 | 63.TT107-M.F | LV CONTROL CABLE INSTALLATION ON TT107 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0347 | TFS |  | TFS00T108MM | N.A. | TFS00T108MMEN | K210 | IP-TFS00T108MMEN-K214-063 | 63.TT108-M.F | LV CONTROL CABLE INSTALLATION ON TT108 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0348 | TFS |  | TFS00T109MM | N.A. | TFS00T109MMEN | K210 | IP-TFS00T109MMEN-K214-063 | 63.TT109-M.F | LV CONTROL CABLE INSTALLATION ON TT109 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
K214-TFS-0349 | TFS |  | TFS00T110MM | N.A. | TFS00T110MMEN | K210 | IP-TFS00T110MMEN-K214-063 | 63.TT110-M.F | LV CONTROL CABLE INSTALLATION ON TT110 | 0 |  | 0 |  | LF | 0 |  | 0 | 0 | 0% | 0% | 0% |  |  |  | 0% | 0 | 0
[25 empty] | CONTROL HOURS | EARNED HOURS | ACTUAL HOURS | % COMPLETE CUM | PF
[25 empty] | 183811.6783 | 103538.6813 | 74744 | 56.33% | 1.3852

## STEEL ERECTION
Progress Item ID | WBS | ROC Set |  |  | Description | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS | MILESTONES |  |  |  |  | TOTAL PROGRESS | EARN HOURS | Actual HOURS | COMMENT / NOTE
[5 empty] | Ship Loose / Ext. Module Struct. Steel Installation | 63030.5153 | -403.1463 | 28213.869 | #DIV/0! |  | 61616.8117 | 1071.5 | 0 | 69825.9523 | 10% | 40% | 45% | 5% | 0% | 70.79% | 43621.2482 | 30710.25
K214-TFS-0001 | TFS | 20.01.01 | TFS00A104MM | N.A. | A-LVL STEEL INSTALLATION ON TA104 | 23 | 0 | 23 | 23 | TN | 437 |  | 0 | 437 | 100% | 100% | 100% | 100% | 0% | 100% | 437 | 0
K214-TFS-0002 | TFS | 20.01.01 | TFS00A105MM | N.A. | A-LVL STEEL INSTALLATION ON TA105 | 37.3 | 0 | 37.3 | 37.3 | TN | 671 |  | 0 | 671 | 100% | 100% | 100% | 100% | 0% | 100% | 671 | 0
K214-TFS-0003 | TFS | 20.01.01 | TFS00A106MM | N.A. | A-LVL STEEL INSTALLATION ON TA106 | 43 | 0 | 43 | 43 | TN | 693 |  | 0 | 693 | 100% | 100% | 100% | 100% | 0% | 100% | 693 | 0
K214-TFS-0004 | TFS | 20.01.01 | TFS00A107MM | N.A. | A-LVL STEEL INSTALLATION ON TA107 | 23.6 | 0 | 23.6 | 23.6 | TN | 459 |  | 0 | 459 | 100% | 100% | 100% | 100% | 0% | 100% | 459 | 0
K214-TFS-0005 | TFS | 20.01.01 | TFS00A108MM | N.A. | A-LVL STEEL INSTALLATION ON TA108 | 42.7 | 0 | 42.7 | 42.7 | TN | 786 |  | 0 | 786 | 100% | 100% | 100% | 100% | 0% | 100% | 786 | 0
K214-TFS-0006 | TFS | 20.01.01 | TFS00A109MM | N.A. | A-LVL STEEL INSTALLATION ON TA109 | 29.69 | 0 | 29.69 | 29.69 | TN | 598 |  | 0 | 598 | 100% | 100% | 100% | 100% | 0% | 100% | 598 | 0
K214-TFS-0007 | TFS | 20.01.01 | TFS00A110MM | N.A. | A-LVL STEEL INSTALLATION ON TA110 | 31.29 | 0 | 31.29 | 31.29 | TN | 590 |  | 0 | 590 | 100% | 100% | 100% | 100% | 0% | 100% | 590 | 0
K214-TFS-0008 | TFS | 20.01.01 | TFS00A111MM | N.A. | A-LVL STEEL INSTALLATION ON TA111 | 29.71 | 0 | 29.71 | 29.71 | TN | 556.33 |  | 0 | 556.33 | 100% | 100% | 100% | 100% | 0% | 100% | 556.33 | 0
K214-TFS-0009 | TFS | 20.01.01 | TFS00A112MM | N.A. | A-LVL STEEL INSTALLATION ON TA112 | 28 | 0 | 28 | 0 | TN | 518 |  | 0 | 518 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0010 | TFS | 20.01.01 | TFS00A101MM | N.A. | A-LVL STEEL INSTALLATION ON TA101 | 18.48 | 0 | 18.48 | 18.48 | TN | 365 |  | 0 | 365 | 100% | 100% | 100% | 100% | 0% | 100% | 365 | 0
K214-TFS-0011 | TFS | 20.01.01 | TFS00A102MM | N.A. | A-LVL STEEL INSTALLATION ON TA102 | 42.4 | 0 | 42.4 | 42.4 | TN | 849 |  | 0 | 849 | 100% | 100% | 100% | 100% | 0% | 100% | 849 | 0
K214-TFS-0012 | TFS | 20.01.01 | TFS00A103MM | N.A. | A-LVL STEEL INSTALLATION ON TA103 | 39.832 | 0 | 39.832 | 39.832 | TN | 770 |  | 0 | 770 | 100% | 100% | 100% | 100% | 0% | 100% | 770 | 0
K214-TFS-0024 | TFS | 20.01.01 | TFS00B101MM | N.A. | A-LVL STEEL INSTALLATION ON TB101 | 42.492 | 0 | 42.492 | 42.492 | TN | 774.358 |  | 0 | 774.358 | 100% | 100% | 100% | 100% | 0% | 100% | 774.358 | 0
K214-TFS-0025 | TFS | 20.01.01 | TFS00B102MM | N.A. | A-LVL STEEL INSTALLATION ON TB102 | 37.2578 | 0 | 37.2578 | 37.2578 | TN | 708.958 |  | 0 | 708.958 | 100% | 100% | 100% | 100% | 0% | 100% | 708.958 | 0
K214-TFS-0026 | TFS | 20.01.01 | TFS00B103MM | N.A. | A-LVL STEEL INSTALLATION ON TB103 | 36.1093 | 0 | 36.1093 | 36.1093 | TN | 623.578 |  | 0 | 623.578 | 100% | 100% | 100% | 100% | 0% | 100% | 623.578 | 0
K214-TFS-0027 | TFS | 20.01.01 | TFS00B104MM | N.A. | A-LVL STEEL INSTALLATION ON TB104 | 27.6693 | 0 | 27.6693 | 27.6693 | TN | 499.586 |  | 0 | 499.586 | 100% | 100% | 100% | 100% | 0% | 100% | 499.586 | 0
K214-TFS-0028 | TFS | 20.01.01 | TFS00B105MM | N.A. | A-LVL STEEL INSTALLATION ON TB105 | 28.6395 | 0 | 28.6395 | 28.6395 | TN | 487.822 |  | 0 | 487.822 | 100% | 100% | 100% | 100% | 0% | 100% | 487.822 | 0
K214-TFS-0029 | TFS | 20.01.01 | TFS00B106MM | N.A. | A-LVL STEEL INSTALLATION ON TB106 | 42.7913 | 0 | 42.7913 | 42.7913 | TN | 760.622 |  | 0 | 760.622 | 100% | 100% | 100% | 100% | 0% | 100% | 760.622 | 0
K214-TFS-0030 | TFS | 20.01.01 | TFS00B107MM | N.A. | A-LVL STEEL INSTALLATION ON TB107 | 19.8403 | 0 | 19.8403 | 19.8403 | TN | 356.202 |  | 0 | 356.202 | 100% | 100% | 100% | 100% | 0% | 100% | 356.202 | 0
K214-TFS-0031 | TFS | 20.01.01 | TFS00B108MM | N.A. | A-LVL STEEL INSTALLATION ON TB108 | 30.1954 | 0 | 30.1954 | 30.1954 | TN | 566.979 |  | 0 | 566.979 | 100% | 100% | 100% | 100% | 0% | 100% | 566.979 | 0
K214-TFS-0032 | TFS | 20.01.01 | TFS00B109MM | N.A. | A-LVL STEEL INSTALLATION ON TB109 | 26.1127 | 0 | 26.1127 | 26.1127 | TN | 480.206 |  | 0 | 480.206 | 100% | 100% | 100% | 100% | 0% | 100% | 480.206 | 0
K214-TFS-0033 | TFS | 20.01.01 | TFS00T101MM | N.A. | A-LVL STEEL INSTALLATION ON TT101 | 0 | 4.28 | 4.28 | 0 | TN | 143.1073 |  | 0 | 143.1073 | 100% | 100% | 100% | 100% | 0% | 100% | 143.1073
K214-TFS-0067 | TFS | 20.01.01 | TFS00T102MM | N.A. | A-LVL STEEL INSTALLATION ON TT102 | 17 |  | 17 | 17 | TN |  |  |  | 338 | 100% | 100% | 100% | 100% | 0% | 100% | 338
K214-TFS-0034 | TFS | 20.01.01 | TFS00T103MM | N.A. | A-LVL STEEL INSTALLATION ON TT103 | 0 | 11.752 | 11.752 | 0 | TN | 350.3114 | 30 | 0 | 350.3114 | 100% | 100% | 100% | 100% | 0% | 100% | 350.3114 | 56
K214-TFS-0035 | TFS | 20.01.01 | TFS00T104MM | N.A. | A-LVL STEEL INSTALLATION ON TT104 | 0 | 2.706 | 2.706 | 0 | TN | 68.8614 |  | 0 | 68.8614 | 100% | 100% | 100% | 100% | 0% | 100% | 68.8614 | 25
K214-TFS-0036 | TFS | 20.01.01 | TFS00T105MM | N.A. | A-LVL STEEL INSTALLATION ON TT105 | 0 | 11.804 | 11.804 | 0 | TN | 353.0812 |  | 0 | 353.0812 | 100% | 100% | 100% | 100% | 0% | 100% | 353.0812 | 0
K214-TFS-0037 | TFS | 20.01.01 | TFS00T106MM | N.A. | A-LVL STEEL INSTALLATION ON TT106 | 0 | 2.706 | 2.706 | 0 | TN | 68.8614 |  | 0 | 68.8614 | 100% | 100% | 100% | 100% | 0% | 100% | 68.8614 | 0
K214-TFS-0038 | TFS | 20.01.01 | TFS00T107MM | N.A. | A-LVL STEEL INSTALLATION ON TT107 | 16 |  | 16 | 15.95 | TN |  |  | 0 | 320 | 100% | 100% | 100% | 100% | 0% | 100% | 320 | 0
K214-TFS-0039 | TFS | 20.01.01 | TFS00T108MM | N.A. | A-LVL STEEL INSTALLATION ON TT108 | 0 | 4.28 | 4.28 | 0 | TN | 131.1468 | 37.25 | 0 | 168.3968 | 100% | 100% | 100% | 100% | 0% | 100% | 168.3968 | 73.5
K214-TFS-0040 | TFS | 20.01.01 | TFS00T109MM | N.A. | A-LVL STEEL INSTALLATION ON TT109 | 0 | 13.8 | 13.8 | 0 | TN | 411.6225 | 129 | 0 | 540.6225 | 100% | 100% | 100% | 100% | 0% | 100% | 540.6225 | 48
K214-TFS-0041 | TFS | 20.01.01 | TFS00T110MM | N.A. | A-LVL STEEL INSTALLATION ON TT110 | 0 |  | 0 | 0 | TN | 0 |  | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | TT110 HAS NO A LEVEL STEEL IT'S A LEVEL IS TT108
K214-TFS-0043 | TFS | 20.01.01 | TFS00E141MM | N.A. | A-LVL STEEL INSTALLATION ON TE141 | 0 | 16.6267 | 16.6267 | 0 | TN | 660.31 |  | 0 | 660.31 | 100% | 100% | 100% | 0% | 0% | 95% | 627.2945 | 0 | Piers became available and module was set (should have been claimed out previously but got missed)
K214-TFS-0046 | TFS | 20.01.01 | TFS00K101MM | N.A. | A-LVL STEEL INSTALLATION ON TK101 | 15.829 | 0 | 15.829 | 15.829 | TN | 526.907 |  | 0 | 526.907 | 100% | 100% | 100% | 100% | 0% | 100% | 526.907 | 0
K214-TFS-0047 | TFS | 20.01.01 | TFS00K102MM | N.A. | A-LVL STEEL INSTALLATION ON TK102 | 14 | 0 | 14 | 14 | TN | 227.66 |  | 0 | 227.66 | 100% | 100% | 100% | 100% | 0% | 100% | 227.66 | 0
K214-TFS-0048 | TFS | 20.01.01 | TFS00K103MM | N.A. | A-LVL STEEL INSTALLATION ON TK103 | 2.762 | 0 | 2.762 | 2.762 | TN | 71.7251 |  | 0 | 71.7251 | 100% | 100% | 100% | 100% | 0% | 100% | 71.7251 | 0
K214-TFS-0049 | TFS | 20.01.01 | TFS00K104MM | N.A. | A-LVL STEEL INSTALLATION ON TK104 | 11.275 | 0 | 11.275 | 11.275 | TN | 333.5698 |  | 0 | 333.5698 | 100% | 100% | 100% | 100% | 0% | 100% | 333.5698 | 0
K214-TFS-0050 | TFS | 20.01.01 | TFS00K105MM | N.A. | A-LVL STEEL INSTALLATION ON TK105 | 2.816 | 0 | 2.816 | 2.816 | TN | 77.1844 |  | 0 | 77.1844 | 100% | 100% | 100% | 100% | 0% | 100% | 77.1844 | 0
K214-TFS-0051 | TFS | 20.01.01 | TFS00K106MM | N.A. | A-LVL STEEL INSTALLATION ON TK106 | 11.265 | 0 | 11.265 | 11.265 | TN | 332.957 |  | 0 | 332.957 | 100% | 100% | 100% | 100% | 0% | 100% | 332.957 | 0
K214-TFS-0052 | TFS | 20.01.01 | TFS00K107MM | N.A. | A-LVL STEEL INSTALLATION ON TK107 | 5.794 | 0 | 5.794 | 5.794 | TN | 158.718 |  | 0 | 158.718 | 100% | 100% | 100% | 100% | 0% | 100% | 158.718 | 0
K214-TFS-0053 | TFS | 20.01.01 | TFS00K108MM | N.A. | A-LVL STEEL INSTALLATION ON TK108 | 14 | 0 | 14 | 14 | TN | 205.3 |  | 0 | 205.3 | 100% | 100% | 100% | 100% | 0% | 100% | 205.3 | 0
K214-TFS-0054 | TFS | 20.01.01 | TFS00K109MM | N.A. | A-LVL STEEL INSTALLATION ON TK109 | 2.89 | 0 | 2.89 | 2.89 | TN | 77.0615 |  | 0 | 77.0615 | 100% | 100% | 100% | 100% | 0% | 100% | 77.0615 | 0
K214-TFS-0055 | TFS | 20.01.01 | TFS00K110MM | N.A. | A-LVL STEEL INSTALLATION ON TK110 | 17.382 | 0 | 17.382 | 17.382 | TN | 577.3807 |  | 0 | 577.3807 | 100% | 100% | 100% | 100% | 0% | 100% | 577.3807 | 0
K214-TFS-0056 | TFS | 20.01.01 | TFS00V101MM | N.A. | A-LVL STEEL INSTALLATION ON TV101 | 11.216 | 0 | 11.216 | 11.216 | TN | 330.2208 |  | 0 | 330.2208 | 100% | 100% | 100% | 100% | 0% | 100% | 330.2208 | 0
K214-TFS-0057 | TFS | 20.01.01 | TFS00V102MM | N.A. | A-LVL STEEL INSTALLATION ON TV102 | 5.232 | 0 | 5.232 | 5.232 | TN | 133.2499 |  | 0 | 133.2499 | 100% | 100% | 100% | 100% | 0% | 100% | 133.2499 | 0
K214-TFS-0058 | TFS | 20.01.01 | TFS00V103MM | N.A. | A-LVL STEEL INSTALLATION ON TV103 | 9.396 | 0 | 9.396 | 9.396 | TN | 263.274 |  | 0 | 263.274 | 100% | 100% | 100% | 100% | 0% | 100% | 263.274 | 0
K214-TFS-0059 | TFS | 20.01.01 | TFS00W101MM | N.A. | A-LVL STEEL INSTALLATION ON TW101 | 14.705 | 0 | 14.705 | 14.705 | TN | 448.665 |  | 0 | 448.665 | 100% | 100% | 100% | 100% | 0% | 100% | 448.665 | 0
K214-TFS-0060 | TFS | 20.01.01 | TFS00W102MM | N.A. | A-LVL STEEL INSTALLATION ON TW102 | 11.369 | 0 | 11.369 | 11.369 | TN | 352.13 |  | 0 | 352.13 | 100% | 100% | 100% | 100% | 0% | 100% | 352.13 | 0
K214-TFS-0061 | TFS | 20.01.01 | TFS00W103MM | N.A. | A-LVL STEEL INSTALLATION ON TW103 | 16.917 | 0 | 16.917 | 16.917 | TN | 569.8662 |  | 0 | 569.8662 | 100% | 100% | 100% | 100% | 0% | 100% | 569.8662 | 0
K214-TFS-0062 | TFS | 20.01.01 | TFS00W104MM | N.A. | A-LVL STEEL INSTALLATION ON TW104 | 48.6975 | 0 | 48.6975 | 0 | TN | 0 |  | 0 | 0 | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-0063 | TFS | 20.01.01 | TFS00W105MM | N.A. | A-LVL STEEL INSTALLATION ON TW105 | 37.6462 | 0 | 37.6462 | 0 | TN | 0 |  | 0 | 0 | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-0064 | TFS | 20.01.01 | TFS00W106MM | N.A. | A-LVL STEEL INSTALLATION ON TW106 | 2.6 | 0 | 2.6 | 2.6 | TN | 101.6979 |  | 0 | 101.6979 | 100% | 100% | 100% | 100% | 0% | 100% | 101.6979 | 0
K214-TFS-0068 | TFS | 20.01.01 | TFS00S101MM | N.A. | A-LVL STEEL INSTALLATION ON TS101 | 26.16 | 0 | 26.16 | 24.852 | TN |  |  |  | 502 | 100% | 100% | 100% | 0% | 0% | 95% | 476.9 | 0
K214-TFS-0069 | TFS | 20.01.01 | TFS00D101MM | N.A. | A-LVL STEEL INSTALLATION ON TD101 | 3.8714 | 0 | 3.8714 | 3.8714 | TN | 148.2298 |  | 0 | 148.2298 | 100% | 100% | 100% | 100% | 0% | 100% | 148.2298 | 0
K214-TFS-0123 | TFS | 20.01.01 | TFS00F101MM | N.A. | A-LVL STEEL INSTALLATION ON TF101 | 16.9 | 0 | 16.9 |  | TN | 4302.0864 |  | 0 | 185.85 | 100% | 100% | 100% | 100% | 0% | 100% | 185.85 | 0
K214-TFS-0124 | TFS | 20.01.01 | TFS00F102MM | N.A. | A-LVL STEEL INSTALLATION ON TF102 | 4.67 | 0 | 4.67 |  | TN | 3948.4821 |  | 0 | 69.74 | 100% | 100% | 100% | 100% | 0% | 100% | 69.74 | 0
K214-TFS-0126 | TFS | 20.01.01 | TFS00H101MM | N.A. | A-LVL STEEL INSTALLATION ON TH101 | 18.064 | 0 | 18.064 |  | TN | 3445.0557 |  | 0 | 221.58 | 100% | 100% | 100% | 100% | 0% | 100% | 221.58 | 0
K214-TFS-0071 | TFS | 20.01.01 | TFS00D103MM | N.A. | A-LVL STEEL INSTALLATION ON TD103 | 4.6945 | 0 | 4.6945 |  | TN | 180.1327 |  | 0 | 180.1327 | 100% | 100% | 100% | 100% | 0% | 100% | 180.1327 | 0
K214-TFS-1369 | TFS | 20.01.01 | TFS00D105MM | N.A. | A-LVL STEEL INSTALLATION ON TD105 | 2.088 | 0 | 2.088 |  | TN | 60.762 |  |  | 60.762 | 100% | 100% | 100% | 100% | 0% | 100% | 60.762 | 0 | Split A-LVL into separate record
K214-TFS-0075 | TFS | 20.01.01 | TFS00D107MM | N.A. | A-LVL STEEL INSTALLATION ON TD107 | 2.871 | 0 | 2.871 |  | TN | 104.7809 |  | 0 | 104.7809 | 100% | 100% | 100% | 100% | 0% | 100% | 104.7809 | 0
K214-TFS-0351 | TFS | 20.01.01 | TFS00SRUOM7 | N.A. | A-LVL STEEL INSTALLATION ON SRU-OM7 |  | 0 | 0 |  |  | 250 |  | 0 | 250 | 100% | 100% | 100% | 100% | 0% | 100% | 250 | 189.5
K214-TFS-0044 | TFS | 20.01.01 | TFS00E142MM | N.A. | MS STEEL ON TE142 | 0 | 11.5009 | 11.5009 | 0 | TN | 469.55 |  | 0 | 469.55 | 100% | 60% | 30% | 0% | 0% | 47.5% | 223.0362 | 0
K214-TFS-0045 | TFS | 20.01.01 | TFS00E143MM | N.A. | MS STEEL ON TE143 | 0 | 7.3981 | 7.3981 | 0 | TN | 323.05 |  | 0 | 323.05 | 100% | 60% | 30% | 0% | 0% | 47.5% | 153.4487 | 0
K214-TFS-0070 | TFS | 20.01.01 | TFS00D102MM | N.A. | MS STEEL ON TD102 | 6.4026 | 0 | 6.4026 | 2.0648 | TN | 274.1846 |  | 0 | 274.1846 | 50% | 40% | 25% | 0% | 0% | 32.25% | 88.4245 | 0
K214-TFS-0072 | TFS | 20.01.01 | TFS00D104MM | N.A. | MS STEEL ON TD104 | 4.0553 | 0 | 4.0553 |  | TN | 163.9425 |  | 0 | 163.9425 | 50% | 40% | 25% | 0% | 0% | 32.25% | 52.8714 | 0
K214-TFS-0073 | TFS | 20.01.01 | TFS00D105MM | N.A. | MS STEEL ON TD105 | 1.701 | 0 | 1.701 |  | TN | 100.762 |  | 0 | 100.762 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | Split A-LVL into separate record
K214-TFS-0074 | TFS | 20.01.01 | TFS00D106MM | N.A. | MS STEEL ON TD106 | 8.3352 | 0 | 8.3352 |  | TN | 382.7438 |  | 0 | 382.7438 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0076 | TFS | 20.01.01 | TFS00D108MM | N.A. | MS STEEL ON TD108 | 3.1565 | 0 | 3.1565 |  | TN | 137.9167 |  | 0 | 137.9167 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0077 | TFS | 20.01.01 | TFS00D109MM | N.A. | MS STEEL ON TD109 | 3.2203 | 0 | 3.2203 |  | TN | 116.1025 |  | 0 | 116.1025 | 80% | 65% | 65% | 0% | 0% | 63.25% | 73.4348 | 0
K214-TFS-0078 | TFS | 20.01.01 | TFS00D110MM | N.A. | MS STEEL ON TD110 | 0.44089 | 0 | 0.44089 |  | TN | 20.1895 |  | 0 | 20.1895 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0079 | TFS | 20.01.01 | TFS00D113MM | N.A. | MS STEEL ON TD113 | 16.3846 | 0 | 16.3846 |  | TN | 678.9668 |  | 0 | 678.9668 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0080 | TFS | 20.01.01 | TFS00D114MM | N.A. | MS STEEL ON TD114 | 4.097 | 0 | 4.097 |  | TN | 156.5442 |  | 0 | 156.5442 | 100% | 80% | 50% | 0% | 0% | 64.5% | 100.971 | 0
K214-TFS-0081 | TFS | 20.01.01 | TFS00D115MM | N.A. | MS STEEL ON TD115 | 0.826 | 0 | 0.826 |  | TN | 38.3644 |  | 0 | 38.3644 | 100% | 80% | 50% | 0% | 0% | 64.5% | 24.7451 | 0
K214-TFS-0082 | TFS | 20.01.01 | TFS00D116MM | N.A. | MS STEEL ON TD116 | 2.591 | 0 | 2.591 |  | TN | 86.3757 |  | 0 | 86.3757 | 100% | 80% | 50% | 0% | 0% | 64.5% | 55.7123 | 0
K214-TFS-0083 | TFS | 20.01.01 | TFS00D117MM | N.A. | MS STEEL ON TD117 | 0.88 | 0 | 0.88 |  | TN | 41.1259 |  | 0 | 41.1259 | 100% | 80% | 100% | 0% | 0% | 87% | 35.7795 | 0
K214-TFS-0084 | TFS | 20.01.01 | TFS00D118MM | N.A. | MS STEEL ON TD118 | 17.3539 | 0 | 17.3539 |  | TN | 721.9771 |  | 0 | 721.9771 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0085 | TFS | 20.01.01 | TFS00D119MM | N.A. | MS STEEL ON TD119 | 7.2168 | 0 | 7.2168 |  | TN | 295.4963 |  | 0 | 295.4963 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0086 | TFS | 20.01.01 | TFS00D120MM | N.A. | MS STEEL ON TD120 | 6.501 | 0 | 6.501 |  | TN | 274.1439 |  | 0 | 274.1439 | 50% | 30% | 20% | 0% | 0% | 26% | 71.2774 | 0
K214-TFS-0087 | TFS | 20.01.01 | TFS00D121MM | N.A. | MS STEEL ON TD121 | 3.807 | 0 | 3.807 |  | TN | 174.5742 |  | 0 | 174.5742 | 50% | 30% | 20% | 0% | 0% | 26% | 45.3893 | 0
K214-TFS-0088 | TFS | 20.01.01 | TFS00D122MM | N.A. | MS STEEL ON TD122 | 3.527 | 0 | 3.527 |  | TN | 150.9918 |  | 0 | 150.9918 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0089 | TFS | 20.01.01 | TFS00E103MM | N.A. | MS STEEL ON TE103 | 4.3977 | 0 | 4.3977 |  | TN | 158.9578 |  | 0 | 158.9578 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0090 | TFS | 20.01.01 | TFS00E104MM | N.A. | MS STEEL ON TE104 | 1.4727 | 0 | 1.4727 |  | TN | 69.1408 |  | 0 | 69.1408 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0091 | TFS | 20.01.01 | TFS00E105MM | N.A. | MS STEEL ON TE105 | 2.0607 | 0 | 2.0607 |  | TN | 72.4071 |  | 0 | 72.4071 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0092 | TFS | 20.01.01 | TFS00E106MM | N.A. | MS STEEL ON TE106 | 0.27153 | 0 | 0.27153 |  | TN | 12.0063 |  | 0 | 12.0063 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0093 | TFS | 20.01.01 | TFS00E107MM | N.A. | MS STEEL ON TE107 | 3.6743 | 0 | 3.6743 |  | TN | 137.0675 |  | 0 | 137.0675 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0094 | TFS | 20.01.01 | TFS00E108MM | N.A. | MS STEEL ON TE108 | 0.71403 | 0 | 0.71403 |  | TN | 33.0886 |  | 0 | 33.0886 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0095 | TFS | 20.01.01 | TFS00E109MM | N.A. | MS STEEL ON TE109 | 3.1185 | 0 | 3.1185 |  | TN | 109.7577 |  | 0 | 335 | 100% | 95% | 95% | 30% | 0% | 92.25% | 309.0375 | 0
K214-TFS-0096 | TFS | 20.01.01 | TFS00E110MM | N.A. | MS STEEL ON TE110 | 0.20605 | 0 | 0.20605 |  | TN | 9.1108 |  | 0 | 175.781 | 100% | 65% | 60% | 15% | 0% | 63.75% | 112.0604 | 0 | Original hrs not accuate for all the ship loose steel
K214-TFS-0097 | TFS | 20.01.01 | TFS00E111MM | N.A. | MS STEEL ON TE111 | 3.0155 | 0 | 3.0155 |  | TN | 96.1788 |  | 0 | 96.1788 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0098 | TFS | 20.01.01 | TFS00E112MM | N.A. | MS STEEL ON TE112 | 2.3849 | 0 | 2.3849 |  | TN | 111.4177 |  | 0 | 111.4177 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0099 | TFS | 20.01.01 | TFS00E113MM | N.A. | MS STEEL ON TE113 | 3.4847 | 0 | 3.4847 |  | TN | 127.6843 |  | 0 | 127.6843 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0100 | TFS | 20.01.01 | TFS00E114MM | N.A. | MS STEEL ON TE114 | 2.0659 | 0 | 2.0659 |  | TN | 97.968 |  | 0 | 97.968 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0101 | TFS | 20.01.01 | TFS00E115MM | N.A. | MS STEEL ON TE115 | 3.3348 | 0 | 3.3348 |  | TN | 111.6957 |  | 0 | 111.6957 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0102 | TFS | 20.01.01 | TFS00E116MM | N.A. | MS STEEL ON TE116 | 0.62988 | 0 | 0.62988 |  | TN | 29.0798 |  | 0 | 29.0798 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0103 | TFS | 20.01.01 | TFS00E117MM | N.A. | MS STEEL ON TE117 | 3.2618 | 0 | 3.2618 |  | TN | 117.3504 |  | 0 | 117.3504 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0104 | TFS | 20.01.01 | TFS00E118MM | N.A. | MS STEEL ON TE118 | 0.41516 | 0 | 0.41516 |  | TN | 19.4409 |  | 0 | 19.4409 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0105 | TFS | 20.01.01 | TFS00E119MM | N.A. | MS STEEL ON TE119 | 2.6467 | 0 | 2.6467 |  | TN | 89.4046 |  | 0 | 89.4046 | 100% | 100% | 100% | 100% | 0% | 100% | 89.4046 | 0
K214-TFS-0106 | TFS | 20.01.01 | TFS00E120MM | N.A. | MS STEEL ON TE120 | 0.19871 | 0 | 0.19871 |  | TN | 10.2071 |  | 0 | 10.2071 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0107 | TFS | 20.01.01 | TFS00E123MM | N.A. | MS STEEL ON TE123 | 18.029 | 0 | 18.029 |  | TN | 729.4702 |  | 0 | 729.4702 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0108 | TFS | 20.01.01 | TFS00E126MM | N.A. | MS STEEL ON TE126 | 6.2151 | 0 | 6.2151 |  | TN | 267.1904 |  | 0 | 267.1904 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0109 | TFS | 20.01.01 | TFS00E128MM | N.A. | MS STEEL ON TE128 | 0.98784 | 0 | 0.98784 |  | TN | 47.2487 |  | 0 | 47.2487 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0110 | TFS | 20.01.01 | TFS00E129MM | N.A. | MS STEEL ON TE129 | 0.38258 | 0 | 0.38258 |  | TN | 16.9165 |  | 0 | 225 | 100% | 85% | 80% | 15% | 0% | 80.75% | 181.6875 | 0 | Original hrs not accuate for all the ship loose steel
K214-TFS-0111 | TFS | 20.01.01 | TFS00E130MM | N.A. | MS STEEL ON TE130 | 2.193 | 0 | 2.193 |  | TN | 106.864 |  | 0 | 106.864 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0112 | TFS | 20.01.01 | TFS00E131MM | N.A. | MS STEEL ON TE131 | 3.0212 | 0 | 3.0212 |  | TN | 138.6551 |  | 0 | 138.6551 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0113 | TFS | 20.01.01 | TFS00E132MM | N.A. | MS STEEL ON TE132 | 12.0883 | 0 | 12.0883 |  | TN | 461.4496 |  | 0 | 461.4496 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0114 | TFS | 20.01.01 | TFS00E133MM | N.A. | MS STEEL ON TE133 | 0.4905 | 0 | 0.4905 |  | TN | 23.8884 |  | 0 | 23.8884 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0115 | TFS | 20.01.01 | TFS00E134MM | N.A. | MS STEEL ON TE134 | 2.9262 | 0 | 2.9262 |  | TN | 126.7098 |  | 0 | 126.7098 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0116 | TFS | 20.01.01 | TFS00E136MM | N.A. | MS STEEL ON TE136 | 18.33 | 0 | 18.33 |  | TN | 742.127 |  | 0 | 742.127 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0117 | TFS | 20.01.01 | TFS00E137MM | N.A. | MS STEEL ON TE137 | 8.6268 | 0 | 8.6268 |  | TN | 359.5391 |  | 0 | 359.5391 | 100% | 90% | 80% | 0% | 0% | 82% | 294.8221 | 0
K214-TFS-0118 | TFS | 20.01.01 | TFS00E138MM | N.A. | MS STEEL ON TE138 | 3.7871 | 0 | 3.7871 |  | TN | 141.7838 |  | 0 | 141.7838 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0119 | TFS | 20.01.01 | TFS00E139MM | N.A. | MS STEEL ON TE139 | 0.27153 | 0 | 0.27153 |  | TN | 12.0063 |  | 0 | 12.0063 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0120 | TFS | 20.01.01 | TFS00E140MM | N.A. | MS STEEL ON TE140 | 0.3363 | 0 | 0.3363 |  | TN | 15.8652 |  | 0 | 15.8652 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0121 | TFS | 20.01.01 | TFS00E144MM | N.A. | MS STEEL ON TE144 | 0.33383 | 0 | 0.33383 |  | TN | 16.3819 |  | 0 | 16.3819 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0122 | TFS | 20.01.01 | TFS00E145MM | N.A. | MS STEEL ON TE145 | 1.7567 | 0 | 1.7567 |  | TN | 70.649 |  | 0 | 70.649 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0125 | TFS | 20.01.01 | TFS00G101MM | N.A. | MS STEEL ON TG101 | 113.1573 | 0 | 113.1573 |  | TN | 3958.7412 |  | 0 | 507 | 100% | 85% | 80% | 0% | 0% | 80% | 405.6 | 0
K214-TFS-0127 | TFS | 20.01.01 | TFS00I101MM | N.A. | MS STEEL ON TI101 | 3.706 | 0 | 3.706 |  | TN | 128.4704 |  | 0 | 128.4704 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0128 | TFS | 20.01.01 | TFS00I102MM | N.A. | MS STEEL ON TI102 | 1.3 | 0 | 1.3 |  | TN | 59.6557 |  | 0 | 59.6557 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0129 | TFS | 20.01.01 | TFS00I103MM | N.A. | MS STEEL ON TI103 | 4.752 | 0 | 4.752 |  | TN | 177.3262 |  | 0 | 177.3262 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0130 | TFS | 20.01.01 | TFS00I104MM | N.A. | MS STEEL ON TI104 | 0.467 | 0 | 0.467 |  | TN | 21.7983 |  | 0 | 21.7983 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0131 | TFS | 20.01.01 | TFS00I105MM | N.A. | MS STEEL ON TI105 | 3.214 | 0 | 3.214 |  | TN | 104.9794 |  | 0 | 104.9794 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0132 | TFS | 20.01.01 | TFS00I106MM | N.A. | MS STEEL ON TI106 | 1.211 | 0 | 1.211 |  | TN | 56.8707 |  | 0 | 56.8707 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0133 | TFS | 20.01.01 | TFS00I107MM | N.A. | MS STEEL ON TI107 | 17.8273 | 0 | 17.8273 |  | TN | 720.0897 |  | 0 | 720.0897 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0134 | TFS | 20.01.01 | TFS00I108MM | N.A. | MS STEEL ON TI108 | 17.816 | 0 | 17.816 |  | TN | 719.5839 |  | 0 | 719.5839 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0135 | TFS | 20.01.01 | TFS00I109MM | N.A. | MS STEEL ON TI109 | 1.47 | 0 | 1.47 |  | TN | 63.3152 |  | 0 | 63.3152 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0136 | TFS | 20.01.01 | TFS00I110MM | N.A. | MS STEEL ON TI110 | 6.765 | 0 | 6.765 |  | TN | 270.6622 |  | 0 | 270.6622 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0137 | TFS | 20.01.01 | TFS00I111MM | N.A. | MS STEEL ON TI111 | 4.131 | 0 | 4.131 |  | TN | 170.3958 |  | 0 | 170.3958 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0138 | TFS | 20.01.01 | TFS00J101MM | N.A. | MS STEEL ON TJ101 | 131.2229 | 0 | 131.2229 |  | TN | 3854.9627 |  | 0 | 3854.9627 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1358 | TFS | 20.01.01 | TFS00K110MM |  | MS STEEL ON TK110 |  | 0 |  |  | TN | 130 |  | 0 | 130.25 | 100% | 80% | 75% | 0% | 0% | 75.75% | 98.6644 | 0
K214-TFS-1184 | TFS | 20.01.01 | TFS00A101MM | N.A. | MS STEEL ON TA101 | 14.26 | 0 | 14.26 | 6.8305 | TN | 354.5 |  | 0 | 354.5 | 67% | 57% | 50% | 21% | 0% | 47.9% | 188.0622 | 0
K214-TFS-1185 | TFS | 20.01.01 | TFS00A107MM | N.A. | MS STEEL ON TA107 | 70.2 | 0 | 70.2 | 69.5331 | TN | 3778 |  | 0 | 3778 | 100% | 100% | 99% | 90% | 0% | 99.05% | 3742.109 | 0
K214-TFS-1186 | TFS | 20.01.01 | TFS00A108MM | N.A. | MS STEEL ON TA108 | 2.63 | 0 | 2.63 | 2.3801 | TN | 1100 |  | 0 | 1100 | 100% | 100% | 90% | 0% | 0% | 90.5% | 995.5 | 0
K214-TFS-1187 | TFS | 20.01.01 | TFS00A104MM | N.A. | MS STEEL ON TA104 | 46.55 | 0 | 46.55 | 39.102 | TN | 1772.71 |  | 0 | 1772.71 | 100% | 95% | 80% | 0% | 0% | 84% | 1489.0764 | 0
K214-TFS-1188 | TFS | 20.01.01 | TFS00A105MM | N.A. | MS STEEL ON TA105 | 20.53 | 0 | 20.53 | 19.5035 | TN | 614 |  | 0 | 614 | 100% | 100% | 100% | 0% | 0% | 95% | 583.3 | 0
K214-TFS-1261 | TFS | 20.01.01 | TFS00F101MM | N.A. | MS STEEL ON TF101 | 8.38 | 0 | 8.38 | 6.704 | TN | 415.15 |  | 0 | 415.15 | 100% | 85% | 80% | 0% | 0% | 80% | 332.12 | 0
K214-TFS-1335 | TFS | 20.01.01 | TFS00F102MM | N.A. | MS STEEL ON TF102 | 92 | 0 | 92 | 73.6 | TN | 658.66 |  | 0 | 658.66 | 100% | 85% | 80% | 0% | 0% | 80% | 526.928 | 0
K214-TFS-1262 | TFS | 20.01.01 | TFS00H101MM | N.A. | MS STEEL ON TH101 | 11.1 | 0 | 11.1 | 9.102 | TN | 414.42 |  | 0 | 414.42 | 100% | 90% | 80% | 0% | 0% | 82% | 339.8244 | 0
K214-TFS-1263 | TFS | 20.01.01 | TFS00A102MM | N.A. | MS STEEL ON TA102 | 37.5 | 0 | 37.5 | 30 | TN | 1689.44 |  | 0 | 1689.44 | 100% | 85% | 80% | 0% | 0% | 80% | 1351.552 | 0
K214-TFS-1313 | TFS | 20.01.01 | TFS00A109MM | N.A. | MS STEEL ON TA109 | 57.93 | 0 | 57.93 | 38.8131 | TN | 2991 |  | 0 | 2991 | 100% | 75% | 60% | 0% | 0% | 67% | 2003.97 | 0
K214-TFS-1336 | TFS | 20.01.01 | TFS00A110MM | N.A. | MS STEEL ON TA110 | 43 | 0 | 43 | 19.565 | TN | 2847 |  | 0 | 2847 | 100% | 55% | 30% | 0% | 0% | 45.5% | 1295.385 | 0
K214-TFS-1337 | TFS | 20.01.01 | TFS00A111MM | N.A. | MS STEEL ON TA111 | 42 | 0 | 42 | 7.98 | TN | 1453.84 |  | 0 | 1453.84 | 85% | 15% | 10% | 0% | 0% | 19% | 276.2296 | 0
K214-TFS-1338 | TFS | 20.01.01 | TFS00A103MM | N.A. | MS STEEL ON TA103 | 37.77 | 0 | 214.4 | 31.8212 | TN | 1469.13 |  | 0 | 1469.13 | 100% | 90% | 85% | 0% | 0% | 84.25% | 1237.742 | 0
| TFS | 20.01.01 | TFS00B101MM | N.A. | MS STEEL ON TB101 | 1 | 0 | [5 empty] | 0 | 17.16 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1339 | TFS | 20.01.01 | TFS00B102MM | N.A. | MS STEEL ON TB102 | 38 | 0 |  |  | TN | 1270.33 |  | 0 | 1270.33 | 20% | 20% | 20% | 0% | 0% | 19% | 241.3627 | 0
| TFS | 20.01.01 | TFS00B103MM | N.A. | MS STEEL ON TB103 | 5.7 | 0 |  |  | TN |  |  | 0 | 166.65 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B104MM | N.A. | MS STEEL ON TB104 |  | 0 | [5 empty] | 0 | 314.12 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B105MM | N.A. | MS STEEL ON TB105 |  | 0 | [5 empty] | 0 | 169.16 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00B106MM | N.A. | MS STEEL ON TB106 |  | 0 | [5 empty] | 0 | 620.25 | 25% | 15% | 10% | 0% | 0% | 13% | 80.6325 | 0
| TFS | 20.01.01 | TFS00B107MM | N.A. | MS STEEL ON TB107 |  | 0 | [5 empty] | 0 | 598.37 | 25% | 10% | 5% | 0% | 0% | 8.75% | 52.3574 | 0
| TFS | 20.01.01 | TFS00B108MM | N.A. | MS STEEL ON TB108 |  | 0 | [5 empty] | 0 | 1957.91 | 10% | 5% | 5% | 0% | 0% | 5.25% | 102.7903 | 0
| TFS | 20.01.01 | TFS00B109MM | N.A. | MS STEEL ON TB109 |  | 0 | [5 empty] | 0 | 624.53 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
| TFS | 20.01.01 | TFS00D101MM | N.A. | MS STEEL ON TD101 | 3 | 0 | [5 empty] | 0 | 150.45 | 50% | 40% | 25% | 0% | 0% | 32.25% | 48.5201
| TFS | 20.01.01 | TFS00D103MM | N.A. | MS STEEL ON TD103 | 0.922 | 0 | [5 empty] | 0 | 125.27 | 50% | 40% | 25% | 0% | 0% | 32.25% | 40.3996
K214-TFS-1231 | TFS | 20.01.01 | TFS00SRU | N.A. | INSTALLATION OF STEEL FOR SRU GRATING |  | 0 | [5 empty] | 0 | 1400 | 100% | 100% | 100% | 0% | 0% | 95% | 1330 | 0
K214-TFS-1264 | TFS | 20.01.01 | TFS00SRU | N.A. | INSTALLATION OF STEEL FOR SRU GIRTS AND SAG RODS |  | 0 | [5 empty] | 0 | 1400 | 100% | 100% | 100% | 0% | 0% | 95% | 1330 | 0
K214-TFS-0139 | TFS | 20.01.01 | TFS00-EH-43 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #43 |  | 0 | 0 |  |  | 300 |  | 0 | 300 | 100% | 100% | 100% | 0% | 0% | 95% | 285 | 204
K214-TFS-0140 | TFS | 20.01.01 | TFS00-EH-44 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #44 |  | 0 | 0 |  |  | 300 |  | 0 | 300 | 100% | 100% | 100% | 0% | 0% | 95% | 285 | 264
K214-TFS-0350 | TFS | 20.01.01 | TFS00-EH-40 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #40 |  | 0 | 0 |  |  | 600 |  | 0 | 600 | 100% | 100% | 50% | 0% | 0% | 72.5% | 435 | 292.625
K214-TFS-0352 | TFS | 20.01.01 | TFS00-EH-41 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #41 |  | 0 | 0 |  |  | 800 |  | 0 | 400 | 100% | 100% | 100% | 0% | 0% | 95% | 380 | 175.25
K214-TFS-1056 | TFS | 20.01.01 | TFS00-EH-42 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #42 |  | 0 | 0 |  |  | 300 |  | 0 | 300 | 100% | 95% | 93% | 0% | 0% | 89.85% | 269.55 | 0
K214-TFS-1059 | TFS | 20.01.01 | TFS00-EH-45 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #45 |  | 0 | 0 |  |  |  |  | 0 | 300 | 100% | 75% | 50% | 0% | 0% | 62.5% | 187.5 | 0
K214-TFS-1060 | TFS | 20.01.01 | TFS00-EH-46 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #46 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1061 | TFS | 20.01.01 | TFS00-EH-47 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #47 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-1062 | TFS | 20.01.01 | TFS00-EH-48 | N.A. | INSTALLATION OF PLATFORM STEEL ON E-HOUSE #48 |  | 0 | 0 |  |  |  |  | 0 | 300 | 100% | 100% | 95% | 0% | 0% | 92.75% | 278.25 | 0

## MODULE SET
Progress Item ID | WBS | ROC Set |  |  | Description | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS | MILESTONES |  |  |  |  | TOTAL PROGRESS | EARN HOURS | Actual HOURS | COMMENT / NOTE
Progress Item ID | WBS | ROC Set | Module | Drawing | Description SETTING | [9 empty] | Stage | Set / Install |  | %
[5 empty] | Setting / Stacking | 184 | 0 | 179 | 24.56 |  | 17741.85 | 247 | 0 | 18180.74 | 5% | 85% | 0% | 10% | 0% |  | 13731.7832 | 11506.75
K214-TFS-0013 | TFS | 40.28.01 | TFS00T101MM | N.A. | INSTALLATION OF MODULE TT101 | 1 | 0 | 1 | 1 | EA | 64.27 | 237 | 0 | 301.27 | 100% | 100% | 0% | 100% | 0% | 100% | 301.27 | 301
K214-TFS-1063 | TFS | 40.28.02 | TFS00T102MM | N.A. | INSTALLATION OF SHOEBOX TT102-B | 1 | 0 | 1 | 1 | EA | 193 |  |  | 192.81 | 100% | 100% | 0% | 100% | 0% | 100% | 192.81 | 0
K214-TFS-0042 | TFS | 40.28.01 | TFS00T103MM | N.A. | INSTALLATION OF MODULE TT103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0014 | TFS | 40.28.01 | TFS00T104MM | N.A. | INSTALLATION OF MODULE TT104 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0015 | TFS | 40.28.01 | TFS00T105MM | N.A. | INSTALLATION OF MODULE TT105 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0016 | TFS | 40.28.01 | TFS00T106MM | N.A. | INSTALLATION OF MODULE TT106 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0017 | TFS | 40.28.01 | TFS00T107MM | N.A. | INSTALLATION OF MODULE TT107 | 1 | 0 | 1 | 1 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0018 | TFS | 40.28.01 | TFS00T108MM | N.A. | INSTALLATION OF MODULE TT108 | 1 | 0 | 1 | 1 | EA | 64.27 | 10 | 0 | 74.27 | 100% | 100% | 0% | 100% | 0% | 100% | 74.27 | 161
K214-TFS-0019 | TFS | 40.28.01 | TFS00T109MM | N.A. | INSTALLATION OF MODULE TT109 | 1 | 0 | 1 | 0 | EA | 87 |  | 0 | 87 | 100% | 100% | 0% | 100% | 0% | 100% | 87 | 87
K214-TFS-0020 | TFS | 40.28.01 | TFS00T110MM | N.A. | INSTALLATION OF MODULE TT110 | 1 | 0 | 1 | 1 | EA | 87 |  | 0 | 87 | 100% | 100% | 0% | 100% | 0% | 100% | 87 | 87
K214-TFS-0021 | TFS | 40.28.01 | TFS00-EH-40 | N.A. | INSTALLATION OF E-HOUSE #40 | 1 | 0 | 1 | 1 | EA | 98.25 |  | 0 | 98.25 | 100% | 100% | 0% | 100% | 0% | 100% | 98.25 | 98.25
K214-TFS-0065 | TFS | 40.28.01 | TFS00-EH-41 | N.A. | INSTALLATION OF E-HOUSE #41 | 1 | 0 | 1 | 1 | EA | 216 |  | 0 | 216 | 100% | 100% | 0% | 100% | 0% | 100% | 216 | 216
K214-TFS-0066 | TFS | 40.28.01 | TFS00-EH-42 | N.A. | INSTALLATION OF E-HOUSE #42 | 1 | 0 | 1 | 1 | EA | 180 |  | 0 | 180 | 100% | 100% | 0% | 100% | 0% | 100% | 180 | 180
K214-TFS-0022 | TFS | 40.28.01 | TFS00-EH-43 | N.A. | INSTALLATION OF E-HOUSE #43 | 1 | 0 | 1 | 1 | EA | 167 |  | 0 | 167 | 100% | 100% | 0% | 100% | 0% | 100% | 167 | 167
K214-TFS-0023 | TFS | 40.28.01 | TFS00-EH-44 | N.A. | INSTALLATION OF E-HOUSE #44 | 1 | 0 | 1 | 1 | EA | 106 |  | 0 | 106 | 100% | 100% | 0% | 100% | 0% | 100% | 106 | 106
K214-TFS-1064 | TFS | 40.28.01 | TFS00-EH-45 | N.A. | INSTALLATION OF E-HOUSE #45 | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 350 | 100% | 100% | 0% | 100% | 0% | 100% | 350 | 0
K214-TFS-1065 | TFS | 40.28.01 | TFS00-EH-46 | N.A. | INSTALLATION OF E-HOUSE #46 | 1 | 0 | 1 | 0.56 | EA | 200 |  | 0 | 350 | 100% | 60% | 40% |  | 0% | 56% | 196 | 0
K214-TFS-1066 | TFS | 40.28.01 | TFS00-EH-47 | N.A. | INSTALLATION OF E-HOUSE #47 | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 0 |  |  | 0% |  | 0% | 0% | 0 | 0
K214-TFS-1067 | TFS | 40.28.01 | TFS00-EH-48 | N.A. | INSTALLATION OF E-HOUSE #48 | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0141 | TFS | 40.28.01 | TFS00A108MM | N.A. | INSTALLATION OF SHOEBOX TA108-B | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0142 | TFS | 40.28.01 | TFS00A108MM | N.A. | INSTALLATION OF SHOEBOX TA108-C | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0143 | TFS | 40.28.01 | TFS00A108MM | N.A. | INSTALLATION OF SHOEBOX TA108-D | 1 | 0 | 1 | 1 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0144 | TFS | 40.28.01 | TFS00W101MM | N.A. | INSTALLATION OF MODULE TW101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0145 | TFS | 40.28.01 | TFS00W102MM | N.A. | INSTALLATION OF MODULE TW102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0148 | TFS | 40.28.01 | TFS00W103MM | N.A. | INSTALLATION OF MODULE TW103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0190 | TFS | 40.28.01 | TFS00K101MM | N.A. | INSTALLATION OF MODULE TK101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0147 | TFS | 40.28.01 | TFS00K103MM | N.A. | INSTALLATION OF MODULE TK103 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0146 | TFS | 40.28.01 | TFS00K106MM | N.A. | INSTALLATION OF MODULE TK106 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0152 | TFS | 40.28.01 | TFS00K105MM | N.A. | INSTALLATION OF MODULE TK105 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0153 | TFS | 40.28.01 | TFS00K107MM | N.A. | INSTALLATION OF MODULE TK107 | 1 | 0 | 1 | 0 | EA | 100 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0154 | TFS | 40.28.01 | TFS00K109MM | N.A. | INSTALLATION OF MODULE TK109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0155 | TFS | 40.28.01 | TFS00D114MM | N.A. | INSTALLATION OF MODULE TD114 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0156 | TFS | 40.28.01 | TFS00D115MM | N.A. | INSTALLATION OF MODULE TD115 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0157 | TFS | 40.28.01 | TFS00D121MM | N.A. | INSTALLATION OF MODULE TD121 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0158 | TFS | 40.28.01 | TFS00D116MM | N.A. | INSTALLATION OF MODULE TD116 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0159 | TFS | 40.28.01 | TFS00D117MM | N.A. | INSTALLATION OF MODULE TD117 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0160 | TFS | 40.28.01 | TFS00D122MM | N.A. | INSTALLATION OF MODULE TD122 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0161 | TFS | 40.28.01 | TFS00W106MM | N.A. | INSTALLATION OF MODULE TW106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0162 | TFS | 40.28.01 | TFS00V101MM | N.A. | INSTALLATION OF MODULE TV101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0163 | TFS | 40.28.01 | TFS00V102MM | N.A. | INSTALLATION OF MODULE TV102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0164 | TFS | 40.28.01 | TFS00D109MM | N.A. | INSTALLATION OF MODULE TD109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0165 | TFS | 40.28.01 | TFS00V103MM | N.A. | INSTALLATION OF MODULE TV103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0166 | TFS | 40.28.01 | TFS00D110MM | N.A. | INSTALLATION OF MODULE TD110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0167 | TFS | 40.28.01 | TFS00D119MM | N.A. | INSTALLATION OF MODULE TD119 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0168 | TFS | 40.28.01 | TFS00K110MM | N.A. | INSTALLATION OF MODULE TK110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0169 | TFS | 40.28.01 | TFS00I101MM | N.A. | INSTALLATION OF MODULE TI101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0170 | TFS | 40.28.01 | TFS00I102MM | N.A. | INSTALLATION OF MODULE TI102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0171 | TFS | 40.28.01 | TFS00I109MM | N.A. | INSTALLATION OF MODULE TI109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0172 | TFS | 40.28.01 | TFS00D101MM | N.A. | INSTALLATION OF MODULE TD101 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0173 | TFS | 40.28.01 | TFS00D102MM | N.A. | INSTALLATION OF MODULE TD102 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0174 | TFS | 40.28.01 | TFS00D103MM | N.A. | INSTALLATION OF MODULE TD103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0175 | TFS | 40.28.01 | TFS00D104MM | N.A. | INSTALLATION OF MODULE TD104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 0% | 0% | 90% | 57.843 | 0
K214-TFS-0176 | TFS | 40.28.01 | TFS00E107MM | N.A. | INSTALLATION OF MODULE TE107 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0177 | TFS | 40.28.01 | TFS00E108MM | N.A. | INSTALLATION OF MODULE TE108 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0178 | TFS | 40.28.01 | TFS00E128MM | N.A. | INSTALLATION OF MODULE TE128 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0179 | TFS | 40.28.01 | TFS00E144MM | N.A. | INSTALLATION OF MODULE TE144 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0180 | TFS | 40.28.01 | TFS00E138MM | N.A. | INSTALLATION OF MODULE TE138 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0181 | TFS | 40.28.01 | TFS00E111MM | N.A. | INSTALLATION OF MODULE TE111 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0182 | TFS | 40.28.01 | TFS00E112MM | N.A. | INSTALLATION OF MODULE TE112 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0183 | TFS | 40.28.01 | TFS00E130MM | N.A. | INSTALLATION OF MODULE TE130 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0184 | TFS | 40.28.01 | TFS00E113MM | N.A. | INSTALLATION OF MODULE TE113 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0185 | TFS | 40.28.01 | TFS00E114MM | N.A. | INSTALLATION OF MODULE TE114 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0186 | TFS | 40.28.01 | TFS00E131MM | N.A. | INSTALLATION OF MODULE TE131 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0187 | TFS | 40.28.01 | TFS00E139MM | N.A. | INSTALLATION OF MODULE TE139 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0188 | TFS | 40.28.01 | TFS00E140MM | N.A. | INSTALLATION OF MODULE TE140 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0149 | TFS | 40.28.01 | TFS00E141MM | N.A. | INSTALLATION OF MODULE TE141 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0150 | TFS | 40.28.01 | TFS00E142MM | N.A. | INSTALLATION OF MODULE TE142 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0151 | TFS | 40.28.01 | TFS00E143MM | N.A. | INSTALLATION OF MODULE TE143 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0189 | TFS | 40.28.01 | TFS00E145MM | N.A. | INSTALLATION OF MODULE TE145 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0191 | TFS | 40.28.01 | TFS00E109MM | N.A. | INSTALLATION OF MODULE TE109 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0192 | TFS | 40.28.01 | TFS00E103MM | N.A. | INSTALLATION OF MODULE TE103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0193 | TFS | 40.28.01 | TFS00E104MM | N.A. | INSTALLATION OF MODULE TE104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0194 | TFS | 40.28.01 | TFS00E119MM | N.A. | INSTALLATION OF MODULE TE119 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0195 | TFS | 40.28.01 | TFS00E120MM | N.A. | INSTALLATION OF MODULE TE120 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0196 | TFS | 40.28.01 | TFS00E134MM | N.A. | INSTALLATION OF MODULE TE134 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 60% | 0% | 0% | 0% | 56% | 35.9912 | 0
K214-TFS-0197 | TFS | 40.28.01 | TFS00E110MM | N.A. | INSTALLATION OF MODULE TE110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0198 | TFS | 40.28.01 | TFS00E129MM | N.A. | INSTALLATION OF MODULE TE129 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 100% | 100% | 0% | 100% | 0% | 100% | 64.27 | 0
K214-TFS-0199 | TFS | 40.28.01 | TFS00E126MM | N.A. | INSTALLATION OF MODULE TE126 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0200 | TFS | 40.28.01 | TFS00E105MM | N.A. | INSTALLATION OF MODULE TE105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0201 | TFS | 40.28.01 | TFS00E106MM | N.A. | INSTALLATION OF MODULE TE106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0202 | TFS | 40.28.01 | TFS00E115MM | N.A. | INSTALLATION OF MODULE TE115 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0203 | TFS | 40.28.01 | TFS00E127MM | N.A. | INSTALLATION OF MODULE TE127 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0204 | TFS | 40.28.01 | TFS00I103MM | N.A. | INSTALLATION OF MODULE TI103 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0205 | TFS | 40.28.01 | TFS00I104MM | N.A. | INSTALLATION OF MODULE TI104 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0206 | TFS | 40.28.01 | TFS00I110MM | N.A. | INSTALLATION OF MODULE TI110 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0207 | TFS | 40.28.01 | TFS00I105MM | N.A. | INSTALLATION OF MODULE TI105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0208 | TFS | 40.28.01 | TFS00I106MM | N.A. | INSTALLATION OF MODULE TI106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0209 | TFS | 40.28.01 | TFS00I111MM | N.A. | INSTALLATION OF MODULE TI111 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0210 | TFS | 40.28.01 | TFS00E116MM | N.A. | INSTALLATION OF MODULE TE116 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0211 | TFS | 40.28.01 | TFS00E132MM | N.A. | INSTALLATION OF MODULE TE132 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0212 | TFS | 40.28.01 | TFS00E117MM | N.A. | INSTALLATION OF MODULE TE117 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0213 | TFS | 40.28.01 | TFS00E118MM | N.A. | INSTALLATION OF MODULE TE118 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0214 | TFS | 40.28.01 | TFS00E133MM | N.A. | INSTALLATION OF MODULE TE133 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0215 | TFS | 40.28.01 | TFS00E137MM | N.A. | INSTALLATION OF MODULE TE137 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0216 | TFS | 40.28.01 | TFS00D105MM | N.A. | INSTALLATION OF MODULE TD105 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0217 | TFS | 40.28.01 | TFS00D106MM | N.A. | INSTALLATION OF MODULE TD106 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0218 | TFS | 40.28.01 | TFS00D107MM | N.A. | INSTALLATION OF MODULE TD107 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0219 | TFS | 40.28.01 | TFS00D108MM | N.A. | INSTALLATION OF MODULE TD108 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0220 | TFS | 40.28.01 | TFS00D120MM | N.A. | INSTALLATION OF MODULE TD120 | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0221 | TFS | 40.28.01 | TFS00A101MM | N.A. | INSTALLATION OF SHOEBOX TA101-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0222 | TFS | 40.28.01 | TFS00A101MM | N.A. | INSTALLATION OF SHOEBOX TA101-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0223 | TFS | 40.28.01 | TFS00A101MM | N.A. | INSTALLATION OF SHOEBOX TA101-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0224 | TFS | 40.28.01 | TFS00A102MM | N.A. | INSTALLATION OF SHOEBOX TA102-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0225 | TFS | 40.28.01 | TFS00A102MM | N.A. | INSTALLATION OF SHOEBOX TA102-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0226 | TFS | 40.28.01 | TFS00A102MM | N.A. | INSTALLATION OF SHOEBOX TA102-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0227 | TFS | 40.28.01 | TFS00A103MM | N.A. | INSTALLATION OF SHOEBOX TA103-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0228 | TFS | 40.28.01 | TFS00A103MM | N.A. | INSTALLATION OF SHOEBOX TA103-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0229 | TFS | 40.28.01 | TFS00A103MM | N.A. | INSTALLATION OF SHOEBOX TA103-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0230 | TFS | 40.28.01 | TFS00A104MM | N.A. | INSTALLATION OF SHOEBOX TA104-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0231 | TFS | 40.28.01 | TFS00A104MM | N.A. | INSTALLATION OF SHOEBOX TA104-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0232 | TFS | 40.28.01 | TFS00A104MM | N.A. | INSTALLATION OF SHOEBOX TA104-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0233 | TFS | 40.28.01 | TFS00A105MM | N.A. | INSTALLATION OF SHOEBOX TA105-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0234 | TFS | 40.28.01 | TFS00A105MM | N.A. | INSTALLATION OF SHOEBOX TA105-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0235 | TFS | 40.28.01 | TFS00A105MM | N.A. | INSTALLATION OF SHOEBOX TA105-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0236 | TFS | 40.28.01 | TFS00A106MM | N.A. | INSTALLATION OF SHOEBOX TA106-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0237 | TFS | 40.28.01 | TFS00A106MM | N.A. | INSTALLATION OF SHOEBOX TA106-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0238 | TFS | 40.28.01 | TFS00A106MM | N.A. | INSTALLATION OF SHOEBOX TA106-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0239 | TFS | 40.28.01 | TFS00A107MM | N.A. | INSTALLATION OF SHOEBOX TA107-B | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0240 | TFS | 40.28.01 | TFS00A107MM | N.A. | INSTALLATION OF SHOEBOX TA107-C | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0241 | TFS | 40.28.01 | TFS00A107MM | N.A. | INSTALLATION OF SHOEBOX TA107-D | 1 | 0 | 1 | 0 | EA | 200 |  | 0 | 200 | 100% | 100% | 0% | 100% | 0% | 100% | 200 | 0
K214-TFS-0242 | TFS | 40.28.01 | TFS00A109MM | N.A. | INSTALLATION OF SHOEBOX TA109-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0243 | TFS | 40.28.01 | TFS00A109MM | N.A. | INSTALLATION OF SHOEBOX TA109-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0244 | TFS | 40.28.01 | TFS00A109MM | N.A. | INSTALLATION OF SHOEBOX TA109-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0245 | TFS | 40.28.01 | TFS00A110MM | N.A. | INSTALLATION OF SHOEBOX TA110-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0246 | TFS | 40.28.01 | TFS00A110MM | N.A. | INSTALLATION OF SHOEBOX TA110-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0247 | TFS | 40.28.01 | TFS00A110MM | N.A. | INSTALLATION OF SHOEBOX TA110-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0248 | TFS | 40.28.01 | TFS00A111MM | N.A. | INSTALLATION OF SHOEBOX TA111-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0249 | TFS | 40.28.01 | TFS00A111MM | N.A. | INSTALLATION OF SHOEBOX TA111-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0250 | TFS | 40.28.01 | TFS00A111MM | N.A. | INSTALLATION OF SHOEBOX TA111-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0251 | TFS | 40.28.01 | TFS00A112MM | N.A. | INSTALLATION OF SHOEBOX TA112-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0252 | TFS | 40.28.01 | TFS00A112MM | N.A. | INSTALLATION OF SHOEBOX TA112-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0253 | TFS | 40.28.01 | TFS00B101MM | N.A. | INSTALLATION OF SHOEBOX TB101-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0254 | TFS | 40.28.01 | TFS00B101MM | N.A. | INSTALLATION OF SHOEBOX TB101-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0255 | TFS | 40.28.01 | TFS00B101MM | N.A. | INSTALLATION OF SHOEBOX TB101-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0256 | TFS | 40.28.01 | TFS00B102MM | N.A. | INSTALLATION OF SHOEBOX TB102-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0257 | TFS | 40.28.01 | TFS00B102MM | N.A. | INSTALLATION OF SHOEBOX TB102-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 100 | 100% | 100% | 0% | 100% | 0% | 100% | 100 | 0
K214-TFS-0258 | TFS | 40.28.01 | TFS00B102MM | N.A. | INSTALLATION OF SHOEBOX TB102-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0259 | TFS | 40.28.01 | TFS00B103MM | N.A. | INSTALLATION OF SHOEBOX TB103-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0260 | TFS | 40.28.01 | TFS00B103MM | N.A. | INSTALLATION OF SHOEBOX TB103-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0261 | TFS | 40.28.01 | TFS00B103MM | N.A. | INSTALLATION OF SHOEBOX TB103-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0262 | TFS | 40.28.01 | TFS00B104MM | N.A. | INSTALLATION OF SHOEBOX TB104-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0263 | TFS | 40.28.01 | TFS00B104MM | N.A. | INSTALLATION OF SHOEBOX TB104-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0264 | TFS | 40.28.01 | TFS00B104MM | N.A. | INSTALLATION OF SHOEBOX TB104-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0265 | TFS | 40.28.01 | TFS00B105MM | N.A. | INSTALLATION OF SHOEBOX TB105-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0266 | TFS | 40.28.01 | TFS00B105MM | N.A. | INSTALLATION OF SHOEBOX TB105-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0267 | TFS | 40.28.01 | TFS00B105MM | N.A. | INSTALLATION OF SHOEBOX TB105-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0268 | TFS | 40.28.01 | TFS00B106MM | N.A. | INSTALLATION OF SHOEBOX TB106-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0269 | TFS | 40.28.01 | TFS00B106MM | N.A. | INSTALLATION OF SHOEBOX TB106-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0270 | TFS | 40.28.01 | TFS00B106MM | N.A. | INSTALLATION OF SHOEBOX TB106-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0271 | TFS | 40.28.01 | TFS00B107MM | N.A. | INSTALLATION OF SHOEBOX TB107-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0272 | TFS | 40.28.01 | TFS00B107MM | N.A. | INSTALLATION OF SHOEBOX TB107-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0273 | TFS | 40.28.01 | TFS00B107MM | N.A. | INSTALLATION OF SHOEBOX TB107-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0274 | TFS | 40.28.01 | TFS00B108MM | N.A. | INSTALLATION OF SHOEBOX TB108-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0275 | TFS | 40.28.01 | TFS00B108MM | N.A. | INSTALLATION OF SHOEBOX TB108-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 100% | 100% | 0% | 100% | 0% | 100% | 85.69 | 0
K214-TFS-0276 | TFS | 40.28.01 | TFS00B108MM | N.A. | INSTALLATION OF SHOEBOX TB108-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0277 | TFS | 40.28.01 | TFS00B109MM | N.A. | INSTALLATION OF SHOEBOX TB109-B | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0278 | TFS | 40.28.01 | TFS00B109MM | N.A. | INSTALLATION OF SHOEBOX TB109-C | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0279 | TFS | 40.28.01 | TFS00B109MM | N.A. | INSTALLATION OF SHOEBOX TB109-D | 1 | 0 | 1 | 0 | EA | 85.69 |  | 0 | 85.69 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0280 | TFS | 40.28.01 | TFS00F101MM | N.A. | INSTALLATION OF SHOEBOX TF101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0281 | TFS | 40.28.01 | TFS00F101MM | N.A. | INSTALLATION OF SHOEBOX TF101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0282 | TFS | 40.28.01 | TFS00F102MM | N.A. | INSTALLATION OF SHOEBOX TF102-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0283 | TFS | 40.28.01 | TFS00F102MM | N.A. | INSTALLATION OF SHOEBOX TF102-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0284 | TFS | 40.28.01 | TFS00G101MM | N.A. | INSTALLATION OF SHOEBOX TG101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0285 | TFS | 40.28.01 | TFS00G101MM | N.A. | INSTALLATION OF SHOEBOX TG101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0286 | TFS | 40.28.01 | TFS00H101MM | N.A. | INSTALLATION OF SHOEBOX TH101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0287 | TFS | 40.28.01 | TFS00H101MM | N.A. | INSTALLATION OF SHOEBOX TH101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0288 | TFS | 40.28.01 | TFS00J101MM | N.A. | INSTALLATION OF SHOEBOX TJ101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0289 | TFS | 40.28.01 | TFS00J101MM | N.A. | INSTALLATION OF SHOEBOX TJ101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0290 | TFS | 40.28.01 | TFS00K102MM | N.A. | INSTALLATION OF SHOEBOX TK102-B | 1 | 0 | 1 | 0 | EA | 192 |  | 0 | 192 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0292 | TFS | 40.28.01 | TFS00K108MM | N.A. | INSTALLATION OF SHOEBOX TK108-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 192 | 100% | 100% | 0% | 100% | 0% | 100% | 192 | 0
K214-TFS-0293 | TFS | 40.28.01 | TFS00L101MM | N.A. | INSTALLATION OF SHOEBOX TL101-B | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0294 | TFS | 40.28.01 | TFS00L101MM | N.A. | INSTALLATION OF SHOEBOX TL101-C | 1 | 0 | 1 | 0 | EA | 64.27 |  | 0 | 64.27 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0295 | TFS | 40.28.01 | TFS00L102MM | N.A. | INSTALLATION OF SHOEBOX TL102-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0
K214-TFS-0296 | TFS | 40.28.01 | TFS00S101MM | N.A. | INSTALLATION OF SHOEBOX TS101-B | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0297 | TFS | 40.28.01 | TFS00S101MM | N.A. | INSTALLATION OF SHOEBOX TS101-C | 1 | 0 | 1 | 0 | EA | 96.4 |  | 0 | 96.4 | 100% | 100% | 0% | 100% | 0% | 100% | 96.4 | 0
K214-TFS-0298 | TFS | 40.28.01 | TFS00W104MM | N.A. | INSTALLATION OF SHOEBOX TW104-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 | 100% | 100% | 0% | 100% | 0% | 100% | 128.54 | 0
K214-TFS-0299 | TFS | 40.28.01 | TFS00W105MM | N.A. | INSTALLATION OF SHOEBOX TW105-B | 1 | 0 | 1 | 0 | EA | 128.54 |  | 0 | 128.54 | 100% | 100% | 0% | 100% | 0% | 100% | 128.54 | 0
K214-TFS-0353 | TFS | 40.28.01 | TFS00K104MM | N.A. | INSTALLATION OF MODULE TK104 | 1 | 0 | 1 | 0 | EA | 90 |  | 0 | 90 | 100% | 100% | 0% | 100% | 0% | 100% | 90 | 0
K214-TFS-0363 | TFS | 40.28.01 | TFS00SRUH06 | N.A. | INSTALLATION OF SRU-H06 | 1 | 1 | 1 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1068 | TFS | 40.28.01 | TFS00SRUS01 | N.A. | INSTALLATION OF SRU-S01 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1069 | TFS | 40.28.01 | TFS00SRUV02 | N.A. | INSTALLATION OF SRU-V02 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1070 | TFS | 40.28.01 | TFS00SRUV03 | N.A. | INSTALLATION OF SRU-V03 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1071 | TFS | 40.28.01 | TFS00SRUV04 | N.A. | INSTALLATION OF SRU-V04 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0
K214-TFS-1072 | TFS | 40.28.01 | TFS00SRUV05 | N.A. | INSTALLATION OF SRU-V05 | 1 | 0 | 0 | 1 | EA | 250 |  | 0 | 250 | 100% | 100% | 0% | 100% | 0% | 100% | 250 | 0

## PIPE INTERCONNECTS
[10 empty] | ORIG QTYS | APPROVED CHANGES | CONTROL QTYS | INSTALL QTYS | UOM | ORIGINAL BASE HRS | REWORK | APPROVED CHANGES | CONTROL BASE HRS | MILESTONES | [5 empty] | TOTAL PROGRESS | EARN HOURS | Actual HOURS | COMMENT / NOTE
[20 empty] | ML01 | ML02 | ML03 | ML04 | ML05
Progress Item ID | WBS | ROC Set | Module | Drawing | CWP | Contract | IWP | SUMMIT WP# | Drawing Number (ISO) | 8852.579 |  |  |  |  | 36699.872 |  | 0 | 48232.326 |  | Prepare & Stage | Complete | Punch / Accept |  |  | 424.3% | 100.14 | 19596
K214-TFS-0364 | TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-05 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | (DWH) | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 23.6 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0365 | TFS | 50.11.01 | TFS00F101MM | LP1Y-S(130)-018051-03 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0366 | TFS | 50.11.01 | TFS00A110MM | LP1Y-APL(100)-019072-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0367 | TFS | 50.11.01 | TFS00A111MM | LP1Y-APL(100)-019072-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0368 | TFS | 50.11.01 | TFS00B101MM | LP1Y-APL(100)-019072-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0369 | TFS | 50.11.01 | TFS00B102MM | LP1Y-APL(100)-019072-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0370 | TFS | 50.11.01 | TFS00A112MM | LP1Y-APL(100)-019072-14 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0371 | TFS | 50.11.01 | TFS00L101MM | LP1Y-APL(100)-019072-16 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | (DWH) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0372 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AWNP-037002-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0373 | TFS | 50.11.01 | TFS00J101MM | LP1Y-AWNP-037002-04 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 21.345 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0374 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AWNP-037002-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0375 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AWNP-037002-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0376 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AWNP-037002-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0377 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AWNP-037002-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0378 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AWNP-037002-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0379 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AWNP-037002-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0380 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AWNP-037002-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.453 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0381 | TFS | 50.11.01 | TFS00B109MM | LP1Y-AWNP-037002-13 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0382 | TFS | 50.11.01 | TFS00S101MM | LP1Y-AWNP-037004-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.317 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0383 | TFS | 50.11.01 | TFS00W105MM | LP1Y-AWNP-037004-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.16 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0384 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AWNP-037006-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0385 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AWNP-037006-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0386 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AWNP-037006-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0387 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AWNP-037006-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0388 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AWNP-037006-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0389 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AWNP-037006-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0390 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AWNP-037007-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0391 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AWNP-037007-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0392 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-101309-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.475 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0393 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-168101-03 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0394 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-168101-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0395 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-168101-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.5 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0396 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-168101-06 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0397 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-802111-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0398 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-802111-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0399 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-802111-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 89.4 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0400 | TFS | 50.11.01 | TFS00F101MM | LP1Y-AWNP-802111-04 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 45.944 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0401 | TFS | 50.11.01 | TFS00A107MM | LP1Y-AWNP-850001-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 75.012 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0402 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AWNP-850001-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 75.012 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0403 | TFS | 50.11.01 | TFS00A109MM | LP1Y-AWNP-850001-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0404 | TFS | 50.11.01 | TFS00H101MM | LP1Y-BS-016012-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.085 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0405 | TFS | 50.11.01 | TFS00A104MM | LP1Y-APL(100)-019072-19 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0406 | TFS | 50.11.01 | TFS00L102MM | LP1Y-APL(100)-019072-20 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0407 | TFS | 50.11.01 | TFS00B108MM | LP1Y-APL(100)-034026-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0408 | TFS | 50.11.01 | TFS00B109MM | LP1Y-APL(100)-034026-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0409 | TFS | 50.11.01 | TFS00B103MM | LP1Y-APL(100)-034026-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0410 | TFS | 50.11.01 | TFS00B104MM | LP1Y-APL(100)-034026-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0411 | TFS | 50.11.01 | TFS00B105MM | LP1Y-APL(100)-034026-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0412 | TFS | 50.11.01 | TFS00B106MM | LP1Y-APL(100)-034026-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0413 | TFS | 50.11.01 | TFS00B107MM | LP1Y-APL(100)-034026-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.767 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0414 | TFS | 50.11.01 | TFS00J101MM | LP1Y-APL(100)-034032-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.074 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0415 | TFS | 50.11.01 | TFS00B108MM | LP1Y-APL(100)-034033-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0416 | TFS | 50.11.01 | TFS00S101MM | LP1Y-APL(100)-034033-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.618 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0417 | TFS | 50.11.01 | TFS00B102MM | LP1Y-APL(100)-034033-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0418 | TFS | 50.11.01 | TFS00B103MM | LP1Y-APL(100)-034033-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0419 | TFS | 50.11.01 | TFS00B104MM | LP1Y-APL(100)-034033-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0420 | TFS | 50.11.01 | TFS00B105MM | LP1Y-APL(100)-034033-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0421 | TFS | 50.11.01 | TFS00B106MM | LP1Y-APL(100)-034033-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0422 | TFS | 50.11.01 | TFS00B107MM | LP1Y-APL(100)-034033-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.941 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0423 | TFS | 50.11.01 | TFS00W105MM | LP1Y-APL(100)-034040-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0424 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AWNP-015001-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0425 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-015001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0426 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-015001-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0427 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-015001-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 DWHU Connection | 2 |  | 2 | 0 | EA | 0 |  | 0 | 81.71 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1314 | TFS | 50.11.01 | TFS00A101MM | LP1Y-AWNP-015001-07 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA101 TO TA102 DWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  |  | 44.7 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0428 | TFS | 50.11.01 | TFS00A102MM | LP1Y-AWNP-015003-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0429 | TFS | 50.11.01 | TFS00A103MM | LP1Y-AWNP-015003-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0430 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AWNP-015003-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0431 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AWNP-015003-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0432 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AWNP-015003-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1370 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AWNP-015003-08 |  |  |  |  | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-0433 | TFS | 50.11.01 | TFS00A110MM | LP1Y-AWNP-015003-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0434 | TFS | 50.11.01 | TFS00A111MM | LP1Y-AWNP-015003-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0435 | TFS | 50.11.01 | TFS00G101MM | LP1Y-AWNP-015004-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0436 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACN-010018-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0437 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACN-010018-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 52 |  | 0 | 52 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0438 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACN-010018-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0439 | TFS | 50.11.01 | TFS00A106MM | LP1Y-ACN-010018-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0440 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACN-010018-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0441 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACN-010018-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0442 | TFS | 50.11.01 | TFS00A109MM | LP1Y-ACN-010018-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0443 | TFS | 50.11.01 | TFS00A110MM | LP1Y-ACN-010018-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0444 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACN-011008-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.602 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0445 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACN-011008-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50.14 |  | 100% | 10% | 100% |  |  | 100% | 50.14 | 0
K214-TFS-0446 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACN-011008-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0447 | TFS | 50.11.01 | TFS00A112MM | LP1Y-ACN-064102-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0448 | TFS | 50.11.01 | TFS00L101MM | LP1Y-ACN-064102-04 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0449 | TFS | 50.11.01 | TFS00L102MM | LP1Y-ACN-064102-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0450 | TFS | 50.11.01 | TFS00A111MM | LP1Y-ACN-177302-06 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0451 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACN-850013-02 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.383 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0452 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACN-850013-03 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.782 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0453 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACNDMSO-010008-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.6 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0454 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACNDMSO-010008-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0455 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACNDMSO-010008-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0456 | TFS | 50.11.01 | TFS00A106MM | LP1Y-ACNDMSO-010008-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0457 | TFS | 50.11.01 | TFS00A107MM | LP1Y-ACNDMSO-010008-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0458 | TFS | 50.11.01 | TFS00A108MM | LP1Y-ACNDMSO-010008-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.766 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0459 | TFS | 50.11.01 | TFS00A109MM | LP1Y-ACNDMSO-010008-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | -1 | 1 | 0 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0 | Not a DWHU
K214-TFS-0460 | TFS | 50.11.01 | TFS00H101MM | LP1Y-ACNDMSO-010032-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0461 | TFS | 50.11.01 | TFS00A104MM | LP1Y-ACNDMSO-010032-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0462 | TFS | 50.11.01 | TFS00A105MM | LP1Y-ACNDMSO-010032-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0463 | TFS | 50.11.01 | TFS00A110MM | LP1Y-ACNDMSO-010032-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 51.824 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1315 | TFS | 50.11.01 | TFS00A101MM | LP1Y-AI(100)-019009-02 |  |  |  |  | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0464 | TFS | 50.11.01 | TFS00A104MM | LP1Y-AI(100)-019009-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0465 | TFS | 50.11.01 | TFS00A105MM | LP1Y-AI(100)-019009-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0466 | TFS | 50.11.01 | TFS00A106MM | LP1Y-AI(100)-019009-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0467 | TFS | 50.11.01 | TFS00A107MM | LP1Y-AI(100)-019009-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0468 | TFS | 50.11.01 | TFS00A108MM | LP1Y-AI(100)-019009-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0469 | TFS | 50.11.01 | TFS00A109MM | LP1Y-AI(100)-019009-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0470 | TFS | 50.11.01 | TFS00A110MM | LP1Y-AI(100)-019009-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0471 | TFS | 50.11.01 | TFS00A111MM | LP1Y-AI(100)-019009-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0472 | TFS | 50.11.01 | TFS00A112MM | LP1Y-AI(100)-019009-12 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0473 | TFS | 50.11.01 | TFS00L101MM | LP1Y-AI(100)-019009-13 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0474 | TFS | 50.11.01 | TFS00B101MM | LP1Y-AI(100)-019009-14 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0475 | TFS | 50.11.01 | TFS00B102MM | LP1Y-AI(100)-019009-15 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0476 | TFS | 50.11.01 | TFS00L102MM | LP1Y-AI(100)-019009-20 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0477 | TFS | 50.11.01 | TFS00B108MM | LP1Y-AI(100)-034028-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0478 | TFS | 50.11.01 | TFS00B109MM | LP1Y-AI(100)-034028-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0479 | TFS | 50.11.01 | TFS00B103MM | LP1Y-AI(100)-034028-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0480 | TFS | 50.11.01 | TFS00B104MM | LP1Y-AI(100)-034028-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0481 | TFS | 50.11.01 | TFS00B105MM | LP1Y-AI(100)-034028-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0482 | TFS | 50.11.01 | TFS00B106MM | LP1Y-AI(100)-034028-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0483 | TFS | 50.11.01 | TFS00B107MM | LP1Y-AI(100)-034028-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0484 | TFS | 50.11.01 | TFS00F101MM | LP1Y-APL(100)-019001-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 45.844 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0485 | TFS | 50.11.01 | TFS00H101MM | LP1Y-APL(100)-019053-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.006 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0486 | TFS | 50.11.01 | TFS00A104MM | LP1Y-APL(100)-019053-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.96 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0487 | TFS | 50.11.01 | TFS00A105MM | LP1Y-APL(100)-019053-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.59 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0488 | TFS | 50.11.01 | TFS00A106MM | LP1Y-APL(100)-019053-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.59 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0489 | TFS | 50.11.01 | TFS00A107MM | LP1Y-APL(100)-019053-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.96 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0490 | TFS | 50.11.01 | TFS00A108MM | LP1Y-APL(100)-019053-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0491 | TFS | 50.11.01 | TFS00A102MM | LP1Y-APL(100)-019072-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0492 | TFS | 50.11.01 | TFS00A103MM | LP1Y-APL(100)-019072-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0493 | TFS | 50.11.01 | TFS00A105MM | LP1Y-APL(100)-019072-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0494 | TFS | 50.11.01 | TFS00A106MM | LP1Y-APL(100)-019072-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0495 | TFS | 50.11.01 | TFS00A107MM | LP1Y-APL(100)-019072-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0496 | TFS | 50.11.01 | TFS00A108MM | LP1Y-APL(100)-019072-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0497 | TFS | 50.11.01 | TFS00A109MM | LP1Y-APL(100)-019072-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 DWHU Connection | 1 | 1 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0498 | TFS | 50.11.01 | TFS00A102MM | LP1Y-BS-100104-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0499 | TFS | 50.11.01 | TFS00A103MM | LP1Y-BS-100104-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0500 | TFS | 50.11.01 | TFS00A104MM | LP1Y-BS-100104-07 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0501 | TFS | 50.11.01 | TFS00A105MM | LP1Y-BS-100104-08 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0502 | TFS | 50.11.01 | TFS00A106MM | LP1Y-BS-100104-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0503 | TFS | 50.11.01 | TFS00B101MM | LP1Y-BS-100104-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0504 | TFS | 50.11.01 | TFS00B102MM | LP1Y-BS-100104-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0505 | TFS | 50.11.01 | TFS00F101MM | LP1Y-CHWR-017024-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0506 | TFS | 50.11.01 | TFS00G101MM | LP1Y-CHWR-017059-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0507 | TFS | 50.11.01 | TFS00A103MM | LP1Y-CHWR-017059-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0508 | TFS | 50.11.01 | TFS00A104MM | LP1Y-CHWR-017059-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0509 | TFS | 50.11.01 | TFS00A105MM | LP1Y-CHWR-017059-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0510 | TFS | 50.11.01 | TFS00A106MM | LP1Y-CHWR-017059-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 130.284 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0511 | TFS | 50.11.01 | TFS00A107MM | LP1Y-CHWR-017059-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0512 | TFS | 50.11.01 | TFS00A108MM | LP1Y-CHWR-017070-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0513 | TFS | 50.11.01 | TFS00A109MM | LP1Y-CHWR-017070-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0514 | TFS | 50.11.01 | TFS00A110MM | LP1Y-CHWR-017070-04 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0515 | TFS | 50.11.01 | TFS00W105MM | LP1Y-CHWR-033041-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0516 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWR-033044-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0517 | TFS | 50.11.01 | TFS00S101MM | LP1Y-CHWR-033044-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.697 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0518 | TFS | 50.11.01 | TFS00B102MM | LP1Y-CHWR-033044-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0519 | TFS | 50.11.01 | TFS00B103MM | LP1Y-CHWR-033044-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0520 | TFS | 50.11.01 | TFS00B104MM | LP1Y-CHWR-033044-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0521 | TFS | 50.11.01 | TFS00B105MM | LP1Y-CHWR-033044-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0522 | TFS | 50.11.01 | TFS00B106MM | LP1Y-CHWR-033044-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0523 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWR-033044-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0524 | TFS | 50.11.01 | TFS00J101MM | LP1Y-CHWR-033047-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 59.233 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0525 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWR-033068-02 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0526 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWR-033068-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0527 | TFS | 50.11.01 | TFS00B109MM | LP1Y-CHWR-033068-04 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0528 | TFS | 50.11.01 | TFS00G101MM | LP1Y-CHWS-017022-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 63.454 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0529 | TFS | 50.11.01 | TFS00A103MM | LP1Y-CHWS-017022-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0530 | TFS | 50.11.01 | TFS00A104MM | LP1Y-CHWS-017022-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 63.524 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0531 | TFS | 50.11.01 | TFS00A105MM | LP1Y-CHWS-017022-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0532 | TFS | 50.11.01 | TFS00A106MM | LP1Y-CHWS-017022-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0533 | TFS | 50.11.01 | TFS00A107MM | LP1Y-CHWS-017022-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.142 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0534 | TFS | 50.11.01 | TFS00A108MM | LP1Y-CHWS-017069-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0535 | TFS | 50.11.01 | TFS00A109MM | LP1Y-CHWS-017069-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0536 | TFS | 50.11.01 | TFS00A110MM | LP1Y-CHWS-017069-04 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.792 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0537 | TFS | 50.11.01 | TFS00F101MM | LP1Y-CHWS-017111-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0538 | TFS | 50.11.01 | TFS00J101MM | LP1Y-CHWS-033023-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 59.233 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0539 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWS-033032-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0540 | TFS | 50.11.01 | TFS00S101MM | LP1Y-CHWS-033032-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 65.697 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0541 | TFS | 50.11.01 | TFS00B102MM | LP1Y-CHWS-033032-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0542 | TFS | 50.11.01 | TFS00B103MM | LP1Y-CHWS-033032-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0543 | TFS | 50.11.01 | TFS00B104MM | LP1Y-CHWS-033032-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0544 | TFS | 50.11.01 | TFS00B105MM | LP1Y-CHWS-033032-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0545 | TFS | 50.11.01 | TFS00B106MM | LP1Y-CHWS-033032-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0546 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWS-033032-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 67.596 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0547 | TFS | 50.11.01 | TFS00W105MM | LP1Y-CHWS-033038-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0548 | TFS | 50.11.01 | TFS00B107MM | LP1Y-CHWS-033067-02 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0549 | TFS | 50.11.01 | TFS00B108MM | LP1Y-CHWS-033067-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0550 | TFS | 50.11.01 | TFS00B109MM | LP1Y-CHWS-033067-04 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 79.427 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0551 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DCM-010017-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0552 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DCM-010017-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.75 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0553 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DCM-010017-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0554 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DCM-010017-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0555 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DCM-010017-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0556 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DCM-010017-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0557 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DCM-010017-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0558 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DCM-010017-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0559 | TFS | 50.11.01 | TFS00A111MM | LP1Y-DCM-177202-06 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0560 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMF-010036-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0561 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMF-010036-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0562 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMF-010036-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0563 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMF-065102-02 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0564 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DMF-065102-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 54.708 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0565 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DMF-065102-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 54.692 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0566 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMF-065102-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 54.708 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0567 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DMF-065102-06 (SUPERSEDED) | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | -1 | 0 | #DIV/0! | EA | 0 |  | 0 | 0 |  | 0% | 0% | 0% |  |  | #DIV/0! | 0 | 0 | Drawing Superseded
K214-TFS-1371 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMF-062302-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-0568 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DMF-062302-06 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0569 | TFS | 50.11.01 | TFS00A111MM | LP1Y-DMF-065102-08 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0570 | TFS | 50.11.01 | TFS00A112MM | LP1Y-DMF-065102-09 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.354 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0571 | TFS | 50.11.01 | TFS00L101MM | LP1Y-DMF-065102-10 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.602 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0572 | TFS | 50.11.01 | TFS00L102MM | LP1Y-DMF-065102-11 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.602 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0573 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMSO-010012-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0574 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMSO-010012-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.75 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0575 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMSO-010012-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0576 | TFS | 50.11.01 | TFS00A107MM | LP1Y-DMSO-010012-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1372 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMSO-010012-07 |  |  |  |  | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.92 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-0577 | TFS | 50.11.01 | TFS00A110MM | LP1Y-DMSO-010012-08 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0578 | TFS | 50.11.01 | TFS00H101MM | LP1Y-DMSO-010033-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.88 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0579 | TFS | 50.11.01 | TFS00A104MM | LP1Y-DMSO-010033-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0580 | TFS | 50.11.01 | TFS00A105MM | LP1Y-DMSO-010033-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0581 | TFS | 50.11.01 | TFS00A106MM | LP1Y-DMSO-010033-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0582 | TFS | 50.11.01 | TFS00A108MM | LP1Y-DMSO-010033-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0583 | TFS | 50.11.01 | TFS00A109MM | LP1Y-DMSO-010033-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 51.84 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0584 | TFS | 50.11.01 | TFS00L102MM | LP1Y-H2SO4-013011-01 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0585 | TFS | 50.11.01 | TFS00L101MM | LP1Y-H2SO4-013011-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0586 | TFS | 50.11.01 | TFS00A112MM | LP1Y-H2SO4-013011-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0587 | TFS | 50.11.01 | TFS00A111MM | LP1Y-H2SO4-013011-04 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0588 | TFS | 50.11.01 | TFS00A110MM | LP1Y-H2SO4-013011-05 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0589 | TFS | 50.11.01 | TFS00A109MM | LP1Y-H2SO4-013011-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0590 | TFS | 50.11.01 | TFS00A108MM | LP1Y-H2SO4-013011-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0591 | TFS | 50.11.01 | TFS00A107MM | LP1Y-H2SO4-013011-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0592 | TFS | 50.11.01 | TFS00A106MM | LP1Y-H2SO4-013011-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0593 | TFS | 50.11.01 | TFS00A105MM | LP1Y-H2SO4-013011-10 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0594 | TFS | 50.11.01 | TFS00A104MM | LP1Y-H2SO4-013011-11 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0595 | TFS | 50.11.01 | TFS00A103MM | LP1Y-H2SO4-013011-12 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0596 | TFS | 50.11.01 | TFS00A102MM | LP1Y-H2SO4-013011-13 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0597 | TFS | 50.11.01 | TFS00B101MM | LP1Y-H2SO4-013011-15 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0598 | TFS | 50.11.01 | TFS00B102MM | LP1Y-H2SO4-013011-16 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0599 | TFS | 50.11.01 | TFS00B108MM | LP1Y-H2SO4-032003-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0600 | TFS | 50.11.01 | TFS00A102MM | LP1Y-H2SO4-032003-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0601 | TFS | 50.11.01 | TFS00A103MM | LP1Y-H2SO4-032003-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0602 | TFS | 50.11.01 | TFS00A104MM | LP1Y-H2SO4-032003-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0603 | TFS | 50.11.01 | TFS00A105MM | LP1Y-H2SO4-032003-06 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0604 | TFS | 50.11.01 | TFS00A106MM | LP1Y-H2SO4-032003-07 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.424 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0605 | TFS | 50.11.01 | TFS00B101MM | LP1Y-H2SO4-032003-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0606 | TFS | 50.11.01 | TFS00B102MM | LP1Y-H2SO4-032003-12 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 56.338 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0607 | TFS | 50.11.01 | TFS00B104MM | LP1Y-H2SO4-032003-14 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0608 | TFS | 50.11.01 | TFS00B105MM | LP1Y-H2SO4-032003-15 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0609 | TFS | 50.11.01 | TFS00B106MM | LP1Y-H2SO4-032003-16 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0610 | TFS | 50.11.01 | TFS00B107MM | LP1Y-H2SO4-032003-17 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0611 | TFS | 50.11.01 | TFS00B109MM | LP1Y-H2SO4-032003-18 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0612 | TFS | 50.11.01 | TFS00J101MM | LP1Y-H2SO4-032018-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 21.345 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0613 | TFS | 50.11.01 | TFS00H101MM | LP1Y-IPA-010016-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0614 | TFS | 50.11.01 | TFS00A104MM | LP1Y-IPA-010016-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 51.7 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0615 | TFS | 50.11.01 | TFS00A105MM | LP1Y-IPA-010016-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0616 | TFS | 50.11.01 | TFS00A106MM | LP1Y-IPA-010016-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0617 | TFS | 50.11.01 | TFS00A107MM | LP1Y-IPA-010016-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0618 | TFS | 50.11.01 | TFS00A108MM | LP1Y-IPA-010016-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0619 | TFS | 50.11.01 | TFS00A109MM | LP1Y-IPA-010016-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.851 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0620 | TFS | 50.11.01 | TFS00A110MM | LP1Y-IPA-010016-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.851 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0621 | TFS | 50.11.01 | TFS00A111MM | LP1Y-IPA-177102-07 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0622 | TFS | 50.11.01 | TFS00H101MM | LP1Y-MTBE-010019-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0623 | TFS | 50.11.01 | TFS00A104MM | LP1Y-MTBE-010019-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0624 | TFS | 50.11.01 | TFS00A105MM | LP1Y-MTBE-010019-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0625 | TFS | 50.11.01 | TFS00A106MM | LP1Y-MTBE-010019-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0626 | TFS | 50.11.01 | TFS00A107MM | LP1Y-MTBE-010019-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0627 | TFS | 50.11.01 | TFS00A108MM | LP1Y-MTBE-010019-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0628 | TFS | 50.11.01 | TFS00A109MM | LP1Y-MTBE-010019-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0629 | TFS | 50.11.01 | TFS00A110MM | LP1Y-MTBE-010019-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0630 | TFS | 50.11.01 | TFS00A111MM | LP1Y-MTBE-010019-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0631 | TFS | 50.11.01 | TFS00A112MM | LP1Y-MTBE-063102-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0632 | TFS | 50.11.01 | TFS00L101MM | LP1Y-MTBE-063102-04 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0633 | TFS | 50.11.01 | TFS00L102MM | LP1Y-MTBE-063102-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0634 | TFS | 50.11.01 | TFS00A102MM | LP1Y-N2(100)-018010-02 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0635 | TFS | 50.11.01 | TFS00A103MM | LP1Y-N2(100)-018010-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0636 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2(100)-018010-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0637 | TFS | 50.11.01 | TFS00A105MM | LP1Y-N2(100)-018010-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0638 | TFS | 50.11.01 | TFS00A106MM | LP1Y-N2(100)-018010-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0639 | TFS | 50.11.01 | TFS00A107MM | LP1Y-N2(100)-018010-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 62 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0640 | TFS | 50.11.01 | TFS00A108MM | LP1Y-N2(100)-018010-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0641 | TFS | 50.11.01 | TFS00A109MM | LP1Y-N2(100)-018010-09 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 DWHU Connection | 1 | 1 | 2 | 0 | EA | 0 |  | 0 | 62.192 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0642 | TFS | 50.11.01 | TFS00A110MM | LP1Y-N2(100)-018010-10 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0643 | TFS | 50.11.01 | TFS00A111MM | LP1Y-N2(100)-018010-11 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0644 | TFS | 50.11.01 | TFS00B102MM | LP1Y-N2(100)-018010-12 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.536 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0645 | TFS | 50.11.01 | TFS00A112MM | LP1Y-N2(100)-018010-13 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.073 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0646 | TFS | 50.11.01 | TFS00B101MM | LP1Y-N2(100)-018010-18 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.768 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0647 | TFS | 50.11.01 | TFS00L101MM | LP1Y-N2(100)-018058-03 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0648 | TFS | 50.11.01 | TFS00L102MM | LP1Y-N2(100)-018058-04 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.329 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0649 | TFS | 50.11.01 | TFS00H101MM | LP1Y-N2(100)-018075-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.006 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0650 | TFS | 50.11.01 | TFS00A103MM | LP1Y-N2(100)-018075-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0651 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2(100)-018075-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 84.426 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0652 | TFS | 50.11.01 | TFS00A105MM | LP1Y-N2(100)-018075-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0653 | TFS | 50.11.01 | TFS00A106MM | LP1Y-N2(100)-018075-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0654 | TFS | 50.11.01 | TFS00A107MM | LP1Y-N2(100)-018075-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0655 | TFS | 50.11.01 | TFS00A108MM | LP1Y-N2(100)-018075-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0656 | TFS | 50.11.01 | TFS00B101MM | LP1Y-N2(100)-018075-08 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0657 | TFS | 50.11.01 | TFS00B102MM | LP1Y-N2(100)-018075-09 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0658 | TFS | 50.11.01 | TFS00B103MM | LP1Y-N2(100)-018075-10 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.138 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0659 | TFS | 50.11.01 | TFS00B104MM | LP1Y-N2(100)-018075-11 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0660 | TFS | 50.11.01 | TFS00B105MM | LP1Y-N2(100)-018075-12 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0661 | TFS | 50.11.01 | TFS00B106MM | LP1Y-N2(100)-018075-13 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0662 | TFS | 50.11.01 | TFS00B107MM | LP1Y-N2(100)-018075-14 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0663 | TFS | 50.11.01 | TFS00A102MM | LP1Y-N2(100)-018075-15 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.165 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0664 | TFS | 50.11.01 | TFS00B108MM | LP1Y-N2(100)-018075-17 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0665 | TFS | 50.11.01 | TFS00B109MM | LP1Y-N2(100)-018075-18 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.143 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0666 | TFS | 50.11.01 | TFS00B108MM | LP1Y-N2(100)-034025-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0667 | TFS | 50.11.01 | TFS00B109MM | LP1Y-N2(100)-034025-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0668 | TFS | 50.11.01 | TFS00B103MM | LP1Y-N2(100)-034025-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0669 | TFS | 50.11.01 | TFS00B104MM | LP1Y-N2(100)-034025-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0670 | TFS | 50.11.01 | TFS00B105MM | LP1Y-N2(100)-034025-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0671 | TFS | 50.11.01 | TFS00B106MM | LP1Y-N2(100)-034025-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0672 | TFS | 50.11.01 | TFS00B107MM | LP1Y-N2(100)-034025-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0673 | TFS | 50.11.01 | TFS00J101MM | LP1Y-N2(100)-034029-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.94 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0674 | TFS | 50.11.01 | TFS00S101MM | LP1Y-N2(100)-034037-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 20.455 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0675 | TFS | 50.11.01 | TFS00W105MM | LP1Y-N2(100)-034037-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.766 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0676 | TFS | 50.11.01 | TFS00A104MM | LP1Y-N2-180029-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0677 | TFS | 50.11.01 | TFS00L101MM | LP1Y-NAOH50-013012-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0678 | TFS | 50.11.01 | TFS00A112MM | LP1Y-NAOH50-013012-03 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0679 | TFS | 50.11.01 | TFS00A111MM | LP1Y-NAOH50-013012-04 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0680 | TFS | 50.11.01 | TFS00A110MM | LP1Y-NAOH50-013012-05 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0681 | TFS | 50.11.01 | TFS00A109MM | LP1Y-NAOH50-013012-06 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0682 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-013012-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0683 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NAOH50-013012-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0684 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NAOH50-013012-09 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0685 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NAOH50-013012-10 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0686 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NAOH50-013012-11 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0687 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NAOH50-013012-12 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0688 | TFS | 50.11.01 | TFS00A102MM | LP1Y-NAOH50-013012-13 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 34.017 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0689 | TFS | 50.11.01 | TFS00B101MM | LP1Y-NAOH50-013012-15 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0690 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NAOH50-013012-16 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.218 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0691 | TFS | 50.11.01 | TFS00G101MM | LP1Y-NAOH50-016011-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0692 | TFS | 50.11.01 | TFS00A109MM | LP1Y-NAOH50-016020-01 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0693 | TFS | 50.11.01 | TFS00B108MM | LP1Y-NAOH50-032002-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0694 | TFS | 50.11.01 | TFS00A102MM | LP1Y-NAOH50-032002-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.424 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0695 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NAOH50-032002-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0696 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NAOH50-032002-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 2 | EA | 0 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 100% | 50 | 0
K214-TFS-0697 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NAOH50-032002-06 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0698 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NAOH50-032002-07 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0699 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NAOH50-032002-08 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0700 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-032002-09 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1373 | TFS | 50.11.01 | TFS00A108MM | LP1Y-NAOH50-032002-10 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 1 |  | 0 | 27.354 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-0701 | TFS | 50.11.01 | TFS00B109MM | LP1Y-NAOH50-032002-11 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0702 | TFS | 50.11.01 | TFS00B101MM | LP1Y-NAOH50-032002-12 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0703 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NAOH50-032002-13 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0704 | TFS | 50.11.01 | TFS00B103MM | LP1Y-NAOH50-032002-14 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0705 | TFS | 50.11.01 | TFS00B104MM | LP1Y-NAOH50-032002-15 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0706 | TFS | 50.11.01 | TFS00B105MM | LP1Y-NAOH50-032002-16 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0707 | TFS | 50.11.01 | TFS00B106MM | LP1Y-NAOH50-032002-17 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0708 | TFS | 50.11.01 | TFS00B107MM | LP1Y-NAOH50-032002-18 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.169 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0709 | TFS | 50.11.01 | TFS00J101MM | LP1Y-NAOH50-032017-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 28.545 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0710 | TFS | 50.11.01 | TFS00G101MM | LP1Y-NG-018007-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.777 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0711 | TFS | 50.11.01 | TFS00A103MM | LP1Y-NG-018007-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0712 | TFS | 50.11.01 | TFS00A104MM | LP1Y-NG-018007-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0713 | TFS | 50.11.01 | TFS00A105MM | LP1Y-NG-018007-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.405 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0714 | TFS | 50.11.01 | TFS00A106MM | LP1Y-NG-018007-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0715 | TFS | 50.11.01 | TFS00A107MM | LP1Y-NG-018007-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0716 | TFS | 50.11.01 | TFS00F101MM | LP1Y-NG-018012-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.777 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0717 | TFS | 50.11.01 | TFS00J101MM | LP1Y-NG-034031-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 10.207 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0718 | TFS | 50.11.01 | TFS00B108MM | LP1Y-NG-034034-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0719 | TFS | 50.11.01 | TFS00S101MM | LP1Y-NG-034034-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.409 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0720 | TFS | 50.11.01 | TFS00B102MM | LP1Y-NG-034034-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0721 | TFS | 50.11.01 | TFS00B103MM | LP1Y-NG-034034-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0722 | TFS | 50.11.01 | TFS00B104MM | LP1Y-NG-034034-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0723 | TFS | 50.11.01 | TFS00B105MM | LP1Y-NG-034034-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0724 | TFS | 50.11.01 | TFS00B106MM | LP1Y-NG-034034-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0725 | TFS | 50.11.01 | TFS00B107MM | LP1Y-NG-034034-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.303 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0726 | TFS | 50.11.01 | TFS00B109MM | LP1Y-NG-034034-10 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.081 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0727 | TFS | 50.11.01 | TFS00W105MM | LP1Y-NG-034039-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.365 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0728 | TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.542 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0729 | TFS | 50.11.01 | TFS00G101MM | LP1Y-PSC-017031-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.071 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0730 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PSC-017031-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.228 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0731 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PSC-017031-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.702 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0732 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PSC-017031-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.706 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0733 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PSC-017031-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.075 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0734 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PSC-017031-11 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0735 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PSC-017031-13 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0736 | TFS | 50.11.01 | TFS00W105MM | LP1Y-PSC-033040-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0737 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PSC-033042-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0738 | TFS | 50.11.01 | TFS00S101MM | LP1Y-PSC-033042-02 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 16.075 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0739 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PSC-033042-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0740 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PSC-033042-05 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0741 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PSC-033042-06 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0742 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PSC-033042-07 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0743 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PSC-033042-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0744 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PSC-033042-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0745 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PSC-033042-10 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0746 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PSC-033049-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 12.702 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0747 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PV-013001-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 41.875 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0748 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PV-013001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.066 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0749 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PV-013001-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.29 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0750 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PV-013001-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.29 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0751 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PV-013001-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.449 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0752 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PV-013001-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.877 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0753 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PV-013001-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.877 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0754 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PV-013001-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.099 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0755 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PV-300064-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.194 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0756 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PV-300064-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.106 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0757 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PV-300065-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.154 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0758 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PVP-013004-02 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0759 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PVP-013004-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0760 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PVP-013004-04 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection (VOIDED) | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0761 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PVP-013004-05 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection *DWG VOIDED* | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.85 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0762 | TFS | 50.11.01 | TFS00L102MM | LP1Y-PVP-013022-05 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 103.4 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0763 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PVP-102109-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.098 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0764 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PVP-110218-02 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0765 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PVP-112109-01 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0766 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PVP-300308-04 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 6 | 0 | 6 | 0 | EA | 0 |  | 0 | 126.384 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0767 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PVP-300308-06 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 42.128 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0768 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014002-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0769 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014002-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0770 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014003-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0771 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014003-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0772 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PWP-014003-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0773 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PWP-014003-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0774 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PWP-014003-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0775 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PWP-014003-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0776 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PWP-014003-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0777 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-014007-02 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0778 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-014007-03 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0779 | TFS | 50.11.01 | TFS00A106MM | LP1Y-PWP-014007-04 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 89.438 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0780 | TFS | 50.11.01 | TFS00A107MM | LP1Y-PWP-014007-05 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 89.438 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0781 | TFS | 50.11.01 | TFS00A108MM | LP1Y-PWP-014007-06 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0782 | TFS | 50.11.01 | TFS00A109MM | LP1Y-PWP-014007-07 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0783 | TFS | 50.11.01 | TFS00A110MM | LP1Y-PWP-014007-08 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0784 | TFS | 50.11.01 | TFS00A111MM | LP1Y-PWP-014007-09 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0785 | TFS | 50.11.01 | TFS00A112MM | LP1Y-PWP-014007-10 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 44.719 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0786 | TFS | 50.11.01 | TFS00L101MM | LP1Y-PWP-014007-11 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.493 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0787 | TFS | 50.11.01 | TFS00L102MM | LP1Y-PWP-014007-12 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.493 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0788 | TFS | 50.11.01 | TFS00G101MM | LP1Y-PWP-014009-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0789 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PWP-014009-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0790 | TFS | 50.11.01 | TFS00S101MM | LP1Y-PWP-036002-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.182 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0791 | TFS | 50.11.01 | TFS00W105MM | LP1Y-PWP-036003-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.813 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0792 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PWP-036047-01 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0793 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PWP-036047-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0794 | TFS | 50.11.01 | TFS00A102MM | LP1Y-PWP-036047-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0795 | TFS | 50.11.01 | TFS00A103MM | LP1Y-PWP-036047-06 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0796 | TFS | 50.11.01 | TFS00B101MM | LP1Y-PWP-036047-07 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0797 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PWP-036047-08 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0798 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PWP-036047-10 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0799 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PWP-036047-11 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0800 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PWP-036047-12 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0801 | TFS | 50.11.01 | TFS00B107MM | LP1Y-PWP-036047-13 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0802 | TFS | 50.11.01 | TFS00B108MM | LP1Y-PWP-036049-02 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0803 | TFS | 50.11.01 | TFS00A102MM | LP1Y-PWP-036049-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0804 | TFS | 50.11.01 | TFS00J101MM | LP1Y-PWP-036049-06 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 20.501 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0805 | TFS | 50.11.01 | TFS00B101MM | LP1Y-PWP-036049-07 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0806 | TFS | 50.11.01 | TFS00B102MM | LP1Y-PWP-036049-08 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0807 | TFS | 50.11.01 | TFS00B103MM | LP1Y-PWP-036049-09 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0808 | TFS | 50.11.01 | TFS00B104MM | LP1Y-PWP-036049-10 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0809 | TFS | 50.11.01 | TFS00B105MM | LP1Y-PWP-036049-11 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0810 | TFS | 50.11.01 | TFS00B106MM | LP1Y-PWP-036049-12 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0811 | TFS | 50.11.01 | TFS00B109MM | LP1Y-PWP-036049-14 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0812 | TFS | 50.11.01 | TFS00A104MM | LP1Y-PWP-850051-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0813 | TFS | 50.11.01 | TFS00A105MM | LP1Y-PWP-850051-08 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0814 | TFS | 50.11.01 | TFS00F101MM | LP1Y-S(130)-018051-01 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 60.077 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0815 | TFS | 50.11.01 | TFS00G101MM | LP1Y-S(130)-018062-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 29.852 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0816 | TFS | 50.11.01 | TFS00A103MM | LP1Y-S(130)-018062-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 29.011 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0817 | TFS | 50.11.01 | TFS00A102MM | LP1Y-S(130)-018062-05 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.938 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0818 | TFS | 50.11.01 | TFS00A104MM | LP1Y-S(130)-018062-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 58.15 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0819 | TFS | 50.11.01 | TFS00A105MM | LP1Y-S(130)-018062-09 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0820 | TFS | 50.11.01 | TFS00A106MM | LP1Y-S(130)-018062-12 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0821 | TFS | 50.11.01 | TFS00A107MM | LP1Y-S(130)-018062-13 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0822 | TFS | 50.11.01 | TFS00A108MM | LP1Y-S(130)-018062-15 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0823 | TFS | 50.11.01 | TFS00A109MM | LP1Y-S(130)-018062-18 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0824 | TFS | 50.11.01 | TFS00A110MM | LP1Y-S(130)-018062-19 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0825 | TFS | 50.11.01 | TFS00A111MM | LP1Y-S(130)-018062-20 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 58.389 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1316 | TFS | 50.11.01 | TFS00A102MM | LP1Y-S(130)-018079-01 |  |  |  |  | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.938 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0826 | TFS | 50.11.01 | TFS00B101MM | LP1Y-S(130)-018079-03 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0827 | TFS | 50.11.01 | TFS00B102MM | LP1Y-S(130)-018079-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0828 | TFS | 50.11.01 | TFS00A112MM | LP1Y-S(130)-018091-02 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0829 | TFS | 50.11.01 | TFS00L101MM | LP1Y-S(130)-018091-03 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0830 | TFS | 50.11.01 | TFS00L102MM | LP1Y-S(130)-018091-04 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.657 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0831 | TFS | 50.11.01 | TFS00J101MM | LP1Y-S(130)-034030-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 29.011 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0832 | TFS | 50.11.01 | TFS00B109MM | LP1Y-S(130)-034035-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0833 | TFS | 50.11.01 | TFS00B102MM | LP1Y-S(130)-034035-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0834 | TFS | 50.11.01 | TFS00B103MM | LP1Y-S(130)-034035-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0835 | TFS | 50.11.01 | TFS00B104MM | LP1Y-S(130)-034035-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0836 | TFS | 50.11.01 | TFS00B105MM | LP1Y-S(130)-034035-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0837 | TFS | 50.11.01 | TFS00B106MM | LP1Y-S(130)-034035-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0838 | TFS | 50.11.01 | TFS00B107MM | LP1Y-S(130)-034035-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0839 | TFS | 50.11.01 | TFS00B108MM | LP1Y-S(130)-034035-18 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.463 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0840 | TFS | 50.11.01 | TFS00S101MM | LP1Y-S(130)-034035-20 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 43.729 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0841 | TFS | 50.11.01 | TFS00W105MM | LP1Y-S(130)-034038-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0842 | TFS | 50.11.01 | TFS00B108MM | LP1Y-S(130)-034077-04 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 9.358 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0843 | TFS | 50.11.01 | TFS00B103MM | LP1Y-S(130)-034109-01 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0844 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SOLV-300404-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 9 | 0 | 9 | 0 | EA | 0 |  | 0 | 253.521 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0845 | TFS | 50.11.01 | TFS00B109MM | LP1Y-SOLV-300404-06 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 10 | 0 | 10 | 0 | EA | 0 |  | 0 | 255.857 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0846 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SOLV-300404-08 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 10 | 0 | 10 | 0 | EA | 0 |  | 0 | 285.45 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0847 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SOLV-300404-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 112.676 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0848 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SOLV-322202-06 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.626 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0849 | TFS | 50.11.01 | TFS00G101MM | LP1Y-SRACNP-011001-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.16 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0850 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SRACNP-011001-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0851 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SRACNP-011001-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 51.82 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0852 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SRACNP-011001-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0853 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SRACNP-011001-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0854 | TFS | 50.11.01 | TFS00A107MM | LP1Y-SRACNP-011001-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.92 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0855 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SRACNP-011001-08 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0856 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SRACNP-108104-03 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0857 | TFS | 50.11.01 | TFS00B101MM | LP1Y-STORMP-015002-13 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0858 | TFS | 50.11.01 | TFS00A102MM | LP1Y-STORMP-015002-15 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0859 | TFS | 50.11.01 | TFS00A104MM | LP1Y-STORMP-015002-17 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0860 | TFS | 50.11.01 | TFS00A105MM | LP1Y-STORMP-015002-18 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0861 | TFS | 50.11.01 | TFS00A106MM | LP1Y-STORMP-015002-19 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0862 | TFS | 50.11.01 | TFS00A107MM | LP1Y-STORMP-015002-20 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0863 | TFS | 50.11.01 | TFS00A108MM | LP1Y-STORMP-015002-21 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0864 | TFS | 50.11.01 | TFS00A109MM | LP1Y-STORMP-015002-22 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0865 | TFS | 50.11.01 | TFS00A110MM | LP1Y-STORMP-015002-23 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0866 | TFS | 50.11.01 | TFS00A111MM | LP1Y-STORMP-015002-24 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0867 | TFS | 50.11.01 | TFS00B108MM | LP1Y-STORMP-037007-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0868 | TFS | 50.11.01 | TFS00B109MM | LP1Y-STORMP-037007-05 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0869 | TFS | 50.11.01 | TFS00B102MM | LP1Y-STORMP-037007-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0870 | TFS | 50.11.01 | TFS00B103MM | LP1Y-STORMP-037007-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0871 | TFS | 50.11.01 | TFS00B107MM | LP1Y-STORMP-037007-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0872 | TFS | 50.11.01 | TFS00B104MM | LP1Y-STORMP-037007-14 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0873 | TFS | 50.11.01 | TFS00B105MM | LP1Y-STORMP-037007-15 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0874 | TFS | 50.11.01 | TFS00B106MM | LP1Y-STORMP-037007-16 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0875 | TFS | 50.11.01 | TFS00J101MM | LP1Y-STORMP-037009-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 20.501 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0876 | TFS | 50.11.01 | TFS00A103MM | LP1Y-STORMP-165334-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.105 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0877 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SWP-014001-03 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0878 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014001-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0879 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014001-05 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 40.855 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0880 | TFS | 50.11.01 | TFS00A111MM | LP1Y-SWP-014004-01 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0881 | TFS | 50.11.01 | TFS00A110MM | LP1Y-SWP-014004-02 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.506 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0882 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014004-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0883 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014004-08 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.51 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0884 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-014005-07 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0885 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-014005-08 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 37.51 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0886 | TFS | 50.11.01 | TFS00G101MM | LP1Y-SWP-014010-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 41.042 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0887 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-014010-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.096 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0888 | TFS | 50.11.01 | TFS00H101MM | LP1Y-SWP-014015-02 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.813 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0889 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SWP-036045-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0890 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036045-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0891 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036045-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0892 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036045-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0893 | TFS | 50.11.01 | TFS00B102MM | LP1Y-SWP-036045-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0894 | TFS | 50.11.01 | TFS00B104MM | LP1Y-SWP-036045-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0895 | TFS | 50.11.01 | TFS00B106MM | LP1Y-SWP-036045-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0896 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SWP-036045-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0897 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036046-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0898 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036046-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0899 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036046-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0900 | TFS | 50.11.01 | TFS00B105MM | LP1Y-SWP-036046-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0901 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-036048-03 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 32.151 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0902 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-036048-04 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 42.24 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0903 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SWP-036048-05 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 46.124 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0904 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-036048-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 33.084 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0905 | TFS | 50.11.01 | TFS00B102MM | LP1Y-SWP-036048-07 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0906 | TFS | 50.11.01 | TFS00B103MM | LP1Y-SWP-036048-08 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0907 | TFS | 50.11.01 | TFS00B104MM | LP1Y-SWP-036048-09 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0908 | TFS | 50.11.01 | TFS00B105MM | LP1Y-SWP-036048-10 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0909 | TFS | 50.11.01 | TFS00B106MM | LP1Y-SWP-036048-11 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0910 | TFS | 50.11.01 | TFS00B107MM | LP1Y-SWP-036048-12 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0911 | TFS | 50.11.01 | TFS00B109MM | LP1Y-SWP-036048-14 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 59.817 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0912 | TFS | 50.11.01 | TFS00B108MM | LP1Y-SWP-036048-15 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0913 | TFS | 50.11.01 | TFS00J101MM | LP1Y-SWP-036052-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 41.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0914 | TFS | 50.11.01 | TFS00B101MM | LP1Y-SWP-100404-02 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0915 | TFS | 50.11.01 | TFS00A102MM | LP1Y-SWP-100404-04 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.912 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0916 | TFS | 50.11.01 | TFS00A103MM | LP1Y-SWP-100404-05 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0917 | TFS | 50.11.01 | TFS00A109MM | LP1Y-SWP-109022-01 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0918 | TFS | 50.11.01 | TFS00A108MM | LP1Y-SWP-109022-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0919 | TFS | 50.11.01 | TFS00A107MM | LP1Y-SWP-109022-03 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 3 | 0 | 3 | 0 | EA | 0 |  | 0 | 56.259 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0920 | TFS | 50.11.01 | TFS00A106MM | LP1Y-SWP-109022-04 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 4 | 0 | 4 | 0 | EA | 0 |  | 0 | 75.012 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0921 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-109022-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 18.753 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0922 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-109022-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0923 | TFS | 50.11.01 | TFS00A105MM | LP1Y-SWP-850004-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0924 | TFS | 50.11.01 | TFS00A104MM | LP1Y-SWP-850004-06 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.752 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0925 | TFS | 50.11.01 | TFS00H101MM | LP1Y-TFA-010004-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.471 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0926 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TFA-010004-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.82 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0927 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TFA-010004-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0928 | TFS | 50.11.01 | TFS00H101MM | LP1Y-TFA-010031-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.471 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0929 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TFA-010031-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0930 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TFA-010031-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.408 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0931 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TFA-010031-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0932 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TFA-010031-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0933 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TFA-010031-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0934 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TFA-010031-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 38.816 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1374 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TFA-010004-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 |  | EA | 0 |  | 0 | 19 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-0935 | TFS | 50.11.01 | TFS00F101MM | LP1Y-TWRP-017021-01 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 118.822 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0936 | TFS | 50.11.01 | TFS00G101MM | LP1Y-TWRP-017063-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0937 | TFS | 50.11.01 | TFS00A103MM | LP1Y-TWRP-017063-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0938 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TWRP-017063-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0939 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TWRP-017063-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 DWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 243.851 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0940 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TWRP-017063-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 121.718 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0941 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWRP-017063-10 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0942 | TFS | 50.11.01 | TFS00B108MM | LP1Y-TWRP-033045-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0943 | TFS | 50.11.01 | TFS00B109MM | LP1Y-TWRP-033045-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.833 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0944 | TFS | 50.11.01 | TFS00B106MM | LP1Y-TWRP-033045-08 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0945 | TFS | 50.11.01 | TFS00B107MM | LP1Y-TWRP-033045-09 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0946 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TWRP-109313-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0947 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TWRP-109313-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0948 | TFS | 50.11.01 | TFS00F101MM | LP1Y-TWSP-017016-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 118.822 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0949 | TFS | 50.11.01 | TFS00G101MM | LP1Y-TWSP-017017-01 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0950 | TFS | 50.11.01 | TFS00A103MM | LP1Y-TWSP-017017-03 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102 TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 77.316 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0951 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWSP-017017-04 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 77 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0952 | TFS | 50.11.01 | TFS00A105MM | LP1Y-TWSP-017017-05 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0953 | TFS | 50.11.01 | TFS00A106MM | LP1Y-TWSP-017017-06 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 121.925 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0954 | TFS | 50.11.01 | TFS00A107MM | LP1Y-TWSP-017017-07 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 121.718 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0955 | TFS | 50.11.01 | TFS00A108MM | LP1Y-TWSP-017020-02 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0956 | TFS | 50.11.01 | TFS00A109MM | LP1Y-TWSP-017020-03 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.44 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0957 | TFS | 50.11.01 | TFS00J101MM | LP1Y-TWSP-033021-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 46.26 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0958 | TFS | 50.11.01 | TFS00B108MM | LP1Y-TWSP-033034-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0959 | TFS | 50.11.01 | TFS00B109MM | LP1Y-TWSP-033034-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.833 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0960 | TFS | 50.11.01 | TFS00B106MM | LP1Y-TWSP-033034-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 90.286 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0961 | TFS | 50.11.01 | TFS00B107MM | LP1Y-TWSP-033034-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 75.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0962 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WFO-017007-70 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0963 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WFO-017007-71 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0964 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WI-037001-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 39.878 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0965 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WI-037001-04 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.376 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0966 | TFS | 50.11.01 | TFS00A102MM | LP1Y-WNP-017007-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.149 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0967 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WNP-017007-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0968 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WNP-017007-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0969 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WNP-017007-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0970 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WNP-017007-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0971 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WNP-017007-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0972 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WNP-017007-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0973 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WFO-017007-50 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0974 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WNP-017007-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0975 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WNP-017007-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.061 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0976 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WNP-017007-16 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0977 | TFS | 50.11.01 | TFS00A101MM | LP1Y-WFO-017060-11 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.21 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0978 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WNP-017007-40 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.21 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0979 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WNP-033018-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0980 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WNP-033018-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0981 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WNP-033018-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0982 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WNP-033018-06 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0983 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WNP-033018-07 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0984 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WNP-033018-08 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.086 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0985 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WNP-033056-03 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.08 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0986 | TFS | 50.11.01 | TFS00G101MM | LP1Y-WPC-017015-02 | TFS00G101MMPP | K214 | IP-TFS00G101MMPP-K214-150 | 50.TG101-M.F | TA102 TO TG101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0987 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WPC-017056-02 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0988 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WPC-017056-03 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.148 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0989 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WPC-017061-04 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.085 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0990 | TFS | 50.11.01 | TFS00A102MM | LP1Y-WPC-017062-01 | TFS00A102MMPP | K214 | IP-TFS00A102MMPP-K214-150 | 50.TA102-M.F | TA101 TO TA102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.079 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0991 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WPC-017062-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0992 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WPC-017062-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0993 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WPC-017062-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0994 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WPC-017062-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0995 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WPC-017062-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0996 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WPC-017062-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0997 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WPC-017062-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-0998 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WPC-017062-09 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-0999 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WPC-017062-10 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 1.994 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1000 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WPC-017062-12 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.062 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1001 | TFS | 50.11.01 | TFS00F101MM | LP1Y-WPC-017064-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.122 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1002 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WPC-033020-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.273 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1003 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WPC-033035-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1004 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WPC-033035-02 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1005 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WPC-033035-05 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1006 | TFS | 50.11.01 | TFS00B103MM | LP1Y-WPC-033035-06 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1007 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WPC-033035-07 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1008 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WPC-033035-08 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1009 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WPC-033035-09 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1010 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WPC-033035-10 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1011 | TFS | 50.11.01 | TFS00S101MM | LP1Y-WPC-033039-01 | TFS00S101MMPP | K214 | IP-TFS00S101MMPP-K214-150 | 50.TS101-M.F | TB101 TO TS101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.449 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1012 | TFS | 50.11.01 | TFS00W105MM | LP1Y-WPC-033039-06 | TFS00W105MMPP | K214 | IP-TFS00W105MMPP-K214-150 | 50.TW105-M.F | TW104 TO TW105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1013 | TFS | 50.11.01 | TFS00F101MM | LP1Y-WS-017025-02 | TFS00F101MMPP | K214 | IP-TFS00F101MMPP-K214-150 | 50.TF101-M.F | TA104 TO TF101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.456 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1014 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WS-017025-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1015 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WS-017025-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1016 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WS-017025-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1017 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WS-017030-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1018 | TFS | 50.11.01 | TFS00B101MM | LP1Y-WS-017030-06 | TFS00B101MMPP | K214 | IP-TFS00B101MMPP-K214-150 | 50.TB101-M.F | TA101 TO TB101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.455 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1019 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WS-017034-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1020 | TFS | 50.11.01 | TFS00A103MM | LP1Y-WS-017034-02 | TFS00A103MMPP | K214 | IP-TFS00A103MMPP-K214-150 | 50.TA103-M.F | TA102TO TA103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1021 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WS-017034-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1022 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WS-017034-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1023 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WS-017034-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 8.66 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1024 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WS-033030-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1025 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WS-033030-03 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1026 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WS-033030-05 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 2.002 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1027 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WS-033031-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1028 | TFS | 50.11.01 | TFS00B108MM | LP1Y-WS-033043-01 | TFS00B108MMPP | K214 | IP-TFS00B108MMPP-K214-150 | 50.TB108-M.F | TB107 TO TB108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1029 | TFS | 50.11.01 | TFS00J101MM | LP1Y-WS-033043-02 | TFS00J101MMPP | K214 | IP-TFS00J101MMPP-K214-150 | 50.TJ101-M.F | TB108 TO TJ101 SWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 8.66 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1030 | TFS | 50.11.01 | TFS00B106MM | LP1Y-WS-033043-04 | TFS00B106MMPP | K214 | IP-TFS00B106MMPP-K214-150 | 50.TB106-M.F | TB105 TO TB106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1031 | TFS | 50.11.01 | TFS00B107MM | LP1Y-WS-033043-05 | TFS00B107MMPP | K214 | IP-TFS00B107MMPP-K214-150 | 50.TB107-M.F | TB106 TO TB107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1032 | TFS | 50.11.01 | TFS00B105MM | LP1Y-WS-033052-01 | TFS00B105MMPP | K214 | IP-TFS00B105MMPP-K214-150 | 50.TB105-M.F | TB104 TO TB105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.33 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1033 | TFS | 50.11.01 | TFS00B102MM | LP1Y-WS-033052-03 | TFS00B102MMPP | K214 | IP-TFS00B102MMPP-K214-150 | 50.TB102-M.F | TB101 TO TB102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1034 | TFS | 50.11.01 | TFS00B103MM | LP1Y-WS-033052-04 | TFS00B103MMPP | K214 | IP-TFS00B103MMPP-K214-150 | 50.TB103-M.F | TB102 TO TB103 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1035 | TFS | 50.11.01 | TFS00B104MM | LP1Y-WS-033052-05 | TFS00B104MMPP | K214 | IP-TFS00B104MMPP-K214-150 | 50.TB104-M.F | TB103 TO TB104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 4.205 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1036 | TFS | 50.11.01 | TFS00H101MM | LP1Y-WTFAP-014011-01 | TFS00H101MMPP | K214 | IP-TFS00H101MMPP-K214-150 | 50.TH101-M.F | TA103 TO TH101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.16 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1037 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WTFAP-014011-03 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 50.14 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1038 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WTFAP-014011-04 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1039 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WTFAP-014011-05 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1040 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WTFAP-014011-06 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1041 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WTFAP-014011-07 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 25.07 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1042 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WTFAP-014011-08 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.167 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1043 | TFS | 50.11.01 | TFS00L102MM | LP1Y-WV-061046-18 | TFS00L102MMPP | K214 | IP-TFS00L102MMPP-K214-150 | 50.TL102-M.F | TL101 TO TL102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1044 | TFS | 50.11.01 | TFS00L101MM | LP1Y-WV-061046-19 | TFS00L101MMPP | K214 | IP-TFS00L101MMPP-K214-150 | 50.TL101-M.F | TA112 TO TL101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 26.664 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1045 | TFS | 50.11.01 | TFS00A112MM | LP1Y-WV-061046-20 | TFS00A112MMPP | K214 | IP-TFS00A112MMPP-K214-150 | 50.TA112-M.F | TA111 TO TA112 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1046 | TFS | 50.11.01 | TFS00A111MM | LP1Y-WV-061046-21 | TFS00A111MMPP | K214 | IP-TFS00A111MMPP-K214-150 | 50.TA111-M.F | TA110 TO TA111 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1047 | TFS | 50.11.01 | TFS00A110MM | LP1Y-WV-061046-22 | TFS00A110MMPP | K214 | IP-TFS00A110MMPP-K214-150 | 50.TA110-M.F | TA109 TO TA110 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1048 | TFS | 50.11.01 | TFS00A109MM | LP1Y-WV-061046-23 | TFS00A109MMPP | K214 | IP-TFS00A109MMPP-K214-150 | 50.TA109-M.F | TA108 TO TA109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1049 | TFS | 50.11.01 | TFS00A108MM | LP1Y-WV-061046-24 | TFS00A108MMPP | K214 | IP-TFS00A108MMPP-K214-150 | 50.TA108-M.F | TA107 TO TA108 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1050 | TFS | 50.11.01 | TFS00A107MM | LP1Y-WV-061046-25 | TFS00A107MMPP | K214 | IP-TFS00A107MMPP-K214-150 | 50.TA107-M.F | TA106 TO TA107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1051 | TFS | 50.11.01 | TFS00A106MM | LP1Y-WV-061046-26 | TFS00A106MMPP | K214 | IP-TFS00A106MMPP-K214-150 | 50.TA106-M.F | TA105 TO TA106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1052 | TFS | 50.11.01 | TFS00A105MM | LP1Y-WV-061046-27 | TFS00A105MMPP | K214 | IP-TFS00A105MMPP-K214-150 | 50.TA105-M.F | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1053 | TFS | 50.11.01 | TFS00A104MM | LP1Y-WV-061046-28 | TFS00A104MMPP | K214 | IP-TFS00A104MMPP-K214-150 | 50.TA104-M.F | TA103 TO TA104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 27.417 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1054 | TFS | 50.11.01 | TFS00B109MM | LP1Y-WV-321011-03 | TFS00B109MMPP | K214 | IP-TFS00B109MMPP-K214-150 | 50.TB109-M.F | TB108 TO TB109 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 19.939 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1189 | TFS | 50.11.01 | TFS00A104MM | LP1Y-TWSP-017063-04 |  |  |  |  | TA104 TO TA105 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 120 |  | 100% | 100% | 100% |  |  | 0% | 0 | 1
K214-TFS-1190 | TFS | 50.11.01 | TFA00A103MM | LP1Y-PV-013001-02 |  |  |  |  | TA103 TO TA104 DWHU Connection | 2 | 0 | 2 | 0 | EA | 0 |  | 0 | 44 |  | 100% | 100% | 100% |  |  | 0% | 0 | 2
K214-TFS-1265 | TFS | 50.11.01 | TFS00F102MM | LP1Y-APL(100)-019001-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 21.62 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1266 | TFS | 50.11.01 | TFS00F102MM | LP1Y-CHWR-017024-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 77.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1267 | TFS | 50.11.01 | TFS00F102MM | LP1Y-CHWS-017111-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 77.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1268 | TFS | 50.11.01 | TFS00F102MM | LP1Y-NG-018012-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 13.41 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
| TFS | 50.11.01 | TFS00F101MM | LP1Y-PSC-017027-05 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 15.609 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1359 | TFS | 50.11.01 | TFS00F102MM | LP1Y-TWRP-017021-02 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 118.82 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1375 | TFS | 50.11.01 | TFS00F102MM | LP1Y-TWSP-017016-03 |  |  |  |  | TF101 TO TF102 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 118.82 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1128 | TFS | 50.11.01 | TFS00A101MS |  | TFS00A101MSPP | K214 | IP-TFS00A101MSPP-K214-050 | 50.TA101-M.F | Assembly of Ship Loose Pipe for Module TA101 | 557.715 | 0 | 557.715 | 0 | LF | 1698.6 |  | 0 | 1698.6 |  | 13% | 13% | 13% |  |  | 0% | 0 | 0
K214-TFS-1317 | TFS | 50.11.01 | TFS00A102MS | [5 empty] | Assembly of Ship Loose Pipe for Module TA102 | 68.923 | 0 | 68.923 | 0 | LF | 1101.7 |  | 0 | 1101.7 |  | 100% | 63% | 60% |  |  | 0% | 0 | 0
K214-TFS-1232 | TFS | 50.11.01 | TFS00A103MS | [5 empty] | Assembly of Ship Loose Pipe for Module TA103 | 438.254 | 0 | 0 | 0 | LF | 1552 |  | 0 | 1552 |  | 100% | 50% | 45% |  |  | 0% | 0 | 1
K214-TFS-1137 | TFS | 50.11.01 | TFS00A104MS |  | TFS00A104MSPP | K214 | IP-TFS00A104MSPP-K214-050 | 50.TA104-M.F | Assembly of Ship Loose Pipe for Module TA104 | 874.01 | 0 | 874.01 | 0 | LF | 1119.188 |  | 0 | 1119.188 |  | 100% | 15% | 10% |  |  | 0% | 0 | 0
K214-TFS-1129 | TFS | 50.11.01 | TFS00A105MS |  | TFS00A105MSPP | K214 | IP-TFS00A105MSPP-K214-050 | 50.TA105-M.F | Assembly of Ship Loose Pipe for Module TA105 | 638.73 | 0 | 638.73 | 0 | LF | 2191.107 |  | 0 | 2191.107 |  | 100% | 63% | 60% |  |  | 0% | 0 | 0
K214-TFS-1130 | TFS | 50.11.01 | TFS00A106MS |  | TFS00A106MSPP | K214 | IP-TFS00A106MSPP-K214-050 | 50.TA106-M.F | Assembly of Ship Loose Pipe for Module TA106 | 882.922 | 0 | 882.922 | 0 | LF | 3348.979 |  | 0 | 3348.979 |  | 100% | 70% | 70% |  |  | 0% | 0 | 0
K214-TFS-1131 | TFS | 50.11.01 | TFS00A107MS |  | TFS00A107MSPP | K214 | IP-TFS00A107MSPP-K214-050 | 50.TA107-M.F | Assembly of Ship Loose Pipe for Module TA107 | 502.36 | 0 | 502.36 | 0 | LF | 1035.622 |  | 0 | 1035.622 |  | 100% | 70% | 70% |  |  | 0% | 0 | 0
K214-TFS-1132 | TFS | 50.11.01 | TFS00A108MS |  | TFS00A108MSPP | K214 | IP-TFS00A108MSPP-K214-050 | 50.TA108-M.F | Assembly of Ship Loose Pipe for Module TA108 | 797.27 | 0 | 797.27 | 0 | LF | 1902.8 |  | 0 | 1902.8 |  | 100% | 60% | 60% |  |  | 0% | 0 | 0
K214-TFS-1138 | TFS | 50.11.01 | TFS00A109MS |  | TFS00A109MSPP | K214 | IP-TFS00A109MSPP-K214-050 | 50.TA109-M.F | Assembly of Ship Loose Pipe for Module TA109 | 726.55 | 0 | 726.55 | 0 | LF | 2615 |  | 0 | 2615 |  | 45% | 0% | 0% |  |  | 0% | 0 | 0
[9 empty] | Assembly of Ship Loose Pipe for Module TA110 | 1140.791 | 0 | 1140.791 |  | LF | 5801.339
[9 empty] | Assembly of Ship Loose Pipe for Module TA111 | 481.994 | 0 | 481.994 |  | LF | 3597.944
[9 empty] | Assembly of Ship Loose Pipe for Module TA112 | 429.06 | 0 | 429.06 |  | LF | 2361.245
K214-TFS-1133 | TFS | 50.11.01 | TFS00F101MS |  | TFS00F101MSPP | K214 | IP-TFS00F101MSPP-K214-050 | 50.TF101-M.F | Assembly of Ship Loose Pipe for Module TF101 | 176 | 0 | 176 | 0 | LF | 1292 |  | 0 | 1292 |  | 100% | 50% | 50% |  |  | 0% | 0 | 0
K214-TFS-1134 | TFS | 50.11.01 | TFS00F102MS |  | TFS00F102MSPP | K214 | IP-TFS00F102MSPP-K214-050 | 50.TF102-M.F | Assembly of Ship Loose Pipe for Module TF102 | 39 | 0 | 39 | 0 | LF | 529 |  | 0 | 529 |  | 100% | 30% | 30% |  |  | 0% | 0 | 0
K214-TFS-1135 | TFS | 50.11.01 | TFS00H101MS |  | TFS00H101MSPP | K214 | IP-TFS00H101MSPP-K214-050 | 50.TH101-M.F | Assembly of Ship Loose Pipe for Module TH101 | 15 | 0 | 15 | 0 | EA | 334 |  | 0 | 334 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1136 | TFS | 50.11.01 | TFS00K102MS |  | TFS00K102MSPP | K214 | IP-TFS00K102MSPP-K214-050 | 50.TK102-M.F | Assembly of Ship Loose Pipe for Module TK102 | 3 | 0 | 3 | 3 | EA | 52.31 |  | 0 | 52 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1191 | TFS | 50.11.01 | TFS00K103MM | [5 empty] | Assembly of Ship Loose Pipe for Module TK103 | 2 | 0 | 2 | 0 | EA | 127.392 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1192 | TFS | 50.11.01 | TFS00K105MM | [5 empty] | Assembly of Ship Loose Pipe for Module TK105 | 2 | 0 | 2 | 0 | EA | 127.392 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1153 | TFS | 50.11.01 | TFS00K103MM | LP1Y-WPC-033024-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 32 |  | 0 | 32 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1154 | TFS | 50.11.01 | TFS00K103MM | LP1Y-CHWR-033050-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1155 | TFS | 50.11.01 | TFS00K103MM | LP1Y-CHWS-033013-03 |  |  |  |  | TK102 TO TK103 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 0% | 0% | 0% |  |  | 0% | 0 | 0
K214-TFS-1156 | TFS | 50.11.01 | TFS00K103MM | LP1Y-APL(100)-034012-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1157 | TFS | 50.11.01 | TFS00K103MM | LP1Y-NG-034009-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1158 | TFS | 50.11.01 | TFS00K103MM | LP1Y-N2(100)-034041-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1159 | TFS | 50.11.01 | TFS00K103MM | LP1Y-SWP-036050-05 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1160 | TFS | 50.11.01 | TFS00K103MM | LP1Y-PSC-033051-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1161 | TFS | 50.11.01 | TFS00K103MM | LP1Y-S(130)-034010-06 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1162 | TFS | 50.11.01 | TFS00K104MM | LP1Y-WPC-033024-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1163 | TFS | 50.11.01 | TFS00K104MM | LP1Y-CHWR-033050-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1164 | TFS | 50.11.01 | TFS00K104MM | LP1Y-CHWS-033013-04 |  |  |  |  | TK103 TO TK104 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.554 |  | 0 | 95.554 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1165 | TFS | 50.11.01 | TFS00K104MM | LP1Y-NG-034009-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1166 | TFS | 50.11.01 | TFS00K104MM | LP1Y-N2(100)-034041-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1167 | TFS | 50.11.01 | TFS00K104MM | LP1Y-SWP-036050-06 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1168 | TFS | 50.11.01 | TFS00K104MM | LP1Y-PSC-033051-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1169 | TFS | 50.11.01 | TFS00K104MM | LP1Y-APL(100)-034012-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1170 | TFS | 50.11.01 | TFS00K104MM | LP1Y-S(130)-034010-07 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1171 | TFS | 50.11.01 | TFS00K105MM | LP1Y-WPC-033024-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1172 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWR-033050-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1173 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWS-033013-05 |  |  |  |  | TK104 TO TK105 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1174 | TFS | 50.11.01 | TFS00K105MM | LP1Y-NG-034009-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1175 | TFS | 50.11.01 | TFS00K105MM | LP1Y-N2(100)-034041-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1176 | TFS | 50.11.01 | TFS00K105MM | LP1Y-SWP-036050-07 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1177 | TFS | 50.11.01 | TFS00K105MM | LP1Y-PSC-033051-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1178 | TFS | 50.11.01 | TFS00K105MM | LP1Y-APL(100)-034012-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1179 | TFS | 50.11.01 | TFS00K105MM | LP1Y-S(130)-034010-10 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1180 | TFS | 50.11.01 | TFS00K106MM | LP1Y-CHWS-033013-06 |  |  |  |  | TK105 TO TK106 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1181 | TFS | 50.11.01 | TFS00K106MM | LP1Y-NG-034009-07 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1182 | TFS | 50.11.01 | TFS00K106MM | LP1Y-PSC-033051-07 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1183 | TFS | 50.11.01 | TFS00K106MM | LP1Y-S(130)-034010-11 |  |  |  |  | TK106 TO TK107 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1193 | TFS | 50.11.01 | TFS00K105MM | LP1Y-WPC-033024-06 | LP1Y-WPC-033024-06 |  |  |  | TK105 TO TK106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
'K214-TFS-1194 | TFS | 50.11.01 | TFS00K105MM | LP1Y-CHWR-033050-06 |  |  |  |  | TK105 TO TK106 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1195 | TFS | 50.11.01 | TFS00K106MM | LP1Y-N2(100)-034041-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1196 | TFS | 50.11.01 | TFS00K106MM | LP1Y-SWP-036050-08 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1197 | TFS | 50.11.01 | TFS00K106MM | LP1Y-APL(100)-034012-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1198 | TFS | 50.11.01 | TFS00K106MM | LP1Y-WPC-033024-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1199 | TFS | 50.11.01 | TFS00K106MM | LP1Y-CHWR-033050-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1200 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWS-033013-07 |  |  |  |  | TK106 TO TK107 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1360 | TFS | 50.11.01 | TFS00K108MM | LP1Y-S(130)-034010-13 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1361 | TFS | 50.11.01 | TFS00K108MM | LP1Y-PSC-033051-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1362 | TFS | 50.11.01 | TFS00K108MM | LP1Y-NG-034009-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1363 | TFS | 50.11.01 | TFS00K108MM | LP1Y-SWP-036050-10 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1364 | TFS | 50.11.01 | TFS00K108MM | LP1Y-N2(100)-034041-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1365 | TFS | 50.11.01 | TFS00K108MM | LP1Y-APL(100)-034012-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-APL(100)-034012-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 47.772 |  |  | 47.772 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-WPC-033024-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 63.696 |  |  | 63.696 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWR-033050-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 191.088 |  |  | 191.088 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWS-033013-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 191.088 |  |  | 191.088 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-N2(100)-034041-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00K108MM | LP1Y-SWP-036050-11 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1376 | TFS | 50.11.01 | TFS00K108MM | LP1Y-PSC-033051-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 31.48 |  | 0 | 31.48 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1377 | TFS | 50.11.01 | TFS00K108MM | LP1Y-NG-034009-09 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 47.72 |  | 0 | 47.72 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1378 | TFS | 50.11.01 | TFS00K108MM | LP1Y-S(130)-034010-13 |  |  |  |  | TK108 TO TK109 DWHU CONNECTION | 1 | 1 | 2 | 0 | EA | 0 |  | 0 | 127.392 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1379 | TFS | 50.11.01 | TFS00K110MM | LP1Y-SWP-036050-12 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1380 | TFS | 50.11.01 | TFS00K110MM | LP1Y-N2(100)-034041-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1381 | TFS | 50.11.01 | TFS00K110MM | LP1Y-PSC-033051-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1382 | TFS | 50.11.01 | TFS00K110MM | LP1Y-S(130)-034010-17 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 63.696 |  | 0 | 63.696 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1383 | TFS | 50.11.01 | TFS00K110MM | LP1Y-APL(100)-034012-10 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1384 | TFS | 50.11.01 | TFS00K110MM | LP1Y-NG-034009-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1385 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWR-033050-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1386 | TFS | 50.11.01 | TFS00K110MM | LP1Y-CHWS-033013-11 |  |  |  |  | TK109 TO TK110 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1366 | TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWR-033050-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.5 |  | 0 | 95.54 |  | 100% | 100% | 100% | 0% | 0% | 0% | 0 | 0
K214-TFS-1367 | TFS | 50.11.01 | TFS00K108MM | LP1Y-CHWS-033013-09 |  |  |  |  | TK107 TO TK108 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.5 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1201 | TFS | 50.11.01 | TFS00W101MM | LP1Y-PSC-033040-03 |  |  |  |  | TW101 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1202 | TFS | 50.11.01 | TFS00W102MM | LP1Y-NG-034039-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1203 | TFS | 50.11.01 | TFS00W102MM | LP1Y-S(130)-034038-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1204 | TFS | 50.11.01 | TFS00W102MM | LP1Y-CHWS-033038-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1205 | TFS | 50.11.01 | TFS00D116MM | LP1Y-AI(100)-019009-19 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1206 | TFS | 50.11.01 | TFS00D116MM | LP1Y-H2SO4-178102-02 |  |  |  |  | TD116 VERTICAL SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.84 |  | 0 | 31.84 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1207 | TFS | 50.11.01 | TFS00W103MM | LP1Y-S(130)-034038-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.84 |  | 0 | 31.84 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1208 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWS-033038-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1209 | TFS | 50.11.01 | TFS00D116MM | LP1Y-N2(100)-180087-03 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1210 | TFS | 50.11.01 | TFS00D116MM | LP1Y-APL(100)019072-18 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
'K214-TFS-1211 | TFS | 50.11.01 | TFS00W103MM | LP1Y-NG-034039-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1212 | TFS | 50.11.01 | TFS00W102MM | LP1Y-APL(100)-034040-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1213 | TFS | 50.11.01 | TFS00W102MM | LP1Y-AWNP-037004-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1215 | TFS | 50.11.01 | TFS00W102MM | LP1Y-CHWR-033041-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1216 | TFS | 50.11.01 | TFS00W102MM | LP1Y-N2(100)-034037-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1217 | TFS | 50.11.01 | TFS00W102MM | LP1Y-PWP-036003-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1218 | TFS | 50.11.01 | TFS00W102MM | LP1Y-WPC-033039-03 |  |  |  |  | TW102 TO TW101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1219 | TFS | 50.11.01 | TFS00W103MM | LP1Y-APL(100)-034040-04 |  |  |  |  | TW103 TO TW102 DWHU CONNECTION | 2 | 0 | 2 | 0 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1220 | TFS | 50.11.01 | TFS00W103MM | LP1Y-AWNP-037004-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1221 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWR-033041-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1222 | TFS | 50.11.01 | TFS00W103MM | LP1Y-N2(100)-034037-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1223 | TFS | 50.11.01 | TFS00W103MM | LP1Y-PWP-036003-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1224 | TFS | 50.11.01 | TFS00W103MM | LP1Y-WPC-033039-04 |  |  |  |  | TW103 TO TW102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 47.772 |  | 0 | 47.772 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-AWNP-037004-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  |  | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-APL(100)-034040-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  |  | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-S(130)-034038-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  |  | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-WPC-033039-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 47.772 |  |  | 47.772 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-NG-034039-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-PWP-036003-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W103MM | LP1Y-N2(100)-034037-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  |  | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1387 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWR-033041-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1388 | TFS | 50.11.01 | TFS00W103MM | LP1Y-CHWS-033038-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.54 |  | 0 | 95.54 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1389 | TFS | 50.11.01 | TFS00W103MM | LP1Y-PSC-033040-04 |  |  |  |  | TW103 TO TW104 SWHU Connection | 1 | 0 | 1 | 0 | EA | 0 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1225 | TFS | 50.11.01 | TFS00D116MM | LP1Y-S(130)-018131-03 |  |  |  |  | TD116 TO TD114 DWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1226 | TFS | 50.11.01 | TFS00D116MM | LP1Y-WFO-017060-19 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1227 | TFS | 50.11.01 | TFS00D116MM | LP1Y-WPC-017061-07 |  |  |  |  | TD116 TO TD114 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1228 | TFS | 50.11.01 | TFS00D117MM | LP1Y-H2SO4-100303-03 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1229 | TFS | 50.11.01 | TFS00D117MM | LP1Y-STORMP-165114-04 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1230 | TFS | 50.11.01 | TFS00D117MM | LP1Y-SWP-165113-04 |  |  |  |  | TD117 TO TD115 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1233 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AI(100)-019013-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1234 | TFS | 50.11.01 | TFS00D103MM | LP1Y-APL(100)-198104-01 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1235 | TFS | 50.11.01 | TFS00D103MM | LP1Y-NAHOH50-101304-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1236 | TFS | 50.11.01 | TFS00D103MM | LP1Y-H2SO4-101303-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1237 | TFS | 50.11.01 | TFS00D103MM | LP1Y-S(130)-018078-03 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1238 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AWNP-101302-02 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 47.773 |  | 0 | 47.773 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1239 | TFS | 50.11.01 | TFS00D103MM | LP1Y-AWNP-101309-06 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 47.773 |  | 0 | 47.773 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1240 | TFS | 50.11.01 | TFS00D101MM | LP1Y-H2SO4-016001-01 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1241 | TFS | 50.11.01 | TFS00D101MM | LP1Y-NAOH50-016002-02 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1269 | TFS | 50.11.01 | TFS00D103MM | LP1Y-WFO-017007-61 |  |  |  |  | TD103 TO TD101 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1270 | TFS | 50.11.01 | TFS00D101MM | LP1Y-APL(100)-019074-03 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1271 | TFS | 50.11.01 | TFS00D101MM | LP1Y-AI(100)-019013-03 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1272 | TFS | 50.11.01 | TFS00D101MM | LP1Y-AWNP-101309-10 |  |  |  |  | TD101 TO TA102 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 47.77 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-AWNP-037004-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-APL(100)-034040-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 23.886 |  | 0 | 23.886 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-S(130)-034038-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-PSC-033040-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 31.848 |  | 0 | 31.848 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-CHWS-033038-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-CHWR-033041-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 95.544 |  | 0 | 95.544 |  | 100% | 100% | 100% |  |  | 0% | 0
| TFS | 50.11.01 | TFS00S101MM | LP1Y-WPC-033039-01 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 47.772 |  | 0 | 47.772 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-PWP-036003-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-NG-034039-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 | [6 empty] | 0% | 0
| TFS | 50.11.01 | TFS00W101MM | LP1Y-N2(100)-034037-02 |  |  |  |  | TS101 TO TW101 SWHU Connection | 1 | 0 | 1 | 0 | EA | 15.924 |  | 0 | 15.924 |  | 100% | 100% | 100% |  |  | 0% | 0
K214-TFS-1273 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1274 | TFS | 50.11.01 | TFS00SRU | AWNP(315)(108)852004-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1275 | TFS | 50.11.01 | TFS00SRU | PWP(315)(108)854014-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1276 | TFS | 50.11.01 | TFS00SRU | SRACNP(315)P(108)852001-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.4 |  | 0 | 7.4 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1318 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)854019-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1319 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)854018-01 |  |  |  |  | H06V02 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1277 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860010-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1320 | TFS | 50.11.01 | TFS00SRU | PSC(002)(101)862003-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1278 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)860001-01 |  |  |  |  | H06V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1279 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1321 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)859007-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1322 | TFS | 50.11.01 | TFS00SRU | SWP(315)(108)859011-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1323 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)856017-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1280 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)859010-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1324 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)856016-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1325 | TFS | 50.11.01 | TFS00SRU | TWSP-(006)(108)859009-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1281 | TFS | 50.11.01 | TFS00SRU | WPC(036)(108)861023-01 |  |  |  |  | H06V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1326 | TFS | 50.11.01 | TFS00SRU | ACN(315)P(108)857003-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1327 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)857012-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1282 | TFS | 50.11.01 | TFS00SRU | TWRP(006)(108)858020-02 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 8 |  | 0 | 8 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1283 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)858019-02 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1328 | TFS | 50.11.01 | TFS00SRU | TWSP(006)(108)857011-01 |  |  |  |  | H06V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 8 |  | 0 | 8 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1284 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1285 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860011-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1286 | TFS | 50.11.01 | TFS00SRU | CIPS(315)P(108)860012-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1287 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1288 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)853002-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1289 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)855002-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1290 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)854017-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1291 | TFS | 50.11.01 | TFS00SRU | S(002)(103)853006-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1292 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)853004-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1293 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)853025-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1294 | TFS | 50.11.01 | TFS00SRU | SC(002)(101)862005-01 |  |  |  |  | V02V03 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1295 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1296 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1297 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)855009-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1298 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)856013-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1299 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)858016-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1300 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)854017-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1301 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)860001-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1302 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)857007-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1303 | TFS | 50.11.01 | TFS00SRU | SC(002)(103)859003-01 |  |  |  |  | V03V04 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1304 | TFS | 50.11.01 | TFS00SRU | AI(90)(315)861001-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1305 | TFS | 50.11.01 | TFS00SRU | N2(100)(315)E860017-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1306 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)856012-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1307 | TFS | 50.11.01 | TFS00SRU | P(315)P(101)858016-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1308 | TFS | 50.11.01 | TFS00SRU | PV(315)(108)858018-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1309 | TFS | 50.11.01 | TFS00SRU | S(002)(103)857008-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1310 | TFS | 50.11.01 | TFS00SRU | S(130)(002)(103)857006-01 |  |  |  |  | V04V05 PIPE SPOOL INSTALLATION | 2 | 0 | 2 | 0 | EA | 7.3 |  | 0 | 7.3 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1311 | TFS | 50.11.01 | TFS00SRU | TWSP-858019-02 |  |  |  |  | H06V05 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 25.47 |  | 0 | 25.47 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1312 | TFS | 50.11.01 | TFS00SRU | TWSP-858020-02 |  |  |  |  | H06V05 SWHU CONNECTION | 1 | 0 | 1 | 0 | EA | 25.47 |  | 0 | 25.47 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1329 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V02) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1330 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V03) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1331 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V04) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1332 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (V05) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0
K214-TFS-1333 | TFS | 50.11.01 | TFS00SRU | N/A |  |  |  |  | Installing SRU valve tags (H06) |  |  |  |  | EA | 50 |  | 0 | 50 |  | 100% | 100% | 100% |  |  | 0% | 0 | 0

## TFS Quantity Curve Steel
LEBANON PLANT 1 (LP1)
TFS STRUCTURAL STEEL INSTALLATION
DESCRIPTION |  |  |  |  | 2025 | [7 empty] | 2026 | [11 empty] | 2027
[5 empty] | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | test | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01
STRUCTURAL STEEL STATISTICS (Included only IFC Quantities)
Estimated Total Quantity: |  | 500 | tn
CONSTRUCTION PHASE
Status As of: 2025-06-27
Plan Install to Date: |  | 0 | tn
Actual Install To Date: |  | 0 | tn
Forecast Install To Date: |  | 0 | tn
Weekly Statistics
[5 empty] | 2025 | [7 empty] | 2026 | [11 empty] | 2027
[5 empty] | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
RECOVERY PLAN CONSTRUCTION | Installation Monthly |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installation Cumulative
PLAN CONSTRUCTION | Installation Monthly |  |  |  | 2025 JUN: 250; 2025 JUL: 250
| Installation Cumulative |  |  |  | 2025 JUN: 250; 2025 JUL: 500
ACTUAL CONSTRUCTION | Installation Monthly |  |  |  | 2025 JUN: 0; 2025 JUL: 0
| Installation Cumulative |  |  |  | 2025 JUN: 0; 2025 JUL: 0
FORECAST CONSTRUCTION | Installation Monthly |  |  |  | 2025 JUN: 250; 2025 JUL: 250
| Installation Cumulative |  |  |  | 2025 JUN: 250; 2025 JUL: 500
Start Date |  |  |  | 2025-06-26 | 2025 MAY: Remarks / Comments; 2026 JUL: Eli Lilly; 2027 FEB: REVISIONS
Finish Date |  |  |  | 2025-07-25 | 2026 JUL: Lebanon Plant 1 (LP1); 2027 FEB: Date; 2027 MAR: Revision; 2027 JUL: Checked; 2027 AUG: Approved
Data Date |  |  |  | 2025-06-26 | 2026 JUL: Indianapolis, US
Run Date |  |  |  | 2026-03-29 | 2026 JUL: QUANTITY PROGRESS S-CURVE
[5 empty] | WEEKLY ACCOMPLISHMENT | [16 empty] | TOTAL
[6 empty] | 2025-06-26 | 2025-07-03 | 2025-07-10 | 2025-07-17
|  |  | Plan Installation Weekly |  | 2025 JUN: 0; 2025 JUL: 0; 2025 AUG: 0; 2025 SEP: 0; 2026 OCT: 0
|  |  | Plan Cumm. Installation |  | 2025 JUN: 0; 2025 JUL: 0; 2025 AUG: 0; 2025 SEP: 0; 2026 OCT: 0
|  |  | Actual Installation Weekly |  | 2025 JUN: 20; 2025 JUL: 0; 2025 AUG: 0; 2025 SEP: 0; 2026 OCT: 20
|  |  | Actual Cumm. Installation |  | 2025 JUN: 20; 2025 JUL: 20; 2025 AUG: 20; 2025 SEP: 20; 2026 OCT: 20
|  |  | Forecast Install. Weekly |  | 2025 JUN: 0; 2025 JUL: 0; 2025 AUG: 0; 2025 SEP: 0; 2026 OCT: 0
|  |  | Forecast Cumm. |  | 2025 JUN: 0; 2025 JUL: 0; 2025 AUG: 0; 2025 SEP: 0; 2026 OCT: 0
Includes:
Main Steel
Misc. Steel
Metal Deck
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
TBD
Total
500
0
0
0
0
0
0
0
0
0
0
0
500