## Detailed Spool Report
Barcode | Contract | Spool | Piece Mark | Isometric | Rev # | Rev Test | Transmittal | On Hold | Off Hold | Hold Status | Hold Source | Hold Justification | Status | Priority | Estimated Ship Date | Job | Line | Fluid | Test Pack | Insulation | Operation Temperature | Operation Pressure | Hydrotest Pressure | Paint Color | Type | PWHT | Location | Unit | Area | Zone | System | Module | Skid | Class | Paint System | Spool Size | MTL | dia-inch | dia-inch R | dia-inch P | Weight | Paint Area | Area Units | Pipe Length | Length Units | RCVD Date | AD | AL | BD | BL | CD | CL | DD | DL | ED | EL | FD | FL | Project RLS Date | I-Test Date | I-Test Status | Contains Partials | RLS to Fab date | MTL Pull Start Date | MTL Pull Complete Date | Pipe Cut Start Date | Pipe Cut Complete Date | Support Start Date | Support Complete Date | Assigned Fabricator | Fabricator Assignment Date | Fit R Start Date | Fit P Start Date | Fit Start Date | Weld R Start Date | Weld P Start Date | Weld Start Date | FIT R Complete | FIT P Complete | FIT Complete | FIT % All | WLD R Complete | WLD P Complete | WLD Complete | WLD % All | VI Report Date | VI Report Numbers | Loader Release Date | RLS to Coater | RLS to NDE | RLS to PWHT | RLS to Pressure Test | RLS to MISC | Release Comment | PWHT Report Date | PWHT Report Numbers | Hydrotest Report Date | Hydrotest Report Numbers | X-RAY Report Date | X-RAY Report Numbers | MP Report Date | MP Report Numbers | LP Report Date | LP Report Numbers | PMI Report Date | PMI Report Numbers | Ferrite Report Date | Ferrite Report Numbers | Hardness Report Date | Hardness Report Numbers | Coatings Report Date | Coatings Report Numbers | PWHT P-L # | Shipment to PWHT | PWHT Custodian | Coater P-L # | Shipment to Coater | Coater Custodian | Blasted | First Coat | Second Coat | Third Coat | Misc P-L # | Shipment to Misc | Misc Custodian | Customer rlse date | Customer rlse | QC release | Rlse Doc. for review | Download Date | Final P-L # | Final Shipment | Final Custodian | Return from Client P-L # | Return from Client | Return from Coater P-L # | Return from Coater | Return from PWHT P-L # | Return from PWHT | Return from Misc P-L # | Return from Misc | RCVD on Site | Loaded | Installed | Welded | Supported | NDE Tested | Accepted | Painted | Spool Note | Documentation Package | Documentation Date
| ChgOrdNO | UDF5 | SecondDwgNO | DwgNO | RevNO | [8 empty] | SubArea | PlanFin |  | LineNumber | PjtSystem |  | InsulType |  |  |  | PaintCode | [7 empty] | UDF2 |  | MatlSpec | PaintCode | PipeSize1 | PipeGrade |  |  |  | UDF7 |  |  | Quantity | UOM (will always be "LFP"). Don't use "ft" | [17 empty] | ActStart | [68 empty] | ActFin
C34-S251394 | 26003H | 3570J | LP1Y-AWNP-850008-06-2 | LP1Y-AWNP-850008-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E015YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251393 | 26003H | 3569J | LP1Y-AWNP-850008-06-1 | LP1Y-AWNP-850008-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E015YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251392 | 26003H | 3568J | LP1Y-AWNP-850008-01-5 | LP1Y-AWNP-850008-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251391 | 26003H | 3567J | LP1Y-AWNP-850008-01-4 | LP1Y-AWNP-850008-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251390 | 26003H | 3566J | LP1Y-AWNP-850008-01-3 | LP1Y-AWNP-850008-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251389 | 26003H | 3565J | LP1Y-AWNP-850008-01-2 | LP1Y-AWNP-850008-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251388 | 26003H | 3564J | LP1Y-AWNP-850008-01-1 | LP1Y-AWNP-850008-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251387 | 26003H | 3563J | LP1Y-AWNP-850001-10-5 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251386 | 26003H | 3562J | LP1Y-AWNP-850001-10-4 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251385 | 26003H | 3561J | LP1Y-AWNP-850001-10-3 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251384 | 26003H | 3560J | LP1Y-AWNP-850001-10-2 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251383 | 26003H | 3559J | LP1Y-AWNP-850001-10-1 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251382 | 26003H | 3558J | LP1Y-AWNP-850001-02-4 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251381 | 26003H | 3557J | LP1Y-AWNP-850001-02-3 | I | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251380 | 26003H | 3556J | LP1Y-AWNP-850001-02-2 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251379 | 26003H | 3555J | LP1Y-AWNP-850001-02-1 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251378 | 26003H | 3554J | LP1Y-AWNP-850001-01-4 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251377 | 26003H | 3553J | LP1Y-AWNP-850001-01-3 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251376 | 26003H | 3552J | LP1Y-AWNP-850001-01-2 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251375 | 26003H | 3551J | LP1Y-AWNP-850001-01-1 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251374 | 26003H | 3550J | LP1Y-AWNP-112417-04-1 | LP1Y-AWNP-112417-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251373 | 26003H | 3549J | LP1Y-AWNP-112417-01-2 | LP1Y-AWNP-112417-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251372 | 26003H | 3548J | LP1Y-AWNP-112417-01-1 | LP1Y-AWNP-112417-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251371 | 26003H | 3547J | LP1Y-AWNP-112407-01-3 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251370 | 26003H | 3546J | LP1Y-AWNP-112407-01-2 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251369 | 26003H | 3545J | LP1Y-AWNP-112407-01-1 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251368 | 26003H | 3544J | LP1Y-AWNP-112405-02-4 | LP1Y-AWNP-112405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251367 | 26003H | 3543J | LP1Y-AWNP-112405-02-3 | LP1Y-AWNP-112405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251366 | 26003H | 3542J | LP1Y-AWNP-112405-02-2 | LP1Y-AWNP-112405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251365 | 26003H | 3541J | LP1Y-AWNP-112405-02-1 | LP1Y-AWNP-112405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251364 | 26003H | 3540J | LP1Y-AWNP-112405-01-2 | LP1Y-AWNP-112405-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251363 | 26003H | 3539J | LP1Y-AWNP-112405-01-1 | LP1Y-AWNP-112405-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112405 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251362 | 26003H | 3538J | LP1Y-AWNP-112404-04-5 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251361 | 26003H | 3537J | LP1Y-AWNP-112404-04-4 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251360 | 26003H | 3536J | LP1Y-AWNP-112404-04-3 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251359 | 26003H | 3535J | LP1Y-AWNP-112404-04-2 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251358 | 26003H | 3534J | LP1Y-AWNP-112404-04-1 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251357 | 26003H | 3533J | LP1Y-AWNP-112404-03-2 | LP1Y-AWNP-112404-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251356 | 26003H | 3532J | LP1Y-AWNP-112404-03-1 | LP1Y-AWNP-112404-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251355 | 26003H | 3531J | LP1Y-AWNP-112404-01-1 | LP1Y-AWNP-112404-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251354 | 26003H | 3530J | LP1Y-AWNP-112402-02-4 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251353 | 26003H | 3529J | LP1Y-AWNP-112402-02-3 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251352 | 26003H | 3528J | LP1Y-AWNP-112402-02-2 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251351 | 26003H | 3527J | LP1Y-AWNP-112402-02-1 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251350 | 26003H | 3526J | LP1Y-AWNP-112402-01-3 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251349 | 26003H | 3525J | LP1Y-AWNP-112402-01-2 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251348 | 26003H | 3524J | LP1Y-AWNP-112402-01-1 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251347 | 26003H | 3523J | LP1Y-AWNP-112217-03-1 | LP1Y-AWNP-112217-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251346 | 26003H | 3522J | LP1Y-AWNP-112217-01-3 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251345 | 26003H | 3521J | LP1Y-AWNP-112217-01-2 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251344 | 26003H | 3520J | LP1Y-AWNP-112217-01-1 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251343 | 26003H | 3519J | LP1Y-AWNP-112207-03-1 | LP1Y-AWNP-112207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251342 | 26003H | 3518J | LP1Y-AWNP-112207-01-3 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251341 | 26003H | 3517J | LP1Y-AWNP-112207-01-2 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251340 | 26003H | 3516J | LP1Y-AWNP-112207-01-1 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251339 | 26003H | 3515J | LP1Y-AWNP-112205-02-4 | LP1Y-AWNP-112205-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251338 | 26003H | 3514J | LP1Y-AWNP-112205-02-3 | LP1Y-AWNP-112205-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251337 | 26003H | 3513J | LP1Y-AWNP-112205-02-2 | LP1Y-AWNP-112205-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251336 | 26003H | 3512J | LP1Y-AWNP-112205-02-1 | LP1Y-AWNP-112205-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251335 | 26003H | 3511J | LP1Y-AWNP-112205-01-2 | LP1Y-AWNP-112205-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251334 | 26003H | 3510J | LP1Y-AWNP-112205-01-1 | LP1Y-AWNP-112205-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112205 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251333 | 26003H | 3509J | LP1Y-AWNP-112204-08-5 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251332 | 26003H | 3508J | LP1Y-AWNP-112204-08-4 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251331 | 26003H | 3507J | LP1Y-AWNP-112204-08-3 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251330 | 26003H | 3506J | LP1Y-AWNP-112204-08-2 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251329 | 26003H | 3505J | LP1Y-AWNP-112204-08-1 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251328 | 26003H | 3504J | LP1Y-AWNP-112204-07-2 | LP1Y-AWNP-112204-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251327 | 26003H | 3503J | LP1Y-AWNP-112204-07-1 | LP1Y-AWNP-112204-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251326 | 26003H | 3502J | LP1Y-AWNP-112204-05-4 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251325 | 26003H | 3501J | LP1Y-AWNP-112204-05-3 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251324 | 26003H | 3500J | LP1Y-AWNP-112204-05-2 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251323 | 26003H | 3499J | LP1Y-AWNP-112204-05-1 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251322 | 26003H | 3498J | LP1Y-AWNP-112204-02-1 | LP1Y-AWNP-112204-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251321 | 26003H | 3497J | LP1Y-AWNP-112204-01-3 | LP1Y-AWNP-112204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251320 | 26003H | 3496J | LP1Y-AWNP-112204-01-2 | LP1Y-AWNP-112204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251319 | 26003H | 3495J | LP1Y-AWNP-112204-01-1 | LP1Y-AWNP-112204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251318 | 26003H | 3494J | LP1Y-AWNP-112202-02-4 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251317 | 26003H | 3493J | LP1Y-AWNP-112202-02-3 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251316 | 26003H | 3492J | LP1Y-AWNP-112202-02-2 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251315 | 26003H | 3491J | LP1Y-AWNP-112202-02-1 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251314 | 26003H | 3490J | LP1Y-AWNP-112202-01-2 | LP1Y-AWNP-112202-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 6" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251313 | 26003H | 3489J | LP1Y-AWNP-112202-01-1 | LP1Y-AWNP-112202-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 6" SS AWNP (315) (108) 112202 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251312 | 26003H | 3488J | LP1Y-AWNP-112092-03-3 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251311 | 26003H | 3487J | LP1Y-AWNP-112092-03-2 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251310 | 26003H | 3486J | LP1Y-AWNP-112092-03-1 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251309 | 26003H | 3485J | LP1Y-AWNP-111092-02-3 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251308 | 26003H | 3484J | LP1Y-AWNP-111092-02-2 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251307 | 26003H | 3483J | LP1Y-AWNP-111092-02-1 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251306 | 26003H | 3482J | LP1Y-AWNP-110094-04-2 | LP1Y-AWNP-110094-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS AWNP (315) (108) 110094 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110094 |  | TFS00E009YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251305 | 26003H | 3481J | LP1Y-AWNP-110094-04-1 | LP1Y-AWNP-110094-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS AWNP (315) (108) 110094 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110094 |  | TFS00E009YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251304 | 26003H | 3480J | LP1Y-AWNP-107093-04-2 | LP1Y-AWNP-107093-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS AWNP (315) (108) 107093 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107093 |  | TFS00E005YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251303 | 26003H | 3479J | LP1Y-AWNP-107093-04-1 | LP1Y-AWNP-107093-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS AWNP (315) (108) 107093 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107093 |  | TFS00E005YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251302 | 26003H | 3478J | LP1Y-AWNP-015009-03-4 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251301 | 26003H | 3477J | LP1Y-AWNP-015009-03-3 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251300 | 26003H | 3476J | LP1Y-AWNP-015009-03-2 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251299 | 26003H | 3475J | LP1Y-AWNP-015009-03-1 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251298 | 26003H | 3474J | LP1Y-AW-199014-01-4 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251297 | 26003H | 3473J | LP1Y-AW-199014-01-3 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251296 | 26003H | 3472J | LP1Y-AW-199014-01-2 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251295 | 26003H | 3471J | LP1Y-AW-199014-01-1 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251294 | 26003H | 3470J | LP1Y-APL(100)-199010-02-1 | LP1Y-APL(100)-199010-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS APL(100) (315) 199010 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199010 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251293 | 26003H | 3469J | LP1Y-APL(100)-199001-04-4 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251292 | 26003H | 3468J | LP1Y-APL(100)-199001-04-3 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251291 | 26003H | 3467J | LP1Y-APL(100)-199001-04-2 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251290 | 26003H | 3466J | LP1Y-APL(100)-199001-04-1 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251289 | 26003H | 3465J | LP1Y-APL(100)-199001-03-2 | LP1Y-APL(100)-199001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251288 | 26003H | 3464J | LP1Y-APL(100)-199001-03-1 | LP1Y-APL(100)-199001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251287 | 26003H | 3463J | LP1Y-APL(100)-199001-02-1 | LP1Y-APL(100)-199001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251286 | 26003H | 3462J | LP1Y-APL(100)-199001-01-2 | LP1Y-APL(100)-199001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251285 | 26003H | 3461J | LP1Y-APL(100)-199001-01-1 | LP1Y-APL(100)-199001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS APL(100) (315) 199001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251284 | 26003H | 3460J | LP1Y-APL(100)-198112-01-2 | LP1Y-APL(100)-198112-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 198112 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198112 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251283 | 26003H | 3459J | LP1Y-APL(100)-198112-01-1 | LP1Y-APL(100)-198112-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 198112 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198112 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251282 | 26003H | 3458J | LP1Y-APL(100)-198093-02-1 | LP1Y-APL(100)-198093-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198093 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198093 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251281 | 26003H | 3457J | LP1Y-APL(100)-198092-05-3 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251280 | 26003H | 3456J | LP1Y-APL(100)-198092-05-2 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251279 | 26003H | 3455J | LP1Y-APL(100)-198092-05-1 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251278 | 26003H | 3454J | LP1Y-APL(100)-198092-04-2 | LP1Y-APL(100)-198092-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251277 | 26003H | 3453J | LP1Y-APL(100)-198092-04-1 | LP1Y-APL(100)-198092-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251276 | 26003H | 3452J | LP1Y-APL(100)-198092-03-3 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251275 | 26003H | 3451J | LP1Y-APL(100)-198092-03-2 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251274 | 26003H | 3450J | LP1Y-APL(100)-198092-03-1 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251273 | 26003H | 3449J | LP1Y-APL(100)-198091-02-1 | LP1Y-APL(100)-198091-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 198091 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198091 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251272 | 26003H | 3448J | LP1Y-APL(100)-198090-02-2 | LP1Y-APL(100)-198090-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS APL(100) (315) 198090 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198090 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251271 | 26003H | 3447J | LP1Y-APL(100)-198090-02-1 | LP1Y-APL(100)-198090-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS APL(100) (315) 198090 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198090 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251270 | 26003H | 3446J | LP1Y-APL(100)-198089-02-1 | LP1Y-APL(100)-198089-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS APL(100) (315) 198089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198089 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251269 | 26003H | 3445J | LP1Y-APL(100)-198085-02-1 | LP1Y-APL(100)-198085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS APL(100) (315) 198085 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198085 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251268 | 26003H | 3444J | LP1Y-APL(100)-198049-03-1 | LP1Y-APL(100)-198049-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251267 | 26003H | 3443J | LP1Y-APL(100)-198049-02-3 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251266 | 26003H | 3442J | LP1Y-APL(100)-198049-02-2 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251265 | 26003H | 3441J | LP1Y-APL(100)-198049-02-1 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251264 | 26003H | 3440J | LP1Y-APL(100)-198049-01-3 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251263 | 26003H | 3439J | LP1Y-APL(100)-198049-01-2 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251262 | 26003H | 3438J | LP1Y-APL(100)-198049-01-1 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251261 | 26003H | 3437J | LP1Y-APL(100)-019085-02-2 | LP1Y-APL(100)-019085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS APL(100) (315) 019085 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019085 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251260 | 26003H | 3436J | LP1Y-APL(100)-019085-02-1 | LP1Y-APL(100)-019085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS APL(100) (315) 019085 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019085 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251259 | 26003H | 3435J | LP1Y-APL(100)-019084-02-2 | LP1Y-APL(100)-019084-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS APL(100) (315) 019084 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019084 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251258 | 26003H | 3434J | LP1Y-APL(100)-019084-02-1 | LP1Y-APL(100)-019084-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS APL(100) (315) 019084 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019084 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251257 | 26003H | 3433J | LP1Y-APL(100)-019083-04-2 | LP1Y-APL(100)-019083-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 0.75" SS APL(100) (315) 019083 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251256 | 26003H | 3432J | LP1Y-APL(100)-019083-04-1 | LP1Y-APL(100)-019083-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 0.75" SS APL(100) (315) 019083 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251255 | 26003H | 3431J | LP1Y-APL(100)-019083-03-3 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251254 | 26003H | 3430J | LP1Y-APL(100)-019083-03-2 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251253 | 26003H | 3429J | LP1Y-APL(100)-019083-03-1 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P024 |  |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251252 | 26003H | 3428J | LP1Y-APL(100)-019082-06-3 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251251 | 26003H | 3427J | LP1Y-APL(100)-019082-06-2 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251250 | 26003H | 3426J | LP1Y-APL(100)-019082-06-1 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251249 | 26003H | 3425J | LP1Y-APL(100)-019082-05-1 | LP1Y-APL(100)-019082-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251248 | 26003H | 3424J | LP1Y-APL(100)-019082-04-2 | LP1Y-APL(100)-019082-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251247 | 26003H | 3423J | LP1Y-APL(100)-019082-04-1 | LP1Y-APL(100)-019082-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS APL(100) (315) 019082 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251246 | 26003H | 3422J | LP1Y-APL(100)-019081-06-3 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251245 | 26003H | 3421J | LP1Y-APL(100)-019081-06-2 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251244 | 26003H | 3420J | LP1Y-APL(100)-019081-06-1 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251243 | 26003H | 3419J | LP1Y-APL(100)-019081-05-1 | LP1Y-APL(100)-019081-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251242 | 26003H | 3418J | LP1Y-APL(100)-019081-04-2 | LP1Y-APL(100)-019081-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251241 | 26003H | 3417J | LP1Y-APL(100)-019081-04-1 | LP1Y-APL(100)-019081-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS APL(100) (315) 019081 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251240 | 26003H | 3416J | LP1Y-APL(100)-019078-06-2 | LP1Y-APL(100)-019078-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251239 | 26003H | 3415J | LP1Y-APL(100)-019078-06-1 | LP1Y-APL(100)-019078-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251238 | 26003H | 3414J | LP1Y-APL(100)-019078-05-1 | LP1Y-APL(100)-019078-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251237 | 26003H | 3413J | LP1Y-APL(100)-019078-04-1 | LP1Y-APL(100)-019078-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS APL(100) (315) 019078 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251236 | 26003H | 3412J | LP1Y-APL(100)-019077-04-1 | LP1Y-APL(100)-019077-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251235 | 26003H | 3411J | LP1Y-APL(100)-019077-03-4 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251234 | 26003H | 3410J | LP1Y-APL(100)-019077-03-3 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251233 | 26003H | 3409J | LP1Y-APL(100)-019077-03-2 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251232 | 26003H | 3408J | LP1Y-APL(100)-019077-03-1 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251231 | 26003H | 3407J | LP1Y-APL(100)-019077-02-5 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251230 | 26003H | 3406J | LP1Y-APL(100)-019077-02-4 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251229 | 26003H | 3405J | LP1Y-APL(100)-019077-02-3 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251228 | 26003H | 3404J | LP1Y-APL(100)-019077-02-2 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251227 | 26003H | 3403J | LP1Y-APL(100)-019077-02-1 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251226 | 26003H | 3402J | LP1Y-APL(100)-019049-04-3 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251225 | 26003H | 3401J | LP1Y-APL(100)-019049-04-2 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251224 | 26003H | 3400J | LP1Y-APL(100)-019049-04-1 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251223 | 26003H | 3399J | LP1Y-APL(100)-019049-02-1 | LP1Y-APL(100)-019049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251222 | 26003H | 3398J | LP1Y-APL(100)-019049-01-2 | LP1Y-APL(100)-019049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251221 | 26003H | 3397J | LP1Y-APL(100)-019049-01-1 | LP1Y-APL(100)-019049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251220 | 26003H | 3396J | LP1Y-APL(100)-019048-04-3 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251219 | 26003H | 3395J | LP1Y-APL(100)-019048-04-2 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251218 | 26003H | 3394J | LP1Y-APL(100)-019048-04-1 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251217 | 26003H | 3393J | LP1Y-APL(100)-019048-02-1 | LP1Y-APL(100)-019048-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251216 | 26003H | 3392J | LP1Y-APL(100)-019048-01-2 | LP1Y-APL(100)-019048-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251215 | 26003H | 3391J | LP1Y-APL(100)-019048-01-1 | LP1Y-APL(100)-019048-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251214 | 26003H | 3390J | LP1Y-APL(100)-019005-03-2 | LP1Y-APL(100)-019005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251213 | 26003H | 3389J | LP1Y-APL(100)-019005-03-1 | LP1Y-APL(100)-019005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251212 | 26003H | 3388J | LP1Y-APL(100)-019005-02-2 | LP1Y-APL(100)-019005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251211 | 26003H | 3387J | LP1Y-APL(100)-019005-02-1 | LP1Y-APL(100)-019005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251210 | 26003H | 3386J | LP1Y-AI(100)-199006-05-5 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251209 | 26003H | 3385J | LP1Y-AI(100)-199006-05-4 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251208 | 26003H | 3384J | LP1Y-AI(100)-199006-05-3 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251207 | 26003H | 3383J | LP1Y-AI(100)-199006-05-2 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251206 | 26003H | 3382J | LP1Y-AI(100)-199006-05-1 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251205 | 26003H | 3381J | LP1Y-AI(100)-199006-02-2 | LP1Y-AI(100)-199006-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251204 | 26003H | 3380J | LP1Y-AI(100)-199006-02-1 | LP1Y-AI(100)-199006-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251203 | 26003H | 3379J | LP1Y-AI(100)-199005-03-3 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251202 | 26003H | 3378J | LP1Y-AI(100)-199005-03-2 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251201 | 26003H | 3377J | LP1Y-AI(100)-199005-03-1 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251200 | 26003H | 3376J | LP1Y-AI(100)-199005-02-3 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251199 | 26003H | 3375J | LP1Y-AI(100)-199005-02-2 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251198 | 26003H | 3374J | LP1Y-AI(100)-199005-02-1 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251197 | 26003H | 3373J | LP1Y-AI(100)-199005-01-2 | LP1Y-AI(100)-199005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251196 | 26003H | 3372J | LP1Y-AI(100)-199005-01-1 | LP1Y-AI(100)-199005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 |  |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251195 | 26003H | 3371J | LP1Y-AI(100)-190023-01-2 | LP1Y-AI(100)-190023-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AI(100) (315) 190023 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-190023 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251194 | 26003H | 3370J | LP1Y-AI(100)-190023-01-1 | LP1Y-AI(100)-190023-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AI(100) (315) 190023 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-190023 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251193 | 26003H | 3369J | LP1Y-AI(100)-019064-02-1 | LP1Y-AI(100)-019064-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS AI(100) (315) 019064 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019064 |  | TFS00E016YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251192 | 26003H | 3368J | LP1Y-AI(100)-019062-02-2 | LP1Y-AI(100)-019062-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS AI(100) (315) 019062 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019062 |  | TFS00E015YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251191 | 26003H | 3367J | LP1Y-AI(100)-019062-02-1 | LP1Y-AI(100)-019062-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS AI(100) (315) 019062 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019062 |  | TFS00E015YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251190 | 26003H | 3366J | LP1Y-AI(100)-019025-02-3 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251189 | 26003H | 3365J | LP1Y-AI(100)-019025-02-2 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251188 | 26003H | 3364J | LP1Y-AI(100)-019025-02-1 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251187 | 26003H | 3363J | LP1Y-AF-162105-01-3 | LP1Y-AF-162105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251186 | 26003H | 3362J | LP1Y-AF-162105-01-2 | LP1Y-AF-162105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251185 | 26003H | 3361J | LP1Y-AF-162105-01-1 | LP1Y-AF-162105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251184 | 26003H | 3360J | LP1Y-AF-162003-06-3 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251183 | 26003H | 3359J | LP1Y-AF-162003-06-2 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251182 | 26003H | 3358J | LP1Y-AF-162003-06-1 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251181 | 26003H | 3357J | LP1Y-AF-162003-05-3 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251180 | 26003H | 3356J | LP1Y-AF-162003-05-2 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251179 | 26003H | 3355J | LP1Y-AF-162003-05-1 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251178 | 26003H | 3354J | LP1Y-AF-162003-04-3 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251177 | 26003H | 3353J | LP1Y-AF-162003-04-2 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251176 | 26003H | 3352J | LP1Y-AF-162003-04-1 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251175 | 26003H | 3351J | LP1Y-AF-162003-03-2 | LP1Y-AF-162003-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 1" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251174 | 26003H | 3350J | LP1Y-AF-162003-03-1 | LP1Y-AF-162003-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 1" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251173 | 26003H | 3349J | LP1Y-AF-162003-02-4 | LP1Y-AF-162003-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251172 | 26003H | 3348J | LP1Y-AF-162003-02-3 | LP1Y-AF-162003-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251171 | 26003H | 3347J | LP1Y-AF-162003-02-2 | LP1Y-AF-162003-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251170 | 26003H | 3346J | LP1Y-AF-162003-02-1 | LP1Y-AF-162003-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251169 | 26003H | 3345J | LP1Y-ACNDMSO-110813-02-2 | LP1Y-ACNDMSO-110813-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251168 | 26003H | 3344J | LP1Y-ACNDMSO-110813-02-1 | LP1Y-ACNDMSO-110813-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251167 | 26003H | 3343J | LP1Y-ACNDMSO-110813-01-2 | LP1Y-ACNDMSO-110813-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251166 | 26003H | 3342J | LP1Y-ACNDMSO-110813-01-1 | LP1Y-ACNDMSO-110813-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251165 | 26003H | 3341J | LP1Y-ACNDMSO-110810-04-3 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251164 | 26003H | 3340J | LP1Y-ACNDMSO-110810-04-2 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251163 | 26003H | 3339J | LP1Y-ACNDMSO-110810-04-1 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251162 | 26003H | 3338J | LP1Y-ACNDMSO-110810-03-4 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251161 | 26003H | 3337J | LP1Y-ACNDMSO-110810-03-3 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251160 | 26003H | 3336J | LP1Y-ACNDMSO-110810-03-2 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251159 | 26003H | 3335J | LP1Y-ACNDMSO-110810-03-1 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251158 | 26003H | 3334J | LP1Y-ACNDMSO-110810-01-1 | LP1Y-ACNDMSO-110810-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251157 | 26003H | 3333J | LP1Y-ACNDMSO-110805-07-3 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251156 | 26003H | 3332J | LP1Y-ACNDMSO-110805-07-2 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251155 | 26003H | 3331J | LP1Y-ACNDMSO-110805-07-1 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251154 | 26003H | 3330J | LP1Y-ACNDMSO-110805-06-1 | LP1Y-ACNDMSO-110805-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251153 | 26003H | 3329J | LP1Y-ACNDMSO-110805-05-3 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251152 | 26003H | 3328J | LP1Y-ACNDMSO-110805-05-2 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251151 | 26003H | 3327J | LP1Y-ACNDMSO-110805-05-1 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251150 | 26003H | 3326J | LP1Y-ACNDMSO-110805-03-2 | LP1Y-ACNDMSO-110805-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251149 | 26003H | 3325J | LP1Y-ACNDMSO-110805-03-1 | LP1Y-ACNDMSO-110805-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251148 | 26003H | 3324J | LP1Y-ACNDMSO-110805-02-2 | LP1Y-ACNDMSO-110805-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251147 | 26003H | 3323J | LP1Y-ACNDMSO-110805-02-1 | LP1Y-ACNDMSO-110805-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250887 | 26003H | 3322J | LP1Y-ACNDMSO-110805-01-4 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250886 | 26003H | 3321J | LP1Y-ACNDMSO-110805-01-3 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250885 | 26003H | 3320J | LP1Y-ACNDMSO-110805-01-2 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250884 | 26003H | 3319J | LP1Y-ACNDMSO-110805-01-1 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250883 | 26003H | 3318J | LP1Y-ACNDMSO-110803-02-3 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250882 | 26003H | 3317J | LP1Y-ACNDMSO-110803-02-2 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250881 | 26003H | 3316J | LP1Y-ACNDMSO-110803-02-1 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250880 | 26003H | 3315J | LP1Y-ACNDMSO-110803-01-3 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250879 | 26003H | 3314J | LP1Y-ACNDMSO-110803-01-2 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250878 | 26003H | 3313J | LP1Y-ACNDMSO-110803-01-1 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250877 | 26003H | 3312J | LP1Y-ACNDMSO-110610-02-3 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250876 | 26003H | 3311J | LP1Y-ACNDMSO-110610-02-2 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250875 | 26003H | 3310J | LP1Y-ACNDMSO-110610-02-1 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250874 | 26003H | 3309J | LP1Y-ACNDMSO-110610-01-1 | LP1Y-ACNDMSO-110610-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250873 | 26003H | 3308J | LP1Y-ACNDMSO-110605-04-4 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250872 | 26003H | 3307J | LP1Y-ACNDMSO-110605-04-3 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250871 | 26003H | 3306J | LP1Y-ACNDMSO-110605-04-2 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250870 | 26003H | 3305J | LP1Y-ACNDMSO-110605-04-1 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250869 | 26003H | 3304J | LP1Y-ACNDMSO-110605-03-3 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250868 | 26003H | 3303J | LP1Y-ACNDMSO-110605-03-2 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250867 | 26003H | 3302J | LP1Y-ACNDMSO-110605-03-1 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250866 | 26003H | 3301J | LP1Y-ACNDMSO-110605-01-1 | LP1Y-ACNDMSO-110605-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250865 | 26003H | 3300J | LP1Y-ACNDMSO-110604-07-4 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250864 | 26003H | 3299J | LP1Y-ACNDMSO-110604-07-3 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250863 | 26003H | 3298J | LP1Y-ACNDMSO-110604-07-2 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250862 | 26003H | 3297J | LP1Y-ACNDMSO-110604-07-1 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250861 | 26003H | 3296J | LP1Y-ACNDMSO-110604-06-2 | LP1Y-ACNDMSO-110604-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250860 | 26003H | 3295J | LP1Y-ACNDMSO-110604-06-1 | LP1Y-ACNDMSO-110604-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250859 | 26003H | 3294J | LP1Y-ACNDMSO-110604-05-1 | LP1Y-ACNDMSO-110604-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250858 | 26003H | 3293J | LP1Y-ACNDMSO-110604-04-2 | LP1Y-ACNDMSO-110604-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250857 | 26003H | 3292J | LP1Y-ACNDMSO-110604-04-1 | LP1Y-ACNDMSO-110604-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250856 | 26003H | 3291J | LP1Y-ACNDMSO-110604-03-2 | LP1Y-ACNDMSO-110604-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250855 | 26003H | 3290J | LP1Y-ACNDMSO-110604-03-1 | LP1Y-ACNDMSO-110604-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250854 | 26003H | 3289J | LP1Y-ACNDMSO-110603-02-4 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250853 | 26003H | 3288J | LP1Y-ACNDMSO-110603-02-3 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250852 | 26003H | 3287J | LP1Y-ACNDMSO-110603-02-2 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250851 | 26003H | 3286J | LP1Y-ACNDMSO-110603-02-1 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250850 | 26003H | 3285J | LP1Y-ACNDMSO-110603-01-3 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250849 | 26003H | 3284J | LP1Y-ACNDMSO-110603-01-2 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250848 | 26003H | 3283J | LP1Y-ACNDMSO-110603-01-1 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250847 | 26003H | 3282J | LP1Y-ACNDMSO-110027-01-4 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250846 | 26003H | 3281J | LP1Y-ACNDMSO-110027-01-3 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250845 | 26003H | 3280J | LP1Y-ACNDMSO-110027-01-2 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250844 | 26003H | 3279J | LP1Y-ACNDMSO-110027-01-1 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250843 | 26003H | 3278J | LP1Y-ACNDMSO-110005-03-1 | LP1Y-ACNDMSO-110005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250842 | 26003H | 3277J | LP1Y-ACNDMSO-110005-01-3 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250841 | 26003H | 3276J | LP1Y-ACNDMSO-110005-01-2 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250840 | 26003H | 3275J | LP1Y-ACNDMSO-110005-01-1 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250839 | 26003H | 3274J | LP1Y-ACNDMSO-110001-03-1 | LP1Y-ACNDMSO-110001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250838 | 26003H | 3273J | LP1Y-ACNDMSO-110001-01-3 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250837 | 26003H | 3272J | LP1Y-ACNDMSO-110001-01-2 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250836 | 26003H | 3271J | LP1Y-ACNDMSO-110001-01-1 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250835 | 26003H | 3270J | LP1Y-ACNDMSO-010027-04-3 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250834 | 26003H | 3269J | LP1Y-ACNDMSO-010027-04-2 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250833 | 26003H | 3268J | LP1Y-ACNDMSO-010027-04-1 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250832 | 26003H | 3267J | LP1Y-ACN-850013-06-2 | LP1Y-ACN-850013-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250831 | 26003H | 3266J | LP1Y-ACN-850013-06-1 | LP1Y-ACN-850013-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250830 | 26003H | 3265J | LP1Y-ACN-850013-05-4 | LP1Y-ACN-850013-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250829 | 26003H | 3264J | LP1Y-ACN-850013-05-3 | LP1Y-ACN-850013-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250828 | 26003H | 3263J | LP1Y-ACN-850013-05-2 | LP1Y-ACN-850013-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250827 | 26003H | 3262J | LP1Y-ACN-850013-05-1 | LP1Y-ACN-850013-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P013 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250826 | 26003H | 3261J | LP1Y-ACN-850013-04-2 | LP1Y-ACN-850013-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250825 | 26003H | 3260J | LP1Y-ACN-850013-04-1 | LP1Y-ACN-850013-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250824 | 26003H | 3259J | LP1Y-ACN-177302-05-6 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250823 | 26003H | 3258J | LP1Y-ACN-177302-05-5 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250822 | 26003H | 3257J | LP1Y-ACN-177302-05-4 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250821 | 26003H | 3256J | LP1Y-ACN-177302-05-3 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250820 | 26003H | 3255J | LP1Y-ACN-177302-05-2 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250819 | 26003H | 3254J | LP1Y-ACN-177302-05-1 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250818 | 26003H | 3253J | LP1Y-ACN-177302-04-2 | LP1Y-ACN-177302-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250817 | 26003H | 3252J | LP1Y-ACN-177302-04-1 | LP1Y-ACN-177302-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250816 | 26003H | 3251J | LP1Y-ACN-177302-03-4 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250815 | 26003H | 3250J | LP1Y-ACN-177302-03-3 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250814 | 26003H | 3249J | LP1Y-ACN-177302-03-2 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250813 | 26003H | 3248J | LP1Y-ACN-177302-03-1 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250812 | 26003H | 3247J | LP1Y-ACN-177302-02-2 | LP1Y-ACN-177302-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250811 | 26003H | 3246J | LP1Y-ACN-177302-02-1 | LP1Y-ACN-177302-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250810 | 26003H | 3245J | LP1Y-ACN-177301-03-1 | LP1Y-ACN-177301-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250809 | 26003H | 3244J | LP1Y-ACN-177301-02-2 | LP1Y-ACN-177301-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250808 | 26003H | 3243J | LP1Y-ACN-177301-02-1 | LP1Y-ACN-177301-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250807 | 26003H | 3242J | LP1Y-ACN-177301-01-4 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250806 | 26003H | 3241J | LP1Y-ACN-177301-01-3 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250805 | 26003H | 3240J | LP1Y-ACN-177301-01-2 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250804 | 26003H | 3239J | LP1Y-ACN-177301-01-1 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250803 | 26003H | 3238J | LP1Y-ACN-111212-03-3 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250802 | 26003H | 3237J | LP1Y-ACN-111212-03-2 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250801 | 26003H | 3236J | LP1Y-ACN-111212-03-1 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250800 | 26003H | 3235J | LP1Y-ACN-111212-01-1 | LP1Y-ACN-111212-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250799 | 26003H | 3234J | LP1Y-ACN-111211-03-1 | LP1Y-ACN-111211-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250798 | 26003H | 3233J | LP1Y-ACN-111211-01-3 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250797 | 26003H | 3232J | LP1Y-ACN-111211-01-2 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250796 | 26003H | 3231J | LP1Y-ACN-111211-01-1 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250795 | 26003H | 3230J | LP1Y-ACN-111207-04-3 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250794 | 26003H | 3229J | LP1Y-ACN-111207-04-2 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250793 | 26003H | 3228J | LP1Y-ACN-111207-04-1 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250792 | 26003H | 3227J | LP1Y-ACN-111207-03-3 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250791 | 26003H | 3226J | LP1Y-ACN-111207-03-2 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250790 | 26003H | 3225J | LP1Y-ACN-111207-03-1 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250789 | 26003H | 3224J | LP1Y-ACN-111207-01-2 | LP1Y-ACN-111207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250788 | 26003H | 3223J | LP1Y-ACN-111207-01-1 | LP1Y-ACN-111207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250787 | 26003H | 3222J | LP1Y-ACN-111205-07-3 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250786 | 26003H | 3221J | LP1Y-ACN-111205-07-2 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250785 | 26003H | 3220J | LP1Y-ACN-111205-07-1 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250784 | 26003H | 3219J | LP1Y-ACN-111205-06-3 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250783 | 26003H | 3218J | LP1Y-ACN-111205-06-2 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250782 | 26003H | 3217J | LP1Y-ACN-111205-06-1 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250781 | 26003H | 3216J | LP1Y-ACN-111205-05-1 | LP1Y-ACN-111205-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250780 | 26003H | 3215J | LP1Y-ACN-111205-04-1 | LP1Y-ACN-111205-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250779 | 26003H | 3214J | LP1Y-ACN-111205-03-2 | LP1Y-ACN-111205-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250778 | 26003H | 3213J | LP1Y-ACN-111205-03-1 | LP1Y-ACN-111205-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250777 | 26003H | 3212J | LP1Y-ACN-111203-02-3 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250776 | 26003H | 3211J | LP1Y-ACN-111203-02-2 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250775 | 26003H | 3210J | LP1Y-ACN-111203-02-1 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250774 | 26003H | 3209J | LP1Y-ACN-111203-01-3 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250773 | 26003H | 3208J | LP1Y-ACN-111203-01-2 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250772 | 26003H | 3207J | LP1Y-ACN-111203-01-1 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250771 | 26003H | 3206J | LP1Y-ACN-111003-07-5 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250770 | 26003H | 3205J | LP1Y-ACN-111003-07-4 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250769 | 26003H | 3204J | LP1Y-ACN-111003-07-3 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250768 | 26003H | 3203J | LP1Y-ACN-111003-07-2 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250767 | 26003H | 3202J | LP1Y-ACN-111003-07-1 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250766 | 26003H | 3201J | LP1Y-ACN-111003-06-4 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250765 | 26003H | 3200J | LP1Y-ACN-111003-06-3 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250764 | 26003H | 3199J | LP1Y-ACN-111003-06-2 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250763 | 26003H | 3198J | LP1Y-ACN-111003-06-1 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 |  |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250762 | 26003H | 3197J | LP1Y-ACN-111003-03-1 | LP1Y-ACN-111003-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250761 | 26003H | 3196J | LP1Y-ACN-111002-06-1 | LP1Y-ACN-111002-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250760 | 26003H | 3195J | LP1Y-ACN-111002-05-3 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250759 | 26003H | 3194J | LP1Y-ACN-111002-05-2 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250758 | 26003H | 3193J | LP1Y-ACN-111002-05-1 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250757 | 26003H | 3192J | LP1Y-ACN-107422-03-1 | LP1Y-ACN-107422-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250756 | 26003H | 3191J | LP1Y-ACN-107422-01-2 | LP1Y-ACN-107422-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250755 | 26003H | 3190J | LP1Y-ACN-107422-01-1 | LP1Y-ACN-107422-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250754 | 26003H | 3189J | LP1Y-ACN-107416-04-1 | LP1Y-ACN-107416-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P 107416 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107416 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250753 | 26003H | 3188J | LP1Y-ACN-107416-01-1 | LP1Y-ACN-107416-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P 107416 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107416 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250752 | 26003H | 3187J | LP1Y-ACN-107411-01-3 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250751 | 26003H | 3186J | LP1Y-ACN-107411-01-2 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250750 | 26003H | 3185J | LP1Y-ACN-107411-01-1 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250749 | 26003H | 3184J | LP1Y-ACN-107407-03-4 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250748 | 26003H | 3183J | LP1Y-ACN-107407-03-3 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250747 | 26003H | 3182J | LP1Y-ACN-107407-03-2 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250746 | 26003H | 3181J | LP1Y-ACN-107407-03-1 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250745 | 26003H | 3180J | LP1Y-ACN-107407-01-1 | LP1Y-ACN-107407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250744 | 26003H | 3179J | LP1Y-ACN-107405-06-1 | LP1Y-ACN-107405-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250743 | 26003H | 3178J | LP1Y-ACN-107405-04-2 | LP1Y-ACN-107405-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250742 | 26003H | 3177J | LP1Y-ACN-107405-04-1 | LP1Y-ACN-107405-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250741 | 26003H | 3176J | LP1Y-ACN-107405-03-1 | LP1Y-ACN-107405-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250740 | 26003H | 3175J | LP1Y-ACN-107405-02-4 | LP1Y-ACN-107405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250739 | 26003H | 3174J | LP1Y-ACN-107405-02-3 | LP1Y-ACN-107405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250738 | 26003H | 3173J | LP1Y-ACN-107405-02-2 | LP1Y-ACN-107405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250737 | 26003H | 3172J | LP1Y-ACN-107405-02-1 | LP1Y-ACN-107405-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250736 | 26003H | 3171J | LP1Y-ACN-107403-02-3 | LP1Y-ACN-107403-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250735 | 26003H | 3170J | LP1Y-ACN-107403-02-2 | LP1Y-ACN-107403-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250734 | 26003H | 3169J | LP1Y-ACN-107403-02-1 | LP1Y-ACN-107403-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250733 | 26003H | 3168J | LP1Y-ACN-107403-01-1 | LP1Y-ACN-107403-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250732 | 26003H | 3167J | LP1Y-ACN-107308-01-1 | LP1Y-ACN-107308-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107308 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107308 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250731 | 26003H | 3166J | LP1Y-ACN-107306-01-4 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250730 | 26003H | 3165J | LP1Y-ACN-107306-01-3 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250729 | 26003H | 3164J | LP1Y-ACN-107306-01-2 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250728 | 26003H | 3163J | LP1Y-ACN-107306-01-1 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250727 | 26003H | 3162J | LP1Y-ACN-107305-04-1 | LP1Y-ACN-107305-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250726 | 26003H | 3161J | LP1Y-ACN-107305-03-1 | LP1Y-ACN-107305-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250725 | 26003H | 3160J | LP1Y-ACN-107305-02-1 | LP1Y-ACN-107305-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250724 | 26003H | 3159J | LP1Y-ACN-107305-01-5 | LP1Y-ACN-107305-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250723 | 26003H | 3158J | LP1Y-ACN-107305-01-4 | LP1Y-ACN-107305-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250722 | 26003H | 3157J | LP1Y-ACN-107305-01-3 | LP1Y-ACN-107305-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250721 | 26003H | 3156J | LP1Y-ACN-107305-01-2 | LP1Y-ACN-107305-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250720 | 26003H | 3155J | LP1Y-ACN-107305-01-1 | LP1Y-ACN-107305-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250719 | 26003H | 3154J | LP1Y-ACN-107303-02-3 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250718 | 26003H | 3153J | LP1Y-ACN-107303-02-2 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250717 | 26003H | 3152J | LP1Y-ACN-107303-02-1 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250716 | 26003H | 3151J | LP1Y-ACN-107303-01-2 | LP1Y-ACN-107303-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250715 | 26003H | 3150J | LP1Y-ACN-107303-01-1 | LP1Y-ACN-107303-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250714 | 26003H | 3149J | LP1Y-ACN-107302-03-1 | LP1Y-ACN-107302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107302 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107302 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250713 | 26003H | 3148J | LP1Y-ACN-107302-01-1 | LP1Y-ACN-107302-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107302 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107302 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250712 | 26003H | 3147J | LP1Y-ACN-107217-01-2 | LP1Y-ACN-107217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107217 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107217 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250711 | 26003H | 3146J | LP1Y-ACN-107217-01-1 | LP1Y-ACN-107217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107217 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107217 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250710 | 26003H | 3145J | LP1Y-ACN-107216-04-1 | LP1Y-ACN-107216-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107216 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107216 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250709 | 26003H | 3144J | LP1Y-ACN-107216-01-1 | LP1Y-ACN-107216-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107216 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107216 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250708 | 26003H | 3143J | LP1Y-ACN-107206-01-4 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250707 | 26003H | 3142J | LP1Y-ACN-107206-01-3 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250706 | 26003H | 3141J | LP1Y-ACN-107206-01-2 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250705 | 26003H | 3140J | LP1Y-ACN-107206-01-1 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250704 | 26003H | 3139J | LP1Y-ACN-107204-05-1 | LP1Y-ACN-107204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250703 | 26003H | 3138J | LP1Y-ACN-107204-03-1 | LP1Y-ACN-107204-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250702 | 26003H | 3137J | LP1Y-ACN-107204-02-1 | LP1Y-ACN-107204-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250701 | 26003H | 3136J | LP1Y-ACN-107204-01-6 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250700 | 26003H | 3135J | LP1Y-ACN-107204-01-5 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250699 | 26003H | 3134J | LP1Y-ACN-107204-01-4 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250698 | 26003H | 3133J | LP1Y-ACN-107204-01-3 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250697 | 26003H | 3132J | LP1Y-ACN-107204-01-2 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250696 | 26003H | 3131J | LP1Y-ACN-107204-01-1 | LP1Y-ACN-107204-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250695 | 26003H | 3130J | LP1Y-ACN-107203-02-3 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250694 | 26003H | 3129J | LP1Y-ACN-107203-02-2 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250693 | 26003H | 3128J | LP1Y-ACN-107203-02-1 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250692 | 26003H | 3127J | LP1Y-ACN-107203-01-2 | LP1Y-ACN-107203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250691 | 26003H | 3126J | LP1Y-ACN-107203-01-1 | LP1Y-ACN-107203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250690 | 26003H | 3125J | LP1Y-ACN-107202-02-7 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250689 | 26003H | 3124J | LP1Y-ACN-107202-02-6 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250688 | 26003H | 3123J | LP1Y-ACN-107202-02-5 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250687 | 26003H | 3122J | LP1Y-ACN-107202-02-4 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250686 | 26003H | 3121J | LP1Y-ACN-107202-02-3 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250685 | 26003H | 3120J | LP1Y-ACN-107202-02-2 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250684 | 26003H | 3119J | LP1Y-ACN-107202-02-1 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250683 | 26003H | 3118J | LP1Y-ACN-107117-04-1 | LP1Y-ACN-107117-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250682 | 26003H | 3117J | LP1Y-ACN-107117-01-2 | LP1Y-ACN-107117-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250681 | 26003H | 3116J | LP1Y-ACN-107117-01-1 | LP1Y-ACN-107117-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250680 | 26003H | 3115J | LP1Y-ACN-107116-01-3 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250679 | 26003H | 3114J | LP1Y-ACN-107116-01-2 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250678 | 26003H | 3113J | LP1Y-ACN-107116-01-1 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250677 | 26003H | 3112J | LP1Y-ACN-107106-01-4 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250676 | 26003H | 3111J | LP1Y-ACN-107106-01-3 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250675 | 26003H | 3110J | LP1Y-ACN-107106-01-2 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250674 | 26003H | 3109J | LP1Y-ACN-107106-01-1 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250673 | 26003H | 3108J | LP1Y-ACN-107105-05-6 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250672 | 26003H | 3107J | LP1Y-ACN-107105-05-5 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250671 | 26003H | 3106J | LP1Y-ACN-107105-05-4 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250670 | 26003H | 3105J | LP1Y-ACN-107105-05-3 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250669 | 26003H | 3104J | LP1Y-ACN-107105-05-2 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250668 | 26003H | 3103J | LP1Y-ACN-107105-05-1 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250667 | 26003H | 3102J | LP1Y-ACN-107105-03-2 | LP1Y-ACN-107105-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250666 | 26003H | 3101J | LP1Y-ACN-107105-03-1 | LP1Y-ACN-107105-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250665 | 26003H | 3100J | LP1Y-ACN-107105-02-3 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250664 | 26003H | 3099J | LP1Y-ACN-107105-02-2 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250663 | 26003H | 3098J | LP1Y-ACN-107105-02-1 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250662 | 26003H | 3097J | LP1Y-ACN-107105-01-6 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250661 | 26003H | 3096J | LP1Y-ACN-107105-01-5 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250660 | 26003H | 3095J | LP1Y-ACN-107105-01-4 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250659 | 26003H | 3094J | LP1Y-ACN-107105-01-3 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250658 | 26003H | 3093J | LP1Y-ACN-107105-01-2 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250657 | 26003H | 3092J | LP1Y-ACN-107105-01-1 | LP1Y-ACN-107105-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250656 | 26003H | 3091J | LP1Y-ACN-107103-02-4 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250655 | 26003H | 3090J | LP1Y-ACN-107103-02-3 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250654 | 26003H | 3089J | LP1Y-ACN-107103-02-2 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250653 | 26003H | 3088J | LP1Y-ACN-107103-02-1 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250652 | 26003H | 3087J | LP1Y-ACN-107103-01-2 | LP1Y-ACN-107103-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250651 | 26003H | 3086J | LP1Y-ACN-107103-01-1 | LP1Y-ACN-107103-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250650 | 26003H | 3085J | LP1Y-ACN-107102-02-7 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250649 | 26003H | 3084J | LP1Y-ACN-107102-02-6 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250648 | 26003H | 3083J | LP1Y-ACN-107102-02-5 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250647 | 26003H | 3082J | LP1Y-ACN-107102-02-4 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250646 | 26003H | 3081J | LP1Y-ACN-107102-02-3 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250645 | 26003H | 3080J | LP1Y-ACN-107102-02-2 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250644 | 26003H | 3079J | LP1Y-ACN-107102-02-1 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250643 | 26003H | 3078J | LP1Y-ACN-107012-04-2 | LP1Y-ACN-107012-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 4" SS ACN (315) P (108) 107012 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250642 | 26003H | 3077J | LP1Y-ACN-107012-04-1 | LP1Y-ACN-107012-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 4" SS ACN (315) P (108) 107012 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250641 | 26003H | 3076J | LP1Y-ACN-063302-07-1 | LP1Y-ACN-063302-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P019 |  |  | LP1Y 3" SS ACN (315) P 063302 | ACN |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-063302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250640 | 26003H | 3075J | LP1Y-ACN-011014-02-1 | LP1Y-ACN-011014-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS ACN (315) P (108) 011014 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011014 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250639 | 26003H | 3074J | LP1Y-ACN-011012-02-1 | LP1Y-ACN-011012-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 4" SS ACN (315) P (108) 011012 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250443 | 26003H | 3073D | LP1Y-WV-175013-06-3 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250442 | 26003H | 3072D | LP1Y-WV-175013-06-2 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250441 | 26003H | 3071D | LP1Y-WV-175013-06-1 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250440 | 26003H | 3070D | LP1Y-WV-175013-05-4 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250439 | 26003H | 3069D | LP1Y-WV-175013-05-3 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250438 | 26003H | 3068D | LP1Y-WV-175013-05-2 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250437 | 26003H | 3067D | LP1Y-WV-175013-05-1 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250436 | 26003H | 3066D | LP1Y-WV-175013-04-2 | LP1Y-WV-175013-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250435 | 26003H | 3065D | LP1Y-WV-175013-04-1 | LP1Y-WV-175013-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250434 | 26003H | 3064J | LP1Y-WV-101715-01-2 | LP1Y-WV-101715-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS WV (315) (108) 101715 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101715 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250433 | 26003H | 3063J | LP1Y-WV-101715-01-1 | LP1Y-WV-101715-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS WV (315) (108) 101715 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101715 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250432 | 26003H | 3062J | LP1Y-WV-101616-01-2 | LP1Y-WV-101616-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS WV (315) (108) 101616 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101616 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250431 | 26003H | 3061J | LP1Y-WV-101616-01-1 | LP1Y-WV-101616-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS WV (315) (108) 101616 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101616 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250430 | 26003H | 3060D | LP1Y-WV-101615-03-3 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250429 | 26003H | 3059D | LP1Y-WV-101615-03-2 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250428 | 26003H | 3058D | LP1Y-WV-101615-03-1 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250427 | 26003H | 3057J | LP1Y-WV-101313-01-4 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250426 | 26003H | 3056J | LP1Y-WV-101313-01-3 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250425 | 26003H | 3055J | LP1Y-WV-101313-01-2 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250424 | 26003H | 3054J | LP1Y-WV-101313-01-1 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250423 | 26003H | 3053J | LP1Y-WV-101113-01-4 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250422 | 26003H | 3052J | LP1Y-WV-101113-01-3 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250421 | 26003H | 3051J | LP1Y-WV-101113-01-2 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250420 | 26003H | 3050J | LP1Y-WV-101113-01-1 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250419 | 26003H | 3049D | LP1Y-WV-101015-01-5 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250418 | 26003H | 3048D | LP1Y-WV-101015-01-4 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250417 | 26003H | 3047D | LP1Y-WV-101015-01-3 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250416 | 26003H | 3046D | LP1Y-WV-101015-01-2 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250415 | 26003H | 3045D | LP1Y-WV-101015-01-1 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250414 | 26003H | 3044J | LP1Y-WV-100407-01-2 | LP1Y-WV-100407-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS WV (315) (108) 100407 | WV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100407 |  | TFS00D003YSPP |  | 315-WV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250413 | 26003H | 3043J | LP1Y-WV-100407-01-1 | LP1Y-WV-100407-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS WV (315) (108) 100407 | WV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100407 |  | TFS00D003YSPP |  | 315-WV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250412 | 26003H | 3042D | LP1Y-WV-061046-30-2 | LP1Y-WV-061046-30 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 061046 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-061046 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250411 | 26003H | 3041D | LP1Y-WV-061046-30-1 | LP1Y-WV-061046-30 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" DUP WV (344) (108) 061046 | WV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-061046 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250410 | 26003H | 3040J | LP1Y-WTFAP-109208-03-1 | LP1Y-WTFAP-109208-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109208 | WTFAP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250409 | 26003H | 3039J | LP1Y-WTFAP-109208-01-7 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250408 | 26003H | 3038J | LP1Y-WTFAP-109208-01-6 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250407 | 26003H | 3037J | LP1Y-WTFAP-109208-01-5 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250406 | 26003H | 3036J | LP1Y-WTFAP-109208-01-4 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250405 | 26003H | 3035J | LP1Y-WTFAP-109208-01-3 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250404 | 26003H | 3034J | LP1Y-WTFAP-109208-01-2 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250403 | 26003H | 3033J | LP1Y-WTFAP-109208-01-1 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250402 | 26003H | 3032J | LP1Y-WTFAP-109116-03-3 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250401 | 26003H | 3031J | LP1Y-WTFAP-109116-03-2 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250400 | 26003H | 3030J | LP1Y-WTFAP-109116-03-1 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250399 | 26003H | 3029J | LP1Y-WTFAP-109116-01-3 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250398 | 26003H | 3028J | LP1Y-WTFAP-109116-01-2 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250397 | 26003H | 3027J | LP1Y-WTFAP-109116-01-1 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250396 | 26003H | 3026J | LP1Y-WTFAP-109105-05-4 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250395 | 26003H | 3025J | LP1Y-WTFAP-109105-05-3 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250394 | 26003H | 3024J | LP1Y-WTFAP-109105-05-2 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250393 | 26003H | 3023J | LP1Y-WTFAP-109105-05-1 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250392 | 26003H | 3022J | LP1Y-WTFAP-109105-02-3 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250391 | 26003H | 3021J | LP1Y-WTFAP-109105-02-2 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250390 | 26003H | 3020J | LP1Y-WTFAP-109105-02-1 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250389 | 26003H | 3019J | LP1Y-WTFAP-109105-01-3 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250388 | 26003H | 3018J | LP1Y-WTFAP-109105-01-2 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250387 | 26003H | 3017J | LP1Y-WTFAP-109105-01-1 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250386 | 26003H | 3016J | LP1Y-WTFAP-109103-02-2 | LP1Y-WTFAP-109103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250385 | 26003H | 3015J | LP1Y-WTFAP-109103-02-1 | LP1Y-WTFAP-109103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250384 | 26003H | 3014J | LP1Y-WTFAP-109103-01-3 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250383 | 26003H | 3013J | LP1Y-WTFAP-109103-01-2 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250382 | 26003H | 3012J | LP1Y-WTFAP-109103-01-1 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250381 | 26003H | 3011J | LP1Y-WTFAP-014006-03-7 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250380 | 26003H | 3010J | LP1Y-WTFAP-014006-03-6 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250379 | 26003H | 3009J | LP1Y-WTFAP-014006-03-5 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250378 | 26003H | 3008J | LP1Y-WTFAP-014006-03-4 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250377 | 26003H | 3007J | LP1Y-WTFAP-014006-03-3 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250376 | 26003H | 3006J | LP1Y-WTFAP-014006-03-2 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250375 | 26003H | 3005J | LP1Y-WTFAP-014006-03-1 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250374 | 26003H | 3004J | LP1Y-WPC-194111-01-5 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250373 | 26003H | 3003J | LP1Y-WPC-194111-01-4 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250372 | 26003H | 3002J | LP1Y-WPC-194111-01-3 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250371 | 26003H | 3001J | LP1Y-WPC-194111-01-2 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250370 | 26003H | 3000J | LP1Y-WPC-194111-01-1 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250369 | 26003H | 2999J | LP1Y-WPC-194109-01-8 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250368 | 26003H | 2998J | LP1Y-WPC-194109-01-7 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250367 | 26003H | 2997J | LP1Y-WPC-194109-01-6 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250366 | 26003H | 2996J | LP1Y-WPC-194109-01-5 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250365 | 26003H | 2995J | LP1Y-WPC-194109-01-4 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250364 | 26003H | 2994J | LP1Y-WPC-194109-01-3 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250363 | 26003H | 2993J | LP1Y-WPC-194109-01-2 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250362 | 26003H | 2992J | LP1Y-WPC-194109-01-1 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250361 | 26003H | 2991J | LP1Y-WPC-194106-01-9 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250360 | 26003H | 2990J | LP1Y-WPC-194106-01-8 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250359 | 26003H | 2989J | LP1Y-WPC-194106-01-7 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250358 | 26003H | 2988J | LP1Y-WPC-194106-01-6 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250357 | 26003H | 2987J | LP1Y-WPC-194106-01-5 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250356 | 26003H | 2986J | LP1Y-WPC-194106-01-4 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250355 | 26003H | 2985J | LP1Y-WPC-194106-01-3 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250354 | 26003H | 2984J | LP1Y-WPC-194106-01-2 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250353 | 26003H | 2983J | LP1Y-WPC-194106-01-1 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250352 | 26003H | 2982J | LP1Y-WPC-194105-04-9 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250351 | 26003H | 2981J | LP1Y-WPC-194105-04-8 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250350 | 26003H | 2980J | LP1Y-WPC-194105-04-7 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250349 | 26003H | 2979J | LP1Y-WPC-194105-04-6 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250348 | 26003H | 2978J | LP1Y-WPC-194105-04-5 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250347 | 26003H | 2977J | LP1Y-WPC-194105-04-4 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250346 | 26003H | 2976J | LP1Y-WPC-194105-04-3 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250345 | 26003H | 2975J | LP1Y-WPC-194105-04-2 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250344 | 26003H | 2974J | LP1Y-WPC-194105-04-1 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250343 | 26003H | 2973J | LP1Y-WPC-194105-01-6 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250342 | 26003H | 2972J | LP1Y-WPC-194105-01-5 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250341 | 26003H | 2971J | LP1Y-WPC-194105-01-4 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250340 | 26003H | 2970J | LP1Y-WPC-194105-01-3 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250339 | 26003H | 2969J | LP1Y-WPC-194105-01-2 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250338 | 26003H | 2968J | LP1Y-WPC-194105-01-1 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250337 | 26003H | 2967J | LP1Y-WPC-194030-02-5 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250336 | 26003H | 2966J | LP1Y-WPC-194030-02-4 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250335 | 26003H | 2965J | LP1Y-WPC-194030-02-3 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250334 | 26003H | 2964J | LP1Y-WPC-194030-02-2 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250333 | 26003H | 2963J | LP1Y-WPC-194030-02-1 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250332 | 26003H | 2962J | LP1Y-WPC-194030-01-6 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250331 | 26003H | 2961J | LP1Y-WPC-194030-01-5 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.8925 | 7.16 | sq ft | 7.16 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250330 | 26003H | 2960J | LP1Y-WPC-194030-01-4 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2313 | 1.22 | sq ft | 1.22 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250329 | 26003H | 2959J | LP1Y-WPC-194030-01-3 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2 | 0.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250328 | 26003H | 2958J | LP1Y-WPC-194030-01-2 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.8263 | 5.99 | sq ft | 5.99 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250327 | 26003H | 2957J | LP1Y-WPC-194030-01-1 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.4963 | 5.87 | sq ft | 5.87 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250326 | 26003H | 2956J | LP1Y-WPC-194029-02-5 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250325 | 26003H | 2955J | LP1Y-WPC-194029-02-4 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250324 | 26003H | 2954J | LP1Y-WPC-194029-02-3 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250323 | 26003H | 2953J | LP1Y-WPC-194029-02-2 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250322 | 26003H | 2952J | LP1Y-WPC-194029-02-1 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250321 | 26003H | 2951J | LP1Y-WPC-194029-01-5 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250320 | 26003H | 2950J | LP1Y-WPC-194029-01-4 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250319 | 26003H | 2949J | LP1Y-WPC-194029-01-3 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250318 | 26003H | 2948J | LP1Y-WPC-194029-01-2 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250317 | 26003H | 2947J | LP1Y-WPC-194029-01-1 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250316 | 26003H | 2946J | LP1Y-WPC-194028-02-4 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250315 | 26003H | 2945J | LP1Y-WPC-194028-02-3 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250314 | 26003H | 2944J | LP1Y-WPC-194028-02-2 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250313 | 26003H | 2943J | LP1Y-WPC-194028-02-1 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250312 | 26003H | 2942J | LP1Y-WPC-194028-01-5 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250311 | 26003H | 2941J | LP1Y-WPC-194028-01-4 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250310 | 26003H | 2940J | LP1Y-WPC-194028-01-3 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250309 | 26003H | 2939J | LP1Y-WPC-194028-01-2 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250308 | 26003H | 2938J | LP1Y-WPC-194028-01-1 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250307 | 26003H | 2937J | LP1Y-WPC-194027-02-6 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250306 | 26003H | 2936J | LP1Y-WPC-194027-02-5 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250305 | 26003H | 2935J | LP1Y-WPC-194027-02-4 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250304 | 26003H | 2934J | LP1Y-WPC-194027-02-3 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250303 | 26003H | 2933J | LP1Y-WPC-194027-02-2 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250302 | 26003H | 2932J | LP1Y-WPC-194027-02-1 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250301 | 26003H | 2931J | LP1Y-WPC-194027-01-11 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250300 | 26003H | 2930J | LP1Y-WPC-194027-01-10 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250299 | 26003H | 2929J | LP1Y-WPC-194027-01-9 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250298 | 26003H | 2928J | LP1Y-WPC-194027-01-8 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250297 | 26003H | 2927J | LP1Y-WPC-194027-01-7 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250296 | 26003H | 2926J | LP1Y-WPC-194027-01-6 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250295 | 26003H | 2925J | LP1Y-WPC-194027-01-5 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250294 | 26003H | 2924J | LP1Y-WPC-194027-01-4 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250293 | 26003H | 2923J | LP1Y-WPC-194027-01-3 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250292 | 26003H | 2922J | LP1Y-WPC-194027-01-2 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250291 | 26003H | 2921J | LP1Y-WPC-194027-01-1 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250290 | 26003H | 2920J | LP1Y-WPC-194013-02-2 | LP1Y-WPC-194013-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250289 | 26003H | 2919J | LP1Y-WPC-194013-02-1 | LP1Y-WPC-194013-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250288 | 26003H | 2918J | LP1Y-WPC-194013-01-10 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250287 | 26003H | 2917J | LP1Y-WPC-194013-01-9 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250286 | 26003H | 2916J | LP1Y-WPC-194013-01-8 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250285 | 26003H | 2915J | LP1Y-WPC-194013-01-7 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250284 | 26003H | 2914J | LP1Y-WPC-194013-01-6 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250283 | 26003H | 2913J | LP1Y-WPC-194013-01-5 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250282 | 26003H | 2912J | LP1Y-WPC-194013-01-4 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250281 | 26003H | 2911J | LP1Y-WPC-194013-01-3 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250280 | 26003H | 2910J | LP1Y-WPC-194013-01-2 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250279 | 26003H | 2909J | LP1Y-WPC-194013-01-1 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250278 | 26003H | 2908J | LP1Y-WPC-194012-01-7 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250277 | 26003H | 2907J | LP1Y-WPC-194012-01-6 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250276 | 26003H | 2906J | LP1Y-WPC-194012-01-5 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250275 | 26003H | 2905J | LP1Y-WPC-194012-01-4 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250274 | 26003H | 2904J | LP1Y-WPC-194012-01-3 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250273 | 26003H | 2903J | LP1Y-WPC-194012-01-2 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250272 | 26003H | 2902J | LP1Y-WPC-194012-01-1 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250271 | 26003H | 2901J | LP1Y-WPC-194008-01-8 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250270 | 26003H | 2900J | LP1Y-WPC-194008-01-7 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250269 | 26003H | 2899J | LP1Y-WPC-194008-01-6 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250268 | 26003H | 2898J | LP1Y-WPC-194008-01-5 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250267 | 26003H | 2897J | LP1Y-WPC-194008-01-4 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250266 | 26003H | 2896J | LP1Y-WPC-194008-01-3 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250265 | 26003H | 2895J | LP1Y-WPC-194008-01-2 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250264 | 26003H | 2894J | LP1Y-WPC-194008-01-1 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250263 | 26003H | 2893J | LP1Y-WPC-194007-01-8 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250262 | 26003H | 2892J | LP1Y-WPC-194007-01-7 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250261 | 26003H | 2891J | LP1Y-WPC-194007-01-6 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250260 | 26003H | 2890J | LP1Y-WPC-194007-01-5 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250259 | 26003H | 2889J | LP1Y-WPC-194007-01-4 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250258 | 26003H | 2888J | LP1Y-WPC-194007-01-3 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250257 | 26003H | 2887J | LP1Y-WPC-194007-01-2 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250256 | 26003H | 2886J | LP1Y-WPC-194007-01-1 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250255 | 26003H | 2885J | LP1Y-WPC-194006-04-10 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250254 | 26003H | 2884J | LP1Y-WPC-194006-04-9 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250253 | 26003H | 2883J | LP1Y-WPC-194006-04-8 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250252 | 26003H | 2882J | LP1Y-WPC-194006-04-7 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250251 | 26003H | 2881J | LP1Y-WPC-194006-04-6 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250250 | 26003H | 2880J | LP1Y-WPC-194006-04-5 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250249 | 26003H | 2879J | LP1Y-WPC-194006-04-4 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250248 | 26003H | 2878J | LP1Y-WPC-194006-04-3 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250247 | 26003H | 2877J | LP1Y-WPC-194006-04-2 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250246 | 26003H | 2876J | LP1Y-WPC-194006-04-1 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250245 | 26003H | 2875J | LP1Y-WPC-194006-01-6 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250244 | 26003H | 2874J | LP1Y-WPC-194006-01-5 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250243 | 26003H | 2873J | LP1Y-WPC-194006-01-4 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250242 | 26003H | 2872J | LP1Y-WPC-194006-01-3 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250241 | 26003H | 2871J | LP1Y-WPC-194006-01-2 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250240 | 26003H | 2870J | LP1Y-WPC-194006-01-1 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250239 | 26003H | 2869J | LP1Y-WPC-194003-02-6 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250238 | 26003H | 2868J | LP1Y-WPC-194003-02-5 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250237 | 26003H | 2867J | LP1Y-WPC-194003-02-4 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250236 | 26003H | 2866J | LP1Y-WPC-194003-02-3 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250235 | 26003H | 2865J | LP1Y-WPC-194003-02-2 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250234 | 26003H | 2864J | LP1Y-WPC-194003-02-1 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250233 | 26003H | 2863J | LP1Y-WPC-194003-01-7 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250232 | 26003H | 2862J | LP1Y-WPC-194003-01-6 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250231 | 26003H | 2861J | LP1Y-WPC-194003-01-5 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250230 | 26003H | 2860J | LP1Y-WPC-194003-01-4 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250229 | 26003H | 2859J | LP1Y-WPC-194003-01-3 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250228 | 26003H | 2858J | LP1Y-WPC-194003-01-2 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250227 | 26003H | 2857J | LP1Y-WPC-194003-01-1 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250226 | 26003H | 2856J | LP1Y-WPC-194002-02-3 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250225 | 26003H | 2855J | LP1Y-WPC-194002-02-2 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250224 | 26003H | 2854J | LP1Y-WPC-194002-02-1 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250223 | 26003H | 2853J | LP1Y-WPC-194002-01-5 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250222 | 26003H | 2852J | LP1Y-WPC-194002-01-4 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250221 | 26003H | 2851J | LP1Y-WPC-194002-01-3 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250220 | 26003H | 2850J | LP1Y-WPC-194002-01-2 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250219 | 26003H | 2849J | LP1Y-WPC-194002-01-1 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250218 | 26003H | 2848J | LP1Y-WPC-033054-02-7 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250217 | 26003H | 2847J | LP1Y-WPC-033054-02-6 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 6.25 | 0 | 6.25 | 17.8025 | 12.32 | sq ft | 1.32 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250216 | 26003H | 2846J | LP1Y-WPC-033054-02-5 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 6 | 10 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250215 | 26003H | 2845J | LP1Y-WPC-033054-02-4 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.545 | 2.48 | sq ft | 2.48 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250214 | 26003H | 2844J | LP1Y-WPC-033054-02-3 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.8475 | 2.59 | sq ft | 2.59 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250213 | 26003H | 2843J | LP1Y-WPC-033054-02-2 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7713 | 1.81 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250212 | 26003H | 2842J | LP1Y-WPC-033054-02-1 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.0275 | 8.34 | sq ft | 8.34 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250211 | 26003H | 2841J | LP1Y-WPC-017071-01-16 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250210 | 26003H | 2840J | LP1Y-WPC-017071-01-15 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250209 | 26003H | 2839J | LP1Y-WPC-017071-01-14 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250208 | 26003H | 2838J | LP1Y-WPC-017071-01-13 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250207 | 26003H | 2837J | LP1Y-WPC-017071-01-12 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250206 | 26003H | 2836J | LP1Y-WPC-017071-01-11 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250205 | 26003H | 2835J | LP1Y-WPC-017071-01-10 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250204 | 26003H | 2834J | LP1Y-WPC-017071-01-9 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250203 | 26003H | 2833J | LP1Y-WPC-017071-01-8 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250202 | 26003H | 2832J | LP1Y-WPC-017071-01-7 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250201 | 26003H | 2831J | LP1Y-WPC-017071-01-6 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250200 | 26003H | 2830J | LP1Y-WPC-017071-01-5 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250199 | 26003H | 2829J | LP1Y-WPC-017071-01-4 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250198 | 26003H | 2828J | LP1Y-WPC-017071-01-3 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250197 | 26003H | 2827J | LP1Y-WPC-017071-01-2 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250196 | 26003H | 2826J | LP1Y-WPC-017071-01-1 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250195 | 26003H | 2825J | LP1Y-WPC-017064-05-8 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250194 | 26003H | 2824J | LP1Y-WPC-017064-05-7 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250193 | 26003H | 2823J | LP1Y-WPC-017064-05-6 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250192 | 26003H | 2822J | LP1Y-WPC-017064-05-5 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250191 | 26003H | 2821J | LP1Y-WPC-017064-05-4 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250190 | 26003H | 2820J | LP1Y-WPC-017064-05-3 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250189 | 26003H | 2819J | LP1Y-WPC-017064-05-2 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250188 | 26003H | 2818J | LP1Y-WPC-017064-05-1 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250187 | 26003H | 2817J | LP1Y-WPC-017061-08-8 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250186 | 26003H | 2816J | LP1Y-WPC-017061-08-7 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250185 | 26003H | 2815J | LP1Y-WPC-017061-08-6 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250184 | 26003H | 2814J | LP1Y-WPC-017061-08-5 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250183 | 26003H | 2813J | LP1Y-WPC-017061-08-4 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250182 | 26003H | 2812J | LP1Y-WPC-017061-08-3 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250181 | 26003H | 2811J | LP1Y-WPC-017061-08-2 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250180 | 26003H | 2810J | LP1Y-WPC-017061-08-1 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250179 | 26003H | 2809J | LP1Y-WPC-017051-01-7 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250178 | 26003H | 2808J | LP1Y-WPC-017051-01-6 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250177 | 26003H | 2807J | LP1Y-WPC-017051-01-5 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250176 | 26003H | 2806J | LP1Y-WPC-017051-01-4 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250175 | 26003H | 2805J | LP1Y-WPC-017051-01-3 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250174 | 26003H | 2804J | LP1Y-WPC-017051-01-2 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250173 | 26003H | 2803J | LP1Y-WPC-017051-01-1 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250172 | 26003H | 2802J | LP1Y-WPC-017050-02-11 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250171 | 26003H | 2801J | LP1Y-WPC-017050-02-10 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250170 | 26003H | 2800J | LP1Y-WPC-017050-02-9 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250169 | 26003H | 2799J | LP1Y-WPC-017050-02-8 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250168 | 26003H | 2798J | LP1Y-WPC-017050-02-7 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250167 | 26003H | 2797J | LP1Y-WPC-017050-02-6 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250166 | 26003H | 2796J | LP1Y-WPC-017050-02-5 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250165 | 26003H | 2795J | LP1Y-WPC-017050-02-4 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250164 | 26003H | 2794J | LP1Y-WPC-017050-02-3 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250163 | 26003H | 2793J | LP1Y-WPC-017050-02-2 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250162 | 26003H | 2792J | LP1Y-WPC-017050-02-1 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250161 | 26003H | 2791J | LP1Y-WPC-017042-03-6 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250160 | 26003H | 2790J | LP1Y-WPC-017042-03-5 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250159 | 26003H | 2789J | LP1Y-WPC-017042-03-4 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250158 | 26003H | 2788J | LP1Y-WPC-017042-03-3 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250157 | 26003H | 2787J | LP1Y-WPC-017042-03-2 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250156 | 26003H | 2786J | LP1Y-WPC-017042-03-1 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250155 | 26003H | 2785J | LP1Y-WPC-017041-03-8 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250154 | 26003H | 2784J | LP1Y-WPC-017041-03-7 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250153 | 26003H | 2783J | LP1Y-WPC-017041-03-6 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250152 | 26003H | 2782J | LP1Y-WPC-017041-03-5 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250151 | 26003H | 2781J | LP1Y-WPC-017041-03-4 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250150 | 26003H | 2780J | LP1Y-WPC-017041-03-3 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250149 | 26003H | 2779J | LP1Y-WPC-017041-03-2 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250148 | 26003H | 2778J | LP1Y-WPC-017041-03-1 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250147 | 26003H | 2777J | LP1Y-WPC-017029-02-6 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250146 | 26003H | 2776J | LP1Y-WPC-017029-02-5 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250145 | 26003H | 2775J | LP1Y-WPC-017029-02-4 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250144 | 26003H | 2774J | LP1Y-WPC-017029-02-3 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250143 | 26003H | 2773J | LP1Y-WPC-017029-02-2 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250142 | 26003H | 2772J | LP1Y-WPC-017029-02-1 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250139 | 26003H | 2771J | LP1Y-WFO-196010-03-6 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WNP (36) 017008 | WNP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250138 | 26003H | 2770J | LP1Y-WFO-196010-03-5 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250137 | 26003H | 2769J | LP1Y-WFO-196010-03-4 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250136 | 26003H | 2768J | LP1Y-WFO-196010-03-3 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250135 | 26003H | 2767J | LP1Y-WFO-196010-03-2 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250134 | 26003H | 2766J | LP1Y-WFO-196010-03-1 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250133 | 26003H | 2765J | LP1Y-WFO-196007-03-5 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250132 | 26003H | 2764J | LP1Y-WFO-196007-03-4 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250131 | 26003H | 2763J | LP1Y-WFO-196007-03-3 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250130 | 26003H | 2762J | LP1Y-WFO-196007-03-2 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250129 | 26003H | 2761J | LP1Y-WFO-196007-03-1 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250128 | 26003H | 2760J | LP1Y-WFO-196006-03-4 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250127 | 26003H | 2759J | LP1Y-WFO-196006-03-3 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250126 | 26003H | 2758J | LP1Y-WFO-196006-03-2 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250125 | 26003H | 2757J | LP1Y-WFO-196006-03-1 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250124 | 26003H | 2756J | LP1Y-WFO-195030-02-1 | LP1Y-WFO-195030-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" SS WFO (36) 195030 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195030 |  | TFS00D001YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250123 | 26003H | 2755J | LP1Y-WFO-195029-02-1 | LP1Y-WFO-195029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" SS WFO (36) 195029 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195029 |  | TFS00D007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250122 | 26003H | 2754J | LP1Y-WFO-195028-03-5 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250121 | 26003H | 2753J | LP1Y-WFO-195028-03-4 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250120 | 26003H | 2752J | LP1Y-WFO-195028-03-3 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250119 | 26003H | 2751J | LP1Y-WFO-195028-03-2 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250118 | 26003H | 2750J | LP1Y-WFO-195028-03-1 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250117 | 26003H | 2749J | LP1Y-WFO-195027-03-5 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250116 | 26003H | 2748J | LP1Y-WFO-195027-03-4 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250115 | 26003H | 2747J | LP1Y-WFO-195027-03-3 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250114 | 26003H | 2746J | LP1Y-WFO-195027-03-2 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250113 | 26003H | 2745J | LP1Y-WFO-195027-03-1 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250112 | 26003H | 2744J | LP1Y-WFO-195008-03-7 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250111 | 26003H | 2743J | LP1Y-WFO-195008-03-6 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250110 | 26003H | 2742J | LP1Y-WFO-195008-03-5 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250109 | 26003H | 2741J | LP1Y-WFO-195008-03-4 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250108 | 26003H | 2740J | LP1Y-WFO-195008-03-3 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250107 | 26003H | 2739J | LP1Y-WFO-195008-03-2 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250106 | 26003H | 2738J | LP1Y-WFO-195008-03-1 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250105 | 26003H | 2737J | LP1Y-WFO-195007-03-7 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250104 | 26003H | 2736J | LP1Y-WFO-195007-03-6 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250103 | 26003H | 2735J | LP1Y-WFO-195007-03-5 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250102 | 26003H | 2734J | LP1Y-WFO-195007-03-4 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250101 | 26003H | 2733J | LP1Y-WFO-195007-03-3 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250100 | 26003H | 2732J | LP1Y-WFO-195007-03-2 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250099 | 26003H | 2731J | LP1Y-WFO-195007-03-1 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250098 | 26003H | 2730J | LP1Y-WFO-195004-03-3 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250097 | 26003H | 2729J | LP1Y-WFO-195004-03-2 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250096 | 26003H | 2728J | LP1Y-WFO-195004-03-1 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250095 | 26003H | 2727J | LP1Y-WFO-195003-03-5 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250094 | 26003H | 2726J | LP1Y-WFO-195003-03-4 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250093 | 26003H | 2725J | LP1Y-WFO-195003-03-3 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250092 | 26003H | 2724J | LP1Y-WFO-195003-03-2 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250091 | 26003H | 2723J | LP1Y-WFO-195003-03-1 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250090 | 26003H | 2722J | LP1Y-WFO-195001-03-5 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250089 | 26003H | 2721J | LP1Y-WFO-195001-03-4 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250088 | 26003H | 2720J | LP1Y-WFO-195001-03-3 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250087 | 26003H | 2719J | LP1Y-WFO-195001-03-2 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250086 | 26003H | 2718J | LP1Y-WFO-195001-03-1 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250085 | 26003H | 2717J | LP1Y-WFO-109210-02-5 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250084 | 26003H | 2716J | LP1Y-WFO-109210-02-4 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250083 | 26003H | 2715J | LP1Y-WFO-109210-02-3 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250082 | 26003H | 2714J | LP1Y-WFO-109210-02-2 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250081 | 26003H | 2713J | LP1Y-WFO-109210-02-1 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250080 | 26003H | 2712J | LP1Y-WFO-109110-02-4 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250079 | 26003H | 2711J | LP1Y-WFO-109110-02-3 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250078 | 26003H | 2710J | LP1Y-WFO-109110-02-2 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250077 | 26003H | 2709J | LP1Y-WFO-109110-02-1 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250076 | 26003H | 2708J | LP1Y-WFO-108224-02-5 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250075 | 26003H | 2707J | LP1Y-WFO-108224-02-4 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250074 | 26003H | 2706J | LP1Y-WFO-108224-02-3 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250073 | 26003H | 2705J | LP1Y-WFO-108224-02-2 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250072 | 26003H | 2704J | LP1Y-WFO-108224-02-1 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250071 | 26003H | 2703J | LP1Y-WFO-108123-02-5 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250070 | 26003H | 2702J | LP1Y-WFO-108123-02-4 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250069 | 26003H | 2701J | LP1Y-WFO-108123-02-3 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250068 | 26003H | 2700J | LP1Y-WFO-108123-02-2 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250067 | 26003H | 2699J | LP1Y-WFO-108123-02-1 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250066 | 26003H | 2698J | LP1Y-WFO-102210-02-4 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250065 | 26003H | 2697J | LP1Y-WFO-102210-02-3 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250064 | 26003H | 2696J | LP1Y-WFO-102210-02-2 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250063 | 26003H | 2695J | LP1Y-WFO-102210-02-1 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250062 | 26003H | 2694J | LP1Y-WFO-102110-02-4 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250061 | 26003H | 2693J | LP1Y-WFO-102110-02-3 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250060 | 26003H | 2692J | LP1Y-WFO-102110-02-2 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250059 | 26003H | 2691J | LP1Y-WFO-102110-02-1 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250058 | 26003H | 2690J | LP1Y-WFO-101710-02-4 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250057 | 26003H | 2689J | LP1Y-WFO-101710-02-3 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250056 | 26003H | 2688J | LP1Y-WFO-101710-02-2 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250055 | 26003H | 2687J | LP1Y-WFO-101710-02-1 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250054 | 26003H | 2686J | LP1Y-WFO-101610-02-4 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250053 | 26003H | 2685J | LP1Y-WFO-101610-02-3 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250052 | 26003H | 2684J | LP1Y-WFO-101610-02-2 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250051 | 26003H | 2683J | LP1Y-WFO-101610-02-1 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250050 | 26003H | 2682J | LP1Y-WFO-101513-02-4 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250049 | 26003H | 2681J | LP1Y-WFO-101513-02-3 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250048 | 26003H | 2680J | LP1Y-WFO-101513-02-2 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250047 | 26003H | 2679J | LP1Y-WFO-101513-02-1 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250046 | 26003H | 2678J | LP1Y-WFO-101311-02-4 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250045 | 26003H | 2677J | LP1Y-WFO-101311-02-3 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250044 | 26003H | 2676J | LP1Y-WFO-101311-02-2 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250043 | 26003H | 2675J | LP1Y-WFO-101311-02-1 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250042 | 26003H | 2674J | LP1Y-WFO-101111-02-4 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250041 | 26003H | 2673J | LP1Y-WFO-101111-02-3 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250040 | 26003H | 2672J | LP1Y-WFO-101111-02-2 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250039 | 26003H | 2671J | LP1Y-WFO-101111-02-1 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250038 | 26003H | 2670J | LP1Y-WFO-100309-02-4 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250037 | 26003H | 2669J | LP1Y-WFO-100309-02-3 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250036 | 26003H | 2668J | LP1Y-WFO-100309-02-2 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250035 | 26003H | 2667J | LP1Y-WFO-100309-02-1 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250034 | 26003H | 2666J | LP1Y-WFO-100209-02-4 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250033 | 26003H | 2665J | LP1Y-WFO-100209-02-3 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250032 | 26003H | 2664J | LP1Y-WFO-100209-02-2 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250031 | 26003H | 2663J | LP1Y-WFO-100209-02-1 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250030 | 26003H | 2662J | LP1Y-WFO-100109-02-4 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250029 | 26003H | 2661J | LP1Y-WFO-100109-02-3 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250028 | 26003H | 2660J | LP1Y-WFO-100109-02-2 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250027 | 26003H | 2659J | LP1Y-WFO-100109-02-1 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250026 | 26003H | 2658J | LP1Y-WFO-033060-04-8 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250025 | 26003H | 2657J | LP1Y-WFO-033060-04-7 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250024 | 26003H | 2656J | LP1Y-WFO-033060-04-6 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250023 | 26003H | 2655J | LP1Y-WFO-033060-04-5 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250022 | 26003H | 2654J | LP1Y-WFO-033060-04-4 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250021 | 26003H | 2653J | LP1Y-WFO-033060-04-3 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250020 | 26003H | 2652J | LP1Y-WFO-033060-04-2 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250019 | 26003H | 2651J | LP1Y-WFO-033060-04-1 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250018 | 26003H | 2650J | LP1Y-WFO-033053-06-6 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250017 | 26003H | 2649J | LP1Y-WFO-033053-06-5 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250016 | 26003H | 2648J | LP1Y-WFO-033053-06-4 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250015 | 26003H | 2647J | LP1Y-WFO-033053-06-3 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250014 | 26003H | 2646J | LP1Y-WFO-033053-06-2 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250013 | 26003H | 2645J | LP1Y-WFO-033053-06-1 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250012 | 26003H | 2644J | LP1Y-WFO-017060-16-5 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250011 | 26003H | 2643J | LP1Y-WFO-017060-16-4 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250010 | 26003H | 2642J | LP1Y-WFO-017060-16-3 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250009 | 26003H | 2641J | LP1Y-WFO-017060-16-2 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250008 | 26003H | 2640J | LP1Y-WFO-017060-16-1 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250007 | 26003H | 2639J | LP1Y-WFO-017060-15-2 | LP1Y-WFO-017060-15 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250006 | 26003H | 2638J | LP1Y-WFO-017060-15-1 | LP1Y-WFO-017060-15 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250005 | 26003H | 2637J | LP1Y-WFO-017060-14-2 | LP1Y-WFO-017060-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250004 | 26003H | 2636J | LP1Y-WFO-017060-14-1 | LP1Y-WFO-017060-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250003 | 26003H | 2635J | LP1Y-WFO-017052-04-8 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250002 | 26003H | 2634J | LP1Y-WFO-017052-04-7 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250001 | 26003H | 2633J | LP1Y-WFO-017052-04-6 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250000 | 26003H | 2632J | LP1Y-WFO-017052-04-5 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249999 | 26003H | 2631J | LP1Y-WFO-017052-04-4 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249998 | 26003H | 2630J | LP1Y-WFO-017052-04-3 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249997 | 26003H | 2629J | LP1Y-WFO-017052-04-2 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249996 | 26003H | 2628J | LP1Y-WFO-017052-04-1 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249995 | 26003H | 2627J | LP1Y-WFO-017049-07-2 | LP1Y-WFO-017049-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249994 | 26003H | 2626J | LP1Y-WFO-017049-07-1 | LP1Y-WFO-017049-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249993 | 26003H | 2625J | LP1Y-WFO-017049-06-3 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249992 | 26003H | 2624J | LP1Y-WFO-017049-06-2 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249991 | 26003H | 2623J | LP1Y-WFO-017049-06-1 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249990 | 26003H | 2622J | LP1Y-WFO-017038-02-8 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249989 | 26003H | 2621J | LP1Y-WFO-017038-02-7 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249988 | 26003H | 2620J | LP1Y-WFO-017038-02-6 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249987 | 26003H | 2619J | LP1Y-WFO-017038-02-5 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249986 | 26003H | 2618J | LP1Y-WFO-017038-02-4 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249985 | 26003H | 2617J | LP1Y-WFO-017038-02-3 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249984 | 26003H | 2616J | LP1Y-WFO-017038-02-2 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249983 | 26003H | 2615J | LP1Y-WFO-017038-02-1 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249982 | 26003H | 2614J | LP1Y-WFO-017009-09-5 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249981 | 26003H | 2613J | LP1Y-WFO-017009-09-4 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249980 | 26003H | 2612J | LP1Y-WFO-017009-09-3 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249979 | 26003H | 2611J | LP1Y-WFO-017009-09-2 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249978 | 26003H | 2610J | LP1Y-WFO-017009-09-1 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249977 | 26003H | 2609J | LP1Y-WFO-017009-08-4 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249976 | 26003H | 2608J | LP1Y-WFO-017009-08-3 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249975 | 26003H | 2607J | LP1Y-WFO-017009-08-2 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249974 | 26003H | 2606J | LP1Y-WFO-017009-08-1 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249973 | 26003H | 2605J | LP1Y-WFO-017009-07-8 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249972 | 26003H | 2604J | LP1Y-WFO-017009-07-7 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249971 | 26003H | 2603J | LP1Y-WFO-017009-07-6 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249970 | 26003H | 2602J | LP1Y-WFO-017009-07-5 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249969 | 26003H | 2601J | LP1Y-WFO-017009-07-4 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249968 | 26003H | 2600J | LP1Y-WFO-017009-07-3 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249967 | 26003H | 2599J | LP1Y-WFO-017009-07-2 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249966 | 26003H | 2598J | LP1Y-WFO-017009-07-1 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249965 | 26003H | 2597J | LP1Y-WFO-017008-10-2 | LP1Y-WFO-017008-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249964 | 26003H | 2596J | LP1Y-WFO-017008-10-1 | LP1Y-WFO-017008-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249963 | 26003H | 2595J | LP1Y-WFO-017008-09-4 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249962 | 26003H | 2594J | LP1Y-WFO-017008-09-3 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249961 | 26003H | 2593J | LP1Y-WFO-017008-09-2 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249960 | 26003H | 2592J | LP1Y-WFO-017008-09-1 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249959 | 26003H | 2591J | LP1Y-WFO-017008-08-3 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249958 | 26003H | 2590J | LP1Y-WFO-017008-08-2 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249957 | 26003H | 2589J | LP1Y-WFO-017008-08-1 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249956 | 26003H | 2588J | LP1Y-WFO-017007-58-3 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249955 | 26003H | 2587J | LP1Y-WFO-017007-58-2 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249954 | 26003H | 2586J | LP1Y-WFO-017007-58-1 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249953 | 26003H | 2585J | LP1Y-WFO-017007-57-2 | LP1Y-WFO-017007-57 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249952 | 26003H | 2584J | LP1Y-WFO-017007-57-1 | LP1Y-WFO-017007-57 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249951 | 26003H | 2583J | LP1Y-WFO-017007-20-2 | LP1Y-WFO-017007-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WFO (36) (108) 017007 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D007YSPP |  | 36-WFO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249950 | 26003H | 2582J | LP1Y-WFO-017007-20-1 | LP1Y-WFO-017007-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 4" SS WFO (36) (108) 017007 | WFO |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D007YSPP |  | 36-WFO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249949 | 26003H | 2581J | LP1Y-WFO-017007-19-5 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249948 | 26003H | 2580J | LP1Y-WFO-017007-19-4 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249947 | 26003H | 2579J | LP1Y-WFO-017007-19-3 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249946 | 26003H | 2578J | LP1Y-WFO-017007-19-2 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249945 | 26003H | 2577J | LP1Y-WFO-017007-19-1 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249944 | 26003H | 2576J | LP1Y-WFO-017004-05-7 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249943 | 26003H | 2575J | LP1Y-WFO-017004-05-6 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249942 | 26003H | 2574J | LP1Y-WFO-017004-05-5 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249941 | 26003H | 2573J | LP1Y-WFO-017004-05-4 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249940 | 26003H | 2572J | LP1Y-WFO-017004-05-1 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249939 | 26003H | 2571J | LP1Y-WFO-017004-05-2 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249938 | 26003H | 2570J | LP1Y-WFO-017004-05-3 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249937 | 26003H | 2569J | LP1Y-WFO-017003-03-6 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249936 | 26003H | 2568J | LP1Y-WFO-017003-03-5 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249935 | 26003H | 2567J | LP1Y-WFO-017003-03-4 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249934 | 26003H | 2566J | LP1Y-WFO-017003-03-3 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249933 | 26003H | 2565J | LP1Y-WFO-017003-03-2 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249932 | 26003H | 2564J | LP1Y-WFO-017003-03-1 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249931 | 26003H | 2563C | LP1Y-TWSP-017020-05-3 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | NONE | 1 1/2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249930 | 26003H | 2562C | LP1Y-TWSP-017020-05-2 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | NONE | 3" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249929 | 26003H | 2561C | LP1Y-TWSP-017020-05-1 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | NONE | 3" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249928 | 26003H | 2560C | LP1Y-TWRP-109313-05-3 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | NONE | 1 1/2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249927 | 26003H | 2559C | LP1Y-TWRP-109313-05-2 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | NONE | 3" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249926 | 26003H | 2558C | LP1Y-TWRP-109313-05-1 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | NONE | 3" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249925 | 26003H | 2557AB | LP1Y-TFA-176023-04-3 | LP1Y-TFA-176023-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249924 | 26003H | 2556AB | LP1Y-TFA-176023-04-2 | LP1Y-TFA-176023-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249923 | 26003H | 2555AB | LP1Y-TFA-176023-04-1 | LP1Y-TFA-176023-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249922 | 26003H | 2554AB | LP1Y-TFA-176023-03-4 | LP1Y-TFA-176023-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249921 | 26003H | 2553AB | LP1Y-TFA-176023-03-3 | LP1Y-TFA-176023-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249920 | 26003H | 2552AB | LP1Y-TFA-176023-03-2 | LP1Y-TFA-176023-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249919 | 26003H | 2551AB | LP1Y-TFA-176023-03-1 | LP1Y-TFA-176023-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249918 | 26003H | 2550AB | LP1Y-TFA-109215-03-1 | LP1Y-TFA-109215-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249917 | 26003H | 2549AB | LP1Y-TFA-109215-01-3 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249916 | 26003H | 2548AB | LP1Y-TFA-109215-01-2 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249915 | 26003H | 2547AB | LP1Y-TFA-109215-01-1 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249914 | 26003H | 2546AB | LP1Y-TFA-109212-01-7 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249913 | 26003H | 2545AB | LP1Y-TFA-109212-01-6 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249912 | 26003H | 2544AB | LP1Y-TFA-109212-01-5 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249911 | 26003H | 2543AB | LP1Y-TFA-109212-01-4 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249910 | 26003H | 2542AB | LP1Y-TFA-109212-01-3 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249909 | 26003H | 2541AB | LP1Y-TFA-109212-01-2 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249908 | 26003H | 2540AB | LP1Y-TFA-109212-01-1 | LP1Y-TFA-109212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249907 | 26003H | 2539AB | LP1Y-TFA-109206-03-4 | LP1Y-TFA-109206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249906 | 26003H | 2538AB | LP1Y-TFA-109206-03-3 | LP1Y-TFA-109206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249905 | 26003H | 2537AB | LP1Y-TFA-109206-03-2 | LP1Y-TFA-109206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249904 | 26003H | 2536AB | LP1Y-TFA-109206-03-1 | LP1Y-TFA-109206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249903 | 26003H | 2535AB | LP1Y-TFA-109206-01-4 | LP1Y-TFA-109206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249902 | 26003H | 2534AB | LP1Y-TFA-109206-01-3 | LP1Y-TFA-109206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249901 | 26003H | 2533AB | LP1Y-TFA-109206-01-2 | LP1Y-TFA-109206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249900 | 26003H | 2532AB | LP1Y-TFA-109206-01-1 | LP1Y-TFA-109206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249899 | 26003H | 2531AB | LP1Y-TFA-109205-06-3 | LP1Y-TFA-109205-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249898 | 26003H | 2530AB | LP1Y-TFA-109205-06-2 | LP1Y-TFA-109205-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249897 | 26003H | 2529AB | LP1Y-TFA-109205-06-1 | LP1Y-TFA-109205-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249896 | 26003H | 2528AB | LP1Y-TFA-109205-05-2 | LP1Y-TFA-109205-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249895 | 26003H | 2527AB | LP1Y-TFA-109205-05-1 | LP1Y-TFA-109205-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249894 | 26003H | 2526AB | LP1Y-TFA-109205-04-3 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249893 | 26003H | 2525AB | LP1Y-TFA-109205-04-2 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249892 | 26003H | 2524AB | LP1Y-TFA-109205-04-1 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249891 | 26003H | 2523AB | LP1Y-TFA-109205-03-3 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249890 | 26003H | 2522AB | LP1Y-TFA-109205-03-2 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249889 | 26003H | 2521AB | LP1Y-TFA-109205-03-1 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249888 | 26003H | 2520AB | LP1Y-TFA-109203-02-3 | LP1Y-TFA-109203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249887 | 26003H | 2519AB | LP1Y-TFA-109203-02-2 | LP1Y-TFA-109203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249886 | 26003H | 2518AB | LP1Y-TFA-109203-02-1 | LP1Y-TFA-109203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249885 | 26003H | 2517AB | LP1Y-TFA-109203-01-3 | LP1Y-TFA-109203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249884 | 26003H | 2516AB | LP1Y-TFA-109203-01-2 | LP1Y-TFA-109203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249883 | 26003H | 2515AB | LP1Y-TFA-109203-01-1 | LP1Y-TFA-109203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249882 | 26003H | 2514AB | LP1Y-TFA-010025-04-5 | LP1Y-TFA-010025-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249881 | 26003H | 2513AB | LP1Y-TFA-010025-04-4 | LP1Y-TFA-010025-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249880 | 26003H | 2512AB | LP1Y-TFA-010025-04-3 | LP1Y-TFA-010025-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249879 | 26003H | 2511AB | LP1Y-TFA-010025-04-2 | LP1Y-TFA-010025-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249878 | 26003H | 2510AB | LP1Y-TFA-010025-04-1 | LP1Y-TFA-010025-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249877 | 26003H | 2509AB | LP1Y-TFA-010025-03-2 | LP1Y-TFA-010025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249876 | 26003H | 2508AB | LP1Y-TFA-010025-03-1 | LP1Y-TFA-010025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249875 | 26003H | 2507J | LP1Y-SWP-166305-03-6 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249874 | 26003H | 2506J | LP1Y-SWP-166305-03-5 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249873 | 26003H | 2505J | LP1Y-SWP-166305-03-4 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249872 | 26003H | 2504J | LP1Y-SWP-166305-03-3 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249871 | 26003H | 2503J | LP1Y-SWP-166305-03-2 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249870 | 26003H | 2502J | LP1Y-SWP-166305-03-1 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249869 | 26003H | 2501J | LP1Y-SWP-166303-01-4 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249868 | 26003H | 2500J | LP1Y-SWP-166303-01-3 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249867 | 26003H | 2499J | LP1Y-SWP-166303-01-2 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249866 | 26003H | 2498J | LP1Y-SWP-166303-01-1 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249865 | 26003H | 2497J | LP1Y-SWP-166213-03-2 | LP1Y-SWP-166213-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249864 | 26003H | 2496J | LP1Y-SWP-166213-03-1 | LP1Y-SWP-166213-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249863 | 26003H | 2495J | LP1Y-SWP-166213-02-3 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249862 | 26003H | 2494J | LP1Y-SWP-166213-02-2 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249861 | 26003H | 2493J | LP1Y-SWP-166213-02-1 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249860 | 26003H | 2492J | LP1Y-SWP-166203-02-2 | LP1Y-SWP-166203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249859 | 26003H | 2491J | LP1Y-SWP-166203-02-1 | LP1Y-SWP-166203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249858 | 26003H | 2490J | LP1Y-SWP-166203-01-3 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249857 | 26003H | 2489J | LP1Y-SWP-166203-01-2 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249856 | 26003H | 2488J | LP1Y-SWP-166203-01-1 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249855 | 26003H | 2487J | LP1Y-SWP-165803-04-3 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249854 | 26003H | 2486J | LP1Y-SWP-165803-04-2 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249853 | 26003H | 2485J | LP1Y-SWP-165803-04-1 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249852 | 26003H | 2484J | LP1Y-SWP-165803-02-2 | LP1Y-SWP-165803-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249851 | 26003H | 2483J | LP1Y-SWP-165803-02-1 | LP1Y-SWP-165803-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249850 | 26003H | 2482J | LP1Y-SWP-165703-03-4 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249849 | 26003H | 2481J | LP1Y-SWP-165703-03-3 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249848 | 26003H | 2480J | LP1Y-SWP-165703-03-2 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249847 | 26003H | 2479J | LP1Y-SWP-165703-03-1 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249846 | 26003H | 2478J | LP1Y-SWP-165703-02-2 | LP1Y-SWP-165703-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249845 | 26003H | 2477J | LP1Y-SWP-165703-02-1 | LP1Y-SWP-165703-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249844 | 26003H | 2476J | LP1Y-SWP-165403-02-3 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249843 | 26003H | 2475J | LP1Y-SWP-165403-02-2 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249842 | 26003H | 2474J | LP1Y-SWP-165403-02-1 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249841 | 26003H | 2473J | LP1Y-SWP-165403-01-3 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249840 | 26003H | 2472J | LP1Y-SWP-165403-01-2 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249839 | 26003H | 2471J | LP1Y-SWP-165403-01-1 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249838 | 26003H | 2470J | LP1Y-SWP-165113-06-2 | LP1Y-SWP-165113-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249837 | 26003H | 2469J | LP1Y-SWP-165113-06-1 | LP1Y-SWP-165113-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249836 | 26003H | 2468J | LP1Y-SWP-165113-05-3 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249835 | 26003H | 2467J | LP1Y-SWP-165113-05-2 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249834 | 26003H | 2466J | LP1Y-SWP-165113-05-1 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249833 | 26003H | 2465J | LP1Y-SWP-165113-02-1 | LP1Y-SWP-165113-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249761 | 26003H | 2464J | LP1Y-SWP-165103-03-4 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249760 | 26003H | 2463J | LP1Y-SWP-165103-03-3 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249759 | 26003H | 2462J | LP1Y-SWP-165103-03-2 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249758 | 26003H | 2461J | LP1Y-SWP-165103-03-1 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249757 | 26003H | 2460J | LP1Y-SWP-165103-02-3 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249756 | 26003H | 2459J | LP1Y-SWP-165103-02-2 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249755 | 26003H | 2458J | LP1Y-SWP-165103-02-1 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249754 | 26003H | 2457J | LP1Y-SWP-109022-10-4 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249753 | 26003H | 2456J | LP1Y-SWP-109022-10-3 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249752 | 26003H | 2455J | LP1Y-SWP-109022-10-2 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249751 | 26003H | 2454J | LP1Y-SWP-109022-10-1 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249750 | 26003H | 2453J | LP1Y-SWP-108084-01-1 | LP1Y-SWP-108084-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SWP (315) (108) 108084 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108084 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249749 | 26003H | 2452J | LP1Y-SWP-102082-01-2 | LP1Y-SWP-102082-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 102082 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102082 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249748 | 26003H | 2451J | LP1Y-SWP-102082-01-1 | LP1Y-SWP-102082-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SWP (315) (108) 102082 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102082 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249747 | 26003H | 2450D | LP1Y-SWP-101509-04-5 | LP1Y-SWP-101509-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249746 | 26003H | 2449D | LP1Y-SWP-101509-04-4 | LP1Y-SWP-101509-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249745 | 26003H | 2448D | LP1Y-SWP-101509-04-3 | LP1Y-SWP-101509-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249744 | 26003H | 2447D | LP1Y-SWP-101509-04-2 | LP1Y-SWP-101509-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249743 | 26003H | 2446D | LP1Y-SWP-101509-04-1 | LP1Y-SWP-101509-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249742 | 26003H | 2445D | LP1Y-SWP-101509-03-2 | LP1Y-SWP-101509-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249741 | 26003H | 2444D | LP1Y-SWP-101509-03-1 | LP1Y-SWP-101509-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249740 | 26003H | 2443D | LP1Y-SWP-101509-01-2 | LP1Y-SWP-101509-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249739 | 26003H | 2442D | LP1Y-SWP-101509-01-1 | LP1Y-SWP-101509-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249738 | 26003H | 2441D | LP1Y-SWP-101506-02-5 | LP1Y-SWP-101506-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249737 | 26003H | 2440D | LP1Y-SWP-101506-02-4 | LP1Y-SWP-101506-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249736 | 26003H | 2439D | LP1Y-SWP-101506-02-3 | LP1Y-SWP-101506-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249735 | 26003H | 2438D | LP1Y-SWP-101506-02-2 | LP1Y-SWP-101506-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249734 | 26003H | 2437D | LP1Y-SWP-101506-02-1 | LP1Y-SWP-101506-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249733 | 26003H | 2436D | LP1Y-SWP-101506-01-5 | LP1Y-SWP-101506-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249732 | 26003H | 2435D | LP1Y-SWP-101506-01-4 | LP1Y-SWP-101506-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249731 | 26003H | 2434D | LP1Y-SWP-101506-01-3 | LP1Y-SWP-101506-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249730 | 26003H | 2433D | LP1Y-SWP-101506-01-2 | LP1Y-SWP-101506-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249729 | 26003H | 2432D | LP1Y-SWP-101506-01-1 | LP1Y-SWP-101506-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249728 | 26003H | 2431D | LP1Y-SWP-101505-02-3 | LP1Y-SWP-101505-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249727 | 26003H | 2430D | LP1Y-SWP-101505-02-2 | LP1Y-SWP-101505-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249726 | 26003H | 2429D | LP1Y-SWP-101505-02-1 | LP1Y-SWP-101505-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249725 | 26003H | 2428D | LP1Y-SWP-101505-01-4 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249724 | 26003H | 2427D | LP1Y-SWP-101505-01-3 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249723 | 26003H | 2426D | LP1Y-SWP-101505-01-2 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249722 | 26003H | 2425D | LP1Y-SWP-101505-01-1 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249721 | 26003H | 2424J | LP1Y-SWP-101026-01-3 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249720 | 26003H | 2423J | LP1Y-SWP-101026-01-2 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249719 | 26003H | 2422J | LP1Y-SWP-101026-01-1 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249718 | 26003H | 2421J | LP1Y-SWP-100411-01-5 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249717 | 26003H | 2420J | LP1Y-SWP-100411-01-4 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249716 | 26003H | 2419J | LP1Y-SWP-100411-01-3 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249715 | 26003H | 2418J | LP1Y-SWP-100411-01-2 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249714 | 26003H | 2417J | LP1Y-SWP-100411-01-1 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249713 | 26003H | 2416J | LP1Y-SWP-100404-01-3 | LP1Y-SWP-100404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249712 | 26003H | 2415J | LP1Y-SWP-100404-01-4 | LP1Y-SWP-100404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249711 | 26003H | 2414J | LP1Y-SWP-100404-01-2 | LP1Y-SWP-100404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249710 | 26003H | 2413J | LP1Y-SWP-100404-01-1 | LP1Y-SWP-100404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249709 | 26003H | 2412D | LP1Y-SWP-014001-23-2 | LP1Y-SWP-014001-23 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249708 | 26003H | 2411D | LP1Y-SWP-014001-23-1 | LP1Y-SWP-014001-23 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249707 | 26003H | 2410D | LP1Y-SWP-014001-22-1 | LP1Y-SWP-014001-22 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249706 | 26003H | 2409D | LP1Y-SWP-014001-21-3 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249705 | 26003H | 2408D | LP1Y-SWP-014001-21-2 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249704 | 26003H | 2407D | LP1Y-SWP-014001-21-1 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249703 | 26003H | 2406D | LP1Y-SWP-014001-20-3 | LP1Y-SWP-014001-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249702 | 26003H | 2405D | LP1Y-SWP-014001-20-2 | LP1Y-SWP-014001-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249701 | 26003H | 2404D | LP1Y-SWP-014001-20-1 | LP1Y-SWP-014001-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249700 | 26003H | 2403D | LP1Y-SWP-014001-19-2 | LP1Y-SWP-014001-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249699 | 26003H | 2402D | LP1Y-SWP-014001-19-1 | LP1Y-SWP-014001-19 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249698 | 26003H | 2401D | LP1Y-SWP-014001-18-2 | LP1Y-SWP-014001-18 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249697 | 26003H | 2400D | LP1Y-SWP-014001-18-1 | LP1Y-SWP-014001-18 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249696 | 26003H | 2399D | LP1Y-SWP-014001-17-2 | LP1Y-SWP-014001-17 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249695 | 26003H | 2398D | LP1Y-SWP-014001-17-1 | LP1Y-SWP-014001-17 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249694 | 26003H | 2397D | LP1Y-SWP-014001-16-2 | LP1Y-SWP-014001-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249693 | 26003H | 2396D | LP1Y-SWP-014001-16-1 | LP1Y-SWP-014001-16 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249692 | 26003H | 2395D | LP1Y-SWP-014001-15-2 | LP1Y-SWP-014001-15 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249691 | 26003H | 2394D | LP1Y-SWP-014001-15-1 | LP1Y-SWP-014001-15 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249690 | 26003H | 2393D | LP1Y-SWP-014001-14-3 | LP1Y-SWP-014001-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249689 | 26003H | 2392D | LP1Y-SWP-014001-14-2 | LP1Y-SWP-014001-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249688 | 26003H | 2391D | LP1Y-SWP-014001-14-1 | LP1Y-SWP-014001-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249687 | 26003H | 2390D | LP1Y-SWP-014001-13-2 | LP1Y-SWP-014001-13 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249686 | 26003H | 2389D | LP1Y-SWP-014001-13-1 | LP1Y-SWP-014001-13 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249685 | 26003H | 2388D | LP1Y-SWP-014001-12-2 | LP1Y-SWP-014001-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249684 | 26003H | 2387D | LP1Y-SWP-014001-12-1 | LP1Y-SWP-014001-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249683 | 26003H | 2386D | LP1Y-SWP-014001-11-2 | LP1Y-SWP-014001-11 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249682 | 26003H | 2385D | LP1Y-SWP-014001-11-1 | LP1Y-SWP-014001-11 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249681 | 26003H | 2384D | LP1Y-SWP-014001-09-2 | LP1Y-SWP-014001-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249680 | 26003H | 2383D | LP1Y-SWP-014001-09-3 | LP1Y-SWP-014001-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249679 | 26003H | 2382D | LP1Y-SWP-014001-09-1 | LP1Y-SWP-014001-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249678 | 26003H | 2381D | LP1Y-SWP-014001-08-1 | LP1Y-SWP-014001-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249677 | 26003H | 2380D | LP1Y-SWP-014001-07-5 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249676 | 26003H | 2379D | LP1Y-SWP-014001-07-4 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249675 | 26003H | 2378D | LP1Y-SWP-014001-07-3 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249674 | 26003H | 2377D | LP1Y-SWP-014001-07-2 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249673 | 26003H | 2376D | LP1Y-SWP-014001-07-1 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249672 | 26003H | 2375D | LP1Y-SWP-014001-01-6 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249671 | 26003H | 2374D | LP1Y-SWP-014001-01-5 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249670 | 26003H | 2373D | LP1Y-SWP-014001-01-4 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249669 | 26003H | 2372D | LP1Y-SWP-014001-01-3 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249668 | 26003H | 2371D | LP1Y-SWP-014001-01-2 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249667 | 26003H | 2370D | LP1Y-SWP-014001-01-1 | LP1Y-SWP-014001-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249666 | 26003H | 2369J | LP1Y-SW-166307-01-1 | LP1Y-SW-166307-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SW (315) 166307 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166307 |  | TFS00E007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249665 | 26003H | 2368J | LP1Y-SW-166302-01-1 | LP1Y-SW-166302-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS SW (315) 166302 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166302 |  | TFS00E007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249664 | 26003H | 2367J | LP1Y-SW-166212-01-1 | LP1Y-SW-166212-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SW (315) 166212 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166212 |  | TFS00E006YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249663 | 26003H | 2366J | LP1Y-SW-166202-01-1 | LP1Y-SW-166202-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SW (315) 166202 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166202 |  | TFS00E006YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249662 | 26003H | 2365J | LP1Y-SW-165802-01-3 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249661 | 26003H | 2364J | LP1Y-SW-165802-01-2 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249660 | 26003H | 2363J | LP1Y-SW-165802-01-1 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249659 | 26003H | 2362J | LP1Y-SW-165702-01-2 | LP1Y-SW-165702-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SW (315) 165702 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165702 |  | TFS00D007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249658 | 26003H | 2361J | LP1Y-SW-165702-01-1 | LP1Y-SW-165702-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS SW (315) 165702 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165702 |  | TFS00D007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249657 | 26003H | 2360J | LP1Y-SW-165402-01-1 | LP1Y-SW-165402-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS SW (315) 165402 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165402 |  | TFS00D006YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249656 | 26003H | 2359J | LP1Y-SW-165112-01-2 | LP1Y-SW-165112-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SW (315) 165112 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165112 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249655 | 26003H | 2358J | LP1Y-SW-165112-01-1 | LP1Y-SW-165112-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SW (315) 165112 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165112 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249654 | 26003H | 2357J | LP1Y-SW-165102-01-2 | LP1Y-SW-165102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SW (315) E 165102 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165102 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249653 | 26003H | 2356J | LP1Y-SW-165102-01-1 | LP1Y-SW-165102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS SW (315) E 165102 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165102 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249652 | 26003H | 2355J | LP1Y-STORMP-166306-03-2 | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249651 | 26003H | 2354J | LP1Y-STORMP-166306-03-1 | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249650 | 26003H | 2353J | LP1Y-STORMP-166304-01-2 | LP1Y-STORMP-166304-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS STORMP (315) (108) 166304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166304 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249649 | 26003H | 2352J | LP1Y-STORMP-166304-01-1 | LP1Y-STORMP-166304-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS STORMP (315) (108) 166304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166304 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249648 | 26003H | 2351J | LP1Y-STORMP-166214-06-1 | LP1Y-STORMP-166214-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249647 | 26003H | 2350J | LP1Y-STORMP-166214-04-2 | LP1Y-STORMP-166214-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249646 | 26003H | 2349J | LP1Y-STORMP-166214-04-1 | LP1Y-STORMP-166214-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249645 | 26003H | 2348J | LP1Y-STORMP-166204-02-2 | LP1Y-STORMP-166204-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS STORMP (315) (108) 166204 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166204 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249644 | 26003H | 2347J | LP1Y-STORMP-166204-02-1 | LP1Y-STORMP-166204-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS STORMP (315) (108) 166204 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166204 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249643 | 26003H | 2346J | LP1Y-STORMP-165804-02-3 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249642 | 26003H | 2345J | LP1Y-STORMP-165804-02-2 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249641 | 26003H | 2344J | LP1Y-STORMP-165804-02-1 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249640 | 26003H | 2343J | LP1Y-STORMP-165704-02-2 | LP1Y-STORMP-165704-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS STORMP (315) (108) 165704 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165704 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249639 | 26003H | 2342J | LP1Y-STORMP-165704-02-1 | LP1Y-STORMP-165704-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS STORMP (315) (108) 165704 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165704 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249638 | 26003H | 2341J | LP1Y-STORMP-165404-01-2 | LP1Y-STORMP-165404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS STORMP (315) (108) 165404 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165404 |  | TFS00D006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249637 | 26003H | 2340J | LP1Y-STORMP-165404-01-1 | LP1Y-STORMP-165404-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS STORMP (315) (108) 165404 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165404 |  | TFS00D006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249636 | 26003H | 2339J | LP1Y-STORMP-165334-06-3 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249635 | 26003H | 2338J | LP1Y-STORMP-165334-06-2 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249634 | 26003H | 2337J | LP1Y-STORMP-165334-06-1 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249633 | 26003H | 2336J | LP1Y-STORMP-165334-02-5 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249632 | 26003H | 2335J | LP1Y-STORMP-165334-02-4 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249631 | 26003H | 2334J | LP1Y-STORMP-165334-02-3 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249630 | 26003H | 2333J | LP1Y-STORMP-165334-02-2 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249629 | 26003H | 2332J | LP1Y-STORMP-165334-02-1 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249628 | 26003H | 2331J | LP1Y-STORMP-165324-02-3 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249627 | 26003H | 2330J | LP1Y-STORMP-165324-02-2 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249626 | 26003H | 2329J | LP1Y-STORMP-165324-02-1 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249625 | 26003H | 2328J | LP1Y-STORMP-165324-01-3 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249624 | 26003H | 2327J | LP1Y-STORMP-165324-01-2 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249623 | 26003H | 2326J | LP1Y-STORMP-165324-01-1 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249622 | 26003H | 2325J | LP1Y-STORMP-165314-03-3 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249621 | 26003H | 2324J | LP1Y-STORMP-165314-03-2 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249620 | 26003H | 2323J | LP1Y-STORMP-165314-03-1 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249619 | 26003H | 2322J | LP1Y-STORMP-165314-01-2 | LP1Y-STORMP-165314-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249618 | 26003H | 2321J | LP1Y-STORMP-165314-01-1 | LP1Y-STORMP-165314-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249617 | 26003H | 2320J | LP1Y-STORMP-165304-03-3 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249616 | 26003H | 2319J | LP1Y-STORMP-165304-03-2 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249615 | 26003H | 2318J | LP1Y-STORMP-165304-03-1 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249614 | 26003H | 2317J | LP1Y-STORMP-165304-01-1 | LP1Y-STORMP-165304-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249613 | 26003H | 2316J | LP1Y-STORMP-165304-01-2 | LP1Y-STORMP-165304-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249612 | 26003H | 2315J | LP1Y-STORMP-165214-01-5 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249611 | 26003H | 2314J | LP1Y-STORMP-165214-01-4 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249610 | 26003H | 2313J | LP1Y-STORMP-165214-01-3 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249609 | 26003H | 2312J | LP1Y-STORMP-165214-01-2 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249608 | 26003H | 2311J | LP1Y-STORMP-165214-01-1 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249607 | 26003H | 2310J | LP1Y-STORMP-165204-04-3 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249606 | 26003H | 2309J | LP1Y-STORMP-165204-04-2 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249605 | 26003H | 2308J | LP1Y-STORMP-165204-04-1 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249604 | 26003H | 2307J | LP1Y-STORMP-165204-01-5 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249603 | 26003H | 2306J | LP1Y-STORMP-165204-01-4 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249602 | 26003H | 2305J | LP1Y-STORMP-165204-01-3 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249601 | 26003H | 2304J | LP1Y-STORMP-165204-01-2 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249600 | 26003H | 2303J | LP1Y-STORMP-165204-01-1 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249599 | 26003H | 2302J | LP1Y-STORMP-165114-06-2 | LP1Y-STORMP-165114-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249598 | 26003H | 2301J | LP1Y-STORMP-165114-06-1 | LP1Y-STORMP-165114-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249597 | 26003H | 2300J | LP1Y-STORMP-165114-05-1 | LP1Y-STORMP-165114-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249596 | 26003H | 2299J | LP1Y-STORMP-165114-02-2 | LP1Y-STORMP-165114-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249595 | 26003H | 2298J | LP1Y-STORMP-165114-02-1 | LP1Y-STORMP-165114-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249594 | 26003H | 2297J | LP1Y-STORMP-165104-03-3 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249593 | 26003H | 2296J | LP1Y-STORMP-165104-03-2 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249592 | 26003H | 2295J | LP1Y-STORMP-165104-03-1 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249591 | 26003H | 2294J | LP1Y-STORMP-165104-02-1 | LP1Y-STORMP-165104-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249590 | 26003H | 2293J | LP1Y-STORMP-100406-02-1 | LP1Y-STORMP-100406-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100406 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249589 | 26003H | 2292J | LP1Y-STORMP-100406-01-3 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249588 | 26003H | 2291J | LP1Y-STORMP-100406-01-2 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249587 | 26003H | 2290J | LP1Y-STORMP-100406-01-1 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249586 | 26003H | 2289J | LP1Y-STORMP-100403-05-4 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249585 | 26003H | 2288J | LP1Y-STORMP-100403-05-3 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249584 | 26003H | 2287J | LP1Y-STORMP-100403-05-2 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249583 | 26003H | 2286J | LP1Y-STORMP-100403-05-1 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249582 | 26003H | 2285J | LP1Y-STORMP-100403-04-2 | LP1Y-STORMP-100403-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249581 | 26003H | 2284J | LP1Y-STORMP-100403-04-1 | LP1Y-STORMP-100403-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249580 | 26003H | 2283J | LP1Y-STORMP-100403-02-3 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249579 | 26003H | 2282J | LP1Y-STORMP-100403-02-2 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249578 | 26003H | 2281J | LP1Y-STORMP-100403-02-1 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249577 | 26003H | 2280J | LP1Y-STORMP-100403-01-5 | LP1Y-STORMP-100403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249576 | 26003H | 2279J | LP1Y-STORMP-100403-01-4 | LP1Y-STORMP-100403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249575 | 26003H | 2278J | LP1Y-STORMP-100403-01-3 | LP1Y-STORMP-100403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249574 | 26003H | 2277J | LP1Y-STORMP-100403-01-2 | LP1Y-STORMP-100403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249573 | 26003H | 2276J | LP1Y-STORMP-100403-01-1 | LP1Y-STORMP-100403-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249572 | 26003H | 2275J | LP1Y-STORMP-100402-02-4 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249571 | 26003H | 2274J | LP1Y-STORMP-100402-02-3 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249570 | 26003H | 2273J | LP1Y-STORMP-100402-02-2 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249569 | 26003H | 2272J | LP1Y-STORMP-100402-02-1 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249568 | 26003H | 2271J | LP1Y-STORMP-100402-01-3 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249567 | 26003H | 2270J | LP1Y-STORMP-100402-01-2 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249566 | 26003H | 2269J | LP1Y-STORMP-100402-01-1 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249565 | 26003H | 2268J | LP1Y-STORMP-037007-04-3 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249564 | 26003H | 2267J | LP1Y-STORMP-037007-04-2 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249563 | 26003H | 2266J | LP1Y-STORMP-037007-04-1 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249562 | 26003H | 2265J | LP1Y-STORMP-015002-25-4 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249561 | 26003H | 2264J | LP1Y-STORMP-015002-25-3 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249560 | 26003H | 2263J | LP1Y-STORMP-015002-25-2 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249559 | 26003H | 2262J | LP1Y-STORMP-015002-25-1 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249558 | 26003H | 2261J | LP1Y-STORMP-015002-12-3 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249557 | 26003H | 2260J | LP1Y-STORMP-015002-12-2 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249556 | 26003H | 2259J | LP1Y-STORMP-015002-12-1 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249555 | 26003H | 2258J | LP1Y-STORM-100409-01-2 | LP1Y-STORM-100409-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORM (315) (108) 100409 | STORM |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100409 |  | TFS00D003YSPP |  | 315-STORM | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249554 | 26003H | 2257J | LP1Y-STORM-100409-01-1 | LP1Y-STORM-100409-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 3" SS STORM (315) (108) 100409 | STORM |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100409 |  | TFS00D003YSPP |  | 315-STORM | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249553 | 26003H | 2256J | LP1Y-STORM-100408-01-2 | LP1Y-STORM-100408-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORM (315) 100408 | STORM |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100408 |  | TFS00D003YSPP |  | 315-STORM | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249552 | 26003H | 2255J | LP1Y-STORM-100408-01-1 | LP1Y-STORM-100408-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS STORM (315) 100408 | STORM |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100408 |  | TFS00D003YSPP |  | 315-STORM | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249551 | 26003H | 2254J | LP1Y-SRACNP-108248-01-4 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249550 | 26003H | 2253J | LP1Y-SRACNP-108248-01-3 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249549 | 26003H | 2252J | LP1Y-SRACNP-108248-01-2 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249548 | 26003H | 2251J | LP1Y-SRACNP-108248-01-1 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249547 | 26003H | 2250J | LP1Y-SRACNP-108235-02-2 | LP1Y-SRACNP-108235-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249546 | 26003H | 2249J | LP1Y-SRACNP-108235-02-1 | LP1Y-SRACNP-108235-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249545 | 26003H | 2248J | LP1Y-SRACNP-108235-01-2 | LP1Y-SRACNP-108235-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249544 | 26003H | 2247J | LP1Y-SRACNP-108235-01-1 | LP1Y-SRACNP-108235-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249543 | 26003H | 2246J | LP1Y-SRACNP-108219-04-2 | LP1Y-SRACNP-108219-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249542 | 26003H | 2245J | LP1Y-SRACNP-108219-04-1 | LP1Y-SRACNP-108219-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249541 | 26003H | 2244J | LP1Y-SRACNP-108219-02-2 | LP1Y-SRACNP-108219-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249540 | 26003H | 2243J | LP1Y-SRACNP-108219-02-1 | LP1Y-SRACNP-108219-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249539 | 26003H | 2242J | LP1Y-SRACNP-108213-02-2 | LP1Y-SRACNP-108213-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249538 | 26003H | 2241J | LP1Y-SRACNP-108213-02-1 | LP1Y-SRACNP-108213-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249537 | 26003H | 2240J | LP1Y-SRACNP-108213-01-1 | LP1Y-SRACNP-108213-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249536 | 26003H | 2239J | LP1Y-SRACNP-108206-03-3 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249535 | 26003H | 2238J | LP1Y-SRACNP-108206-03-2 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249534 | 26003H | 2237J | LP1Y-SRACNP-108206-03-1 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249533 | 26003H | 2236J | LP1Y-SRACNP-108206-02-5 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249532 | 26003H | 2235J | LP1Y-SRACNP-108206-02-4 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249531 | 26003H | 2234J | LP1Y-SRACNP-108206-02-3 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249530 | 26003H | 2233J | LP1Y-SRACNP-108206-02-2 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249529 | 26003H | 2232J | LP1Y-SRACNP-108206-02-1 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249528 | 26003H | 2231J | LP1Y-SRACNP-108206-01-2 | LP1Y-SRACNP-108206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249527 | 26003H | 2230J | LP1Y-SRACNP-108206-01-1 | LP1Y-SRACNP-108206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249526 | 26003H | 2229J | LP1Y-SRACNP-108205-02-3 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249525 | 26003H | 2228J | LP1Y-SRACNP-108205-02-2 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249524 | 26003H | 2227J | LP1Y-SRACNP-108205-02-1 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249523 | 26003H | 2226J | LP1Y-SRACNP-108204-05-1 | LP1Y-SRACNP-108204-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249522 | 26003H | 2225J | LP1Y-SRACNP-108204-03-1 | LP1Y-SRACNP-108204-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249521 | 26003H | 2224J | LP1Y-SRACNP-108204-02-2 | LP1Y-SRACNP-108204-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249520 | 26003H | 2223J | LP1Y-SRACNP-108204-02-1 | LP1Y-SRACNP-108204-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249519 | 26003H | 2222J | LP1Y-SRACNP-108204-01-5 | LP1Y-SRACNP-108204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249518 | 26003H | 2221J | LP1Y-SRACNP-108204-01-4 | LP1Y-SRACNP-108204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249517 | 26003H | 2220J | LP1Y-SRACNP-108204-01-3 | LP1Y-SRACNP-108204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249516 | 26003H | 2219J | LP1Y-SRACNP-108204-01-2 | LP1Y-SRACNP-108204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249515 | 26003H | 2218J | LP1Y-SRACNP-108204-01-1 | LP1Y-SRACNP-108204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249514 | 26003H | 2217J | LP1Y-SRACNP-108203-02-4 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249513 | 26003H | 2216J | LP1Y-SRACNP-108203-02-3 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249512 | 26003H | 2215J | LP1Y-SRACNP-108203-02-2 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249511 | 26003H | 2214J | LP1Y-SRACNP-108203-02-1 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249510 | 26003H | 2213J | LP1Y-SRACNP-108203-01-2 | LP1Y-SRACNP-108203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249509 | 26003H | 2212J | LP1Y-SRACNP-108203-01-1 | LP1Y-SRACNP-108203-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249508 | 26003H | 2211J | LP1Y-SRACNP-108135-02-3 | LP1Y-SRACNP-108135-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249507 | 26003H | 2210J | LP1Y-SRACNP-108135-02-2 | LP1Y-SRACNP-108135-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249506 | 26003H | 2209J | LP1Y-SRACNP-108135-02-1 | LP1Y-SRACNP-108135-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249505 | 26003H | 2208J | LP1Y-SRACNP-108135-01-2 | LP1Y-SRACNP-108135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249504 | 26003H | 2207J | LP1Y-SRACNP-108135-01-1 | LP1Y-SRACNP-108135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249503 | 26003H | 2206J | LP1Y-SRACNP-108119-03-3 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249502 | 26003H | 2205J | LP1Y-SRACNP-108119-03-4 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249501 | 26003H | 2204J | LP1Y-SRACNP-108119-03-2 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249500 | 26003H | 2203J | LP1Y-SRACNP-108119-03-1 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249499 | 26003H | 2202J | LP1Y-SRACNP-108119-01-3 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249498 | 26003H | 2201J | LP1Y-SRACNP-108119-01-2 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249497 | 26003H | 2200J | LP1Y-SRACNP-108119-01-1 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249496 | 26003H | 2199J | LP1Y-SRACNP-108111-03-3 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249495 | 26003H | 2198J | LP1Y-SRACNP-108111-03-2 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249494 | 26003H | 2197J | LP1Y-SRACNP-108111-03-1 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247984 | 26003H | 2196J | LP1Y-SRACNP-108111-02-1 | LP1Y-SRACNP-108111-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247983 | 26003H | 2195J | LP1Y-SRACNP-108106-04-3 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247982 | 26003H | 2194J | LP1Y-SRACNP-108106-04-2 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247981 | 26003H | 2193J | LP1Y-SRACNP-108106-04-1 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247980 | 26003H | 2192J | LP1Y-SRACNP-108106-03-5 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247979 | 26003H | 2191J | LP1Y-SRACNP-108106-03-4 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247978 | 26003H | 2190J | LP1Y-SRACNP-108106-03-3 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247977 | 26003H | 2189J | LP1Y-SRACNP-108106-03-2 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247976 | 26003H | 2188J | LP1Y-SRACNP-108106-03-1 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247975 | 26003H | 2187J | LP1Y-SRACNP-108106-02-2 | LP1Y-SRACNP-108106-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247974 | 26003H | 2186J | LP1Y-SRACNP-108106-02-1 | LP1Y-SRACNP-108106-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247973 | 26003H | 2185J | LP1Y-SRACNP-108105-01-3 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247972 | 26003H | 2184J | LP1Y-SRACNP-108105-01-2 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247971 | 26003H | 2183J | LP1Y-SRACNP-108105-01-1 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247970 | 26003H | 2182J | LP1Y-SRACNP-108104-09-3 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247969 | 26003H | 2181J | LP1Y-SRACNP-108104-09-2 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247968 | 26003H | 2180J | LP1Y-SRACNP-108104-09-1 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247967 | 26003H | 2179J | LP1Y-SRACNP-108104-08-2 | LP1Y-SRACNP-108104-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247966 | 26003H | 2178J | LP1Y-SRACNP-108104-08-1 | LP1Y-SRACNP-108104-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247965 | 26003H | 2177J | LP1Y-SRACNP-108104-07-2 | LP1Y-SRACNP-108104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247964 | 26003H | 2176J | LP1Y-SRACNP-108104-07-1 | LP1Y-SRACNP-108104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247963 | 26003H | 2175J | LP1Y-SRACNP-108104-06-5 | LP1Y-SRACNP-108104-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247962 | 26003H | 2174J | LP1Y-SRACNP-108104-06-4 | LP1Y-SRACNP-108104-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247961 | 26003H | 2173J | LP1Y-SRACNP-108104-06-3 | LP1Y-SRACNP-108104-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247960 | 26003H | 2172J | LP1Y-SRACNP-108104-06-2 | LP1Y-SRACNP-108104-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247959 | 26003H | 2171J | LP1Y-SRACNP-108104-06-1 | LP1Y-SRACNP-108104-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247958 | 26003H | 2170J | LP1Y-SRACNP-108103-02-5 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247957 | 26003H | 2169J | LP1Y-SRACNP-108103-02-4 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247956 | 26003H | 2168J | LP1Y-SRACNP-108103-02-3 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247955 | 26003H | 2167J | LP1Y-SRACNP-108103-02-2 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247954 | 26003H | 2166J | LP1Y-SRACNP-108103-02-1 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247953 | 26003H | 2165J | LP1Y-SRACNP-108103-01-3 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247952 | 26003H | 2164J | LP1Y-SRACNP-108103-01-2 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247951 | 26003H | 2163J | LP1Y-SRACNP-108103-01-1 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247950 | 26003H | 2162J | LP1Y-SRACNP-108102-01-6 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247949 | 26003H | 2161J | LP1Y-SRACNP-108102-01-5 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247948 | 26003H | 2160J | LP1Y-SRACNP-108102-01-4 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247947 | 26003H | 2159J | LP1Y-SRACNP-108102-01-3 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247946 | 26003H | 2158J | LP1Y-SRACNP-108102-01-2 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247945 | 26003H | 2157J | LP1Y-SRACNP-108102-01-1 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247944 | 26003H | 2156J | LP1Y-SRACNP-108009-01-3 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247943 | 26003H | 2155J | LP1Y-SRACNP-108009-01-2 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247942 | 26003H | 2154J | LP1Y-SRACNP-108009-01-1 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247941 | 26003H | 2153J | LP1Y-SRACNP-108006-03-2 | LP1Y-SRACNP-108006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247940 | 26003H | 2152J | LP1Y-SRACNP-108006-03-1 | LP1Y-SRACNP-108006-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247939 | 26003H | 2151J | LP1Y-SRACNP-108006-01-5 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247938 | 26003H | 2150J | LP1Y-SRACNP-108006-01-4 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247937 | 26003H | 2149J | LP1Y-SRACNP-108006-01-3 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247936 | 26003H | 2148J | LP1Y-SRACNP-108006-01-2 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247935 | 26003H | 2147J | LP1Y-SRACNP-108006-01-1 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247934 | 26003H | 2146J | LP1Y-SRACNP-011010-04-4 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247933 | 26003H | 2145J | LP1Y-SRACNP-011010-04-3 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247932 | 26003H | 2144J | LP1Y-SRACNP-011010-04-2 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247931 | 26003H | 2143J | LP1Y-SRACNP-011010-04-1 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247930 | 26003H | 2142C | LP1Y-SC-034181-01-1 | LP1Y-SC-034181-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 0.75" CS SC (2) (101) 034181 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034181 |  | TFS00D001YSPP |  | 2-SC | NONE | 3/4" | CS | 1.5 | 0 | 1.5 | 6.9092 | 5.72 | sq ft | 4.22 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247929 | 26003H | 2141C | LP1Y-SC-034108-01-1 | LP1Y-SC-034108-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 1" CS SC (2) (101) 034108 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034108 |  | TFS00D001YSPP |  | 2-SC | NONE | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247928 | 26003H | 2140C | LP1Y-SC-034106-01-1 | LP1Y-SC-034106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 1" CS SC (2) (101) 034106 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034106 |  | TFS00D001YSPP |  | 2-SC | NONE | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247927 | 26003H | 2139C | LP1Y-SC-034104-01-1 | LP1Y-SC-034104-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 1" CS SC (2) (101) 034104 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034104 |  | TFS00D001YSPP |  | 2-SC | NONE | 1" | CS | 2 | 0 | 2 | 9.4101 | 5.38 | sq ft | 3.88 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247926 | 26003H | 2138C | LP1Y-SC-018161-01-1 | LP1Y-SC-018161-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018161 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018161 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247925 | 26003H | 2137C | LP1Y-SC-018159-01-1 | LP1Y-SC-018159-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS SC (2) (101) 018159 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018159 |  | TFS00D007YSPP |  | 2-SC | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247924 | 26003H | 2136C | LP1Y-SC-018153-01-1 | LP1Y-SC-018153-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS SC (2) (101) 018153 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018153 |  | TFS00D007YSPP |  | 2-SC | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247923 | 26003H | 2135C | LP1Y-SC-018146-01-1 | LP1Y-SC-018146-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 0.75" CS SC (2) (101) 018146 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018146 |  | TFS00D001YSPP |  | 2-SC | NONE | 3/4" | CS | 1.5 | 0 | 1.5 | 6.5341 | 5.47 | sq ft | 3.97 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247922 | 26003H | 2134C | LP1Y-SC-018144-01-1 | LP1Y-SC-018144-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 |  |  | LP1Y 0.75" CS SC (2) (101) 018144 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018144 |  | TFS00D001YSPP |  | 2-SC | NONE | 3/4" | CS | 1.5 | 0 | 1.5 | 6.5188 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247921 | 26003H | 2133C | LP1Y-SC-018110-01-1 | LP1Y-SC-018110-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018110 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018110 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247920 | 26003H | 2132C | LP1Y-SC-018108-01-1 | LP1Y-SC-018108-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018108 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018108 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247919 | 26003H | 2131C | LP1Y-SC-018106-01-1 | LP1Y-SC-018106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018106 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018106 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247918 | 26003H | 2130C | LP1Y-SC-018104-01-1 | LP1Y-SC-018104-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018104 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018104 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247917 | 26003H | 2129C | LP1Y-SC-018102-01-1 | LP1Y-SC-018102-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS SC (2) (101) 018102 | SC |  | 101 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018102 |  | TFS00D007YSPP |  | 2-SC | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247916 | 26003H | 2128J | LP1Y-S(130)-166309-01-3 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247915 | 26003H | 2127J | LP1Y-S(130)-166309-01-2 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247914 | 26003H | 2126J | LP1Y-S(130)-166309-01-1 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247913 | 26003H | 2125J | LP1Y-S(130)-166308-01-3 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247912 | 26003H | 2124J | LP1Y-S(130)-166308-01-2 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247911 | 26003H | 2123J | LP1Y-S(130)-166308-01-1 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247910 | 26003H | 2122J | LP1Y-S(130)-166206-01-3 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247909 | 26003H | 2121J | LP1Y-S(130)-166206-01-2 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247908 | 26003H | 2120J | LP1Y-S(130)-166206-01-1 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247907 | 26003H | 2119J | LP1Y-S(130)-166205-01-3 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247906 | 26003H | 2118J | LP1Y-S(130)-166205-01-2 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247905 | 26003H | 2117J | LP1Y-S(130)-166205-01-1 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247904 | 26003H | 2116J | LP1Y-S(130)-165805-01-3 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 28.2138 | 20.88 | sq ft | 19.88 | ft | 2026-02-13 |  |  |  |  | 2026-03-19 | Jacob Perez | 2026-03-19 | George Allahverdian | 2026-03-19 | Jacob Perez | 2026-03-19 | Jacob Perez | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247903 | 26003H | 2115J | LP1Y-S(130)-165805-01-7 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 2.2731 | 1.73 | sq ft | 1.23 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247902 | 26003H | 2114J | LP1Y-S(130)-165805-01-6 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 9.2412 | 10.46 | sq ft | 5.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247901 | 26003H | 2113J | LP1Y-S(130)-165805-01-5 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 2 | 2 | 0 | 11.6188 | 9.54 | sq ft | 8.04 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247900 | 26003H | 2112J | LP1Y-S(130)-165805-01-4 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 8.1167 | 8.36 | sq ft | 5.36 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247899 | 26003H | 2111J | LP1Y-S(130)-165805-01-2 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 6 | 6 | 0 | 5.9638 | 10.71 | sq ft | 3.21 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247898 | 26003H | 2110J | LP1Y-S(130)-165805-01-1 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 28.2138 | 20.88 | sq ft | 19.88 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247897 | 26003H | 2109J | LP1Y-S(130)-165705-01-3 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247896 | 26003H | 2108J | LP1Y-S(130)-165705-01-6 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247895 | 26003H | 2107J | LP1Y-S(130)-165705-01-5 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247894 | 26003H | 2106J | LP1Y-S(130)-165705-01-4 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247893 | 26003H | 2105J | LP1Y-S(130)-165705-01-2 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247892 | 26003H | 2104J | LP1Y-S(130)-165705-01-1 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247891 | 26003H | 2103J | LP1Y-S(130)-165405-01-3 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247890 | 26003H | 2102J | LP1Y-S(130)-165405-01-2 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247889 | 26003H | 2101J | LP1Y-S(130)-165405-01-1 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247888 | 26003H | 2100J | LP1Y-S(130)-165318-01-2 | LP1Y-S(130)-165318-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165318 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165318 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247887 | 26003H | 2099J | LP1Y-S(130)-165318-01-1 | LP1Y-S(130)-165318-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165318 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165318 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247886 | 26003H | 2098J | LP1Y-S(130)-165317-01-2 | LP1Y-S(130)-165317-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165317 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165317 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247885 | 26003H | 2097J | LP1Y-S(130)-165317-01-1 | LP1Y-S(130)-165317-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165317 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165317 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247884 | 26003H | 2096J | LP1Y-S(130)-165316-01-2 | LP1Y-S(130)-165316-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165316 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165316 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247883 | 26003H | 2095J | LP1Y-S(130)-165316-01-1 | LP1Y-S(130)-165316-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165316 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165316 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247882 | 26003H | 2094J | LP1Y-S(130)-165315-01-2 | LP1Y-S(130)-165315-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165315 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165315 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247881 | 26003H | 2093J | LP1Y-S(130)-165315-01-1 | LP1Y-S(130)-165315-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS S(130) (315) (103) 165315 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165315 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247880 | 26003H | 2092J | LP1Y-S(130)-165216-01-3 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247879 | 26003H | 2091J | LP1Y-S(130)-165216-01-2 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247878 | 26003H | 2090J | LP1Y-S(130)-165216-01-1 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247877 | 26003H | 2089J | LP1Y-S(130)-165215-01-3 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247876 | 26003H | 2088J | LP1Y-S(130)-165215-01-2 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247875 | 26003H | 2087J | LP1Y-S(130)-165215-01-1 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247874 | 26003H | 2086J | LP1Y-S(130)-165116-01-3 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247873 | 26003H | 2085J | LP1Y-S(130)-165116-01-2 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247872 | 26003H | 2084J | LP1Y-S(130)-165116-01-1 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247871 | 26003H | 2083J | LP1Y-S(130)-165115-01-3 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247870 | 26003H | 2082J | LP1Y-S(130)-165115-01-2 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247869 | 26003H | 2081J | LP1Y-S(130)-165115-01-1 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247868 | 26003H | 2080C | LP1Y-S(130)-034180-01-3 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247867 | 26003H | 2079C | LP1Y-S(130)-034180-01-2 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247866 | 26003H | 2078C | LP1Y-S(130)-034180-01-1 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247865 | 26003H | 2077C | LP1Y-S(130)-034107-02-3 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247864 | 26003H | 2076C | LP1Y-S(130)-034107-02-2 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247863 | 26003H | 2075C | LP1Y-S(130)-034107-02-1 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247862 | 26003H | 2074C | LP1Y-S(130)-034105-02-3 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247861 | 26003H | 2073C | LP1Y-S(130)-034105-02-2 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247860 | 26003H | 2072C | LP1Y-S(130)-034105-02-1 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247859 | 26003H | 2071C | LP1Y-S(130)-034103-02-3 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247858 | 26003H | 2070C | LP1Y-S(130)-034103-02-2 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247857 | 26003H | 2069C | LP1Y-S(130)-034103-02-1 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247856 | 26003H | 2068C | LP1Y-S(130)-034058-02-4 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247855 | 26003H | 2067C | LP1Y-S(130)-034058-02-3 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247854 | 26003H | 2066C | LP1Y-S(130)-034058-02-2 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247853 | 26003H | 2065C | LP1Y-S(130)-034058-02-1 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247852 | 26003H | 2064C | LP1Y-S(130)-034046-01-2 | LP1Y-S(130)-034046-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034046 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034046 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247851 | 26003H | 2063C | LP1Y-S(130)-034046-01-1 | LP1Y-S(130)-034046-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034046 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034046 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247850 | 26003H | 2062C | LP1Y-S(130)-018160-02-3 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247849 | 26003H | 2061C | LP1Y-S(130)-018160-02-2 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247848 | 26003H | 2060C | LP1Y-S(130)-018160-02-1 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247847 | 26003H | 2059C | LP1Y-S(130)-018158-01-3 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247846 | 26003H | 2058C | LP1Y-S(130)-018158-01-2 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247845 | 26003H | 2057C | LP1Y-S(130)-018158-01-1 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247844 | 26003H | 2056C | LP1Y-S(130)-018152-01-6 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247843 | 26003H | 2055C | LP1Y-S(130)-018152-01-5 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247842 | 26003H | 2054C | LP1Y-S(130)-018152-01-4 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247841 | 26003H | 2053C | LP1Y-S(130)-018152-01-3 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247840 | 26003H | 2052C | LP1Y-S(130)-018152-01-2 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247839 | 26003H | 2051C | LP1Y-S(130)-018152-01-1 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247838 | 26003H | 2050C | LP1Y-S(130)-018145-02-3 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247837 | 26003H | 2049C | LP1Y-S(130)-018145-02-2 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247836 | 26003H | 2048C | LP1Y-S(130)-018145-02-1 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247835 | 26003H | 2047C | LP1Y-S(130)-018143-02-3 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247834 | 26003H | 2046C | LP1Y-S(130)-018143-02-2 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247833 | 26003H | 2045C | LP1Y-S(130)-018143-02-1 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247832 | 26003H | 2044C | LP1Y-S(130)-018137-02-2 | LP1Y-S(130)-018137-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247831 | 26003H | 2043C | LP1Y-S(130)-018137-02-1 | LP1Y-S(130)-018137-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247830 | 26003H | 2042C | LP1Y-S(130)-018137-01-2 | LP1Y-S(130)-018137-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247829 | 26003H | 2041C | LP1Y-S(130)-018137-01-1 | LP1Y-S(130)-018137-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247828 | 26003H | 2040C | LP1Y-S(130)-018136-01-3 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247827 | 26003H | 2039C | LP1Y-S(130)-018136-01-2 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247826 | 26003H | 2038C | LP1Y-S(130)-018136-01-1 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247825 | 26003H | 2037C | LP1Y-S(130)-018135-01-4 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247824 | 26003H | 2036C | LP1Y-S(130)-018135-01-3 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247823 | 26003H | 2035C | LP1Y-S(130)-018135-01-2 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247822 | 26003H | 2034C | LP1Y-S(130)-018135-01-1 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247821 | 26003H | 2033C | LP1Y-S(130)-018134-01-4 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247820 | 26003H | 2032C | LP1Y-S(130)-018134-01-3 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247819 | 26003H | 2031C | LP1Y-S(130)-018134-01-2 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247818 | 26003H | 2030C | LP1Y-S(130)-018134-01-1 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247817 | 26003H | 2029C | LP1Y-S(130)-018132-01-3 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247816 | 26003H | 2028C | LP1Y-S(130)-018132-01-2 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247815 | 26003H | 2027C | LP1Y-S(130)-018132-01-1 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247814 | 26003H | 2026C | LP1Y-S(130)-018131-02-2 | LP1Y-S(130)-018131-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247813 | 26003H | 2025C | LP1Y-S(130)-018131-02-1 | LP1Y-S(130)-018131-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247812 | 26003H | 2024C | LP1Y-S(130)-018131-01-2 | LP1Y-S(130)-018131-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 12.75 | 12 | 0.75 | 34.3717 | 24.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247811 | 26003H | 2023C | LP1Y-S(130)-018131-01-1 | LP1Y-S(130)-018131-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 4 | 4 | 0 | 17.0466 | 7.31 | sq ft | 2.81 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247810 | 26003H | 2022C | LP1Y-S(130)-018109-02-3 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247809 | 26003H | 2021C | LP1Y-S(130)-018109-02-2 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247808 | 26003H | 2020C | LP1Y-S(130)-018109-02-1 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247807 | 26003H | 2019C | LP1Y-S(130)-018107-02-3 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247806 | 26003H | 2018C | LP1Y-S(130)-018107-02-2 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247805 | 26003H | 2017C | LP1Y-S(130)-018107-02-1 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247804 | 26003H | 2016C | LP1Y-S(130)-018105-02-3 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247803 | 26003H | 2015C | LP1Y-S(130)-018105-02-2 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247802 | 26003H | 2014C | LP1Y-S(130)-018105-02-1 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247801 | 26003H | 2013C | LP1Y-S(130)-018103-02-4 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247800 | 26003H | 2012C | LP1Y-S(130)-018103-02-3 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247799 | 26003H | 2011C | LP1Y-S(130)-018103-02-2 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247798 | 26003H | 2010C | LP1Y-S(130)-018103-02-1 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247797 | 26003H | 2009C | LP1Y-S(130)-018101-02-3 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247796 | 26003H | 2008C | LP1Y-S(130)-018101-02-2 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247795 | 26003H | 2007C | LP1Y-S(130)-018101-02-1 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247794 | 26003H | 2006C | LP1Y-S(130)-018082-02-3 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247793 | 26003H | 2005C | LP1Y-S(130)-018082-02-2 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247792 | 26003H | 2004C | LP1Y-S(130)-018082-02-1 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247791 | 26003H | 2003C | LP1Y-S(130)-018079-11-2 | LP1Y-S(130)-018079-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 12.75 | 12 | 0.75 | 33.7633 | 24.17 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247790 | 26003H | 2002C | LP1Y-S(130)-018079-11-1 | LP1Y-S(130)-018079-11 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 2 | 2 | 0 | 18.2047 | 6.34 | sq ft | 3.34 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247789 | 26003H | 2001C | LP1Y-S(130)-018079-10-2 | LP1Y-S(130)-018079-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247788 | 26003H | 2000C | LP1Y-S(130)-018079-10-1 | LP1Y-S(130)-018079-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247787 | 26003H | 1999C | LP1Y-S(130)-018079-08-4 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247786 | 26003H | 1998C | LP1Y-S(130)-018079-08-3 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247785 | 26003H | 1997C | LP1Y-S(130)-018079-08-2 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247784 | 26003H | 1996C | LP1Y-S(130)-018079-08-1 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247783 | 26003H | 1995C | LP1Y-S(130)-018079-05-2 | LP1Y-S(130)-018079-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247782 | 26003H | 1994C | LP1Y-S(130)-018079-05-1 | LP1Y-S(130)-018079-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247781 | 26003H | 1993C | LP1Y-S(130)-018078-04-6 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247780 | 26003H | 1992C | LP1Y-S(130)-018078-04-4 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247779 | 26003H | 1991C | LP1Y-S(130)-018078-04-3 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247778 | 26003H | 1990C | LP1Y-S(130)-018078-04-2 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247777 | 26003H | 1989C | LP1Y-S(130)-018078-04-5 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247776 | 26003H | 1988C | LP1Y-S(130)-018078-04-1 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247775 | 26003H | 1987C | LP1Y-S(130)-018078-01-2 | LP1Y-S(130)-018078-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247774 | 26003H | 1986C | LP1Y-S(130)-018078-01-1 | LP1Y-S(130)-018078-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247773 | 26003H | 1985C | LP1Y-S(130)-018077-07-3 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247772 | 26003H | 1984C | LP1Y-S(130)-018077-07-2 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247771 | 26003H | 1983C | LP1Y-S(130)-018077-07-1 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247770 | 26003H | 1982C | LP1Y-S(130)-018077-06-2 | LP1Y-S(130)-018077-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247769 | 26003H | 1981C | LP1Y-S(130)-018077-06-1 | LP1Y-S(130)-018077-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247768 | 26003H | 1980C | LP1Y-S(130)-018077-05-1 | LP1Y-S(130)-018077-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247767 | 26003H | 1979C | LP1Y-S(130)-018077-04-3 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247766 | 26003H | 1978C | LP1Y-S(130)-018077-04-2 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247765 | 26003H | 1977C | LP1Y-S(130)-018077-04-1 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247764 | 26003H | 1976C | LP1Y-S(130)-018076-04-3 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247763 | 26003H | 1975C | LP1Y-S(130)-018076-04-2 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247762 | 26003H | 1974C | LP1Y-S(130)-018076-04-1 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247761 | 26003H | 1973C | LP1Y-S(130)-018076-02-4 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247760 | 26003H | 1972C | LP1Y-S(130)-018076-02-3 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247759 | 26003H | 1971C | LP1Y-S(130)-018076-02-2 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247758 | 26003H | 1970C | LP1Y-S(130)-018076-02-1 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247757 | 26003H | 1969C | LP1Y-S(130)-018071-05-4 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247756 | 26003H | 1968C | LP1Y-S(130)-018071-05-3 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247755 | 26003H | 1967C | LP1Y-S(130)-018071-05-2 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247754 | 26003H | 1966C | LP1Y-S(130)-018071-05-1 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247753 | 26003H | 1965C | LP1Y-S(130)-018071-04-3 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247752 | 26003H | 1964C | LP1Y-S(130)-018071-04-2 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247751 | 26003H | 1963C | LP1Y-S(130)-018071-04-1 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247750 | 26003H | 1962C | LP1Y-S(130)-018070-04-5 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247749 | 26003H | 1961C | LP1Y-S(130)-018070-04-4 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247748 | 26003H | 1960C | LP1Y-S(130)-018070-04-3 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247747 | 26003H | 1959C | LP1Y-S(130)-018070-04-2 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247746 | 26003H | 1958C | LP1Y-S(130)-018070-04-1 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247745 | 26003H | 1957C | LP1Y-S(130)-018070-03-3 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247744 | 26003H | 1956C | LP1Y-S(130)-018070-03-2 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247743 | 26003H | 1955C | LP1Y-S(130)-018070-03-1 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247742 | 26003H | 1954C | LP1Y-S(130)-018062-14-2 | LP1Y-S(130)-018062-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018062 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018062 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247741 | 26003H | 1953C | LP1Y-S(130)-018062-14-1 | LP1Y-S(130)-018062-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" CS S(130) (2) (103) 018062 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018062 |  | TFS00D003YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247740 | 26003H | 1952C | LP1Y-S(130)-018013-01-3 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247739 | 26003H | 1951C | LP1Y-S(130)-018013-01-2 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247738 | 26003H | 1950C | LP1Y-S(130)-018013-01-1 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | NONE | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247737 | 26003H | 1949C | LP1Y-S(130)-018009-01-2 | LP1Y-S(130)-018009-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018009 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018009 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247736 | 26003H | 1948C | LP1Y-S(130)-018009-01-1 | LP1Y-S(130)-018009-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018009 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018009 |  | TFS00D007YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247735 | 26003H | 1947J | LP1Y-RV-180097-01-1 | LP1Y-RV-180097-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS RV (315) 180097 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180097 |  | TFS00D007YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247734 | 26003H | 1946J | LP1Y-RV-180096-01-1 | LP1Y-RV-180096-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS RV (315) 180096 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180096 |  | TFS00D007YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247733 | 26003H | 1945J | LP1Y-RV-162310-01-2 | LP1Y-RV-162310-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS RV (315) P (108) 162310 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162310 |  | TFS00E006YSPP |  | 315-RV | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247732 | 26003H | 1944J | LP1Y-RV-162310-01-1 | LP1Y-RV-162310-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS RV (315) P (108) 162310 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162310 |  | TFS00E006YSPP |  | 315-RV | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247731 | 26003H | 1943AB | LP1Y-RV-109214-01-3 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247730 | 26003H | 1942AB | LP1Y-RV-109214-01-2 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247729 | 26003H | 1941AB | LP1Y-RV-109214-01-1 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247728 | 26003H | 1940AB | LP1Y-RV-109211-01-1 | LP1Y-RV-109211-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST RV (332) P (108) 109211 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109211 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247727 | 26003H | 1939J | LP1Y-RV-109207-01-4 | LP1Y-RV-109207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247726 | 26003H | 1938J | LP1Y-RV-109207-01-3 | LP1Y-RV-109207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247725 | 26003H | 1937J | LP1Y-RV-109207-01-2 | LP1Y-RV-109207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247724 | 26003H | 1936J | LP1Y-RV-109207-01-1 | LP1Y-RV-109207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247723 | 26003H | 1935J | LP1Y-RV-109121-01-1 | LP1Y-RV-109121-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS RV (315) (108) 109121 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109121 |  | TFS00E007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247722 | 26003H | 1934J | LP1Y-RV-109107-01-6 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247721 | 26003H | 1933J | LP1Y-RV-109107-01-5 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247720 | 26003H | 1932J | LP1Y-RV-109107-01-4 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247719 | 26003H | 1931J | LP1Y-RV-109107-01-3 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247718 | 26003H | 1930J | LP1Y-RV-109107-01-2 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247717 | 26003H | 1929J | LP1Y-RV-109107-01-1 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247716 | 26003H | 1928J | LP1Y-RV-108238-01-2 | LP1Y-RV-108238-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108238 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108238 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247715 | 26003H | 1927J | LP1Y-RV-108238-01-1 | LP1Y-RV-108238-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108238 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108238 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247714 | 26003H | 1926J | LP1Y-RV-108236-01-2 | LP1Y-RV-108236-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS RV (315) P (108) 108236 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108236 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247713 | 26003H | 1925J | LP1Y-RV-108236-01-1 | LP1Y-RV-108236-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS RV (315) P (108) 108236 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108236 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247712 | 26003H | 1924J | LP1Y-RV-108234-01-2 | LP1Y-RV-108234-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108234 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108234 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247711 | 26003H | 1923J | LP1Y-RV-108234-01-1 | LP1Y-RV-108234-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108234 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108234 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247460 | 26003H | 1922J | LP1Y-RV-108227-01-6 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247459 | 26003H | 1921J | LP1Y-RV-108227-01-5 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247458 | 26003H | 1920J | LP1Y-RV-108227-01-3 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247457 | 26003H | 1919J | LP1Y-RV-108227-01-2 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247456 | 26003H | 1918J | LP1Y-RV-108227-01-1 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247455 | 26003H | 1917J | LP1Y-RV-108138-01-2 | LP1Y-RV-108138-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108138 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108138 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247454 | 26003H | 1916J | LP1Y-RV-108138-01-1 | LP1Y-RV-108138-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108138 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108138 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247453 | 26003H | 1915J | LP1Y-RV-108136-01-1 | LP1Y-RV-108136-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS RV (315) P (108) 108136 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108136 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247452 | 26003H | 1914J | LP1Y-RV-108134-01-1 | LP1Y-RV-108134-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 3" SS RV (315) P (108) 108134 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108134 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247451 | 26003H | 1913J | LP1Y-RV-108125-01-6 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247450 | 26003H | 1912J | LP1Y-RV-108125-01-5 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247449 | 26003H | 1911J | LP1Y-RV-108125-01-3 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247448 | 26003H | 1910J | LP1Y-RV-108125-01-2 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247447 | 26003H | 1909J | LP1Y-RV-108125-01-1 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247446 | 26003H | 1908J | LP1Y-RV-102224-01-3 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247445 | 26003H | 1907J | LP1Y-RV-102224-01-2 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247444 | 26003H | 1906J | LP1Y-RV-102224-01-1 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247443 | 26003H | 1905J | LP1Y-RV-102207-01-5 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247442 | 26003H | 1904J | LP1Y-RV-102207-01-4 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247441 | 26003H | 1903J | LP1Y-RV-102207-01-3 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247440 | 26003H | 1902J | LP1Y-RV-102207-01-2 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247439 | 26003H | 1901J | LP1Y-RV-102207-01-1 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247438 | 26003H | 1900J | LP1Y-RV-102107-01-2 | LP1Y-RV-102107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS RV (315) P 102107 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102107 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247437 | 26003H | 1899J | LP1Y-RV-102107-01-1 | LP1Y-RV-102107-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS RV (315) P 102107 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102107 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247436 | 26003H | 1898J | LP1Y-RV-102015-01-6 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247435 | 26003H | 1897J | LP1Y-RV-102015-01-5 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247434 | 26003H | 1896J | LP1Y-RV-102015-01-4 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247433 | 26003H | 1895J | LP1Y-RV-102015-01-3 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247432 | 26003H | 1894J | LP1Y-RV-102015-01-2 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247431 | 26003H | 1893J | LP1Y-RV-102015-01-1 | LP1Y-RV-102015-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247430 | 26003H | 1892J | LP1Y-RV-101718-01-2 | LP1Y-RV-101718-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS RV (315) (108) 101718 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101718 |  | TFS00D005YSPP |  | 315-RV | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247429 | 26003H | 1891J | LP1Y-RV-101718-01-1 | LP1Y-RV-101718-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS RV (315) (108) 101718 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101718 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247428 | 26003H | 1890D | LP1Y-RV-101517-01-3 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247427 | 26003H | 1889D | LP1Y-RV-101517-01-2 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247426 | 26003H | 1888D | LP1Y-RV-101517-01-1 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247425 | 26003H | 1887J | LP1Y-RV-101017-03-1 | LP1Y-RV-101017-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS RV (315) (108) 101017 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101017 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247424 | 26003H | 1886J | LP1Y-RV-101017-01-1 | LP1Y-RV-101017-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS RV (315) (108) 101017 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101017 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247423 | 26003H | 1885J | LP1Y-RV-101008-01-2 | LP1Y-RV-101008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247422 | 26003H | 1884J | LP1Y-RV-101008-01-1 | LP1Y-RV-101008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247421 | 26003H | 1883J | LP1Y-RV-101007-01-2 | LP1Y-RV-101007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247420 | 26003H | 1882J | LP1Y-RV-101007-01-1 | LP1Y-RV-101007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247419 | 26003H | 1881J | LP1Y-RV-100410-01-1 | LP1Y-RV-100410-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS RV (315) (108) 100410 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100410 |  | TFS00D003YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247418 | 26003H | 1880J | LP1Y-RV-100317-04-2 | LP1Y-RV-100317-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247417 | 26003H | 1879J | LP1Y-RV-100317-04-1 | LP1Y-RV-100317-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247416 | 26003H | 1878J | LP1Y-RV-100317-01-1 | LP1Y-RV-100317-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247415 | 26003H | 1877J | LP1Y-RV-100316-01-2 | LP1Y-RV-100316-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100316 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100316 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 15.25 | 13 | 2.25 | 73.15 | 30.21 | sq ft | 7.21 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247414 | 26003H | 1876J | LP1Y-RV-100316-01-1 | LP1Y-RV-100316-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100316 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100316 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 6 | 6 | 0 | 16.8988 | 7.73 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S247413 | 26003H | 1875J | LP1Y-RV-100313-01-2 | LP1Y-RV-100313-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100313 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100313 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 11 | 11 | 0 | 59.0538 | 21.84 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247412 | 26003H | 1874J | LP1Y-RV-100313-01-1 | LP1Y-RV-100313-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100313 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100313 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247411 | 26003H | 1873J | LP1Y-RV-100308-01-5 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247410 | 26003H | 1872J | LP1Y-RV-100308-01-4 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247409 | 26003H | 1871J | LP1Y-RV-100308-01-3 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247408 | 26003H | 1870J | LP1Y-RV-100308-01-2 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247407 | 26003H | 1869J | LP1Y-RV-100308-01-1 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247406 | 26003H | 1868J | LP1Y-RV-100212-01-1 | LP1Y-RV-100212-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100212 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100212 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 21.25 | 19 | 2.25 | 80.1213 | 33.52 | sq ft | 9.02 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247405 | 26003H | 1867J | LP1Y-RV-100208-01-2 | LP1Y-RV-100208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100208 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100208 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247404 | 26003H | 1866J | LP1Y-RV-100208-01-1 | LP1Y-RV-100208-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS RV (315) P (108) 100208 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100208 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247403 | 26003H | 1865J | LP1Y-RV-017083-01-3 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247402 | 26003H | 1864J | LP1Y-RV-017083-01-2 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247401 | 26003H | 1863J | LP1Y-RV-017083-01-1 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247400 | 26003H | 1862J | LP1Y-RV-015008-01-1 | LP1Y-RV-015008-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D003YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247399 | 26003H | 1861J | LP1Y-RV-015007-01-1 | LP1Y-RV-015007-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D003YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247398 | 26003H | 1860J | LP1Y-PWP-850051-01-3 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247397 | 26003H | 1859J | LP1Y-PWP-850051-01-2 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247396 | 26003H | 1858J | LP1Y-PWP-850051-01-1 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247395 | 26003H | 1857J | LP1Y-PWP-108074-05-1 | LP1Y-PWP-108074-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247394 | 26003H | 1856J | LP1Y-PWP-108074-04-2 | LP1Y-PWP-108074-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247393 | 26003H | 1855J | LP1Y-PWP-108074-04-1 | LP1Y-PWP-108074-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247392 | 26003H | 1854J | LP1Y-PWP-108074-01-3 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247391 | 26003H | 1853J | LP1Y-PWP-108074-01-2 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247390 | 26003H | 1852J | LP1Y-PWP-108074-01-1 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247389 | 26003H | 1851J | LP1Y-PWP-102072-02-1 | LP1Y-PWP-102072-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PWP (315) (108) 102072 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102072 |  | TFS00D006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247388 | 26003H | 1850J | LP1Y-PWP-102072-01-1 | LP1Y-PWP-102072-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PWP (315) P (108) 102072 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102072 |  | TFS00D006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247387 | 26003H | 1849J | LP1Y-PWP-101716-02-4 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247386 | 26003H | 1848J | LP1Y-PWP-101716-02-3 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247385 | 26003H | 1847J | LP1Y-PWP-101716-02-2 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247384 | 26003H | 1846J | LP1Y-PWP-101716-02-1 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247383 | 26003H | 1845J | LP1Y-PWP-101716-01-2 | LP1Y-PWP-101716-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247382 | 26003H | 1844J | LP1Y-PWP-101716-01-1 | LP1Y-PWP-101716-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247381 | 26003H | 1843J | LP1Y-PWP-101707-04-4 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247380 | 26003H | 1842J | LP1Y-PWP-101707-04-3 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247379 | 26003H | 1841J | LP1Y-PWP-101707-04-2 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247378 | 26003H | 1840J | LP1Y-PWP-101707-04-1 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247377 | 26003H | 1839J | LP1Y-PWP-101707-03-2 | LP1Y-PWP-101707-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247376 | 26003H | 1838J | LP1Y-PWP-101707-03-1 | LP1Y-PWP-101707-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247375 | 26003H | 1837J | LP1Y-PWP-101707-01-1 | LP1Y-PWP-101707-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247374 | 26003H | 1836D | LP1Y-PWP-101706-10-4 | LP1Y-PWP-101706-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247373 | 26003H | 1835D | LP1Y-PWP-101706-10-3 | LP1Y-PWP-101706-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247372 | 26003H | 1834D | LP1Y-PWP-101706-10-2 | LP1Y-PWP-101706-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247371 | 26003H | 1833D | LP1Y-PWP-101706-10-1 | LP1Y-PWP-101706-10 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247370 | 26003H | 1832D | LP1Y-PWP-101706-09-2 | LP1Y-PWP-101706-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247369 | 26003H | 1831D | LP1Y-PWP-101706-09-1 | LP1Y-PWP-101706-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247368 | 26003H | 1830D | LP1Y-PWP-101706-08-2 | LP1Y-PWP-101706-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247367 | 26003H | 1829D | LP1Y-PWP-101706-08-1 | LP1Y-PWP-101706-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247366 | 26003H | 1828D | LP1Y-PWP-101706-07-6 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247365 | 26003H | 1827D | LP1Y-PWP-101706-07-5 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247364 | 26003H | 1826D | LP1Y-PWP-101706-07-4 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247363 | 26003H | 1825D | LP1Y-PWP-101706-07-3 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247362 | 26003H | 1824D | LP1Y-PWP-101706-07-2 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247361 | 26003H | 1823D | LP1Y-PWP-101706-07-1 | LP1Y-PWP-101706-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247360 | 26003H | 1822D | LP1Y-PWP-101706-06-1 | LP1Y-PWP-101706-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 2" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247359 | 26003H | 1821D | LP1Y-PWP-101706-02-3 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247358 | 26003H | 1820D | LP1Y-PWP-101706-02-2 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247357 | 26003H | 1819D | LP1Y-PWP-101706-02-1 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247356 | 26003H | 1818J | LP1Y-PWP-101705-02-3 | LP1Y-PWP-101705-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247355 | 26003H | 1817J | LP1Y-PWP-101705-02-2 | LP1Y-PWP-101705-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247354 | 26003H | 1816J | LP1Y-PWP-101705-02-1 | LP1Y-PWP-101705-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247353 | 26003H | 1815J | LP1Y-PWP-101705-01-3 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247352 | 26003H | 1814J | LP1Y-PWP-101705-01-2 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247351 | 26003H | 1813J | LP1Y-PWP-101705-01-1 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247350 | 26003H | 1812J | LP1Y-PWP-101702-04-5 | LP1Y-PWP-101702-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247349 | 26003H | 1811J | LP1Y-PWP-101702-04-4 | LP1Y-PWP-101702-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247348 | 26003H | 1810J | LP1Y-PWP-101702-04-3 | LP1Y-PWP-101702-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247347 | 26003H | 1809J | LP1Y-PWP-101702-04-2 | LP1Y-PWP-101702-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247346 | 26003H | 1808J | LP1Y-PWP-101702-04-1 | LP1Y-PWP-101702-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247345 | 26003H | 1807J | LP1Y-PWP-101702-03-2 | LP1Y-PWP-101702-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247344 | 26003H | 1806J | LP1Y-PWP-101702-03-1 | LP1Y-PWP-101702-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247343 | 26003H | 1805J | LP1Y-PWP-101609-01-5 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247342 | 26003H | 1804J | LP1Y-PWP-101609-01-4 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247341 | 26003H | 1803J | LP1Y-PWP-101609-01-3 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247340 | 26003H | 1802J | LP1Y-PWP-101609-01-2 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247339 | 26003H | 1801J | LP1Y-PWP-101609-01-1 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247338 | 26003H | 1800J | LP1Y-PWP-101607-04-4 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247337 | 26003H | 1799J | LP1Y-PWP-101607-04-3 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247336 | 26003H | 1798J | LP1Y-PWP-101607-04-2 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247335 | 26003H | 1797J | LP1Y-PWP-101607-04-1 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247334 | 26003H | 1796J | LP1Y-PWP-101607-03-2 | LP1Y-PWP-101607-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247333 | 26003H | 1795J | LP1Y-PWP-101607-03-1 | LP1Y-PWP-101607-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247332 | 26003H | 1794J | LP1Y-PWP-101607-01-1 | LP1Y-PWP-101607-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247331 | 26003H | 1793J | LP1Y-PWP-101606-03-3 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247330 | 26003H | 1792J | LP1Y-PWP-101606-03-2 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247329 | 26003H | 1791J | LP1Y-PWP-101606-03-1 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247328 | 26003H | 1790J | LP1Y-PWP-101606-02-3 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247327 | 26003H | 1789J | LP1Y-PWP-101606-02-2 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247326 | 26003H | 1788J | LP1Y-PWP-101606-02-1 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247325 | 26003H | 1787J | LP1Y-PWP-101606-01-2 | LP1Y-PWP-101606-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247324 | 26003H | 1786J | LP1Y-PWP-101606-01-1 | LP1Y-PWP-101606-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247323 | 26003H | 1785J | LP1Y-PWP-101604-02-3 | LP1Y-PWP-101604-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247322 | 26003H | 1784J | LP1Y-PWP-101604-02-2 | LP1Y-PWP-101604-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247321 | 26003H | 1783J | LP1Y-PWP-101604-02-1 | LP1Y-PWP-101604-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247320 | 26003H | 1782J | LP1Y-PWP-101604-01-4 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247319 | 26003H | 1781J | LP1Y-PWP-101604-01-3 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247318 | 26003H | 1780J | LP1Y-PWP-101604-01-2 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247317 | 26003H | 1779J | LP1Y-PWP-101604-01-1 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247316 | 26003H | 1778J | LP1Y-PWP-101025-03-5 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247315 | 26003H | 1777J | LP1Y-PWP-101025-03-4 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247314 | 26003H | 1776J | LP1Y-PWP-101025-03-3 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 120 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247313 | 26003H | 1775J | LP1Y-PWP-101025-03-2 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 119 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247312 | 26003H | 1774J | LP1Y-PWP-101025-03-1 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 118 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247311 | 26003H | 1773J | LP1Y-PWP-101025-01-2 | LP1Y-PWP-101025-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 117 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247310 | 26003H | 1772J | LP1Y-PWP-101025-01-1 | LP1Y-PWP-101025-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 116 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247309 | 26003H | 1771J | LP1Y-PWP-036049-01-2 | LP1Y-PWP-036049-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 036049 | PWP |  | 115 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036049 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247308 | 26003H | 1770J | LP1Y-PWP-036049-01-1 | LP1Y-PWP-036049-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 036049 | PWP |  | 114 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036049 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247307 | 26003H | 1769J | LP1Y-PWP-036047-09-2 | LP1Y-PWP-036047-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 036047 | PWP |  | 113 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036047 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247306 | 26003H | 1768J | LP1Y-PWP-036047-09-1 | LP1Y-PWP-036047-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 036047 | PWP |  | 112 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036047 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247305 | 26003H | 1767D | LP1Y-PWP-014007-18-3 | LP1Y-PWP-014007-18 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 111 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247304 | 26003H | 1766D | LP1Y-PWP-014007-18-2 | LP1Y-PWP-014007-18 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 110 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247303 | 26003H | 1765D | LP1Y-PWP-014007-18-1 | LP1Y-PWP-014007-18 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 109 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247302 | 26003H | 1764J | LP1Y-PWP-014003-01-2 | LP1Y-PWP-014003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014003 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014003 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247301 | 26003H | 1763J | LP1Y-PWP-014003-01-1 | LP1Y-PWP-014003-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014003 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014003 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247300 | 26003H | 1762J | LP1Y-PWP-014002-15-1 | LP1Y-PWP-014002-15 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 4" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247299 | 26003H | 1761J | LP1Y-PWP-014002-14-2 | LP1Y-PWP-014002-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247298 | 26003H | 1760J | LP1Y-PWP-014002-14-1 | LP1Y-PWP-014002-14 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247297 | 26003H | 1759J | LP1Y-PWP-014002-13-2 | LP1Y-PWP-014002-13 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247296 | 26003H | 1758J | LP1Y-PWP-014002-13-1 | LP1Y-PWP-014002-13 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247295 | 26003H | 1757J | LP1Y-PWP-014002-12-5 | LP1Y-PWP-014002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247294 | 26003H | 1756J | LP1Y-PWP-014002-12-4 | LP1Y-PWP-014002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247293 | 26003H | 1755J | LP1Y-PWP-014002-12-3 | LP1Y-PWP-014002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247292 | 26003H | 1754J | LP1Y-PWP-014002-12-2 | LP1Y-PWP-014002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247291 | 26003H | 1753J | LP1Y-PWP-014002-12-1 | LP1Y-PWP-014002-12 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247290 | 26003H | 1752J | LP1Y-PWP-014002-11-2 | LP1Y-PWP-014002-11 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247289 | 26003H | 1751J | LP1Y-PWP-014002-11-1 | LP1Y-PWP-014002-11 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247288 | 26003H | 1750J | LP1Y-PWP-014002-09-4 | LP1Y-PWP-014002-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247287 | 26003H | 1749J | LP1Y-PWP-014002-09-3 | LP1Y-PWP-014002-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247286 | 26003H | 1748J | LP1Y-PWP-014002-09-2 | LP1Y-PWP-014002-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247285 | 26003H | 1747J | LP1Y-PWP-014002-09-1 | LP1Y-PWP-014002-09 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247284 | 26003H | 1746J | LP1Y-PWP-014002-08-1 | LP1Y-PWP-014002-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247283 | 26003H | 1745J | LP1Y-PWP-014002-07-2 | LP1Y-PWP-014002-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247282 | 26003H | 1744J | LP1Y-PWP-014002-07-1 | LP1Y-PWP-014002-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247281 | 26003H | 1743J | LP1Y-PWP-014002-01-2 | LP1Y-PWP-014002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247280 | 26003H | 1742J | LP1Y-PWP-014002-01-1 | LP1Y-PWP-014002-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247279 | 26003H | 1741J | LP1Y-PVP-176001-04-4 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247278 | 26003H | 1740J | LP1Y-PVP-176001-04-3 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247277 | 26003H | 1739J | LP1Y-PVP-176001-04-2 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247276 | 26003H | 1738J | LP1Y-PVP-176001-04-1 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247275 | 26003H | 1737AB | LP1Y-PVP-109213-01-3 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247274 | 26003H | 1736AB | LP1Y-PVP-109213-01-2 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247273 | 26003H | 1735AB | LP1Y-PVP-109213-01-1 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247272 | 26003H | 1734J | LP1Y-PVP-108231-01-4 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247271 | 26003H | 1733J | LP1Y-PVP-108231-01-3 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247270 | 26003H | 1732J | LP1Y-PVP-108231-01-2 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247269 | 26003H | 1731J | LP1Y-PVP-108231-01-1 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247268 | 26003H | 1730J | LP1Y-PVP-108129-01-4 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247267 | 26003H | 1729J | LP1Y-PVP-108129-01-3 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247266 | 26003H | 1728J | LP1Y-PVP-108129-01-2 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247265 | 26003H | 1727J | LP1Y-PVP-108129-01-1 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247264 | 26003H | 1726J | LP1Y-PVP-102209-01-4 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247263 | 26003H | 1725J | LP1Y-PVP-102209-01-3 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247262 | 26003H | 1724J | LP1Y-PVP-102209-01-2 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247261 | 26003H | 1723J | LP1Y-PVP-102209-01-1 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247260 | 26003H | 1722J | LP1Y-PVP-102202-01-2 | LP1Y-PVP-102202-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102202 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102202 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247259 | 26003H | 1721J | LP1Y-PVP-102202-01-1 | LP1Y-PVP-102202-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102202 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102202 |  | TFS00D006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247258 | 26003H | 1720J | LP1Y-PVP-102111-01-2 | LP1Y-PVP-102111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS PVP (315) P 102111 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102111 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247257 | 26003H | 1719J | LP1Y-PVP-102111-01-1 | LP1Y-PVP-102111-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS PVP (315) P 102111 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102111 |  | TFS00D006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247256 | 26003H | 1718J | LP1Y-PVP-102109-04-2 | LP1Y-PVP-102109-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247255 | 26003H | 1717J | LP1Y-PVP-102109-04-1 | LP1Y-PVP-102109-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D007YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247254 | 26003H | 1716J | LP1Y-PVP-102109-01-4 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247253 | 26003H | 1715J | LP1Y-PVP-102109-01-3 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247252 | 26003H | 1714J | LP1Y-PVP-102109-01-2 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247251 | 26003H | 1713J | LP1Y-PVP-102109-01-1 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247250 | 26003H | 1712J | LP1Y-PV-121006-02-1 | LP1Y-PV-121006-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 121006 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121006 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247249 | 26003H | 1711J | LP1Y-PV-121006-01-1 | LP1Y-PV-121006-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 121006 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121006 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247248 | 26003H | 1710J | LP1Y-PV-109112-01-3 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247247 | 26003H | 1709J | LP1Y-PV-109112-01-2 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247246 | 26003H | 1708J | LP1Y-PV-109112-01-1 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247245 | 26003H | 1707AB | LP1Y-PV-109062-02-4 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247244 | 26003H | 1706AB | LP1Y-PV-109062-02-3 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247243 | 26003H | 1705AB | LP1Y-PV-109062-02-2 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247242 | 26003H | 1704AB | LP1Y-PV-109062-02-1 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247241 | 26003H | 1703AB | LP1Y-PV-109062-01-1 | LP1Y-PV-109062-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247240 | 26003H | 1702J | LP1Y-PV-109061-03-2 | LP1Y-PV-109061-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247239 | 26003H | 1701J | LP1Y-PV-109061-03-1 | LP1Y-PV-109061-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247238 | 26003H | 1700J | LP1Y-PV-109061-02-5 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247237 | 26003H | 1699J | LP1Y-PV-109061-02-4 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247236 | 26003H | 1698J | LP1Y-PV-109061-02-3 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247235 | 26003H | 1697J | LP1Y-PV-109061-02-2 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247234 | 26003H | 1696J | LP1Y-PV-109061-02-1 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P017 |  |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247233 | 26003H | 1695J | LP1Y-PV-108062-02-2 | LP1Y-PV-108062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247232 | 26003H | 1694J | LP1Y-PV-108062-02-1 | LP1Y-PV-108062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247231 | 26003H | 1693J | LP1Y-PV-108062-01-2 | LP1Y-PV-108062-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247230 | 26003H | 1692J | LP1Y-PV-108062-01-1 | LP1Y-PV-108062-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247229 | 26003H | 1691J | LP1Y-PV-108061-04-2 | LP1Y-PV-108061-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247228 | 26003H | 1690J | LP1Y-PV-108061-04-1 | LP1Y-PV-108061-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247227 | 26003H | 1689J | LP1Y-PV-108061-02-1 | LP1Y-PV-108061-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247226 | 26003H | 1688J | LP1Y-PV-108061-01-2 | LP1Y-PV-108061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247225 | 26003H | 1687J | LP1Y-PV-108061-01-1 | LP1Y-PV-108061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247224 | 26003H | 1686J | LP1Y-PV-102062-02-2 | LP1Y-PV-102062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247223 | 26003H | 1685J | LP1Y-PV-102062-02-1 | LP1Y-PV-102062-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247222 | 26003H | 1684J | LP1Y-PV-102062-01-2 | LP1Y-PV-102062-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247221 | 26003H | 1683J | LP1Y-PV-102062-01-1 | LP1Y-PV-102062-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247220 | 26003H | 1682J | LP1Y-PV-102061-01-4 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247219 | 26003H | 1681J | LP1Y-PV-102061-01-3 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247218 | 26003H | 1680J | LP1Y-PV-102061-01-2 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247217 | 26003H | 1679J | LP1Y-PV-102061-01-1 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247216 | 26003H | 1678J | LP1Y-PV-101717-01-3 | LP1Y-PV-101717-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247215 | 26003H | 1677J | LP1Y-PV-101717-01-2 | LP1Y-PV-101717-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247214 | 26003H | 1676J | LP1Y-PV-101717-01-1 | LP1Y-PV-101717-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247213 | 26003H | 1675J | LP1Y-PV-101712-02-2 | LP1Y-PV-101712-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 12 | 11 | 1 | 50.0495 | 26.6 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247212 | 26003H | 1674J | LP1Y-PV-101712-02-1 | LP1Y-PV-101712-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 272.921 | 16.35 | sq ft | 2.35 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247211 | 26003H | 1673J | LP1Y-PV-101712-01-5 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 32.4655 | 8.55 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247210 | 26003H | 1672J | LP1Y-PV-101712-01-4 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 3 | 3 | 0 | 129.4264 | 29.89 | sq ft | 29.89 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247209 | 26003H | 1671J | LP1Y-PV-101712-01-3 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 179.7 | 41.5 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247208 | 26003H | 1670J | LP1Y-PV-101712-01-2 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 15 | 15 | 0 | 113.3697 | 28.22 | sq ft | 22.22 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247207 | 26003H | 1669J | LP1Y-PV-101712-01-1 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S246248 | 26003H | 1668J | LP1Y-PV-101617-01-2 | LP1Y-PV-101617-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247019 | 26003H | 1667JA | LP1Y-PV-101617-01-3 | LP1Y-PV-101617-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246247 | 26003H | 1667J | LP1Y-PV-101617-01-1 | LP1Y-PV-101617-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246246 | 26003H | 1666J | LP1Y-PV-101612-02-2 | LP1Y-PV-101612-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 12 | 11 | 1 | 50.478 | 26.7 | sq ft | 2.2 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246245 | 26003H | 1665J | LP1Y-PV-101612-02-1 | LP1Y-PV-101612-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 272.921 | 16.35 | sq ft | 2.35 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246244 | 26003H | 1664J | LP1Y-PV-101612-01-3 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251749 | 26003H | 1663JX | LP1Y-PV-101612-01-2X | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246243 | 26003H | 1663J | LP1Y-PV-101612-01-2 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | 2026-03-12 | 2026-03-23 | released |  |  | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247014 | 26003H | 1662J-L1 | LP1Y-PV-101612-01-1-L1 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246242 | 26003H | 1662J | LP1Y-PV-101612-01-1 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246241 | 26003H | 1661J | LP1Y-PV-101518-01-2 | LP1Y-PV-101518-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250444 | 26003H | 1660JA | LP1Y-PV-101518-01-1A | LP1Y-PV-101518-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246240 | 26003H | 1660J | LP1Y-PV-101518-01-1 | LP1Y-PV-101518-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246239 | 26003H | 1659D | LP1Y-PV-101510-02-2 | LP1Y-PV-101510-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 12 | 11 | 1 | 47.4733 | 27.06 | sq ft | 2.56 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246238 | 26003H | 1658D | LP1Y-PV-101510-02-1 | LP1Y-PV-101510-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 6 | 6 | 0 | 28.319 | 8.65 | sq ft | 0.65 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246237 | 26003H | 1657D | LP1Y-PV-101510-01-2 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 18 | 18 | 0 | 69.1227 | 17.02 | sq ft | 8.52 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247013 | 26003H | 1656D-L1 | LP1Y-PV-101510-01-1-L1 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246236 | 26003H | 1656D | LP1Y-PV-101510-01-1 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 21 | 21 | 0 | 116.9636 | 30.11 | sq ft | 20.11 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246235 | 26003H | 1655J | LP1Y-PV-101065-01-2 | LP1Y-PV-101065-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 3" SS PV (315) (108) 101065 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101065 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 24.5493 | 8 | 16.5493 | 60.7406 | 16.95 | sq ft | 3.71 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246234 | 26003H | 1654J | LP1Y-PV-101065-01-1 | LP1Y-PV-101065-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101065 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101065 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246233 | 26003H | 1653J | LP1Y-PV-101063-03-3 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 39 | 38 | 1 | 665.6867 | 70.13 | sq ft | 24.33 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246232 | 26003H | 1652J | LP1Y-PV-101063-03-2 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 16 | 16 | 0 | 78.2702 | 19.32 | sq ft | 11.6 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246231 | 26003H | 1651J | LP1Y-PV-101063-03-1 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 8 | 8 | 0 | 52.085 | 12 | sq ft | 8.5 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246230 | 26003H | 1650J | LP1Y-PV-101063-01-2 | LP1Y-PV-101063-01 | 1 | N | PRIORITY-1 | 2026-03-18 |  | active | client | rfi | On Hold | P014 |  |  | LP1Y 3" SS PV (315) (108) 101063 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246229 | 26003H | 1649J | LP1Y-PV-101063-01-1 | LP1Y-PV-101063-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101063 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246228 | 26003H | 1648J | LP1Y-PV-101062-01-2 | LP1Y-PV-101062-01 | 2 | N | PRIORITY-1 | 2026-03-18 |  | active | client | rfi | On Hold | P014 |  |  | LP1Y 3" SS PV (315) (108) 101062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101062 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246227 | 26003H | 1647J | LP1Y-PV-101062-01-1 | LP1Y-PV-101062-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 3" SS PV (315) (108) 101062 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101062 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246226 | 26003H | 1646J | LP1Y-PV-100307-01-2 | LP1Y-PV-100307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS PV (315) (108) 100307 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100307 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246225 | 26003H | 1645J | LP1Y-PV-100307-01-1 | LP1Y-PV-100307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS PV (315) (108) 100307 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100307 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247012 | 26003H | 1644J-L1 | LP1Y-PV-100306-01-1-L1 | LP1Y-PV-100306-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS PV (315) P (108) 100306 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100306 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246224 | 26003H | 1644J | LP1Y-PV-100306-01-1 | LP1Y-PV-100306-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS PV (315) P (108) 100306 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100306 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.525 | 7.94 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246223 | 26003H | 1643J | LP1Y-PV-100210-01-4 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246222 | 26003H | 1642J | LP1Y-PV-100210-01-3 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246221 | 26003H | 1641J | LP1Y-PV-100210-01-2 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247011 | 26003H | 1640J-L1 | LP1Y-PV-100210-01-1-L1 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246220 | 26003H | 1640J | LP1Y-PV-100210-01-1 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246219 | 26003H | 1639J | LP1Y-NAOH50-178202-07-5 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12 | 12 | 0 | 70.8228 | 17.34 | sq ft | 11.45 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246218 | 26003H | 1638J | LP1Y-NAOH50-178202-07-4 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246217 | 26003H | 1637J | LP1Y-NAOH50-178202-07-3 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 12 | 12 | 0 | 67.0998 | 19.9 | sq ft | 3.14 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246216 | 26003H | 1636J | LP1Y-NAOH50-178202-07-2 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246215 | 26003H | 1635J | LP1Y-NAOH50-178202-07-1 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 19 | 18 | 1 | 60.84 | 19.8 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246214 | 26003H | 1634J | LP1Y-NAOH50-178202-04-5 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9 | 13.83 | sq ft | 1.83 | ft | 2026-02-13 |  |  |  |  | 2026-03-18 | Jacob Perez | 2026-03-18 | George Allahverdian | 2026-03-18 | Jacob Perez | 2026-03-18 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246213 | 26003H | 1633J | LP1Y-NAOH50-178202-04-4 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246212 | 26003H | 1632J | LP1Y-NAOH50-178202-04-3 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246211 | 26003H | 1631J | LP1Y-NAOH50-178202-04-2 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 9 | 9 | 0 | 35.8045 | 24.6 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247010 | 26003H | 1630J-L1 | LP1Y-NAOH50-178202-04-1-L1 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246210 | 26003H | 1630J | LP1Y-NAOH50-178202-04-1 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.675 | 2.44 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246209 | 26003H | 1629J | LP1Y-NAOH50-178202-03-1 | LP1Y-NAOH50-178202-03 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 32 | 32 | 0 | 129.0575 | 31.9 | sq ft | 19.08 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246208 | 26003H | 1628J | LP1Y-NAOH50-178202-02-3 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246207 | 26003H | 1627J | LP1Y-NAOH50-178202-02-2 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246206 | 26003H | 1626J | LP1Y-NAOH50-178202-02-1 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246205 | 26003H | 1625J | LP1Y-NAOH50-178202-01-2 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247009 | 26003H | 1624J-L1 | LP1Y-NAOH50-178202-01-1-L1 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143091
C34-S246204 | 26003H | 1624J | LP1Y-NAOH50-178202-01-1 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 8 | 8 | 0 | 35.1103 | 8.64 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143234
C34-S246203 | 26003H | 1623J | LP1Y-NAOH50-178201-03-1 | LP1Y-NAOH50-178201-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 3" SS NAOH50 (315) P 178201 | NAOH50 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 9 | 3 | 6 | 32.0773 | 27.05 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246202 | 26003H | 1622J | LP1Y-NAOH50-178201-02-2 | LP1Y-NAOH50-178201-02 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 28 | 27 | 1 | 308.0905 | 33.55 | sq ft | 5.05 | ft | 2026-02-13 | CD: 2026-03-17; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246201 | 26003H | 1621J | LP1Y-NAOH50-178201-02-1 | LP1Y-NAOH50-178201-02 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 6 | 6 | 0 | 103.068 | 23.8 | sq ft | 22.3 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S246200 | 26003H | 1620J | LP1Y-NAOH50-178201-01-4 | LP1Y-NAOH50-178201-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 6.8602 | 2.77 | sq ft | 1.27 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246199 | 26003H | 1619J | LP1Y-NAOH50-178201-01-3 | LP1Y-NAOH50-178201-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 6 | 6 | 0 | 118.6515 | 27.4 | sq ft | 25.9 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Henrique Barahona | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S246198 | 26003H | 1618J | LP1Y-NAOH50-178201-01-2 | LP1Y-NAOH50-178201-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247008 | 26003H | 1617J-L1 | LP1Y-NAOH50-178201-01-1-L1 | LP1Y-NAOH50-178201-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246197 | 26003H | 1617J | LP1Y-NAOH50-178201-01-1 | LP1Y-NAOH50-178201-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246196 | 26003H | 1616J | LP1Y-NAOH50-108122-01-2 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247007 | 26003H | 1615J-L1 | LP1Y-NAOH50-108122-01-1-L1 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246195 | 26003H | 1615J | LP1Y-NAOH50-108122-01-1 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.3184 | 7.39 | sq ft | 1.89 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246194 | 26003H | 1614J | LP1Y-NAOH50-108121-01-3 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 25.9087 | 18.38 | sq ft | 18.38 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100%
C34-S246193 | 26003H | 1613J | LP1Y-NAOH50-108121-01-2 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247006 | 26003H | 1612J-L1 | LP1Y-NAOH50-108121-01-1-L1 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246192 | 26003H | 1612J | LP1Y-NAOH50-108121-01-1 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P016 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.2597 | 7.34 | sq ft | 1.84 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246191 | 26003H | 1611J | LP1Y-NAOH50-101704-03-5 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 47.9875 | 20.18 | sq ft | 15.68 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 80% |  |  |  | 0%
C34-S246190 | 26003H | 1610J | LP1Y-NAOH50-101704-03-4 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 9 | 9 | 0 | 26.9375 | 14.64 | sq ft | 8.14 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246189 | 26003H | 1609J | LP1Y-NAOH50-101704-03-3 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 3 | 3 | 0 | 8.8067 | 9.86 | sq ft | 4.36 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246188 | 26003H | 1608J | LP1Y-NAOH50-101704-03-2 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246187 | 26003H | 1607J | LP1Y-NAOH50-101704-03-1 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.5566 | 12.11 | sq ft | 0.61 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246186 | 26003H | 1606D | LP1Y-NAOH50-101515-01-3 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.7588 | 8.71 | sq ft | 0.71 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246185 | 26003H | 1605D | LP1Y-NAOH50-101515-01-2 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.8542 | 8.78 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246184 | 26003H | 1604D | LP1Y-NAOH50-101515-01-1 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 2" | 2205 | 6 | 6 | 0 | 11.7842 | 12.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246183 | 26003H | 1603J | LP1Y-NAOH50-101304-03-4 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 52.6488 | 21.94 | sq ft | 17.44 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 60% |  |  |  | 0%
C34-S246182 | 26003H | 1602J | LP1Y-NAOH50-101304-03-3 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.6319 | 14.19 | sq ft | 5.19 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246181 | 26003H | 1601J | LP1Y-NAOH50-101304-03-2 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247005 | 26003H | 1600J-L1 | LP1Y-NAOH50-101304-03-1-L1 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246180 | 26003H | 1600J | LP1Y-NAOH50-101304-03-1 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 4.842 | 8.35 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246179 | 26003H | 1599J | LP1Y-NAOH50-101012-03-3 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 5 | 5 | 0 | 8.7064 | 12.54 | sq ft | 3.54 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246178 | 26003H | 1598J | LP1Y-NAOH50-101012-03-2 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246177 | 26003H | 1597J | LP1Y-NAOH50-101012-03-1 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.7769 | 12.27 | sq ft | 0.77 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246176 | 26003H | 1596J | LP1Y-NAOH50-101012-02-3 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 11.0275 | 6.18 | sq ft | 1.68 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246175 | 26003H | 1595J | LP1Y-NAOH50-101012-02-2 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 32.12 | 13.5 | sq ft | 10.5 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246174 | 26003H | 1594J | LP1Y-NAOH50-101012-02-1 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 31.7763 | 13.37 | sq ft | 10.37 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 50% |  |  |  | 0%
C34-S246173 | 26003H | 1593J | LP1Y-NAOH50-100211-01-2 | LP1Y-NAOH50-100211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS NAOH50 (315) P 100211 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100211 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12 | 12 | 0 | 99.6813 | 40.43 | sq ft | 37.43 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246172 | 26003H | 1592J | LP1Y-NAOH50-100211-01-1 | LP1Y-NAOH50-100211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS NAOH50 (315) P 100211 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100211 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 14 | 14 | 0 | 68.695 | 28.69 | sq ft | 22.69 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 71% |  |  |  | 0%
C34-S246171 | 26003H | 1591J | LP1Y-NAOH50-100207-02-1 | LP1Y-NAOH50-100207-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 60.5425 | 26.61 | sq ft | 18.61 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246170 | 26003H | 1590J | LP1Y-NAOH50-100207-01-3 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 68.2 | 26.5 | sq ft | 25 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246169 | 26003H | 1589J | LP1Y-NAOH50-100207-01-2 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.8688 | 8.86 | sq ft | 5.86 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246168 | 26003H | 1588J | LP1Y-NAOH50-100207-01-1 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.4675 | 10.14 | sq ft | 7.14 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247004 | 26003H | 1587J-L1 | LP1Y-NAOH50-100206-02-1-L1 | LP1Y-NAOH50-100206-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-19 | 2026-03-19 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143089
C34-S246167 | 26003H | 1587J | LP1Y-NAOH50-100206-02-1 | LP1Y-NAOH50-100206-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 10.25 | 8 | 2.25 | 75.645 | 28.1 | sq ft | 6.6 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246166 | 26003H | 1586J | LP1Y-NAOH50-100206-01-3 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 37.9125 | 16.95 | sq ft | 9.95 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246165 | 26003H | 1585J | LP1Y-NAOH50-100206-01-2 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 7 | 7 | 0 | 35.4588 | 18.9 | sq ft | 11.4 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246164 | 26003H | 1584J | LP1Y-NAOH50-100206-01-1 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246163 | 26003H | 1583J | LP1Y-NAOH50-100204-06-2 | LP1Y-NAOH50-100204-06 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 18 | 18 | 0 | 323.8505 | 27.05 | sq ft | 12.55 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246162 | 26003H | 1582J | LP1Y-NAOH50-100204-06-1 | LP1Y-NAOH50-100204-06 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 56.6558 | 13.08 | sq ft | 11.58 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S246161 | 26003H | 1581J | LP1Y-NAOH50-100204-05-1 | LP1Y-NAOH50-100204-05 | 2 | N | PRIORITY-1 | 2026-03-18 |  | active | client | rfi | On Hold | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246160 | 26003H | 1580J | LP1Y-NAOH50-100204-02-1 | LP1Y-NAOH50-100204-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246159 | 26003H | 1579J | LP1Y-NAOH50-100204-01-4 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 9 | 8 | 1 | 32.967 | 13.7 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246158 | 26003H | 1578J | LP1Y-NAOH50-100204-01-3 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246157 | 26003H | 1577J | LP1Y-NAOH50-100204-01-2 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 10 | 9 | 1 | 47.9791 | 22.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247003 | 26003H | 1576J-L1 | LP1Y-NAOH50-100204-01-1-L1 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246156 | 26003H | 1576J | LP1Y-NAOH50-100204-01-1 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 12.0929 | 2.79 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246155 | 26003H | 1575J | LP1Y-NAOH50-100203-02-2 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247002 | 26003H | 1574J-L1 | LP1Y-NAOH50-100203-02-1-L1 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246154 | 26003H | 1574J | LP1Y-NAOH50-100203-02-1 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246153 | 26003H | 1573J | LP1Y-NAOH50-100203-01-2 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 20 | 20 | 0 | 72.8638 | 22.3 | sq ft | 9.29 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247001 | 26003H | 1572J-L1 | LP1Y-NAOH50-100203-01-1-L1 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143090
C34-S246152 | 26003H | 1572J | LP1Y-NAOH50-100203-01-1 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246151 | 26003H | 1571J | LP1Y-NAOH50-016009-01-4 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.97 | 18.46 | sq ft | 16.96 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 |  |  | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 50% |  |  |  | 0%
C34-S246150 | 26003H | 1570J | LP1Y-NAOH50-016009-01-3 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 39.8788 | 17.69 | sq ft | 10.69 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246149 | 26003H | 1569J | LP1Y-NAOH50-016009-01-2 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.1263 | 8.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246148 | 26003H | 1568J | LP1Y-NAOH50-016009-01-1 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 49.4138 | 24.92 | sq ft | 11.42 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246147 | 26003H | 1567J | LP1Y-NAOH50-016004-03-3 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246146 | 26003H | 1566J | LP1Y-NAOH50-016004-03-2 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.2758 | 16.13 | sq ft | 9.63 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246145 | 26003H | 1565J | LP1Y-NAOH50-016004-03-1 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.1913 | 16.56 | sq ft | 13.56 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246144 | 26003H | 1564J | LP1Y-NAOH50-016002-01-4 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12 | 12 | 0 | 47.7575 | 21.43 | sq ft | 15.43 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246143 | 26003H | 1563J | LP1Y-NAOH50-016002-01-3 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 5 | 5 | 0 | 16.1881 | 12.98 | sq ft | 5.48 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246142 | 26003H | 1562J | LP1Y-NAOH50-016002-01-2 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247000 | 26003H | 1561J-L1 | LP1Y-NAOH50-016002-01-1-L1 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246141 | 26003H | 1561J | LP1Y-NAOH50-016002-01-1 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P012 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 4.7025 | 8.25 | sq ft | 1.25 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246140 | 26003H | 1560J | LP1Y-NAOH50-013012-17-1 | LP1Y-NAOH50-013012-17 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 4" SS NAOH50 (315) P (108) 013012 | NAOH50 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-013012 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246139 | 26003H | 1559J | LP1Y-N2-181118-01-3 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246138 | 26003H | 1558J | LP1Y-N2-181118-01-2 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246137 | 26003H | 1557J | LP1Y-N2-181118-01-1 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246136 | 26003H | 1556J | LP1Y-N2-181117-01-3 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246135 | 26003H | 1555J | LP1Y-N2-181117-01-2 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246134 | 26003H | 1554J | LP1Y-N2-181117-01-1 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246133 | 26003H | 1553J | LP1Y-N2-181084-01-3 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246132 | 26003H | 1552J | LP1Y-N2-181084-01-2 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246131 | 26003H | 1551J | LP1Y-N2-181084-01-1 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246130 | 26003H | 1550J | LP1Y-N2-181066-01-3 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian; ED: 2026-03-16; EL: Jacob Perez; FD: 2026-03-16; FL: Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246129 | 26003H | 1549J | LP1Y-N2-181066-01-2 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246128 | 26003H | 1548J | LP1Y-N2-181066-01-1 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246127 | 26003H | 1547J | LP1Y-N2-180099-01-3 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 14.59 | 10.5 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246126 | 26003H | 1546J | LP1Y-N2-180099-01-2 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246125 | 26003H | 1545J | LP1Y-N2-180099-01-1 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246124 | 26003H | 1544J | LP1Y-N2-180095-01-4 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.6736 | 29.24 | sq ft | 3.24 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246123 | 26003H | 1543J | LP1Y-N2-180095-01-3 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.59 | 8.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246122 | 26003H | 1542J | LP1Y-N2-180095-01-2 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 25.895 | 13.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246121 | 26003H | 1541J | LP1Y-N2-180095-01-1 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 35.1588 | 13.98 | sq ft | 12.48 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 50% |  |  |  | 0%
C34-S246120 | 26003H | 1540J | LP1Y-N2-180094-02-5 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 66.5775 | 27.22 | sq ft | 22.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142959
C34-S246119 | 26003H | 1539J | LP1Y-N2-180094-02-4 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 52.7313 | 21.31 | sq ft | 18.31 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142942
C34-S246118 | 26003H | 1538J | LP1Y-N2-180094-02-3 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 10 | 10 | 0 | 19.8 | 9.5 | sq ft | 5 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | [6 empty] | 80% |  |  |  | 0%
C34-S246117 | 26003H | 1537J | LP1Y-N2-180094-02-2 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 44.385 | 18.81 | sq ft | 14.31 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 |  |  |  | 75% |  |  |  | 50%
C34-S246999 | 26003H | 1536J-L1 | LP1Y-N2-180094-02-1-L1 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 1 | 0 | 1 | 2.22 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246116 | 26003H | 1536J | LP1Y-N2-180094-02-1 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 11 | 0 | 33.8561 | 16.96 | sq ft | 10.46 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246115 | 26003H | 1535J | LP1Y-N2-180094-01-1 | LP1Y-N2-180094-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 33.75 | 31.5 | 2.25 | 69.867 | 53.76 | sq ft | 9.26 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246114 | 26003H | 1534J | LP1Y-N2-180076-01-3 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246113 | 26003H | 1533J | LP1Y-N2-180076-01-2 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246112 | 26003H | 1532J | LP1Y-N2-180076-01-1 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246111 | 26003H | 1531J | LP1Y-N2-180075-01-3 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246110 | 26003H | 1530J | LP1Y-N2-180075-01-2 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246109 | 26003H | 1529J | LP1Y-N2-180075-01-1 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 32.6245 | 27.6 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246108 | 26003H | 1528J | LP1Y-N2-180074-01-3 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 19.1138 | 12.21 | sq ft | 2.21 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246107 | 26003H | 1527J | LP1Y-N2-180074-01-2 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.1575 | 9.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246106 | 26003H | 1526J | LP1Y-N2-180074-01-1 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 14 | 14 | 0 | 41.4395 | 32.2 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246105 | 26003H | 1525J | LP1Y-N2-180073-01-3 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246104 | 26003H | 1524J | LP1Y-N2-180073-01-2 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246103 | 26003H | 1523J | LP1Y-N2-180073-01-1 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246102 | 26003H | 1522J | LP1Y-N2-180072-01-3 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246101 | 26003H | 1521J | LP1Y-N2-180072-01-2 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246100 | 26003H | 1520J | LP1Y-N2-180072-01-1 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246099 | 26003H | 1519J | LP1Y-N2-180070-01-3 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246098 | 26003H | 1518J | LP1Y-N2-180070-01-2 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246097 | 26003H | 1517J | LP1Y-N2-180070-01-1 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246096 | 26003H | 1516J | LP1Y-N2-180029-02-3 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.4536 | 29.16 | sq ft | 3.16 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246095 | 26003H | 1515J | LP1Y-N2-180029-02-2 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.04 | 8.58 | sq ft | 0.58 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249768 | 26003H | 1514JX | LP1Y-N2-180029-02-1X | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 35.4513 | 16.68 | sq ft | 8.18 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246094 | 26003H | 1514J | LP1Y-N2-180029-02-1 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Released to Fabrication | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 2 | 2 | 0 | 29.9613 | 12.02 | sq ft | 10.52 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S246093 | 26003H | 1513J | LP1Y-N2-180029-01-2 | LP1Y-N2-180029-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 57.1763 | 24.91 | sq ft | 16.41 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246092 | 26003H | 1512J | LP1Y-N2-180029-01-1 | LP1Y-N2-180029-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 33.75 | 31.5 | 2.25 | 71.177 | 55.51 | sq ft | 7.01 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246998 | 26003H | 1511J-L1 | LP1Y-N2-102212-01-1-L1 | LP1Y-N2-102212-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P015 |  |  | LP1Y 1" SS N2 (315) 102212 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102212 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 2.38 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246091 | 26003H | 1511J | LP1Y-N2-102212-01-1 | LP1Y-N2-102212-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 1" SS N2 (315) 102212 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102212 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 8 | 5 | 3 | 30.6828 | 26.53 | sq ft | 7.53 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246997 | 26003H | 1510J-L2 | LP1Y-N2-102112-01-1-L2 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0.5 | 0 | 0.5 | 0.95 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246996 | 26003H | 1510J-L1 | LP1Y-N2-102112-01-1-L1 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P015 |  |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 2.38 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246090 | 26003H | 1510J | LP1Y-N2-102112-01-1 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 7 | 5 | 2 | 30.0608 | 26.02 | sq ft | 8.02 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246089 | 26003H | 1509J | LP1Y-N2-101713-01-2 | LP1Y-N2-101713-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS N2 (315) (108) 101713 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101713 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 6 | 4 | 2 | 7.4253 | 11.09 | sq ft | 3.59 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246088 | 26003H | 1508J | LP1Y-N2-101713-01-1 | LP1Y-N2-101713-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS N2 (315) (108) 101713 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101713 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 7 | 7 | 0 | 31.6402 | 26.24 | sq ft | 7.74 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246087 | 26003H | 1507J | LP1Y-N2-101613-01-2 | LP1Y-N2-101613-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS N2 (315) (108) 101613 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101613 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 6 | 4 | 2 | 7.3519 | 11.04 | sq ft | 3.54 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246086 | 26003H | 1506J | LP1Y-N2-101613-01-1 | LP1Y-N2-101613-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" SS N2 (315) (108) 101613 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101613 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 7 | 7 | 0 | 31.7209 | 26.3 | sq ft | 7.8 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246085 | 26003H | 1505D | LP1Y-N2-101511-01-2 | LP1Y-N2-101511-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" DUP N2 (344) (108) 101511 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101511 |  | TFS00D005YSPP |  | 344-N2 | NONE | 1" | 2205 | 5 | 5 | 0 | 10.9945 | 10.39 | sq ft | 4.39 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246084 | 26003H | 1504D | LP1Y-N2-101511-01-1 | LP1Y-N2-101511-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P014 |  |  | LP1Y 1" DUP N2 (344) (108) 101511 | N2 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101511 |  | TFS00D005YSPP |  | 344-N2 | NONE | 1" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246083 | 26003H | 1503J | LP1Y-N2(100)-181105-02-3 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 39.215 | 16.85 | sq ft | 12.35 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | [6 empty] | 67% |  |  |  | 0%
C34-S246082 | 26003H | 1502J | LP1Y-N2(100)-181105-02-2 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 76.8213 | 24.43 | sq ft | 9.93 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246995 | 26003H | 1501J-L1 | LP1Y-N2(100)-181105-02-1-L1 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246081 | 26003H | 1501J | LP1Y-N2(100)-181105-02-1 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 13.78 | 8.92 | sq ft | 3.42 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246080 | 26003H | 1500J | LP1Y-N2(100)-181105-01-1 | LP1Y-N2(100)-181105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181105 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 108.4513 | 34.35 | sq ft | 3.35 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246079 | 26003H | 1499J | LP1Y-N2(100)-181104-01-2 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 26.4 | 11.33 | sq ft | 8.33 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246994 | 26003H | 1498J-L1 | LP1Y-N2(100)-181104-01-1-L1 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246078 | 26003H | 1498J | LP1Y-N2(100)-181104-01-1 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 76.04 | 26.5 | sq ft | 9.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-10 | George Allahverdian | 2026-03-10 | Jacob Perez | 2026-03-10 | Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246077 | 26003H | 1497J | LP1Y-N2(100)-181090-02-3 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 80.1388 | 33.03 | sq ft | 28.53 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246076 | 26003H | 1496J | LP1Y-N2(100)-181090-02-2 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 58.1669 | 43.73 | sq ft | 6.23 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246075 | 26003H | 1495J | LP1Y-N2(100)-181090-02-1 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 7 | 7 | 0 | 31.5545 | 27.6 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246074 | 26003H | 1494J | LP1Y-N2(100)-181082-01-3 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 61.3638 | 22.71 | sq ft | 3.71 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246073 | 26003H | 1493J | LP1Y-N2(100)-181082-01-2 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 72.0663 | 32.2 | sq ft | 22.2 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246072 | 26003H | 1492J | LP1Y-N2(100)-181082-01-1 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Released to Fabrication | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 72.1188 | 27.98 | sq ft | 26.48 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 50% |  |  |  | 0%
C34-S246071 | 26003H | 1491J | LP1Y-N2(100)-181078-01-2 | LP1Y-N2(100)-181078-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181078 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181078 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 68.775 | 25.52 | sq ft | 6.52 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246070 | 26003H | 1490J | LP1Y-N2(100)-181078-01-1 | LP1Y-N2(100)-181078-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 181078 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181078 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 44.0713 | 20.93 | sq ft | 12.43 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246069 | 26003H | 1489J | LP1Y-N2(100)-181077-01-2 | LP1Y-N2(100)-181077-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181077 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181077 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.9213 | 10.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246068 | 26003H | 1488J | LP1Y-N2(100)-181077-01-1 | LP1Y-N2(100)-181077-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181077 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181077 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 82.6063 | 32.41 | sq ft | 11.91 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246067 | 26003H | 1487J | LP1Y-N2(100)-181076-02-2 | LP1Y-N2(100)-181076-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181076 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181076 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 72.8313 | 27.06 | sq ft | 8.06 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246066 | 26003H | 1486J | LP1Y-N2(100)-181076-02-1 | LP1Y-N2(100)-181076-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181076 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181076 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.7163 | 10.66 | sq ft | 3.66 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246065 | 26003H | 1485J | LP1Y-N2(100)-181010-01-5 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 59.1563 | 17.66 | sq ft | 2.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246064 | 26003H | 1484J | LP1Y-N2(100)-181010-01-4 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 35.3095 | 30.89 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246063 | 26003H | 1483J | LP1Y-N2(100)-181010-01-3 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 55.4267 | 40.67 | sq ft | 6.17 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246062 | 26003H | 1482J | LP1Y-N2(100)-181010-01-2 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 31.0375 | 13.76 | sq ft | 10.76 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246061 | 26003H | 1481J | LP1Y-N2(100)-181010-01-1 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.0075 | 18.76 | sq ft | 15.76 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S246060 | 26003H | 1480J | LP1Y-N2(100)-181007-02-2 | LP1Y-N2(100)-181007-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181007 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181007 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 92.577 | 53.82 | sq ft | 19.32 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246059 | 26003H | 1479J | LP1Y-N2(100)-181007-02-1 | LP1Y-N2(100)-181007-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181007 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181007 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 91.0525 | 36.49 | sq ft | 31.99 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246058 | 26003H | 1478J | LP1Y-N2(100)-181006-02-2 | LP1Y-N2(100)-181006-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181006 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181006 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 92.5173 | 53.77 | sq ft | 19.27 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246057 | 26003H | 1477J | LP1Y-N2(100)-181006-02-1 | LP1Y-N2(100)-181006-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS N2(100) (315) E 181006 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181006 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 88.0825 | 35.36 | sq ft | 30.86 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 80% |  |  |  | 0%
C34-S246993 | 26003H | 1476J-L1 | LP1Y-N2(100)-180091-01-1-L1 | LP1Y-N2(100)-180091-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2(100) (315) E 180091 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180091 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246056 | 26003H | 1476J | LP1Y-N2(100)-180091-01-1 | LP1Y-N2(100)-180091-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2(100) (315) E 180091 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180091 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 40 | 40 | 0 | 212.7328 | 91.87 | sq ft | 11.37 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246055 | 26003H | 1475J | LP1Y-N2(100)-180089-01-2 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 24.2 | 10.5 | sq ft | 7.5 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S246992 | 26003H | 1474J-L1 | LP1Y-N2(100)-180089-01-1-L1 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246054 | 26003H | 1474J | LP1Y-N2(100)-180089-01-1 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 87.2463 | 31.41 | sq ft | 12.91 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246053 | 26003H | 1473J | LP1Y-N2(100)-180088-04-2 | LP1Y-N2(100)-180088-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 75.0313 | 27.22 | sq ft | 9.72 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246052 | 26003H | 1472J | LP1Y-N2(100)-180088-04-1 | LP1Y-N2(100)-180088-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 33.3538 | 19.55 | sq ft | 8.05 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246051 | 26003H | 1471J | LP1Y-N2(100)-180088-02-3 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.7413 | 12.6 | sq ft | 9.6 | ft | 2026-02-13 |  |  |  |  | 2026-03-09 | Jacob Perez | 2026-03-09 | George Allahverdian | 2026-03-09 | Jacob Perez | 2026-03-09 | Jacob Perez | 2026-03-09 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | [6 empty] | 75% |  |  |  | 0%
C34-S246050 | 26003H | 1470J | LP1Y-N2(100)-180088-02-2 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 18.7413 | 9.1 | sq ft | 4.6 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142897
C34-S246049 | 26003H | 1469J | LP1Y-N2(100)-180088-02-1 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 85.7925 | 31.45 | sq ft | 10.45 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246048 | 26003H | 1468J | LP1Y-N2(100)-180087-04-2 | LP1Y-N2(100)-180087-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 64.7325 | 23.99 | sq ft | 4.99 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246047 | 26003H | 1467J | LP1Y-N2(100)-180087-04-1 | LP1Y-N2(100)-180087-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 42.4075 | 20.3 | sq ft | 11.8 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246046 | 26003H | 1466J | LP1Y-N2(100)-180087-01-1 | LP1Y-N2(100)-180087-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 100.5325 | 37.7 | sq ft | 15.2 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246045 | 26003H | 1465J | LP1Y-N2(100)-180050-02-2 | LP1Y-N2(100)-180050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180050 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180050 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 67.345 | 24.98 | sq ft | 5.98 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246044 | 26003H | 1464J | LP1Y-N2(100)-180050-02-1 | LP1Y-N2(100)-180050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180050 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180050 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 26.1075 | 16.14 | sq ft | 6.14 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246043 | 26003H | 1463J | LP1Y-N2(100)-180048-04-3 | LP1Y-N2(100)-180048-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.7163 | 21.66 | sq ft | 6.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246042 | 26003H | 1462J | LP1Y-N2(100)-180048-04-2 | LP1Y-N2(100)-180048-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 16.885 | 7.73 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 67% |  |  |  | 0%
C34-S246041 | 26003H | 1461J | LP1Y-N2(100)-180048-04-1 | LP1Y-N2(100)-180048-04 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 37.4 | 15.5 | sq ft | 12.5 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142899
C34-S246040 | 26003H | 1460J | LP1Y-N2(100)-180047-02-2 | LP1Y-N2(100)-180047-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180047 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180047 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 79.8163 | 29.7 | sq ft | 10.7 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246039 | 26003H | 1459J | LP1Y-N2(100)-180047-02-1 | LP1Y-N2(100)-180047-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180047 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180047 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 42.58 | 23.04 | sq ft | 11.54 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246038 | 26003H | 1458J | LP1Y-N2(100)-180046-02-3 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 69.6813 | 25.93 | sq ft | 6.93 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246037 | 26003H | 1457J | LP1Y-N2(100)-180046-02-2 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 21.0513 | 8.64 | sq ft | 7.14 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142960
C34-S246036 | 26003H | 1456J | LP1Y-N2(100)-180046-02-1 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 43.4738 | 23.38 | sq ft | 11.88 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246035 | 26003H | 1455J | LP1Y-N2(100)-180045-02-2 | LP1Y-N2(100)-180045-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180045 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180045 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 68.42 | 28.29 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246034 | 26003H | 1454J | LP1Y-N2(100)-180045-02-1 | LP1Y-N2(100)-180045-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 180045 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180045 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 28.745 | 14.23 | sq ft | 9.73 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246033 | 26003H | 1453J | LP1Y-N2(100)-180043-01-2 | LP1Y-N2(100)-180043-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180043 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180043 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 69.1738 | 25.67 | sq ft | 6.67 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246032 | 26003H | 1452J | LP1Y-N2(100)-180043-01-1 | LP1Y-N2(100)-180043-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180043 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180043 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 61.0938 | 28.71 | sq ft | 17.21 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246031 | 26003H | 1451J | LP1Y-N2(100)-180027-02-2 | LP1Y-N2(100)-180027-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180027 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 81.4933 | 53.23 | sq ft | 14.23 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246030 | 26003H | 1450J | LP1Y-N2(100)-180027-02-1 | LP1Y-N2(100)-180027-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS N2(100) (315) E 180027 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.9738 | 14.67 | sq ft | 13.17 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142853
C34-S246029 | 26003H | 1449J | LP1Y-N2(100)-180027-01-2 | LP1Y-N2(100)-180027-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E (108) 180027 | N2(100) |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 7 | 7 | 0 | 31.5545 | 27.6 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246028 | 26003H | 1448J | LP1Y-N2(100)-180027-01-1 | LP1Y-N2(100)-180027-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E (108) 180027 | N2(100) |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 53.8625 | 14.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246027 | 26003H | 1447J | LP1Y-N2(100)-180009-03-2 | LP1Y-N2(100)-180009-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 42.3395 | 27.66 | sq ft | 2.66 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246026 | 26003H | 1446J | LP1Y-N2(100)-180009-03-1 | LP1Y-N2(100)-180009-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 85.4558 | 37.41 | sq ft | 3.41 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246025 | 26003H | 1445J | LP1Y-N2(100)-180009-02-2 | LP1Y-N2(100)-180009-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.5038 | 20.46 | sq ft | 17.46 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246024 | 26003H | 1444J | LP1Y-N2(100)-180009-02-1 | LP1Y-N2(100)-180009-02 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 80.08 | 31.67 | sq ft | 28.67 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246023 | 26003H | 1443J | LP1Y-N2(100)-180008-03-2 | LP1Y-N2(100)-180008-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 85.4558 | 37.41 | sq ft | 3.41 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246022 | 26003H | 1442J | LP1Y-N2(100)-180008-03-1 | LP1Y-N2(100)-180008-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 42.3395 | 27.66 | sq ft | 2.66 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246021 | 26003H | 1441J | LP1Y-N2(100)-180008-02-4 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 16.94 | 9.08 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 33% |  |  |  | 0%
C34-S246020 | 26003H | 1440J | LP1Y-N2(100)-180008-02-3 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | 2026-03-13 | 2026-03-13 | released |  |  | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-13 | 2026-03-13 | Passed | No | 2026-03-13 | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100%
C34-S249767 | 26003H | 1439JX | LP1Y-N2(100)-180008-02-2X | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 24.42 | 9.92 | sq ft | 8.42 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S246019 | 26003H | 1439J | LP1Y-N2(100)-180008-02-2 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 40.6313 | 15.39 | sq ft | 15.39 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100%
C34-S246018 | 26003H | 1438J | LP1Y-N2(100)-180008-02-1 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.1925 | 5.57 | sq ft | 2.57 | ft | 2026-02-13 | DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | [6 empty] | 50% |  |  |  | 0%
C34-S246017 | 26003H | 1437J | LP1Y-N2(100)-180005-02-3 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 89.7013 | 39.06 | sq ft | 6.06 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246016 | 26003H | 1436J | LP1Y-N2(100)-180005-02-2 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.2025 | 10.03 | sq ft | 5.53 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 |  | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 75% |  |  |  | 0%
C34-S246015 | 26003H | 1435J | LP1Y-N2(100)-180005-02-1 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.5338 | 14.51 | sq ft | 13.01 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100%
C34-S246014 | 26003H | 1434J | LP1Y-N2(100)-180004-01-3 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.52 | 14.5 | sq ft | 13 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 |  |  |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% |  |  |  | 0%
C34-S246013 | 26003H | 1433J | LP1Y-N2(100)-180004-01-2 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 22.8388 | 10.65 | sq ft | 6.15 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 |  |  |  | 75% |  |  |  | 50%
C34-S246012 | 26003H | 1432J | LP1Y-N2(100)-180004-01-1 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.9088 | 21.73 | sq ft | 6.23 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246011 | 26003H | 1431J | LP1Y-N2(100)-018057-02-2 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 69.1625 | 20.2 | sq ft | 8.7 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246991 | 26003H | 1430J-L1 | LP1Y-N2(100)-018057-02-1-L1 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246010 | 26003H | 1430J | LP1Y-N2(100)-018057-02-1 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 6.59 | 3.83 | sq ft | 2.33 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143233
C34-S246009 | 26003H | 1429J | LP1Y-N2(100)-018035-02-2 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.4113 | 16.64 | sq ft | 13.64 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S246990 | 26003H | 1428J-L1 | LP1Y-N2(100)-018035-02-1-L1 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246008 | 26003H | 1428J | LP1Y-N2(100)-018035-02-1 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 57.1725 | 15.66 | sq ft | 4.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246989 | 26003H | 1427J-L1 | LP1Y-N2(100)-018031-02-1-L1 | LP1Y-N2(100)-018031-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 018031 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018031 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246007 | 26003H | 1427J | LP1Y-N2(100)-018031-02-1 | LP1Y-N2(100)-018031-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS N2(100) (315) E 018031 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018031 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 96.03 | 31.71 | sq ft | 17.21 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246006 | 26003H | 1426J | LP1Y-N2(100)-018019-02-2 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 6 | 2 | 36.96 | 15.33 | sq ft | 12.33 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  |  | 2026-03-21 |  | 75% |  |  |  | 0%
C34-S246988 | 26003H | 1425J-L1 | LP1Y-N2(100)-018019-02-1-L1 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246005 | 26003H | 1425J | LP1Y-N2(100)-018019-02-1 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 57.5438 | 16.46 | sq ft | 3.46 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246004 | 26003H | 1424J | LP1Y-N2(100)-018016-01-2 | LP1Y-N2(100)-018016-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS N2(100) (315) E 018016 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018016 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.8225 | 15.28 | sq ft | 12.28 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142938
C34-S246003 | 26003H | 1423J | LP1Y-N2(100)-018016-01-1 | LP1Y-N2(100)-018016-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS N2(100) (315) E 018016 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018016 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 65.5363 | 20.74 | sq ft | 3.74 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245518 | 26003H | 1422J | LP1Y-N2(100)-018010-15-2 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 26.0975 | 11.89 | sq ft | 7.39 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | [6 empty] | 75% |  |  |  | 0%
C34-S246987 | 26003H | 1421J-L1 | LP1Y-N2(100)-018010-15-1-L1 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142535
C34-S245517 | 26003H | 1421J | LP1Y-N2(100)-018010-15-1 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 75.24 | 23.17 | sq ft | 10.17 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245516 | 26003H | 1420J | LP1Y-H2SO4-178102-07-4 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245515 | 26003H | 1419J | LP1Y-H2SO4-178102-07-3 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 12 | 0 | 67.0998 | 19.9 | sq ft | 3.14 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245514 | 26003H | 1418J | LP1Y-H2SO4-178102-07-2 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245513 | 26003H | 1417J | LP1Y-H2SO4-178102-07-6 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 8 | 0 | 48.2281 | 11.18 | sq ft | 7.81 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142903
C34-S245512 | 26003H | 1416J | LP1Y-H2SO4-178102-07-5 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 12 | 0 | 99.232 | 22.94 | sq ft | 16.12 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245511 | 26003H | 1415J | LP1Y-H2SO4-178102-07-1 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 19 | 18 | 1 | 60.8425 | 19.55 | sq ft | 1.92 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245510 | 26003H | 1414J | LP1Y-H2SO4-178102-06-3 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245509 | 26003H | 1413J | LP1Y-H2SO4-178102-06-2 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 12 | 0 | 86.3931 | 21.77 | sq ft | 2.98 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246986 | 26003H | 1412J-L1 | LP1Y-H2SO4-178102-06-1-L1 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142534
C34-S245508 | 26003H | 1412J | LP1Y-H2SO4-178102-06-1 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 8 | 0 | 35.0519 | 8.62 | sq ft | 1.85 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143237
C34-S245507 | 26003H | 1411J | LP1Y-H2SO4-178102-04-5 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9 | 13.83 | sq ft | 1.83 | ft | 2026-02-13 |  |  |  |  | 2026-03-18 | Jacob Perez | 2026-03-18 | George Allahverdian | 2026-03-18 | Jacob Perez | 2026-03-18 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245506 | 26003H | 1410J | LP1Y-H2SO4-178102-04-4 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245505 | 26003H | 1409J | LP1Y-H2SO4-178102-04-3 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245504 | 26003H | 1408J | LP1Y-H2SO4-178102-04-2 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 35.8045 | 24.6 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246985 | 26003H | 1407J-L1 | LP1Y-H2SO4-178102-04-1-L1 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245503 | 26003H | 1407J | LP1Y-H2SO4-178102-04-1 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.675 | 2.44 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S245502 | 26003H | 1406J | LP1Y-H2SO4-178102-03-3 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 14 | 13 | 1 | 44.2525 | 16.95 | sq ft | 1.25 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-04 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245501 | 26003H | 1405J | LP1Y-H2SO4-178102-03-2 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 19 | 19 | 0 | 97.2069 | 25.42 | sq ft | 6.02 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-04 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245500 | 26003H | 1404J | LP1Y-H2SO4-178102-03-1 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 4 | 4 | 0 | 102.3413 | 22.75 | sq ft | 17.46 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-04 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 |  |  |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% |  |  |  | 0%
C34-S245499 | 26003H | 1402J | LP1Y-H2SO4-178101-03-1 | LP1Y-H2SO4-178101-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 3" SS H2SO4 (315) P 178101 | H2SO4 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.0277 | 27.03 | sq ft | 1.53 | ft | 2026-02-13 |  |  |  |  | 2026-03-03 | Jacob Perez | 2026-03-03 | George Allahverdian | 2026-03-04 | Jacob Perez | 2026-03-04 | Jacob Perez | 2026-03-04 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245498 | 26003H | 1401J | LP1Y-H2SO4-178101-02-2 | LP1Y-H2SO4-178101-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 28 | 27 | 1 | 78.0288 | 35.38 | sq ft | 6.88 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245497 | 26003H | 1400J | LP1Y-H2SO4-178101-02-1 | LP1Y-H2SO4-178101-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 6 | 6 | 0 | 105.9547 | 24.47 | sq ft | 22.97 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245496 | 26003H | 1399J | LP1Y-H2SO4-178101-01-4 | LP1Y-H2SO4-178101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 6.8602 | 2.77 | sq ft | 1.27 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245495 | 26003H | 1398J | LP1Y-H2SO4-178101-01-3 | LP1Y-H2SO4-178101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 9 | 0 | 170.9723 | 39.48 | sq ft | 37.98 | ft | 2026-02-13 | DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245494 | 26003H | 1397J | LP1Y-H2SO4-178101-01-2 | LP1Y-H2SO4-178101-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246984 | 26003H | 1396J-L1 | LP1Y-H2SO4-178101-01-1-L1 | LP1Y-H2SO4-178101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S245493 | 26003H | 1396J | LP1Y-H2SO4-178101-01-1 | LP1Y-H2SO4-178101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 7 | 7 | 0 | 20.2 | 9.67 | sq ft | 1.67 | ft | 2026-02-13 | DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245492 | 26003H | 1395J | LP1Y-H2SO4-108220-01-3 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 1 | 1 | 0 | 25.4838 | 19.38 | sq ft | 17.88 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143238
C34-S245491 | 26003H | 1394J | LP1Y-H2SO4-108220-01-2 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246983 | 26003H | 1393J-L1 | LP1Y-H2SO4-108220-01-1-L1 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245490 | 26003H | 1393J | LP1Y-H2SO4-108220-01-1 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.1422 | 7.26 | sq ft | 1.76 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245489 | 26003H | 1392J | LP1Y-H2SO4-108118-02-3 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 1 | 1 | 0 | 25.4691 | 19.36 | sq ft | 17.86 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245488 | 26003H | 1391J | LP1Y-H2SO4-108118-02-2 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246982 | 26003H | 1390J-L1 | LP1Y-H2SO4-108118-02-1-L1 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245487 | 26003H | 1390J | LP1Y-H2SO4-108118-02-1 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P016 |  |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.1275 | 7.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245486 | 26003H | 1389J | LP1Y-H2SO4-101703-03-4 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.8663 | 18.33 | sq ft | 15.33 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 67% |  |  |  | 0%
C34-S245485 | 26003H | 1388J | LP1Y-H2SO4-101703-03-3 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 11 | 11 | 0 | 34.1798 | 21.41 | sq ft | 10.91 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245484 | 26003H | 1387J | LP1Y-H2SO4-101703-03-2 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245483 | 26003H | 1386J | LP1Y-H2SO4-101703-03-1 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 11.9247 | 13.68 | sq ft | 0.68 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245482 | 26003H | 1385D | LP1Y-H2SO4-101516-01-3 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.0611 | 8.21 | sq ft | 0.21 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245481 | 26003H | 1384D | LP1Y-H2SO4-101516-01-2 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 1" | 2205 | 3 | 3 | 0 | 6.193 | 10.32 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245480 | 26003H | 1383D | LP1Y-H2SO4-101516-01-1 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 2" | 2205 | 6 | 6 | 0 | 11.5345 | 12.1 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245479 | 26003H | 1382J | LP1Y-H2SO4-101303-03-4 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 56.925 | 23.56 | sq ft | 19.06 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142958
C34-S245478 | 26003H | 1381J | LP1Y-H2SO4-101303-03-3 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.3028 | 14.07 | sq ft | 5.07 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245477 | 26003H | 1380J | LP1Y-H2SO4-101303-03-2 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246981 | 26003H | 1379J-L1 | LP1Y-H2SO4-101303-03-1-L1 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245476 | 26003H | 1379J | LP1Y-H2SO4-101303-03-1 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 4.0773 | 6.51 | sq ft | 1.01 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245475 | 26003H | 1378J | LP1Y-H2SO4-101011-02-4 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 53.2125 | 21.49 | sq ft | 18.49 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142937
C34-S245474 | 26003H | 1377J | LP1Y-H2SO4-101011-02-3 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.8066 | 14.38 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245473 | 26003H | 1376J | LP1Y-H2SO4-101011-02-2 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245472 | 26003H | 1375J | LP1Y-H2SO4-101011-02-1 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 12.1303 | 13.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245471 | 26003H | 1374J | LP1Y-H2SO4-100314-02-2 | LP1Y-H2SO4-100314-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8 | 8 | 0 | 47.96 | 20.17 | sq ft | 15.67 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 75% |  |  |  | 0%
C34-S245470 | 26003H | 1373J | LP1Y-H2SO4-100314-02-1 | LP1Y-H2SO4-100314-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 14.8925 | 7.99 | sq ft | 2.99 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245469 | 26003H | 1372J | LP1Y-H2SO4-100314-01-3 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Released to Fabrication | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 74.6213 | 28.93 | sq ft | 27.43 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | [6 empty] | 67% |  |  |  | 0%
C34-S245468 | 26003H | 1371J | LP1Y-H2SO4-100314-01-2 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8 | 8 | 0 | 32.7113 | 14.39 | sq ft | 9.89 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 75% |  |  |  | 0%
C34-S245467 | 26003H | 1370J | LP1Y-H2SO4-100314-01-1 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 20.1713 | 8.31 | sq ft | 6.81 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142940
C34-S245466 | 26003H | 1369J | LP1Y-H2SO4-100304-02-4 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 13 | 13 | 0 | 45.8713 | 24.85 | sq ft | 14.35 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245465 | 26003H | 1368J | LP1Y-H2SO4-100304-02-3 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 20.695 | 14.56 | sq ft | 3.06 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245464 | 26003H | 1367J | LP1Y-H2SO4-100304-02-2 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 73.27 | 27.29 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246980 | 26003H | 1366J-L1 | LP1Y-H2SO4-100304-02-1-L1 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142532
C34-S245463 | 26003H | 1366J | LP1Y-H2SO4-100304-02-1 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 12.6263 | 6.7 | sq ft | 1.2 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245462 | 26003H | 1365J | LP1Y-H2SO4-100304-01-2 | LP1Y-H2SO4-100304-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 84.6313 | 33.39 | sq ft | 30.39 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 60% |  |  |  | 0%
C34-S245461 | 26003H | 1364J | LP1Y-H2SO4-100304-01-1 | LP1Y-H2SO4-100304-01 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P011 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245460 | 26003H | 1363J | LP1Y-H2SO4-100303-06-2 | LP1Y-H2SO4-100303-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 15 | 15 | 0 | 63.0963 | 15.62 | sq ft | 8.63 | ft | 2026-02-13 |  |  |  |  | 2026-03-05 | Jacob Perez | 2026-03-05 | George Allahverdian | 2026-03-05 | Jacob Perez | 2026-03-05 | Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Omar Puente | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 60% |  |  |  | 40%
C34-S245459 | 26003H | 1362J | LP1Y-H2SO4-100303-06-1 | LP1Y-H2SO4-100303-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 12 | 12 | 0 | 63.521 | 15.85 | sq ft | 11.35 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 75%
C34-S245458 | 26003H | 1361J | LP1Y-H2SO4-100303-02-3 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 21 | 21 | 0 | 51.4229 | 24.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245457 | 26003H | 1360J | LP1Y-H2SO4-100303-02-2 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245456 | 26003H | 1359J | LP1Y-H2SO4-100303-02-1 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 8 | 8 | 0 | 32.6116 | 12.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245455 | 26003H | 1358J | LP1Y-H2SO4-100303-01-4 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 24.4771 | 6.71 | sq ft | 2.71 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245454 | 26003H | 1357J | LP1Y-H2SO4-100303-01-3 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.0121 | 13.71 | sq ft | 1.21 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245453 | 26003H | 1356J | LP1Y-H2SO4-100303-01-2 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246978 | 26003H | 1355JA-L1 | LP1Y-H2SO4-100303-01-5-L1 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 2.5 | 2.5 | 0 | 4.17 | 8 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246979 | 26003H | 1355JA | LP1Y-H2SO4-100303-01-5 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 12.7244 | 2.94 | sq ft | 1.44 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245452 | 26003H | 1355J | LP1Y-H2SO4-100303-01-1 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 13 | 12 | 1 | 51.2266 | 23.05 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245451 | 26003H | 1354J | LP1Y-H2SO4-100302-02-2 | LP1Y-H2SO4-100302-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245450 | 26003H | 1353J | LP1Y-H2SO4-100302-02-1 | LP1Y-H2SO4-100302-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245449 | 26003H | 1352J | LP1Y-H2SO4-100302-01-2 | LP1Y-H2SO4-100302-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 20 | 20 | 0 | 58.5758 | 19.24 | sq ft | 6.74 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245448 | 26003H | 1351J | LP1Y-H2SO4-100302-01-1 | LP1Y-H2SO4-100302-01 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P011 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245447 | 26003H | 1350J | LP1Y-H2SO4-016018-04-2 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 68.66 | 24.96 | sq ft | 3.96 | ft | 2026-02-13 |  |  |  |  | 2026-03-05 | Jacob Perez | 2026-03-05 | George Allahverdian | 2026-03-05 | Jacob Perez | 2026-03-05 | Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246977 | 26003H | 1349J-L1 | LP1Y-H2SO4-016018-04-1-L1 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0.5 | 0 | 0.5 | 4.73 | 5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245446 | 26003H | 1349J | LP1Y-H2SO4-016018-04-1 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 6.16 | 3 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 142593
C34-S245445 | 26003H | 1348J | LP1Y-H2SO4-016018-02-3 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 5 | 5 | 0 | 13.0638 | 11.01 | sq ft | 1.01 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245444 | 26003H | 1347J | LP1Y-H2SO4-016018-02-2 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 3.5 | 1 | 2.5 | 6.9158 | 12.86 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245443 | 26003H | 1346J | LP1Y-H2SO4-016018-02-1 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245442 | 26003H | 1345J | LP1Y-H2SO4-016003-02-3 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245441 | 26003H | 1344J | LP1Y-H2SO4-016003-02-2 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 29.1513 | 15.47 | sq ft | 8.97 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245440 | 26003H | 1343J | LP1Y-H2SO4-016003-02-1 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 42.9 | 18.25 | sq ft | 13.75 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 80% |  |  |  | 0%
C34-S245439 | 26003H | 1342J | LP1Y-H2SO4-016001-02-4 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12 | 12 | 0 | 66.7288 | 27.94 | sq ft | 21.94 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245438 | 26003H | 1341J | LP1Y-H2SO4-016001-02-3 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 5 | 5 | 0 | 16.3203 | 13.07 | sq ft | 5.57 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245437 | 26003H | 1340J | LP1Y-H2SO4-016001-02-2 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246976 | 26003H | 1339J-L1 | LP1Y-H2SO4-016001-02-1-L1 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245436 | 26003H | 1339J | LP1Y-H2SO4-016001-02-1 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P012 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 4.2977 | 6.66 | sq ft | 1.16 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-23 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245435 | 26003H | 1338J | LP1Y-H2SO4-013011-17-1 | LP1Y-H2SO4-013011-17 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P018 |  |  | LP1Y 4" SS H2SO4 (315) P (108) 013011 | H2SO4 |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-013011 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246975 | 26003H | 1337J-L1 | LP1Y-ENZ-162305-01-2-L1 | LP1Y-ENZ-162305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245434 | 26003H | 1337J | LP1Y-ENZ-162305-01-2 | LP1Y-ENZ-162305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 31.5 | 30 | 1.5 | 62.7604 | 38.28 | sq ft | 13.28 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246974 | 26003H | 1336J-L1 | LP1Y-ENZ-162305-01-1-L1 | LP1Y-ENZ-162305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2 | 2 | 0 | 45.26 | 10.5 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245433 | 26003H | 1336J | LP1Y-ENZ-162305-01-1 | LP1Y-ENZ-162305-01 | 0 | N | PRIORITY-1 | 2026-03-18 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245432 | 26003H | 1335J | LP1Y-ENZ-162001-07-2 | LP1Y-ENZ-162001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 10.5519 | 16.56 | sq ft | 15.06 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245431 | 26003H | 1334J | LP1Y-ENZ-162001-07-1 | LP1Y-ENZ-162001-07 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245430 | 26003H | 1333J | LP1Y-ENZ-162001-06-1 | LP1Y-ENZ-162001-06 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246973 | 26003H | 1332J-L1 | LP1Y-ENZ-162001-02-2-L1 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 2 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245429 | 26003H | 1332J | LP1Y-ENZ-162001-02-2 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245428 | 26003H | 1331J | LP1Y-ENZ-162001-02-1 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 3 | 0 | 3 | 16.5108 | 27.08 | sq ft | 22.58 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | [6 empty] | 83% |  |  |  | 0%
C34-S245427 | 26003H | 1330J | LP1Y-ENZ-162001-01-3 | LP1Y-ENZ-162001-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 4 | 0 | 4 | 9.672 | 17.73 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245426 | 26003H | 1329J | LP1Y-ENZ-162001-01-2 | LP1Y-ENZ-162001-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 8.25 | 6 | 2.25 | 19.1306 | 28.27 | sq ft | 3.77 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246972 | 26003H | 1328J-L1 | LP1Y-ENZ-162001-01-1-L1 | LP1Y-ENZ-162001-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 |  |  |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% |  |  |  | 0%
C34-S245425 | 26003H | 1328J | LP1Y-ENZ-162001-01-1 | LP1Y-ENZ-162001-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1" | 316 SS | 5.75 | 3.75 | 2 | 5.8021 | 7.95 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245424 | 26003H | 1327J | LP1Y-ENZ-108221-01-2 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 3.4203 | 5.12 | sq ft | 2.12 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246971 | 26003H | 1326J-L1 | LP1Y-ENZ-108221-01-1-L1 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142531
C34-S245423 | 26003H | 1326J | LP1Y-ENZ-108221-01-1 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2.5 | 0 | 2.5 | 6.2377 | 8.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245422 | 26003H | 1325J | LP1Y-ENZ-108115-01-3 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 1.5 | 0.5 | 1 | 25.8705 | 40.24 | sq ft | 37.24 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245421 | 26003H | 1324J | LP1Y-ENZ-108115-01-2 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246970 | 26003H | 1323J-L1 | LP1Y-ENZ-108115-01-1-L1 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2.5 | 2 | 0.5 | 10.26 | 6.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245420 | 26003H | 1323J | LP1Y-ENZ-108115-01-1 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 1.5 | 0 | 1.5 | 3.5592 | 6.14 | sq ft | 1.64 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246969 | 26003H | 1322J-L1 | LP1Y-ENZ-108008-02-1-L1 | LP1Y-ENZ-108008-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108008 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108008 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 2 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245419 | 26003H | 1322J | LP1Y-ENZ-108008-02-1 | LP1Y-ENZ-108008-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.5" SS ENZ (315) P (108) 108008 | ENZ |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108008 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 1.6296 | 2.43 | sq ft | 2.43 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-16 | Passed | No | 2026-03-16 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100%
C34-S245418 | 26003H | 1321J | LP1Y-DMF-175102-08-2 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P036 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245417 | 26003H | 1320J | LP1Y-DMF-175102-08-3 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Released to Production | P036 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 18 | 17 | 1 | 74.0532 | 21.32 | sq ft | 11.82 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245416 | 26003H | 1319J | LP1Y-DMF-175102-08-1 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 33.97 | 12 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245415 | 26003H | 1318J | LP1Y-DMF-175102-06-6 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245414 | 26003H | 1317J | LP1Y-DMF-175102-06-5 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245413 | 26003H | 1316J | LP1Y-DMF-175102-06-4 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245412 | 26003H | 1315J | LP1Y-DMF-175102-06-3 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245411 | 26003H | 1314J | LP1Y-DMF-175102-06-2 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246968 | 26003H | 1313J-L1 | LP1Y-DMF-175102-06-1-L1 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245410 | 26003H | 1313J | LP1Y-DMF-175102-06-1 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245409 | 26003H | 1312J | LP1Y-DMF-175102-04-2 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 338.8652 | 30.52 | sq ft | 17.52 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247018 | 26003H | 1311JA | LP1Y-DMF-175102-04-3 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | 2026-03-17 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245408 | 26003H | 1311J | LP1Y-DMF-175102-04-1 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 3 | 3 | 0 | 36.1365 | 9.4 | sq ft | 5.4 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Henrique Barahona | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S245407 | 26003H | 1310J | LP1Y-DMF-175102-02-2 | LP1Y-DMF-175102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 15 | 15 | 0 | 135.7785 | 31.35 | sq ft | 26.85 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245406 | 26003H | 1309J | LP1Y-DMF-175102-02-1 | LP1Y-DMF-175102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 9 | 0 | 61.2871 | 15.21 | sq ft | 9.71 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 67%
C34-S245405 | 26003H | 1308J | LP1Y-DMF-175102-01-2 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 18 | 18 | 0 | 67.7248 | 24.98 | sq ft | 5.48 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246967 | 26003H | 1307J-L1 | LP1Y-DMF-175102-01-1-L1 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142858
C34-S245404 | 26003H | 1307J | LP1Y-DMF-175102-01-1 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 26.4216 | 7.16 | sq ft | 1.66 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143028
C34-S245403 | 26003H | 1305J | LP1Y-DMF-175101-03-1 | LP1Y-DMF-175101-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 3 | 6 | 32.393 | 27.12 | sq ft | 1.62 | ft | 2026-02-13 |  |  |  |  | 2026-03-03 | Jacob Perez | 2026-03-03 | George Allahverdian | 2026-03-03 | Jacob Perez | 2026-03-03 | Jacob Perez | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245402 | 26003H | 1304J | LP1Y-DMF-175101-02-2 | LP1Y-DMF-175101-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 19 | 18 | 1 | 54.0284 | 29.84 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245401 | 26003H | 1303J | LP1Y-DMF-175101-02-1 | LP1Y-DMF-175101-02 | 0 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Released to Fabrication | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 139.3135 | 33.35 | sq ft | 30.35 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-11 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | [6 empty] | 75% |  |  |  | 0%
C34-S245400 | 26003H | 1302J | LP1Y-DMF-175101-01-2 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246966 | 26003H | 1301J-L1 | LP1Y-DMF-175101-01-1-L1 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245399 | 26003H | 1301J | LP1Y-DMF-175101-01-1 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S245398 | 26003H | 1300J | LP1Y-DMF-102211-03-1 | LP1Y-DMF-102211-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 68.2513 | 25.56 | sq ft | 7.06 | ft | 2026-02-13 |  |  |  |  | 2026-03-02 | Jacob Perez | 2026-03-02 | George Allahverdian | 2026-03-02 | Jacob Perez | 2026-03-02 | Jacob Perez | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245397 | 26003H | 1299J | LP1Y-DMF-102211-01-2 | LP1Y-DMF-102211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12 | 12 | 0 | 23.8738 | 12.38 | sq ft | 6.38 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245396 | 26003H | 1298J | LP1Y-DMF-102211-01-1 | LP1Y-DMF-102211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 36.2925 | 18.7 | sq ft | 9.2 | ft | 2026-02-13 |  |  |  |  | 2026-03-02 | Jacob Perez | 2026-03-02 | George Allahverdian | 2026-03-02 | Jacob Perez | 2026-03-02 | Jacob Perez | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245395 | 26003H | 1297J | LP1Y-DMF-102206-03-5 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 10 | 10 | 0 | 78.9388 | 31.9 | sq ft | 27.4 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 80% |  |  |  | 0%
C34-S245394 | 26003H | 1296J | LP1Y-DMF-102206-03-4 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.1975 | 7.01 | sq ft | 3.01 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245393 | 26003H | 1295J | LP1Y-DMF-102206-03-3 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.0038 | 11.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245392 | 26003H | 1294J | LP1Y-DMF-102206-03-2 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 74.865 | 28.56 | sq ft | 3.56 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246965 | 26003H | 1293J-L1 | LP1Y-DMF-102206-03-1-L1 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142529
C34-S245391 | 26003H | 1293J | LP1Y-DMF-102206-03-1 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245390 | 26003H | 1292J | LP1Y-DMF-102206-01-1 | LP1Y-DMF-102206-01 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 2" SS DMF (315) 102206 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245389 | 26003H | 1291J | LP1Y-DMF-102205-03-3 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 12.705 | 6.81 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% |  |  |  | 0%
C34-S245388 | 26003H | 1290J | LP1Y-DMF-102205-03-2 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 81.6338 | 32.26 | sq ft | 29.26 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100%
C34-S245387 | 26003H | 1289J | LP1Y-DMF-102205-03-1 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.2263 | 8.49 | sq ft | 3.49 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245386 | 26003H | 1288J | LP1Y-DMF-102205-01-1 | LP1Y-DMF-102205-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 6 | 6 | 0 | 31.9138 | 13.42 | sq ft | 10.42 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142906
C34-S245385 | 26003H | 1287J | LP1Y-DMF-102204-03-2 | LP1Y-DMF-102204-03 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 3" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245384 | 26003H | 1286J | LP1Y-DMF-102204-03-1 | LP1Y-DMF-102204-03 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 3" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245383 | 26003H | 1285J | LP1Y-DMF-102204-02-1 | LP1Y-DMF-102204-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 28 | 28 | 0 | 157.1491 | 44.29 | sq ft | 5.07 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245382 | 26003H | 1284J | LP1Y-DMF-102204-01-3 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245381 | 26003H | 1283J | LP1Y-DMF-102204-01-2 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246964 | 26003H | 1282J-L1 | LP1Y-DMF-102204-01-1-L1 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245380 | 26003H | 1282J | LP1Y-DMF-102204-01-1 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245379 | 26003H | 1281J | LP1Y-DMF-102203-02-2 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246963 | 26003H | 1280J-L1 | LP1Y-DMF-102203-02-1-L1 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245378 | 26003H | 1280J | LP1Y-DMF-102203-02-1 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245377 | 26003H | 1279J | LP1Y-DMF-102203-01-1 | LP1Y-DMF-102203-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 6" SS DMF (315) 102203 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 30 | 28 | 2 | 208.9378 | 44.2 | sq ft | 13.22 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245376 | 26003H | 1278J | LP1Y-DMF-102108-03-3 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.2263 | 8.49 | sq ft | 3.49 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245375 | 26003H | 1277J | LP1Y-DMF-102108-03-2 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.2638 | 29.46 | sq ft | 26.46 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian; FD: 2026-03-02; FL: Jacob Perez | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 142955
C34-S245374 | 26003H | 1276J | LP1Y-DMF-102108-03-1 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 16.9813 | 8.43 | sq ft | 3.93 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-18 | 143001
C34-S245373 | 26003H | 1275J | LP1Y-DMF-102108-01-1 | LP1Y-DMF-102108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 21.4363 | 8.79 | sq ft | 7.29 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245372 | 26003H | 1274J | LP1Y-DMF-102106-03-5 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 17.655 | 8.69 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 142677
C34-S245371 | 26003H | 1273J | LP1Y-DMF-102106-03-4 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 76.99 | 30.42 | sq ft | 26.42 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247104 | 26003H | 1272JA | LP1Y-DMF-102106-03-7 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.4663 | 7.87 | sq ft | 3.87 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-10 | 142622
C34-S245370 | 26003H | 1272J | LP1Y-DMF-102106-03-3 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 10.8525 | 6.03 | sq ft | 0.53 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245369 | 26003H | 1271J | LP1Y-DMF-102106-03-2 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 63.9163 | 22.49 | sq ft | 2.99 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246962 | 26003H | 1270J-L1 | LP1Y-DMF-102106-03-1-L1 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142530
C34-S247017 | 26003H | 1270JA | LP1Y-DMF-102106-03-6 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.025 | 6.85 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245368 | 26003H | 1270J | LP1Y-DMF-102106-03-1 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245367 | 26003H | 1269J | LP1Y-DMF-102106-01-1 | LP1Y-DMF-102106-01 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 2" SS DMF (315) 102106 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245366 | 26003H | 1268J | LP1Y-DMF-102105-03-1 | LP1Y-DMF-102105-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102105 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102105 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 67.9488 | 25.44 | sq ft | 6.94 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245365 | 26003H | 1267J | LP1Y-DMF-102105-01-1 | LP1Y-DMF-102105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS DMF (315) P 102105 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102105 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 44.3638 | 22.42 | sq ft | 11.42 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245364 | 26003H | 1266J | LP1Y-DMF-102104-07-3 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245363 | 26003H | 1265J | LP1Y-DMF-102104-07-4 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245362 | 26003H | 1264J | LP1Y-DMF-102104-07-2 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245361 | 26003H | 1263J | LP1Y-DMF-102104-07-1 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245360 | 26003H | 1262J | LP1Y-DMF-102104-04-1 | LP1Y-DMF-102104-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 21 | 20 | 1 | 78.459 | 24.9 | sq ft | 9.9 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245359 | 26003H | 1261J | LP1Y-DMF-102104-03-1 | LP1Y-DMF-102104-03 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P015 |  |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245358 | 26003H | 1260J | LP1Y-DMF-102104-02-3 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245357 | 26003H | 1259J | LP1Y-DMF-102104-02-2 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246961 | 26003H | 1258J-L1 | LP1Y-DMF-102104-02-1-L1 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245356 | 26003H | 1258J | LP1Y-DMF-102104-02-1 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245355 | 26003H | 1257J | LP1Y-DMF-102103-02-2 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246960 | 26003H | 1256J-L1 | LP1Y-DMF-102103-02-1-L1 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245354 | 26003H | 1256J | LP1Y-DMF-102103-02-1 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P015 |  |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245353 | 26003H | 1255J | LP1Y-DMF-102103-01-1 | LP1Y-DMF-102103-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 30 | 28 | 2 | 208.9378 | 44.2 | sq ft | 13.22 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245352 | 26003H | 1254J | LP1Y-DMF-102102-02-5 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 21 | 21 | 0 | 157.2982 | 36.32 | sq ft | 30.32 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 86% |  |  |  | 57%
C34-S245351 | 26003H | 1253J | LP1Y-DMF-102102-02-4 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 3 | 3 | 0 | 51.4043 | 12.93 | sq ft | 8.93 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-14 | 2026-03-14 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100%
C34-S245350 | 26003H | 1252J | LP1Y-DMF-102102-02-3 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 32.9166 | 8.66 | sq ft | 3.16 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 143027
C34-S245349 | 26003H | 1251J | LP1Y-DMF-102102-02-2 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.1762 | 16.87 | sq ft | 2.87 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246959 | 26003H | 1250J-L1 | LP1Y-DMF-102102-02-1-L1 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142855
C34-S245348 | 26003H | 1250J | LP1Y-DMF-102102-02-1 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 26.4216 | 7.16 | sq ft | 1.66 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245347 | 26003H | 1249J | LP1Y-DMF-062302-16-1 | LP1Y-DMF-062302-16 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P036 |  |  | LP1Y 3" SS DMF (315) P 062302 | DMF |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-062302 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245346 | 26003H | 1248AB | LP1Y-BS-178304-01-1 | LP1Y-BS-178304-01 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-12 | released |  |  | In Engineering | P018 |  |  | LP1Y 3" HAST BS (332) P 178304 | BS |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178304 |  | TFS00D001YSPP |  | 332-BS | NONE | 3" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245345 | 26003H | 1247J | LP1Y-AWNP-168101-08-2 | LP1Y-AWNP-168101-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS AWNP (315) (108) 168101 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-168101 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.2325 | 7.78 | sq ft | 3.78 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245344 | 26003H | 1246J | LP1Y-AWNP-168101-08-1 | LP1Y-AWNP-168101-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 2" SS AWNP (315) (108) 168101 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-168101 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.5088 | 10.94 | sq ft | 1.44 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143007
C34-S245343 | 26003H | 1245J | LP1Y-AWNP-108094-01-1 | LP1Y-AWNP-108094-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 2" SS AWNP (315) (108) 108094 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108094 |  | TFS00E006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 18.25 | 14 | 4.25 | 89.2888 | 34.11 | sq ft | 11.61 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245342 | 26003H | 1244J | LP1Y-AWNP-102092-03-3 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 11.87 | 5.75 | sq ft | 1.75 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142825
C34-S245341 | 26003H | 1243J | LP1Y-AWNP-102092-03-2 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4.75 | 4 | 0.75 | 16.05 | 12 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245340 | 26003H | 1242J | LP1Y-AWNP-102092-03-1 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 70.63 | 26.38 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246958 | 26003H | 1241J-L1 | LP1Y-AWNP-101314-01-1-L1 | LP1Y-AWNP-101314-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 10" SS AWNP (315) 101314 | AWNP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101314 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245339 | 26003H | 1241J | LP1Y-AWNP-101314-01-1 | LP1Y-AWNP-101314-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 10" SS AWNP (315) 101314 | AWNP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101314 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245338 | 26003H | 1240J | LP1Y-AWNP-101310-02-2 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246957 | 26003H | 1239J-L1 | LP1Y-AWNP-101310-02-1-L1 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142856
C34-S245337 | 26003H | 1239J | LP1Y-AWNP-101310-02-1 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 17 | 1 | 54.3431 | 25.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245336 | 26003H | 1238J | LP1Y-AWNP-101310-01-4 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 27 | 27 | 0 | 59.0298 | 27.38 | sq ft | 5.31 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245335 | 26003H | 1237J | LP1Y-AWNP-101310-01-3 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 80.115 | 18.5 | sq ft | 15.5 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245334 | 26003H | 1236J | LP1Y-AWNP-101310-01-2 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 6 | 5 | 1 | 73.5471 | 21.21 | sq ft | 14.71 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245333 | 26003H | 1235J | LP1Y-AWNP-101310-01-1 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 18 | 0 | 68.6658 | 23.08 | sq ft | 8.58 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245332 | 26003H | 1234J | LP1Y-AWNP-101309-11-1 | LP1Y-AWNP-101309-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 8" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D007YSPP |  | 315-AWNP | NONE | 8" | 316 SS | 46 | 46 | 0 | 174.6738 | 32.94 | sq ft | 1.54 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245331 | 26003H | 1233J | LP1Y-AWNP-101309-09-2 | LP1Y-AWNP-101309-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 17.75 | 12 | 5.75 | 113.8219 | 32.29 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245330 | 26003H | 1232J | LP1Y-AWNP-101309-09-1 | LP1Y-AWNP-101309-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 126.9313 | 27.21 | sq ft | 6.9 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S245329 | 26003H | 1231J | LP1Y-AWNP-101309-05-4 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245328 | 26003H | 1230J | LP1Y-AWNP-101309-05-3 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245327 | 26003H | 1229J | LP1Y-AWNP-101309-05-2 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246956 | 26003H | 1228J-L1 | LP1Y-AWNP-101309-05-1-L1 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247016 | 26003H | 1228JA | LP1Y-AWNP-101309-05-5 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245326 | 26003H | 1228J | LP1Y-AWNP-101309-05-1 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245325 | 26003H | 1227J | LP1Y-AWNP-101309-04-5 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 40 | 38 | 2 | 283.8528 | 59.6 | sq ft | 22.39 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245324 | 26003H | 1226J | LP1Y-AWNP-101309-04-4 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 93.3328 | 18.3 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143074
C34-S245323 | 26003H | 1225J | LP1Y-AWNP-101309-04-3 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 105.2641 | 22.92 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143073
C34-S245322 | 26003H | 1224J | LP1Y-AWNP-101309-04-2 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 88.8281 | 17.43 | sq ft | 2.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142987
C34-S245321 | 26003H | 1223J | LP1Y-AWNP-101309-04-1 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 27 | 26 | 1 | 124.4141 | 29.44 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245320 | 26003H | 1222J | LP1Y-AWNP-101309-01-3 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142839
C34-S245319 | 26003H | 1221J | LP1Y-AWNP-101309-01-2 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 22 | 22 | 0 | 100.0263 | 23.26 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143077
C34-S245318 | 26003H | 1220J | LP1Y-AWNP-101309-01-1 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 36 | 36 | 0 | 107.7359 | 22.68 | sq ft | 4.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Aristeo Banda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 67%
C34-S245317 | 26003H | 1219J | LP1Y-AWNP-101308-01-4 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245316 | 26003H | 1218J | LP1Y-AWNP-101308-01-3 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245315 | 26003H | 1217J | LP1Y-AWNP-101308-01-2 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246955 | 26003H | 1216J-L1 | LP1Y-AWNP-101308-01-1-L1 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247015 | 26003H | 1216JA | LP1Y-AWNP-101308-01-5 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245314 | 26003H | 1216J | LP1Y-AWNP-101308-01-1 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245313 | 26003H | 1215J | LP1Y-AWNP-101307-01-3 | LP1Y-AWNP-101307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245312 | 26003H | 1214J | LP1Y-AWNP-101307-01-2 | LP1Y-AWNP-101307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246954 | 26003H | 1213J-L1 | LP1Y-AWNP-101307-01-1-L1 | LP1Y-AWNP-101307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245311 | 26003H | 1213J | LP1Y-AWNP-101307-01-1 | LP1Y-AWNP-101307-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245310 | 26003H | 1212J | LP1Y-AWNP-101305-02-2 | LP1Y-AWNP-101305-02 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246953 | 26003H | 1211J-L1 | LP1Y-AWNP-101305-02-1-L1 | LP1Y-AWNP-101305-02 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245309 | 26003H | 1211J | LP1Y-AWNP-101305-02-1 | LP1Y-AWNP-101305-02 | 2 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245308 | 26003H | 1210J | LP1Y-AWNP-101305-01-5 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 86.8734 | 19.46 | sq ft | 2.59 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 |  |  |  | 67% |  |  |  | 33%
C34-S245307 | 26003H | 1209J | LP1Y-AWNP-101305-01-4 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 121.7063 | 25.76 | sq ft | 11.31 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian; FD: 2026-03-02; FL: Jacob Perez | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245306 | 26003H | 1208J | LP1Y-AWNP-101305-01-3 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 39.1688 | 9.79 | sq ft | 2.44 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245305 | 26003H | 1207J | LP1Y-AWNP-101305-01-2 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 10 | 2 | 81.9816 | 18.94 | sq ft | 4.41 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246952 | 26003H | 1206J-L1 | LP1Y-AWNP-101305-01-1-L1 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142528
C34-S245304 | 26003H | 1206J | LP1Y-AWNP-101305-01-1 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 43.3 | 8.5 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 142849
C34-S245303 | 26003H | 1205J | LP1Y-AWNP-101302-04-3 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 101.2281 | 19.83 | sq ft | 3.57 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142851
C34-S245302 | 26003H | 1204J | LP1Y-AWNP-101302-04-2 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 138.6141 | 30.42 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143072
C34-S246951 | 26003H | 1203J-L1 | LP1Y-AWNP-101302-04-1-L1 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142533
C34-S245301 | 26003H | 1203J | LP1Y-AWNP-101302-04-1 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 68.3953 | 13.93 | sq ft | 2.52 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% |  |  |  | 67%
C34-S245300 | 26003H | 1202J | LP1Y-AWNP-101302-03-3 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 1" | 316 SS | 2 | 2 | 0 | 22.26 | 18 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245299 | 26003H | 1201J | LP1Y-AWNP-101302-03-2 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 43.5 | 40.5 | 3 | 190.8655 | 53.58 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245298 | 26003H | 1200J | LP1Y-AWNP-101302-03-1 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 203.5391 | 39.97 | sq ft | 20.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142879
C34-S246950 | 26003H | 1199J-L1 | LP1Y-AWNP-101114-01-1-L1 | LP1Y-AWNP-101114-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 10" SS AWNP (315) 101114 | AWNP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101114 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245297 | 26003H | 1199J | LP1Y-AWNP-101114-01-1 | LP1Y-AWNP-101114-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 10" SS AWNP (315) 101114 | AWNP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101114 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245296 | 26003H | 1198J | LP1Y-AWNP-101110-04-2 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | 2026-03-06 |  | active | client | rfi | On Hold | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246949 | 26003H | 1197J-L1 | LP1Y-AWNP-101110-04-1-L1 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142857
C34-S245295 | 26003H | 1197J | LP1Y-AWNP-101110-04-1 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 17 | 1 | 53.3082 | 24.57 | sq ft | 4.57 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245294 | 26003H | 1196J | LP1Y-AWNP-101110-03-2 | LP1Y-AWNP-101110-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 30.75 | 29 | 1.75 | 59.5208 | 31.86 | sq ft | 4.75 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245293 | 26003H | 1195J | LP1Y-AWNP-101110-03-1 | LP1Y-AWNP-101110-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 4" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 79.3081 | 18.31 | sq ft | 13.81 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-14 | 2026-03-14 | 2026-03-14 |  |  |  | 60% |  |  |  | 40%
C34-S245292 | 26003H | 1194J | LP1Y-AWNP-101110-01-2 | LP1Y-AWNP-101110-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 37.6544 | 8.69 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142806
C34-S245291 | 26003H | 1193J | LP1Y-AWNP-101110-01-1 | LP1Y-AWNP-101110-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.7595 | 15.95 | sq ft | 4.45 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245290 | 26003H | 1192J | LP1Y-AWNP-101108-01-4 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 110.5844 | 22.09 | sq ft | 7.05 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245289 | 26003H | 1191J | LP1Y-AWNP-101108-01-3 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 20 | 1 | 105.9516 | 25.42 | sq ft | 2.79 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245288 | 26003H | 1190J | LP1Y-AWNP-101108-01-2 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246948 | 26003H | 1189J-L1 | LP1Y-AWNP-101108-01-1-L1 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245287 | 26003H | 1189J | LP1Y-AWNP-101108-01-1 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 34 | 33 | 1 | 130.103 | 37.41 | sq ft | 6.27 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245286 | 26003H | 1188J | LP1Y-AWNP-101107-01-3 | LP1Y-AWNP-101107-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245285 | 26003H | 1187J | LP1Y-AWNP-101107-01-2 | LP1Y-AWNP-101107-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246947 | 26003H | 1186J-L1 | LP1Y-AWNP-101107-01-1-L1 | LP1Y-AWNP-101107-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245284 | 26003H | 1186J | LP1Y-AWNP-101107-01-1 | LP1Y-AWNP-101107-01 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245283 | 26003H | 1185J | LP1Y-AWNP-101106-03-3 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 60.8828 | 11.9 | sq ft | 2.89 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142809
C34-S245282 | 26003H | 1184J | LP1Y-AWNP-101106-03-2 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 84.275 | 16.55 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 142850
C34-S245281 | 26003H | 1183J | LP1Y-AWNP-101106-03-1 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 9 | 8 | 1 | 70.1547 | 17.8 | sq ft | 3.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245280 | 26003H | 1182J | LP1Y-AWNP-101106-02-3 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 28 | 26 | 2 | 234.2966 | 49.44 | sq ft | 18.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245279 | 26003H | 1181J | LP1Y-AWNP-101106-02-2 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 90.9594 | 17.84 | sq ft | 2.47 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142829
C34-S245278 | 26003H | 1180J | LP1Y-AWNP-101106-02-1 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 50 | 12.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 142563
C34-S245277 | 26003H | 1179J | LP1Y-AWNP-101106-01-5 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 124.4609 | 26.73 | sq ft | 6.63 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S245276 | 26003H | 1178J | LP1Y-AWNP-101106-01-4 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 20 | 1 | 105.9031 | 25.41 | sq ft | 2.78 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245275 | 26003H | 1177J | LP1Y-AWNP-101106-01-3 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245274 | 26003H | 1176J | LP1Y-AWNP-101106-01-2 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 66.2156 | 13.51 | sq ft | 2.28 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143236
C34-S246946 | 26003H | 1175J-L1 | LP1Y-AWNP-101106-01-1-L1 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245273 | 26003H | 1175J | LP1Y-AWNP-101106-01-1 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 16 | 15 | 1 | 69.8936 | 25.06 | sq ft | 4.64 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245272 | 26003H | 1174J | LP1Y-AWNP-101105-02-2 | LP1Y-AWNP-101105-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246945 | 26003H | 1173J-L1 | LP1Y-AWNP-101105-02-1-L1 | LP1Y-AWNP-101105-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245271 | 26003H | 1173J | LP1Y-AWNP-101105-02-1 | LP1Y-AWNP-101105-02 | 1 | N | PRIORITY-1 | [5 empty] | In Engineering | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245270 | 26003H | 1172J | LP1Y-AWNP-101105-01-4 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 113.5672 | 25.2 | sq ft | 4.28 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-19 | N/A | N/A | Aristeo Banda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 80%
C34-S245269 | 26003H | 1171J | LP1Y-AWNP-101105-01-3 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 98.8391 | 20.77 | sq ft | 10.04 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143031
C34-S245268 | 26003H | 1170J | LP1Y-AWNP-101105-01-2 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 28 | 2 | 116.2097 | 27.77 | sq ft | 6.32 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246944 | 26003H | 1169J-L1 | LP1Y-AWNP-101105-01-1-L1 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142526
C34-S245267 | 26003H | 1169J | LP1Y-AWNP-101105-01-1 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 43.3 | 8.5 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142747
C34-S245266 | 26003H | 1168J | LP1Y-AWNP-037006-04-1 | LP1Y-AWNP-037006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS AWNP (315) (108) 037006 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037006 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 14 | 14 | 0 | 69.4625 | 24.24 | sq ft | 5.74 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245265 | 26003H | 1167J | LP1Y-AWNP-037002-03-2 | LP1Y-AWNP-037002-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 037002 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037002 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 217.0984 | 42.71 | sq ft | 18.51 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142807
C34-S245264 | 26003H | 1166J | LP1Y-AWNP-037002-03-1 | LP1Y-AWNP-037002-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 037002 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037002 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 104.6719 | 21.07 | sq ft | 2.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142746
C34-S245263 | 26003H | 1165J | LP1Y-AWNP-015003-12-1 | LP1Y-AWNP-015003-12 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS AWNP (315) (108) 015003 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015003 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.9638 | 21.76 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245262 | 26003H | 1164J | LP1Y-AWNP-015001-13-3 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 48 | 48 | 0 | 210.8078 | 45.65 | sq ft | 14.14 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S245261 | 26003H | 1163J | LP1Y-AWNP-015001-13-4 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 178.7844 | 35.29 | sq ft | 14.39 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 |  |  |  | 67% |  |  |  | 67%
C34-S245260 | 26003H | 1162J | LP1Y-AWNP-015001-13-2 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 73.7538 | 18.75 | sq ft | 1.71 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143235
C34-S245259 | 26003H | 1161J | LP1Y-AWNP-015001-13-1 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 23 | 22 | 1 | 84.703 | 24.11 | sq ft | 3.55 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245258 | 26003H | 1160J | LP1Y-AWNP-015001-12-3 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 96.3844 | 18.89 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142852
C34-S245257 | 26003H | 1159J | LP1Y-AWNP-015001-12-2 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 138.6141 | 30.42 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S246943 | 26003H | 1158J-L1 | LP1Y-AWNP-015001-12-1-L1 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142527
C34-S245256 | 26003H | 1158J | LP1Y-AWNP-015001-12-1 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 68.3953 | 13.93 | sq ft | 2.52 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-16 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142812
C34-S245255 | 26003H | 1157J | LP1Y-AWNP-015001-11-2 | LP1Y-AWNP-015001-11 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 44.5 | 41.5 | 3 | 196.1308 | 54.84 | sq ft | 8.85 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245254 | 26003H | 1156J | LP1Y-AWNP-015001-11-1 | LP1Y-AWNP-015001-11 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 203.5391 | 39.97 | sq ft | 20.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142862
C34-S245253 | 26003H | 1155J | LP1Y-AWNP-015001-09-3 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 148.1234 | 29.36 | sq ft | 11.09 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142767
C34-S245252 | 26003H | 1154J | LP1Y-AWNP-015001-09-2 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 123.2719 | 24.67 | sq ft | 4.76 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 50%
C34-S245251 | 26003H | 1153J | LP1Y-AWNP-015001-09-1 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 9 | 8 | 1 | 115.3469 | 26.54 | sq ft | 8.64 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245250 | 26003H | 1152J | LP1Y-AWNP-015001-01-1 | LP1Y-AWNP-015001-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 84 | 78 | 6 | 354.2728 | 86.89 | sq ft | 21.21 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245249 | 26003H | 1151J | LP1Y-AW-165332-01-1 | LP1Y-AW-165332-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS AW (315) 165332 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165332 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 14.5 | 14.5 | 0 | 70.2269 | 27.51 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245248 | 26003H | 1150J | LP1Y-AW-165322-01-1 | LP1Y-AW-165322-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS AW (315) 165322 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165322 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 14.5 | 14.5 | 0 | 70.2269 | 27.51 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245247 | 26003H | 1149J | LP1Y-AW-165312-01-1 | LP1Y-AW-165312-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS AW (315) 165312 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165312 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 14.5 | 14.5 | 0 | 70.2269 | 27.51 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245246 | 26003H | 1148J | LP1Y-AW-165302-01-1 | LP1Y-AW-165302-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS AW (315) 165302 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165302 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 14.5 | 14.5 | 0 | 70.2269 | 27.51 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245245 | 26003H | 1147J | LP1Y-AW-165212-01-1 | LP1Y-AW-165212-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS AW (315) 165212 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165212 |  | TFS00D003YSPP |  | 315-AW | NONE | 2" | 316 SS | 14.5 | 14.5 | 0 | 68.256 | 25.51 | sq ft | 6.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245244 | 26003H | 1146J | LP1Y-AW-165202-01-1 | LP1Y-AW-165202-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS AW (315) 165202 | AW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165202 |  | TFS00D003YSPP |  | 315-AW | NONE | 2" | 316 SS | 12.5 | 12.5 | 0 | 66.3883 | 25.76 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245243 | 26003H | 1145J | LP1Y-APL(100)-198113-01-1 | LP1Y-APL(100)-198113-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS APL(100) (315) 198113 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198113 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 57.4788 | 25.03 | sq ft | 16.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 |  |  |  | 83% |  |  |  | 67%
C34-S245242 | 26003H | 1144J | LP1Y-APL(100)-198109-02-1 | LP1Y-APL(100)-198109-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 |  |  | LP1Y 2" SS APL(100) (315) 198109 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198109 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 25.4075 | 13.55 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142808
C34-S245241 | 26003H | 1143J | LP1Y-APL(100)-198108-02-1 | LP1Y-APL(100)-198108-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 198108 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198108 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 42.7738 | 20.8 | sq ft | 12.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Aristeo Banda | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 83%
C34-S245240 | 26003H | 1142J | LP1Y-APL(100)-198107-02-1 | LP1Y-APL(100)-198107-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198107 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198107 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142827
C34-S245239 | 26003H | 1141J | LP1Y-APL(100)-198106-02-1 | LP1Y-APL(100)-198106-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198106 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198106 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 143087
C34-S245238 | 26003H | 1140J | LP1Y-APL(100)-198105-02-1 | LP1Y-APL(100)-198105-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198105 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198105 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 143088
C34-S245237 | 26003H | 1139J | LP1Y-APL(100)-198104-02-1 | LP1Y-APL(100)-198104-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 2" SS APL(100) (315) 198104 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198104 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 32.3925 | 16.86 | sq ft | 8.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 67%
C34-S245236 | 26003H | 1138J | LP1Y-APL(100)-198103-02-1 | LP1Y-APL(100)-198103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 2" SS APL(100) (315) 198103 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198103 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 42.9388 | 20.86 | sq ft | 12.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143085
C34-S245235 | 26003H | 1137J | LP1Y-APL(100)-198102-01-1 | LP1Y-APL(100)-198102-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS APL(100) (315) 198102 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198102 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 51.24 | 22.67 | sq ft | 15.67 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 50%
C34-S245234 | 26003H | 1136J | LP1Y-APL(100)-198101-01-1 | LP1Y-APL(100)-198101-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS APL(100) (315) 198101 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198101 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 59.5138 | 25.13 | sq ft | 18.13 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 |  | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% |  |  |  | 50%
C34-S245233 | 26003H | 1135J | LP1Y-APL(100)-198088-02-1 | LP1Y-APL(100)-198088-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 |  |  | LP1Y 2" SS APL(100) (315) 198088 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198088 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 42.56 | 18.04 | sq ft | 12.54 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142985
C34-S245232 | 26003H | 1134J | LP1Y-APL(100)-198087-01-1 | LP1Y-APL(100)-198087-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS APL(100) (315) 198087 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198087 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.7925 | 11.78 | sq ft | 7.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245231 | 26003H | 1133J | LP1Y-APL(100)-198086-01-1 | LP1Y-APL(100)-198086-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS APL(100) (315) 198086 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198086 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 19.2263 | 8.54 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 142592
C34-S245230 | 26003H | 1132J | LP1Y-APL(100)-198065-01-1 | LP1Y-APL(100)-198065-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 |  |  | LP1Y 2" SS APL(100) (315) 198065 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198065 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 18 | 18 | 0 | 48.3013 | 23.56 | sq ft | 13.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143032
C34-S245229 | 26003H | 1131J | LP1Y-APL(100)-198064-03-3 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.2499 | 3.65 | sq ft | 1.15 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100%
C34-S245228 | 26003H | 1130J | LP1Y-APL(100)-198064-03-2 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 6.097 | 7.38 | sq ft | 2.38 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245227 | 26003H | 1129J | LP1Y-APL(100)-198064-03-1 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 9.0678 | 11.17 | sq ft | 6.67 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | [6 empty] | 83% |  |  |  | 0%
C34-S245226 | 26003H | 1128J | LP1Y-APL(100)-198064-01-3 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 34.281 | 30.49 | sq ft | 5.99 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245225 | 26003H | 1127J | LP1Y-APL(100)-198064-01-2 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 5.75 | 2 | 3.75 | 26.5536 | 17.28 | sq ft | 7.78 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245224 | 26003H | 1126J | LP1Y-APL(100)-198064-01-1 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 |  |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.0988 | 13.4 | sq ft | 8.9 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142811
C34-S245223 | 26003H | 1125J | LP1Y-APL(100)-198058-04-4 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.1002 | 3.2 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245222 | 26003H | 1124J | LP1Y-APL(100)-198058-04-3 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 2.6967 | 5.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245221 | 26003H | 1123J | LP1Y-APL(100)-198058-04-2 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 3.1864 | 5.29 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S245220 | 26003H | 1122J | LP1Y-APL(100)-198058-04-1 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.5761 | 9.09 | sq ft | 5.59 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | [6 empty] | 75% |  |  |  | 0%
C34-S245219 | 26003H | 1121J | LP1Y-APL(100)-198058-02-3 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 19.6075 | 8.76 | sq ft | 5.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 |  |  |  | 50% |  |  |  | 25%
C34-S245218 | 26003H | 1120J | LP1Y-APL(100)-198058-02-2 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.9 | 12.75 | sq ft | 11.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143006
C34-S245217 | 26003H | 1119J | LP1Y-APL(100)-198058-02-1 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 24.2088 | 10.61 | sq ft | 5.61 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S245216 | 26003H | 1118J | LP1Y-APL(100)-198058-01-1 | LP1Y-APL(100)-198058-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 9.75 | 0 | 9.75 | 37.5438 | 37.56 | sq ft | 5.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245215 | 26003H | 1117J | LP1Y-APL(100)-198044-04-1 | LP1Y-APL(100)-198044-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 19.029 | 17.51 | sq ft | 4.51 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245214 | 26003H | 1116J | LP1Y-APL(100)-198044-03-1 | LP1Y-APL(100)-198044-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 9.2079 | 13.52 | sq ft | 7.02 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | [6 empty] | 75% |  |  |  | 0%
C34-S245213 | 26003H | 1115JA | LP1Y-APL(100)-198044-02-3 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143227
C34-S245212 | 26003H | 1115J | LP1Y-APL(100)-198044-02-2 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4435 | 6.86 | sq ft | 1.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245211 | 26003H | 1114J | LP1Y-APL(100)-198044-02-1 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 20.05 | 22 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245210 | 26003H | 1113J | LP1Y-APL(100)-198044-01-3 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.7275 | 15.26 | sq ft | 8.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 67% |  |  |  | 0%
C34-S245209 | 26003H | 1112J | LP1Y-APL(100)-198044-01-2 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 39.1875 | 15.51 | sq ft | 14.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142877
C34-S245208 | 26003H | 1111J | LP1Y-APL(100)-198044-01-1 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 76.8488 | 24.44 | sq ft | 9.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245207 | 26003H | 1110J | LP1Y-APL(100)-198042-05-1 | LP1Y-APL(100)-198042-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 19.2888 | 17.81 | sq ft | 4.81 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245206 | 26003H | 1109J | LP1Y-APL(100)-198042-04-1 | LP1Y-APL(100)-198042-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 11.2056 | 15.84 | sq ft | 9.34 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | [6 empty] | 88% |  |  |  | 0%
C34-S245205 | 26003H | 1108JA | LP1Y-APL(100)-198042-03-3 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143228, 143229
C34-S245204 | 26003H | 1108J | LP1Y-APL(100)-198042-03-2 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 4.49 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 |  |  |  | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% |  |  |  | 0%
C34-S245203 | 26003H | 1107J | LP1Y-APL(100)-198042-03-1 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 20.9632 | 22.82 | sq ft | 1.32 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245202 | 26003H | 1106J | LP1Y-APL(100)-198042-01-3 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.0325 | 13.57 | sq ft | 8.57 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 60% |  |  |  | 0%
C34-S245201 | 26003H | 1105J | LP1Y-APL(100)-198042-01-2 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 56.815 | 22.85 | sq ft | 19.85 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142789
C34-S245200 | 26003H | 1104J | LP1Y-APL(100)-198042-01-1 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 25.9463 | 10.49 | sq ft | 8.99 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245199 | 26003H | 1103J | LP1Y-APL(100)-198013-04-2 | LP1Y-APL(100)-198013-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 7.4241 | 9.61 | sq ft | 3.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245198 | 26003H | 1102J | LP1Y-APL(100)-198013-04-1 | LP1Y-APL(100)-198013-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.789 | 5.51 | sq ft | 2.51 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245197 | 26003H | 1101J | LP1Y-APL(100)-198013-03-1 | LP1Y-APL(100)-198013-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 |  |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 11.25 | 0 | 11.25 | 38.0069 | 37.53 | sq ft | 4.03 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245196 | 26003H | 1100J | LP1Y-APL(100)-198013-02-2 | LP1Y-APL(100)-198013-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS APL(100) (315) 198013 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 7 | 4 | 3 | 24.7178 | 16.68 | sq ft | 10.18 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245195 | 26003H | 1099J | LP1Y-APL(100)-198013-02-1 | LP1Y-APL(100)-198013-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  |  | LP1Y 2" SS APL(100) (315) 198013 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 45.705 | 17.98 | sq ft | 16.48 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% |  |  |  | 50%
C34-S245194 | 26003H | 1098J | LP1Y-APL(100)-198008-05-1 | LP1Y-APL(100)-198008-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 19.6695 | 18.26 | sq ft | 5.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245193 | 26003H | 1097J | LP1Y-APL(100)-198008-04-1 | LP1Y-APL(100)-198008-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 11.1698 | 15.8 | sq ft | 9.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | [6 empty] | 88% |  |  |  | 0%
C34-S245192 | 26003H | 1096J | LP1Y-APL(100)-198008-03-3 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143230
C34-S245191 | 26003H | 1095J | LP1Y-APL(100)-198008-03-2 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4928 | 6.92 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245190 | 26003H | 1094J | LP1Y-APL(100)-198008-03-1 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 20.05 | 22 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245189 | 26003H | 1093J | LP1Y-APL(100)-198008-02-2 | LP1Y-APL(100)-198008-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.2463 | 15.08 | sq ft | 8.58 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 142954
C34-S245188 | 26003H | 1092J | LP1Y-APL(100)-198008-02-1 | LP1Y-APL(100)-198008-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 |  |  | LP1Y 2" SS APL(100) (315) 198008 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 43.8213 | 17.93 | sq ft | 14.93 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142900
C34-S245187 | 26003H | 1091J | LP1Y-APL(100)-198001-04-4 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.344 | 3.76 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245186 | 26003H | 1090J | LP1Y-APL(100)-198001-04-3 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0354 | 6.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245185 | 26003H | 1089J | LP1Y-APL(100)-198001-04-2 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 5.4716 | 6.23 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245184 | 26003H | 1088J | LP1Y-APL(100)-198001-04-1 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.6019 | 3.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245183 | 26003H | 1087J | LP1Y-APL(100)-198001-03-1 | LP1Y-APL(100)-198001-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 13.25 | 5 | 8.25 | 45.1248 | 43.57 | sq ft | 10.57 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245182 | 26003H | 1086J | LP1Y-APL(100)-198001-02-3 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 4 | 4 | 0 | 24.5492 | 21.44 | sq ft | 16.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 75% |  |  |  | 0%
C34-S245181 | 26003H | 1085J | LP1Y-APL(100)-198001-02-2 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 3 | 3 | 0 | 12.5339 | 11.62 | sq ft | 8.62 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Omar Puente | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 67% |  |  |  | 0%
C34-S245180 | 26003H | 1084J | LP1Y-APL(100)-198001-02-1 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 3 | 3 | 0 | 17.6342 | 15.11 | sq ft | 12.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Omar Puente | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | [6 empty] | 67% |  |  |  | 0%
C34-S245179 | 26003H | 1083JA | LP1Y-APL(100)-034162-04-4 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245178 | 26003H | 1083J | LP1Y-APL(100)-034162-04-3 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 16.5507 | 13.94 | sq ft | 2.44 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245177 | 26003H | 1082J | LP1Y-APL(100)-034162-04-2 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.5819 | 6.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245176 | 26003H | 1081J | LP1Y-APL(100)-034162-04-1 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 6.9671 | 8.73 | sq ft | 4.23 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245175 | 26003H | 1080J | LP1Y-APL(100)-034162-03-1 | LP1Y-APL(100)-034162-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8.25 | 0 | 8.25 | 9.9333 | 16.67 | sq ft | 3.67 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245174 | 26003H | 1079J | LP1Y-APL(100)-034162-02-2 | LP1Y-APL(100)-034162-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 13.8875 | 6.59 | sq ft | 3.59 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-10 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% |  |  |  | 0%
C34-S245173 | 26003H | 1078J | LP1Y-APL(100)-034162-02-1 | LP1Y-APL(100)-034162-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 46.9838 | 19.13 | sq ft | 16.13 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  |  |  | 67% |  |  |  | 67%
C34-S245172 | 26003H | 1077J | LP1Y-APL(100)-034060-02-3 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 33.752 | 19.81 | sq ft | 4.31 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245171 | 26003H | 1076J | LP1Y-APL(100)-034060-02-2 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 |  |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 29.0125 | 11.66 | sq ft | 10.16 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143005
C34-S245170 | 26003H | 1075J | LP1Y-APL(100)-034060-02-1 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 |  |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 44.7425 | 17.61 | sq ft | 16.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 142888
C34-S245169 | 26003H | 1074J | LP1Y-APL(100)-019089-07-1 | LP1Y-APL(100)-019089-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 19.4858 | 18.04 | sq ft | 5.04 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245168 | 26003H | 1073J | LP1Y-APL(100)-019089-06-1 | LP1Y-APL(100)-019089-06 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 9.5618 | 13.93 | sq ft | 7.43 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | [6 empty] | 88% |  |  |  | 0%
C34-S245167 | 26003H | 1072J | LP1Y-APL(100)-019089-05-3 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245166 | 26003H | 1071J | LP1Y-APL(100)-019089-05-2 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4794 | 6.91 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245165 | 26003H | 1070J | LP1Y-APL(100)-019089-05-1 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 20.05 | 22 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245164 | 26003H | 1069J | LP1Y-APL(100)-019089-02-4 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 32.0438 | 15.38 | sq ft | 8.88 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | [6 empty] | 67% |  |  |  | 0%
C34-S245163 | 26003H | 1068J | LP1Y-APL(100)-019089-02-3 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.3688 | 15.11 | sq ft | 12.11 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 67% |  |  |  | 0%
C34-S245162 | 26003H | 1067J | LP1Y-APL(100)-019089-02-2 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 41.6625 | 17.11 | sq ft | 14.11 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A |  |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | [6 empty] | 75% |  |  |  | 0%
C34-S245161 | 26003H | 1066J | LP1Y-APL(100)-019089-02-1 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 18 | 16 | 2 | 93.21 | 32.96 | sq ft | 15.46 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245160 | 26003H | 1065J | LP1Y-APL(100)-019080-04-3 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.3664 | 3.79 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245159 | 26003H | 1064J | LP1Y-APL(100)-019080-04-2 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0085 | 6.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245158 | 26003H | 1063J | LP1Y-APL(100)-019080-04-1 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 |  |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.6434 | 9.52 | sq ft | 5.02 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143231
C34-S245157 | 26003H | 1062J | LP1Y-APL(100)-019080-03-4 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 15.25 | 7 | 8.25 | 45.3043 | 46.57 | sq ft | 10.07 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245156 | 26003H | 1061J | LP1Y-APL(100)-019080-03-3 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 118.0438 | 39.38 | sq ft | 26.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245155 | 26003H | 1060J | LP1Y-APL(100)-019080-03-2 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 57.9 | 25.58 | sq ft | 19.58 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 |  | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  |  |  | 80% |  |  |  | 80%
C34-S245154 | 26003H | 1059J | LP1Y-APL(100)-019080-03-1 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Released to Fabrication | P017 |  |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.635 | 29.6 | sq ft | 26.6 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  |  |  | 50% |  |  |  | 50%
C34-S245153 | 26003H | 1058J | LP1Y-APL(100)-019079-05-3 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 1.8494 | 2.91 | sq ft | 0.91 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245152 | 26003H | 1057J | LP1Y-APL(100)-019079-05-2 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 2.6519 | 5.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143232
C34-S245151 | 26003H | 1056J | LP1Y-APL(100)-019079-05-1 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.068 | 9.87 | sq ft | 5.37 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245150 | 26003H | 1055J | LP1Y-APL(100)-019079-03-3 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 28.82 | 12.25 | sq ft | 9.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142863
C34-S245149 | 26003H | 1054J | LP1Y-APL(100)-019079-03-2 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.0963 | 18.04 | sq ft | 15.04 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% |  |  |  | 67%
C34-S245148 | 26003H | 1053J | LP1Y-APL(100)-019079-03-1 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.3063 | 7.33 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S245147 | 26003H | 1052J | LP1Y-APL(100)-019079-02-1 | LP1Y-APL(100)-019079-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 |  |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 10.5 | 0 | 10.5 | 38.1798 | 38.3 | sq ft | 6.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245146 | 26003H | 1051J | LP1Y-APL(100)-019072-21-4 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.326 | 3.74 | sq ft | 1.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245145 | 26003H | 1050J | LP1Y-APL(100)-019072-21-3 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0578 | 6.17 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245144 | 26003H | 1049J | LP1Y-APL(100)-019072-21-2 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 5.5567 | 6.33 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100%
C34-S245143 | 26003H | 1048J | LP1Y-APL(100)-019072-21-1 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.7363 | 3.94 | sq ft | 1.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245142 | 26003H | 1047J | LP1Y-APL(100)-019072-17-5 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 33.66 | 13.42 | sq ft | 11.92 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142986
C34-S245141 | 26003H | 1046J | LP1Y-APL(100)-019072-17-4 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.1988 | 12.48 | sq ft | 10.98 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245140 | 26003H | 1045J | LP1Y-APL(100)-019072-17-3 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.1113 | 2.22 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142828
C34-S245139 | 26003H | 1044J | LP1Y-APL(100)-019072-17-2 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.5963 | 7.24 | sq ft | 5.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-10 | 142623
C34-S245138 | 26003H | 1043J | LP1Y-APL(100)-019072-17-1 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.6575 | 6.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% |  |  |  | 0%
C34-S245137 | 26003H | 1042J | LP1Y-APL(100)-019072-15-3 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 17.6257 | 15.19 | sq ft | 3.69 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245136 | 26003H | 1041J | LP1Y-APL(100)-019072-15-2 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 18.5108 | 20.29 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245135 | 26003H | 1040J | LP1Y-APL(100)-019072-15-1 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 |  |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 1.5 | 0 | 1.5 | 3.8735 | 4.86 | sq ft | 1.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245134 | 26003H | 1039J | LP1Y-APL(100)-019071-02-2 | LP1Y-APL(100)-019071-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS APL(100) (315) 019071 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019071 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 53.6845 | 30.11 | sq ft | 11.61 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245133 | 26003H | 1038J | LP1Y-APL(100)-019071-02-1 | LP1Y-APL(100)-019071-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 2" SS APL(100) (315) 019071 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019071 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.765 | 20.56 | sq ft | 17.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142896
C34-S245132 | 26003H | 1037J | LP1Y-APL(100)-019047-04-3 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.7605 | 4.24 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143225
C34-S245131 | 26003H | 1036J | LP1Y-APL(100)-019047-04-2 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.3176 | 6.47 | sq ft | 1.47 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143226
C34-S245130 | 26003H | 1035J | LP1Y-APL(100)-019047-04-1 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.0074 | 8.78 | sq ft | 4.28 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245129 | 26003H | 1034J | LP1Y-APL(100)-019047-02-1 | LP1Y-APL(100)-019047-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 0 | 9 | 38.3247 | 37.7 | sq ft | 4.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245128 | 26003H | 1033J | LP1Y-APL(100)-019047-01-3 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 |  |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 17.05 | 8.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 142723
C34-S245127 | 26003H | 1032J | LP1Y-APL(100)-019047-01-2 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.6963 | 12.2 | sq ft | 9.2 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | [6 empty] | 67% |  |  |  | 0%
C34-S245126 | 26003H | 1031J | LP1Y-APL(100)-019047-01-1 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 |  |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.58 | 13.87 | sq ft | 9.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Aristeo Banda | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 80%
C34-S245125 | 26003H | 1030J | LP1Y-APL(100)-019045-03-5 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 1.78 | 1.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100%
C34-S245124 | 26003H | 1029J | LP1Y-APL(100)-019045-03-4 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 17.9214 | 15.54 | sq ft | 4.04 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245123 | 26003H | 1028J | LP1Y-APL(100)-019045-03-3 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.2913 | 6.69 | sq ft | 1.19 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245122 | 26003H | 1027J | LP1Y-APL(100)-019045-03-2 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 4.9398 | 6.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245121 | 26003H | 1026J | LP1Y-APL(100)-019045-03-1 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.2805 | 8.74 | sq ft | 5.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | [6 empty] | 75% |  |  |  | 0%
C34-S245120 | 26003H | 1025J | LP1Y-APL(100)-019045-01-2 | LP1Y-APL(100)-019045-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10.75 | 4 | 6.75 | 41.7472 | 32.43 | sq ft | 7.43 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245119 | 26003H | 1024J | LP1Y-APL(100)-019045-01-1 | LP1Y-APL(100)-019045-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 2" SS APL(100) (315) 019045 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 42.02 | 17.25 | sq ft | 14.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142826
C34-S245118 | 26003H | 1023J | LP1Y-APL(100)-019044-03-3 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 3.9699 | 6.65 | sq ft | 0.65 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245117 | 26003H | 1022J | LP1Y-APL(100)-019044-03-2 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 4.5994 | 5.91 | sq ft | 1.91 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143224
C34-S245116 | 26003H | 1021J | LP1Y-APL(100)-019044-03-1 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.1327 | 8.57 | sq ft | 5.07 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245115 | 26003H | 1020J | LP1Y-APL(100)-019044-01-5 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 |  |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 3.056 | 2.74 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143223
C34-S245114 | 26003H | 1019J | LP1Y-APL(100)-019044-01-4 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 18.0781 | 15.72 | sq ft | 4.22 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245113 | 26003H | 1018J | LP1Y-APL(100)-019044-01-3 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 18.3636 | 16.71 | sq ft | 2.21 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245112 | 26003H | 1017J | LP1Y-APL(100)-019044-01-2 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 |  |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 20.745 | 13.94 | sq ft | 3.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245111 | 26003H | 1016J | LP1Y-APL(100)-019044-01-1 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 |  |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 39.3838 | 16.92 | sq ft | 13.92 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  |  |  | 67% |  |  |  | 33%
C34-S245110 | 26003H | 1015J | LP1Y-AI(100)-191008-01-2 | LP1Y-AI(100)-191008-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  |  | LP1Y 2" SS AI(100) (315) 191008 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-191008 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.3725 | 11.53 | sq ft | 6.03 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245109 | 26003H | 1014J | LP1Y-AI(100)-191008-01-1 | LP1Y-AI(100)-191008-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 |  |  | LP1Y 2" SS AI(100) (315) 191008 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-191008 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.2313 | 10.22 | sq ft | 8.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 142878, 142905
C34-S245108 | 26003H | 1013J | LP1Y-AI(100)-034061-02-2 | LP1Y-AI(100)-034061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 |  |  | LP1Y 2" SS AI(100) (315) 034061 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034061 |  | TFS00D001YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 33.8461 | 19.48 | sq ft | 4.48 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245107 | 26003H | 1012J | LP1Y-AI(100)-034061-02-1 | LP1Y-AI(100)-034061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 |  |  | LP1Y 2" SS AI(100) (315) 034061 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034061 |  | TFS00D001YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 27.8025 | 11.86 | sq ft | 8.86 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% |  |  |  | 67%
C34-S245106 | 26003H | 1011J | LP1Y-AI(100)-019056-02-1 | LP1Y-AI(100)-019056-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 |  |  | LP1Y 2" SS AI(100) (315) 019056 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019056 |  | TFS00D007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 55.7763 | 28.87 | sq ft | 10.87 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245105 | 26003H | 1010J | LP1Y-AI(100)-019034-02-1 | LP1Y-AI(100)-019034-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  |  | LP1Y 2" SS AI(100) (315) 019034 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019034 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 22 | 22 | 0 | 142.7486 | 59.56 | sq ft | 22.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245104 | 26003H | 1009J | LP1Y-AI(100)-019015-03-1 | LP1Y-AI(100)-019015-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 |  |  | LP1Y 2" SS AI(100) (315) 019015 | AI(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019015 |  | TFS00D005YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 78.4057 | 41.15 | sq ft | 17.65 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245103 | 26003H | 1008J | LP1Y-ACN-108212-02-2 | LP1Y-ACN-108212-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 159.5688 | 35.85 | sq ft | 26.88 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | [6 empty] | 67% |  |  |  | 0%
C34-S245102 | 26003H | 1007J | LP1Y-ACN-108212-02-1 | LP1Y-ACN-108212-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 48.8603 | 12.44 | sq ft | 3.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142904
C34-S245101 | 26003H | 1006J | LP1Y-ACN-108212-01-2 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.4545 | 13.04 | sq ft | 1.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142790
C34-S246942 | 26003H | 1005J-L1 | LP1Y-ACN-108212-01-1-L1 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142537
C34-S245100 | 26003H | 1005J | LP1Y-ACN-108212-01-1 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.7209 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-25 | Jacob Perez | 2026-02-25 | Jacob Perez | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142748
C34-S245099 | 26003H | 1004J | LP1Y-ACN-108112-02-2 | LP1Y-ACN-108112-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 48.8603 | 12.44 | sq ft | 3.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142907
C34-S245098 | 26003H | 1003J | LP1Y-ACN-108112-02-1 | LP1Y-ACN-108112-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 159.598 | 35.86 | sq ft | 26.88 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 |  |  | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-14 | 2026-03-14 | 2026-03-14 |  |  |  | 67% |  |  |  | 33%
C34-S245097 | 26003H | 1002J | LP1Y-ACN-108112-01-2 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.4545 | 13.04 | sq ft | 1.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142898
C34-S246941 | 26003H | 1001J-L1 | LP1Y-ACN-108112-01-1-L1 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142536
C34-S245096 | 26003H | 1001J | LP1Y-ACN-108112-01-1 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.7209 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142750