## Detailed Spool Report
Barcode | Contract | Spool | Piece Mark | Isometric | Rev # | Rev Test | Transmittal | On Hold | Off Hold | Hold Status | Hold Source | Hold Justification | Status | Priority | Estimated Ship Date | Job | Line | Fluid | Test Pack | Insulation | Operation Temperature | Operation Pressure | Hydrotest Pressure | Paint Color | Type | PWHT | Location | Unit | Area | Zone | System | Module | Skid | Class | Paint System | Spool Size | MTL | dia-inch | dia-inch R | dia-inch P | Weight | Paint Area | Area Units | Pipe Length | Length Units | RCVD Date | AD | AL | BD | BL | CD | CL | DD | DL | ED | EL | FD | FL | Project RLS Date | I-Test Date | I-Test Status | Contains Partials | RLS to Fab date | MTL Pull Start Date | MTL Pull Complete Date | Pipe Cut Start Date | Pipe Cut Complete Date | Support Start Date | Support Complete Date | Assigned Fabricator | Fabricator Assignment Date | Fit R Start Date | Fit P Start Date | Fit Start Date | Weld R Start Date | Weld P Start Date | Weld Start Date | FIT R Complete | FIT P Complete | FIT Complete | FIT % All | WLD R Complete | WLD P Complete | WLD Complete | WLD % All | VI Report Date | VI Report Numbers | Loader Release Date | RLS to Coater | RLS to NDE | RLS to PWHT | RLS to Pressure Test | RLS to MISC | Release Comment | PWHT Report Date | PWHT Report Numbers | Hydrotest Report Date | Hydrotest Report Numbers | X-RAY Report Date | X-RAY Report Numbers | MP Report Date | MP Report Numbers | LP Report Date | LP Report Numbers | PMI Report Date | PMI Report Numbers | Ferrite Report Date | Ferrite Report Numbers | Hardness Report Date | Hardness Report Numbers | Coatings Report Date | Coatings Report Numbers | PWHT P-L # | Shipment to PWHT | PWHT Custodian | Coater P-L # | Shipment to Coater | Coater Custodian | Blasted | First Coat | Second Coat | Third Coat | Misc P-L # | Shipment to Misc | Misc Custodian | Customer rlse date | Customer rlse | QC release | Rlse Doc. for review | Download Date | Final P-L # | Final Shipment | Final Custodian | Return from Client P-L # | Return from Client | Return from Coater P-L # | Return from Coater | Return from PWHT P-L # | Return from PWHT | Return from Misc P-L # | Return from Misc | RCVD on Site | Loaded | Installed | Welded | Supported | NDE Tested | Accepted | Painted | Spool Note | Documentation Package | Documentation Date
C34-S245097 | 26003H | 1002J | LP1Y-ACN-108112-01-2 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.4545 | 13.04 | sq ft | 1.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142898
C34-S245096 | 26003H | 1001J | LP1Y-ACN-108112-01-1 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.7209 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142750
C34-S246941 | 26003H | 1001J-L1 | LP1Y-ACN-108112-01-1-L1 | LP1Y-ACN-108112-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142536
C34-S245098 | 26003H | 1003J | LP1Y-ACN-108112-02-1 | LP1Y-ACN-108112-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 159.598 | 35.86 | sq ft | 26.88 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 |  |  | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-14 | 2026-03-14 | 2026-03-14 |  |  |  | 67% |  |  |  | 33%
C34-S245099 | 26003H | 1004J | LP1Y-ACN-108112-02-2 | LP1Y-ACN-108112-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108112 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108112 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 48.8603 | 12.44 | sq ft | 3.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142907
C34-S246942 | 26003H | 1005J-L1 | LP1Y-ACN-108212-01-1-L1 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142537
C34-S245100 | 26003H | 1005J | LP1Y-ACN-108212-01-1 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.7209 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-25 | Jacob Perez | 2026-02-25 | Jacob Perez | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142748
C34-S245101 | 26003H | 1006J | LP1Y-ACN-108212-01-2 | LP1Y-ACN-108212-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.4545 | 13.04 | sq ft | 1.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142790
C34-S245103 | 26003H | 1008J | LP1Y-ACN-108212-02-2 | LP1Y-ACN-108212-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 159.5688 | 35.85 | sq ft | 26.88 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 67%
C34-S245102 | 26003H | 1007J | LP1Y-ACN-108212-02-1 | LP1Y-ACN-108212-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS ACN (315) P (108) 108212 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108212 |  | TFS00E006YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 48.8603 | 12.44 | sq ft | 3.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142904
C34-S245104 | 26003H | 1009J | LP1Y-AI(100)-019015-03-1 | LP1Y-AI(100)-019015-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 019015 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019015 |  | TFS00D005YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245105 | 26003H | 1010J | LP1Y-AI(100)-019034-02-1 | LP1Y-AI(100)-019034-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 019034 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019034 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 22 | 22 | 0 | 142.7486 | 59.56 | sq ft | 22.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245106 | 26003H | 1011J | LP1Y-AI(100)-019056-02-1 | LP1Y-AI(100)-019056-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS AI(100) (315) 019056 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019056 |  | TFS00D007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 55.7763 | 28.87 | sq ft | 10.87 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245108 | 26003H | 1013J | LP1Y-AI(100)-034061-02-2 | LP1Y-AI(100)-034061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 034061 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034061 |  | TFS00D001YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 33.8461 | 19.48 | sq ft | 4.48 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245107 | 26003H | 1012J | LP1Y-AI(100)-034061-02-1 | LP1Y-AI(100)-034061-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 034061 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034061 |  | TFS00D001YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 27.8025 | 11.86 | sq ft | 8.86 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144986
C34-S245110 | 26003H | 1015J | LP1Y-AI(100)-191008-01-2 | LP1Y-AI(100)-191008-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 191008 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-191008 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.3725 | 11.53 | sq ft | 6.03 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144658
C34-S245109 | 26003H | 1014J | LP1Y-AI(100)-191008-01-1 | LP1Y-AI(100)-191008-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS AI(100) (315) 191008 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-191008 |  | TFS00E007YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.2313 | 10.22 | sq ft | 8.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 142878, 142905
C34-S245111 | 26003H | 1016J | LP1Y-APL(100)-019044-01-1 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 39.3838 | 16.92 | sq ft | 13.92 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-10 | 2026-03-10 | 2026-03-10 |  |  |  | 67% |  |  |  | 33%
C34-S245113 | 26003H | 1018J | LP1Y-APL(100)-019044-01-3 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.6136 | 6.71 | sq ft | 2.21 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245115 | 26003H | 1020J | LP1Y-APL(100)-019044-01-5 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 3.056 | 2.74 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143223 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245112 | 26003H | 1017J | LP1Y-APL(100)-019044-01-2 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 20.745 | 13.94 | sq ft | 3.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-27 | 145611
C34-S245114 | 26003H | 1019J | LP1Y-APL(100)-019044-01-4 | LP1Y-APL(100)-019044-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 4.3281 | 5.72 | sq ft | 4.22 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Roberto Tobias (WF) | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 |  |  |  | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% |  |  |  | 0%
C34-S245118 | 26003H | 1023J | LP1Y-APL(100)-019044-03-3 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 3.9699 | 6.65 | sq ft | 0.65 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144446 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245117 | 26003H | 1022J | LP1Y-APL(100)-019044-03-2 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 4.5994 | 5.91 | sq ft | 1.91 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143224 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245116 | 26003H | 1021J | LP1Y-APL(100)-019044-03-1 | LP1Y-APL(100)-019044-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019044 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.1327 | 8.57 | sq ft | 5.07 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146037
C34-S245119 | 26003H | 1024J | LP1Y-APL(100)-019045-01-1 | LP1Y-APL(100)-019045-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 42.02 | 17.25 | sq ft | 14.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142826 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245120 | 26003H | 1025J | LP1Y-APL(100)-019045-01-2 | LP1Y-APL(100)-019045-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 4 | 6 | 27.9972 | 22.43 | sq ft | 7.43 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 |  |  | 90% |  |  |  | 0%
C34-S245124 | 26003H | 1029J | LP1Y-APL(100)-019045-03-4 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 4.1714 | 5.54 | sq ft | 4.04 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Roberto Tobias (WF) | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-25 | 145569 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245121 | 26003H | 1026J | LP1Y-APL(100)-019045-03-1 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.2805 | 8.74 | sq ft | 5.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 75%
C34-S245122 | 26003H | 1027J | LP1Y-APL(100)-019045-03-2 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 4.9398 | 6.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245125 | 26003H | 1030J | LP1Y-APL(100)-019045-03-5 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 1.78 | 1.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143241 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245123 | 26003H | 1028J | LP1Y-APL(100)-019045-03-3 | LP1Y-APL(100)-019045-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 0.75" SS APL(100) (315) 019045 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019045 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.2913 | 6.69 | sq ft | 1.19 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144461 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245126 | 26003H | 1031J | LP1Y-APL(100)-019047-01-1 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.58 | 13.87 | sq ft | 9.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Aristeo Banda | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143681
C34-S245127 | 26003H | 1032J | LP1Y-APL(100)-019047-01-2 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.6963 | 12.2 | sq ft | 9.2 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144128
C34-S245128 | 26003H | 1033J | LP1Y-APL(100)-019047-01-3 | LP1Y-APL(100)-019047-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 17.05 | 8.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 142723
C34-S245129 | 26003H | 1034J | LP1Y-APL(100)-019047-02-1 | LP1Y-APL(100)-019047-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 0 | 9 | 38.3247 | 37.7 | sq ft | 4.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245130 | 26003H | 1035J | LP1Y-APL(100)-019047-04-1 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 | 2026-08-24 |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.0074 | 8.78 | sq ft | 4.28 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245132 | 26003H | 1037J | LP1Y-APL(100)-019047-04-3 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.7605 | 4.24 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143225
C34-S245131 | 26003H | 1036J | LP1Y-APL(100)-019047-04-2 | LP1Y-APL(100)-019047-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 0.75" SS APL(100) (315) 019047 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019047 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.3176 | 6.47 | sq ft | 1.47 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143226
C34-S245133 | 26003H | 1038J | LP1Y-APL(100)-019071-02-1 | LP1Y-APL(100)-019071-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019071 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019071 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.765 | 20.56 | sq ft | 17.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142896
C34-S245134 | 26003H | 1039J | LP1Y-APL(100)-019071-02-2 | LP1Y-APL(100)-019071-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS APL(100) (315) 019071 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019071 |  | TFS00D007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 53.6845 | 30.11 | sq ft | 11.61 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245137 | 26003H | 1042J | LP1Y-APL(100)-019072-15-3 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 3.8757 | 5.19 | sq ft | 3.69 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143901 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245135 | 26003H | 1040J | LP1Y-APL(100)-019072-15-1 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 1.5 | 0 | 1.5 | 3.8735 | 4.86 | sq ft | 1.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 143478 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245136 | 26003H | 1041J | LP1Y-APL(100)-019072-15-2 | LP1Y-APL(100)-019072-15 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.7608 | 10.29 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Guillen | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144706 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245139 | 26003H | 1044J | LP1Y-APL(100)-019072-17-2 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.5963 | 7.24 | sq ft | 5.74 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-10 | 142623 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245142 | 26003H | 1047J | LP1Y-APL(100)-019072-17-5 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 33.66 | 13.42 | sq ft | 11.92 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142986 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245138 | 26003H | 1043J | LP1Y-APL(100)-019072-17-1 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.6575 | 6.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143610 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245141 | 26003H | 1046J | LP1Y-APL(100)-019072-17-4 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.1988 | 12.48 | sq ft | 10.98 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143665 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245140 | 26003H | 1045J | LP1Y-APL(100)-019072-17-3 | LP1Y-APL(100)-019072-17 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.1113 | 2.22 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142828 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245143 | 26003H | 1048J | LP1Y-APL(100)-019072-21-1 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.7363 | 3.94 | sq ft | 1.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143593 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245144 | 26003H | 1049J | LP1Y-APL(100)-019072-21-2 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 5.5567 | 6.33 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143324 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245145 | 26003H | 1050J | LP1Y-APL(100)-019072-21-3 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0578 | 6.17 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 143475 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245146 | 26003H | 1051J | LP1Y-APL(100)-019072-21-4 | LP1Y-APL(100)-019072-21 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 019072 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019072 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.326 | 3.74 | sq ft | 1.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143591 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245147 | 26003H | 1052J | LP1Y-APL(100)-019079-02-1 | LP1Y-APL(100)-019079-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 10.5 | 0 | 10.5 | 38.1798 | 38.3 | sq ft | 6.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245148 | 26003H | 1053J | LP1Y-APL(100)-019079-03-1 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.3063 | 7.33 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144073, 144078
C34-S245150 | 26003H | 1055J | LP1Y-APL(100)-019079-03-3 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 28.82 | 12.25 | sq ft | 9.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142863
C34-S245149 | 26003H | 1054J | LP1Y-APL(100)-019079-03-2 | LP1Y-APL(100)-019079-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.0963 | 18.04 | sq ft | 15.04 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% |  |  |  | 67%
C34-S245153 | 26003H | 1058J | LP1Y-APL(100)-019079-05-3 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 1.8494 | 2.91 | sq ft | 0.91 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143592
C34-S245151 | 26003H | 1056J | LP1Y-APL(100)-019079-05-1 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.068 | 9.87 | sq ft | 5.37 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245152 | 26003H | 1057J | LP1Y-APL(100)-019079-05-2 | LP1Y-APL(100)-019079-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 019079 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019079 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 2.6519 | 5.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143232
C34-S245157 | 26003H | 1062J | LP1Y-APL(100)-019080-03-4 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 15.25 | 7 | 8.25 | 45.3043 | 46.57 | sq ft | 10.07 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245156 | 26003H | 1061J | LP1Y-APL(100)-019080-03-3 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 118.0438 | 39.38 | sq ft | 26.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245154 | 26003H | 1059J | LP1Y-APL(100)-019080-03-1 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.635 | 29.6 | sq ft | 26.6 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145724
C34-S245155 | 26003H | 1060J | LP1Y-APL(100)-019080-03-2 | LP1Y-APL(100)-019080-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 57.9 | 25.58 | sq ft | 19.58 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-23 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 80%
C34-S245159 | 26003H | 1064J | LP1Y-APL(100)-019080-04-2 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0085 | 6.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144465
C34-S245158 | 26003H | 1063J | LP1Y-APL(100)-019080-04-1 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.6434 | 9.52 | sq ft | 5.02 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143231
C34-S245160 | 26003H | 1065J | LP1Y-APL(100)-019080-04-3 | LP1Y-APL(100)-019080-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019080 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019080 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.3664 | 3.79 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144466
C34-S245163 | 26003H | 1068J | LP1Y-APL(100)-019089-02-3 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.3688 | 15.11 | sq ft | 12.11 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143594 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245161 | 26003H | 1066J | LP1Y-APL(100)-019089-02-1 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245164 | 26003H | 1069J | LP1Y-APL(100)-019089-02-4 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 32.0438 | 15.38 | sq ft | 8.88 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143745 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245162 | 26003H | 1067J | LP1Y-APL(100)-019089-02-2 | LP1Y-APL(100)-019089-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 41.6625 | 17.11 | sq ft | 14.11 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-27 | 143680 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245166 | 26003H | 1071J | LP1Y-APL(100)-019089-05-2 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4794 | 6.91 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144442 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245165 | 26003H | 1070J | LP1Y-APL(100)-019089-05-1 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245167 | 26003H | 1072J | LP1Y-APL(100)-019089-05-3 | LP1Y-APL(100)-019089-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143240 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245168 | 26003H | 1073J | LP1Y-APL(100)-019089-06-1 | LP1Y-APL(100)-019089-06 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 9.5618 | 13.93 | sq ft | 7.43 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 88% |  |  |  | 88%
C34-S245169 | 26003H | 1074J | LP1Y-APL(100)-019089-07-1 | LP1Y-APL(100)-019089-07 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 019089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019089 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245172 | 26003H | 1077J | LP1Y-APL(100)-034060-02-3 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 33.752 | 19.81 | sq ft | 4.31 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245171 | 26003H | 1076J | LP1Y-APL(100)-034060-02-2 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 29.0125 | 11.66 | sq ft | 10.16 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143005
C34-S245170 | 26003H | 1075J | LP1Y-APL(100)-034060-02-1 | LP1Y-APL(100)-034060-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034060 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034060 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 44.7425 | 17.61 | sq ft | 16.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-16 | 142888
C34-S245173 | 26003H | 1078J | LP1Y-APL(100)-034162-02-1 | LP1Y-APL(100)-034162-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 46.9838 | 19.13 | sq ft | 16.13 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143831
C34-S245174 | 26003H | 1079J | LP1Y-APL(100)-034162-02-2 | LP1Y-APL(100)-034162-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 13.8875 | 6.59 | sq ft | 3.59 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-10 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145205
C34-S245175 | 26003H | 1080J | LP1Y-APL(100)-034162-03-1 | LP1Y-APL(100)-034162-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8.25 | 0 | 8.25 | 9.9333 | 16.67 | sq ft | 3.67 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245178 | 26003H | 1083J | LP1Y-APL(100)-034162-04-3 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 16.5507 | 13.94 | sq ft | 2.44 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245176 | 26003H | 1081J | LP1Y-APL(100)-034162-04-1 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 6.9671 | 8.73 | sq ft | 4.23 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245177 | 26003H | 1082J | LP1Y-APL(100)-034162-04-2 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.5819 | 6.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245179 | 26003H | 1083JA | LP1Y-APL(100)-034162-04-4 | LP1Y-APL(100)-034162-04 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 034162 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034162 |  | TFS00D001YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143239
C34-S245180 | 26003H | 1084J | LP1Y-APL(100)-198001-02-1 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 3 | 3 | 0 | 17.6342 | 15.11 | sq ft | 12.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Omar Puente | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143741 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245182 | 26003H | 1086J | LP1Y-APL(100)-198001-02-3 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 4 | 4 | 0 | 24.5492 | 21.44 | sq ft | 16.94 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143829 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245181 | 26003H | 1085J | LP1Y-APL(100)-198001-02-2 | LP1Y-APL(100)-198001-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 3 | 3 | 0 | 12.5339 | 11.62 | sq ft | 8.62 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-10 | Passed | No | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | Omar Puente | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143830 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245183 | 26003H | 1087J | LP1Y-APL(100)-198001-03-1 | LP1Y-APL(100)-198001-03 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 1" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 10.25 | 5 | 5.25 | 17.6248 | 23.57 | sq ft | 10.57 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-07 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-21 | 2026-04-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145684
C34-S245185 | 26003H | 1089J | LP1Y-APL(100)-198001-04-2 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 5.4716 | 6.23 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143590 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245187 | 26003H | 1091J | LP1Y-APL(100)-198001-04-4 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.344 | 3.76 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143589 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245186 | 26003H | 1090J | LP1Y-APL(100)-198001-04-3 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.0354 | 6.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143525 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245184 | 26003H | 1088J | LP1Y-APL(100)-198001-04-1 | LP1Y-APL(100)-198001-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 0.75" SS APL(100) (315) 198001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198001 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.6019 | 3.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 143477 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245188 | 26003H | 1092J | LP1Y-APL(100)-198008-02-1 | LP1Y-APL(100)-198008-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 43.8213 | 17.93 | sq ft | 14.93 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142900 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245189 | 26003H | 1093J | LP1Y-APL(100)-198008-02-2 | LP1Y-APL(100)-198008-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.2463 | 15.08 | sq ft | 8.58 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 142954 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245190 | 26003H | 1094J | LP1Y-APL(100)-198008-03-1 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245191 | 26003H | 1095J | LP1Y-APL(100)-198008-03-2 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4928 | 6.92 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145288 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245192 | 26003H | 1096J | LP1Y-APL(100)-198008-03-3 | LP1Y-APL(100)-198008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143230 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245193 | 26003H | 1097J | LP1Y-APL(100)-198008-04-1 | LP1Y-APL(100)-198008-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 11.1698 | 15.8 | sq ft | 9.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | [6 empty] | 88% |  |  |  | 0%
C34-S245194 | 26003H | 1098J | LP1Y-APL(100)-198008-05-1 | LP1Y-APL(100)-198008-05 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198008 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198008 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245196 | 26003H | 1100J | LP1Y-APL(100)-198013-02-2 | LP1Y-APL(100)-198013-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS APL(100) (315) 198013 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 7 | 4 | 3 | 24.7178 | 16.68 | sq ft | 10.18 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-03-24 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-02 |  |  | 67%
C34-S245195 | 26003H | 1099J | LP1Y-APL(100)-198013-02-1 | LP1Y-APL(100)-198013-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 | 2026-06-01 |  | LP1Y 2" SS APL(100) (315) 198013 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 45.705 | 17.98 | sq ft | 16.48 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145725
C34-S245197 | 26003H | 1101J | LP1Y-APL(100)-198013-03-1 | LP1Y-APL(100)-198013-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245198 | 26003H | 1102J | LP1Y-APL(100)-198013-04-1 | LP1Y-APL(100)-198013-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.789 | 5.51 | sq ft | 2.51 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144445 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245199 | 26003H | 1103J | LP1Y-APL(100)-198013-04-2 | LP1Y-APL(100)-198013-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 0.75" SS APL(100) (315) 198013 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198013 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 7.4241 | 9.61 | sq ft | 3.11 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245200 | 26003H | 1104J | LP1Y-APL(100)-198042-01-1 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 25.9463 | 10.49 | sq ft | 8.99 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144656 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245201 | 26003H | 1105J | LP1Y-APL(100)-198042-01-2 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 56.815 | 22.85 | sq ft | 19.85 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142789 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245202 | 26003H | 1106J | LP1Y-APL(100)-198042-01-3 | LP1Y-APL(100)-198042-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.0325 | 13.57 | sq ft | 8.57 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 60% |  |  |  | 40%
C34-S245203 | 26003H | 1107J | LP1Y-APL(100)-198042-03-1 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245204 | 26003H | 1108J | LP1Y-APL(100)-198042-03-2 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 4.49 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144516 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245205 | 26003H | 1108JA | LP1Y-APL(100)-198042-03-3 | LP1Y-APL(100)-198042-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143228, 143229 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245206 | 26003H | 1109J | LP1Y-APL(100)-198042-04-1 | LP1Y-APL(100)-198042-04 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 11.2056 | 15.84 | sq ft | 9.34 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144830 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245207 | 26003H | 1110J | LP1Y-APL(100)-198042-05-1 | LP1Y-APL(100)-198042-05 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198042 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198042 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245210 | 26003H | 1113J | LP1Y-APL(100)-198044-01-3 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.7275 | 15.26 | sq ft | 8.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144227 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245209 | 26003H | 1112J | LP1Y-APL(100)-198044-01-2 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 39.1875 | 15.51 | sq ft | 14.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142877 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245208 | 26003H | 1111J | LP1Y-APL(100)-198044-01-1 | LP1Y-APL(100)-198044-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245212 | 26003H | 1115J | LP1Y-APL(100)-198044-02-2 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4435 | 6.86 | sq ft | 1.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% |  |  |  | 0%
C34-S245213 | 26003H | 1115JA | LP1Y-APL(100)-198044-02-3 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143227 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245211 | 26003H | 1114J | LP1Y-APL(100)-198044-02-1 | LP1Y-APL(100)-198044-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-02-25 | Jacob Perez | 2026-02-25 | George Allahverdian | 2026-02-26 | Jacob Perez | 2026-02-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245214 | 26003H | 1116J | LP1Y-APL(100)-198044-03-1 | LP1Y-APL(100)-198044-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 9.2079 | 13.52 | sq ft | 7.02 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144770 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245215 | 26003H | 1117J | LP1Y-APL(100)-198044-04-1 | LP1Y-APL(100)-198044-04 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198044 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198044 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245216 | 26003H | 1118J | LP1Y-APL(100)-198058-01-1 | LP1Y-APL(100)-198058-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 9.75 | 0 | 9.75 | 37.5438 | 37.56 | sq ft | 5.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245218 | 26003H | 1120J | LP1Y-APL(100)-198058-02-2 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.9 | 12.75 | sq ft | 11.25 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143006
C34-S245217 | 26003H | 1119J | LP1Y-APL(100)-198058-02-1 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 24.2088 | 10.61 | sq ft | 5.61 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143595
C34-S245219 | 26003H | 1121J | LP1Y-APL(100)-198058-02-3 | LP1Y-APL(100)-198058-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 19.6075 | 8.76 | sq ft | 5.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% |  |  |  | 75%
C34-S245222 | 26003H | 1124J | LP1Y-APL(100)-198058-04-3 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 2.6967 | 5.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143325
C34-S245223 | 26003H | 1125J | LP1Y-APL(100)-198058-04-4 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 2.1002 | 3.2 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245220 | 26003H | 1122J | LP1Y-APL(100)-198058-04-1 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 6.5761 | 9.09 | sq ft | 5.59 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 75% |  |  |  | 75%
C34-S245221 | 26003H | 1123J | LP1Y-APL(100)-198058-04-2 | LP1Y-APL(100)-198058-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.75" SS APL(100) (315) 198058 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198058 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 3.1864 | 5.29 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Roberto Tobias (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144467
C34-S245225 | 26003H | 1127J | LP1Y-APL(100)-198064-01-2 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 5.75 | 2 | 3.75 | 26.5536 | 17.28 | sq ft | 7.78 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245224 | 26003H | 1126J | LP1Y-APL(100)-198064-01-1 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.0988 | 13.4 | sq ft | 8.9 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142811
C34-S245226 | 26003H | 1128J | LP1Y-APL(100)-198064-01-3 | LP1Y-APL(100)-198064-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 34.281 | 30.49 | sq ft | 5.99 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245227 | 26003H | 1129J | LP1Y-APL(100)-198064-03-1 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 9.0678 | 11.17 | sq ft | 6.67 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 83% |  |  |  | 50%
C34-S245228 | 26003H | 1130J | LP1Y-APL(100)-198064-03-2 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 6.097 | 7.38 | sq ft | 2.38 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144443
C34-S245229 | 26003H | 1131J | LP1Y-APL(100)-198064-03-3 | LP1Y-APL(100)-198064-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 0.75" SS APL(100) (315) 198064 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198064 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.2499 | 3.65 | sq ft | 1.15 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143243
C34-S245230 | 26003H | 1132J | LP1Y-APL(100)-198065-01-1 | LP1Y-APL(100)-198065-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198065 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198065 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 18 | 18 | 0 | 48.3013 | 23.56 | sq ft | 13.56 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143032
C34-S245231 | 26003H | 1133J | LP1Y-APL(100)-198086-01-1 | LP1Y-APL(100)-198086-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 198086 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198086 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 19.2263 | 8.54 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 142592
C34-S245232 | 26003H | 1134J | LP1Y-APL(100)-198087-01-1 | LP1Y-APL(100)-198087-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS APL(100) (315) 198087 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198087 |  | TFS00E006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.7925 | 11.78 | sq ft | 7.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 |  |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% |  |  |  | 0%
C34-S245233 | 26003H | 1135J | LP1Y-APL(100)-198088-02-1 | LP1Y-APL(100)-198088-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198088 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198088 |  | TFS00E007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 42.56 | 18.04 | sq ft | 12.54 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142985
C34-S245234 | 26003H | 1136J | LP1Y-APL(100)-198101-01-1 | LP1Y-APL(100)-198101-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 198101 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198101 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 59.5138 | 25.13 | sq ft | 18.13 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-28 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143754 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245235 | 26003H | 1137J | LP1Y-APL(100)-198102-01-1 | LP1Y-APL(100)-198102-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 198102 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198102 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 51.24 | 22.67 | sq ft | 15.67 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143618 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245236 | 26003H | 1138J | LP1Y-APL(100)-198103-02-1 | LP1Y-APL(100)-198103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 198103 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198103 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 42.9388 | 20.86 | sq ft | 12.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143085 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245237 | 26003H | 1139J | LP1Y-APL(100)-198104-02-1 | LP1Y-APL(100)-198104-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS APL(100) (315) 198104 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198104 |  | TFS00D003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 32.3925 | 16.86 | sq ft | 8.36 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 143679 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245238 | 26003H | 1140J | LP1Y-APL(100)-198105-02-1 | LP1Y-APL(100)-198105-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198105 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198105 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 143088 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245239 | 26003H | 1141J | LP1Y-APL(100)-198106-02-1 | LP1Y-APL(100)-198106-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198106 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198106 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 143087 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245240 | 26003H | 1142J | LP1Y-APL(100)-198107-02-1 | LP1Y-APL(100)-198107-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198107 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198107 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.8938 | 20.46 | sq ft | 11.96 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142827 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245241 | 26003H | 1143J | LP1Y-APL(100)-198108-02-1 | LP1Y-APL(100)-198108-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS APL(100) (315) 198108 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198108 |  | TFS00D005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 42.7738 | 20.8 | sq ft | 12.3 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Aristeo Banda | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143678 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245242 | 26003H | 1144J | LP1Y-APL(100)-198109-02-1 | LP1Y-APL(100)-198109-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS APL(100) (315) 198109 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198109 |  | TFS00D006YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 25.4075 | 13.55 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142808 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245243 | 26003H | 1145J | LP1Y-APL(100)-198113-01-1 | LP1Y-APL(100)-198113-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS APL(100) (315) 198113 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198113 |  | TFS00D002YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 57.4788 | 25.03 | sq ft | 16.53 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143613 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245244 | 26003H | 1146J | LP1Y-AW-165202-01-1 | LP1Y-AW-165202-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS AW (315) 165202 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165202 |  | TFS00D003YSPP |  | 315-AW | NONE | 2" | 316 SS | 10.5 | 8.5 | 2 | 22.3883 | 15.76 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-21 | 2026-04-21 |  | 2026-04-21 |  |  |  | 2026-04-21 |  |  | 83% |  |  |  | 0%
C34-S245245 | 26003H | 1147J | LP1Y-AW-165212-01-1 | LP1Y-AW-165212-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS AW (315) 165212 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165212 |  | TFS00D003YSPP |  | 315-AW | NONE | 2" | 316 SS | 12.5 | 10.5 | 2 | 24.256 | 15.51 | sq ft | 6.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  |  | 2026-04-21 |  | 86% |  |  |  | 0%
C34-S245246 | 26003H | 1148J | LP1Y-AW-165302-01-1 | LP1Y-AW-165302-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS AW (315) 165302 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165302 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245247 | 26003H | 1149J | LP1Y-AW-165312-01-1 | LP1Y-AW-165312-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS AW (315) 165312 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165312 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245248 | 26003H | 1150J | LP1Y-AW-165322-01-1 | LP1Y-AW-165322-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS AW (315) 165322 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165322 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245249 | 26003H | 1151J | LP1Y-AW-165332-01-1 | LP1Y-AW-165332-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS AW (315) 165332 | AW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165332 |  | TFS00D005YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245250 | 26003H | 1152J | LP1Y-AWNP-015001-01-1 | LP1Y-AWNP-015001-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-22 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 90 | 84 | 6 | 354.2728 | 86.89 | sq ft | 21.21 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-22 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-22 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-13 | 2026-04-16 | 2026-04-13 | 2026-04-14 | 2026-04-17 | 2026-04-14 |  | 2026-04-24 |  | 88% |  | 2026-04-25 |  | 80%
C34-S245253 | 26003H | 1155J | LP1Y-AWNP-015001-09-3 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 148.1234 | 29.36 | sq ft | 11.09 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 142767 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245252 | 26003H | 1154J | LP1Y-AWNP-015001-09-2 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 123.2719 | 24.67 | sq ft | 4.76 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143330 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245251 | 26003H | 1153J | LP1Y-AWNP-015001-09-1 | LP1Y-AWNP-015001-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 9 | 8 | 1 | 115.3469 | 26.54 | sq ft | 8.64 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-05-01 | 2026-05-01 |  | 2026-05-01 |  |  |  | 2026-05-01 |  |  | 75% |  |  |  | 0%
C34-S245254 | 26003H | 1156J | LP1Y-AWNP-015001-11-1 | LP1Y-AWNP-015001-11 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 203.5391 | 39.97 | sq ft | 20.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142862 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245255 | 26003H | 1157J | LP1Y-AWNP-015001-11-2 | LP1Y-AWNP-015001-11 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 40.5 | 33.5 | 7 | 152.1308 | 44.84 | sq ft | 8.85 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245258 | 26003H | 1160J | LP1Y-AWNP-015001-12-3 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 96.3844 | 18.89 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142852 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245256 | 26003H | 1158J | LP1Y-AWNP-015001-12-1 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 68.3953 | 13.93 | sq ft | 2.52 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-16 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142812 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245257 | 26003H | 1159J | LP1Y-AWNP-015001-12-2 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 138.6141 | 30.42 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Omar Puente | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143271 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246943 | 26003H | 1158J-L1 | LP1Y-AWNP-015001-12-1-L1 | LP1Y-AWNP-015001-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142527 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245260 | 26003H | 1162J | LP1Y-AWNP-015001-13-2 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 73.7538 | 18.75 | sq ft | 1.71 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143235 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245259 | 26003H | 1161J | LP1Y-AWNP-015001-13-1 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 23 | 22 | 1 | 84.703 | 24.11 | sq ft | 3.55 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-05-01 | 2026-04-30 | 2026-05-01 | 100% | 2026-05-01 | 146014
C34-S245261 | 26003H | 1163J | LP1Y-AWNP-015001-13-4 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 178.7844 | 35.29 | sq ft | 14.39 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144701 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245262 | 26003H | 1164J | LP1Y-AWNP-015001-13-3 | LP1Y-AWNP-015001-13 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 015001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015001 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 48 | 48 | 0 | 210.8078 | 45.65 | sq ft | 14.14 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143522 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245263 | 26003H | 1165J | LP1Y-AWNP-015003-12-1 | LP1Y-AWNP-015003-12 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS AWNP (315) (108) 015003 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015003 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 4 | 2 | 25.9638 | 11.76 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-14 | 2026-04-14 |  | 2026-04-14 |  |  |  | 2026-04-14 |  |  | 67% |  |  |  | 0%
C34-S245264 | 26003H | 1166J | LP1Y-AWNP-037002-03-1 | LP1Y-AWNP-037002-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 037002 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037002 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 104.6719 | 21.07 | sq ft | 2.76 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142746 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245265 | 26003H | 1167J | LP1Y-AWNP-037002-03-2 | LP1Y-AWNP-037002-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 037002 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037002 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 217.0984 | 42.71 | sq ft | 18.51 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142807 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245266 | 26003H | 1168J | LP1Y-AWNP-037006-04-1 | LP1Y-AWNP-037006-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS AWNP (315) (108) 037006 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037006 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12 | 10 | 2 | 25.4625 | 14.24 | sq ft | 5.74 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-11 | 2026-04-11 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-15 | 2026-04-15 |  | 2026-04-15 | [6 empty] | 67% |  |  |  | 0%
C34-S246944 | 26003H | 1169J-L1 | LP1Y-AWNP-101105-01-1-L1 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142526 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245267 | 26003H | 1169J | LP1Y-AWNP-101105-01-1 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 43.3 | 8.5 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Edgar Castaneda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 142747 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245269 | 26003H | 1171J | LP1Y-AWNP-101105-01-3 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 98.8391 | 20.77 | sq ft | 10.04 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143031 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245270 | 26003H | 1172J | LP1Y-AWNP-101105-01-4 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 113.5672 | 25.2 | sq ft | 4.28 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-19 | N/A | N/A | Aristeo Banda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143397 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245268 | 26003H | 1170J | LP1Y-AWNP-101105-01-2 | LP1Y-AWNP-101105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 28 | 2 | 116.2097 | 27.77 | sq ft | 6.32 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-27 | 2026-04-13 | 2026-04-15 | 2026-04-10 | 2026-04-15 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145681
C34-S246946 | 26003H | 1175J-L1 | LP1Y-AWNP-101106-01-1-L1 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | Carlos Guillen | 2026-03-24 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143954 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245274 | 26003H | 1176J | LP1Y-AWNP-101106-01-2 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 66.2156 | 13.51 | sq ft | 2.28 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143236 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245275 | 26003H | 1177J | LP1Y-AWNP-101106-01-3 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 18 | 3 | 105.2689 | 21.35 | sq ft | 3.36 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-06 | 2026-04-01 | 2026-04-06 | 100% | 2026-04-07 | 144230 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245277 | 26003H | 1179J | LP1Y-AWNP-101106-01-5 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 124.4609 | 26.73 | sq ft | 6.63 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143611 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245276 | 26003H | 1178J | LP1Y-AWNP-101106-01-4 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 20 | 1 | 105.9031 | 25.41 | sq ft | 2.78 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-05-01 | 2026-04-30 |  | 2026-04-30 | 2026-05-01 |  | 2026-05-01 |  |  |  | 67% |  |  |  | 17%
C34-S245273 | 26003H | 1175J | LP1Y-AWNP-101106-01-1 | LP1Y-AWNP-101106-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 15 | 13 | 2 | 52.3936 | 15.06 | sq ft | 4.64 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Carlos Montoya | 2026-05-01 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 |  |  | 80%
C34-S245278 | 26003H | 1180J | LP1Y-AWNP-101106-02-1 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 50 | 12.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 142563 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245279 | 26003H | 1181J | LP1Y-AWNP-101106-02-2 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 90.9594 | 17.84 | sq ft | 2.47 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142829 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245280 | 26003H | 1182J | LP1Y-AWNP-101106-02-3 | LP1Y-AWNP-101106-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 28 | 26 | 2 | 234.2966 | 49.44 | sq ft | 18.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144846 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245281 | 26003H | 1183J | LP1Y-AWNP-101106-03-1 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 9 | 8 | 1 | 70.1547 | 17.8 | sq ft | 3.78 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245282 | 26003H | 1184J | LP1Y-AWNP-101106-03-2 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 84.275 | 16.55 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 142850 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245283 | 26003H | 1185J | LP1Y-AWNP-101106-03-3 | LP1Y-AWNP-101106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101106 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101106 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 60.8828 | 11.9 | sq ft | 2.89 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142809 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245288 | 26003H | 1190J | LP1Y-AWNP-101108-01-2 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 18 | 3 | 106.2376 | 21.54 | sq ft | 3.47 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-07 | 2026-04-01 | 2026-04-07 | 100% | 2026-04-07 | 144231 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245287 | 26003H | 1189J | LP1Y-AWNP-101108-01-1 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 33 | 31 | 2 | 112.603 | 27.41 | sq ft | 6.27 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246948 | 26003H | 1189J-L1 | LP1Y-AWNP-101108-01-1-L1 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143953 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245289 | 26003H | 1191J | LP1Y-AWNP-101108-01-3 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 20 | 1 | 105.9516 | 25.42 | sq ft | 2.79 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Carlos Montoya | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | [6 empty] | 67% |  |  |  | 0%
C34-S245290 | 26003H | 1192J | LP1Y-AWNP-101108-01-4 | LP1Y-AWNP-101108-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101108 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101108 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 110.5844 | 22.09 | sq ft | 7.05 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143327 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245292 | 26003H | 1194J | LP1Y-AWNP-101110-01-2 | LP1Y-AWNP-101110-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 37.6544 | 8.69 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-13 | 142806 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245294 | 26003H | 1196J | LP1Y-AWNP-101110-03-2 | LP1Y-AWNP-101110-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 30.75 | 29 | 1.75 | 59.5208 | 31.86 | sq ft | 4.75 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | [6 empty] | 58% |  |  |  | 0%
C34-S245293 | 26003H | 1195J | LP1Y-AWNP-101110-03-1 | LP1Y-AWNP-101110-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 79.3081 | 18.31 | sq ft | 13.81 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143672 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245296 | 26003H | 1198J | LP1Y-AWNP-101110-04-2 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 22.5602 | 6.27 | sq ft | 2.27 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Omar Puente | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144406 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246949 | 26003H | 1197J-L1 | LP1Y-AWNP-101110-04-1-L1 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142857 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245295 | 26003H | 1197J | LP1Y-AWNP-101110-04-1 | LP1Y-AWNP-101110-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 11 | 1 | 41.3082 | 14.57 | sq ft | 4.57 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-30 | 2026-04-30 |  | 2026-04-30 | [6 empty] | 67% |  |  |  | 0%
C34-S246950 | 26003H | 1199JA | LP1Y-AWNP-101114-01-2 | LP1Y-AWNP-101114-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 10" SS AWNP (315) 101114 | AWNP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101114 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 78 | 11.28 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143884 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245297 | 26003H | 1199J | LP1Y-AWNP-101114-01-1 | LP1Y-AWNP-101114-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 10" SS AWNP (315) 101114 | AWNP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101114 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 32 | 20 | 12 | 497.7848 | 78.38 | sq ft | 26.21 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144238 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245298 | 26003H | 1200J | LP1Y-AWNP-101302-03-1 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 203.5391 | 39.97 | sq ft | 20.7 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-11 | Passed | No | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142879 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245299 | 26003H | 1201J | LP1Y-AWNP-101302-03-2 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 39.5 | 32.5 | 7 | 146.8655 | 43.58 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245300 | 26003H | 1202J | LP1Y-AWNP-101302-03-3 | LP1Y-AWNP-101302-03 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 1" | 316 SS | 1 | 0 | 1 | 4.76 | 8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 146012
C34-S245301 | 26003H | 1203J | LP1Y-AWNP-101302-04-1 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 68.3953 | 13.93 | sq ft | 2.52 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143453 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246951 | 26003H | 1203J-L1 | LP1Y-AWNP-101302-04-1-L1 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142533 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245302 | 26003H | 1204J | LP1Y-AWNP-101302-04-2 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 30 | 30 | 0 | 138.6141 | 30.42 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143072 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245303 | 26003H | 1205J | LP1Y-AWNP-101302-04-3 | LP1Y-AWNP-101302-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101302 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101302 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 101.2281 | 19.83 | sq ft | 3.57 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142851 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246952 | 26003H | 1206J-L1 | LP1Y-AWNP-101305-01-1-L1 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142528 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245307 | 26003H | 1209J | LP1Y-AWNP-101305-01-4 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 121.7063 | 25.76 | sq ft | 11.31 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian; FD: 2026-03-02; FL: Jacob Perez | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143242 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245304 | 26003H | 1206J | LP1Y-AWNP-101305-01-1 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 43.3 | 8.5 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 142849 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245305 | 26003H | 1207J | LP1Y-AWNP-101305-01-2 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 10 | 2 | 81.9816 | 18.94 | sq ft | 4.41 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Omar Puente | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-14 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144852 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245308 | 26003H | 1210J | LP1Y-AWNP-101305-01-5 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 86.8734 | 19.46 | sq ft | 2.59 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Carlos Guillen | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143402 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245306 | 26003H | 1208J | LP1Y-AWNP-101305-01-3 | LP1Y-AWNP-101305-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 39.1688 | 9.79 | sq ft | 2.44 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143270 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246955 | 26003H | 1216JB | LP1Y-AWNP-101308-01-6 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143897 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245317 | 26003H | 1219J | LP1Y-AWNP-101308-01-4 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 18 | 18 | 0 | 111.2625 | 22.22 | sq ft | 7.13 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 144041 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245315 | 26003H | 1217J | LP1Y-AWNP-101308-01-2 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 18 | 3 | 107.061 | 21.69 | sq ft | 3.56 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 100% | 2026-04-02 | 2026-04-01 | 2026-04-02 | 100% | 2026-04-07 | 144204 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247015 | 26003H | 1216JA | LP1Y-AWNP-101308-01-5 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 65.1984 | 13.31 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144229 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245314 | 26003H | 1216J | LP1Y-AWNP-101308-01-1 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 15 | 13 | 2 | 49.4772 | 14.5 | sq ft | 3.78 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-30 |  | 2026-04-30 | 2026-04-28 |  |  | 80% |  |  |  | 20%
C34-S245316 | 26003H | 1218J | LP1Y-AWNP-101308-01-3 | LP1Y-AWNP-101308-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101308 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101308 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 20 | 1 | 105.1256 | 25.51 | sq ft | 2.45 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-28 |  | 2026-04-28 | 2026-04-30 |  | 2026-04-30 |  |  |  | 67% |  |  |  | 67%
C34-S245319 | 26003H | 1221J | LP1Y-AWNP-101309-01-2 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 22 | 22 | 0 | 100.0263 | 23.26 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143077 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245320 | 26003H | 1222J | LP1Y-AWNP-101309-01-3 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142839 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245318 | 26003H | 1220J | LP1Y-AWNP-101309-01-1 | LP1Y-AWNP-101309-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 36 | 36 | 0 | 107.7359 | 22.68 | sq ft | 4.38 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Aristeo Banda | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143365 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245324 | 26003H | 1226J | LP1Y-AWNP-101309-04-4 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 93.3328 | 18.3 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143074 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245322 | 26003H | 1224J | LP1Y-AWNP-101309-04-2 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 88.8281 | 17.43 | sq ft | 2.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-03-11 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Omar Puente | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142987 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245323 | 26003H | 1225J | LP1Y-AWNP-101309-04-3 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 105.2641 | 22.92 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143073 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245321 | 26003H | 1223J | LP1Y-AWNP-101309-04-1 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 27 | 26 | 1 | 124.4141 | 29.44 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  |  |  |  | 2026-04-30 |  | 86% |  |  |  | 0%
C34-S245325 | 26003H | 1227J | LP1Y-AWNP-101309-04-5 | LP1Y-AWNP-101309-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 40 | 38 | 2 | 283.8528 | 59.6 | sq ft | 22.39 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-02-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 |  | 2026-04-14 | 2026-04-14 |  | 2026-04-14 |  |  |  | 50% |  |  |  | 50%
C34-S245329 | 26003H | 1231J | LP1Y-AWNP-101309-05-4 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 121.7969 | 26.22 | sq ft | 6.34 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145135 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245327 | 26003H | 1229J | LP1Y-AWNP-101309-05-2 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 21 | 18 | 3 | 107.061 | 21.69 | sq ft | 3.56 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | N/A | N/A | Henrique Barahona | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-02 | 2026-04-06 | 100% | 2026-04-07 | 144239 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247016 | 26003H | 1228JA | LP1Y-AWNP-101309-05-5 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 65.1984 | 13.31 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 144037 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245328 | 26003H | 1230J | LP1Y-AWNP-101309-05-3 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 27 | 26 | 1 | 110.5047 | 26.3 | sq ft | 3.28 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-28 | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 |  | 2026-05-01 | [6 empty] | 71% |  |  |  | 0%
C34-S246956 | 26003H | 1228JB | LP1Y-AWNP-101309-05-6 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144319 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245326 | 26003H | 1228J | LP1Y-AWNP-101309-05-1 | LP1Y-AWNP-101309-05 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 15 | 13 | 2 | 50.0202 | 14.61 | sq ft | 4.38 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-05-01 | 2026-04-30 | 2026-05-01 | 2026-04-30 |  |  |  | 2026-05-01 |  |  | 80% |  |  |  | 0%
C34-S245331 | 26003H | 1233J | LP1Y-AWNP-101309-09-2 | LP1Y-AWNP-101309-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 17.75 | 12 | 5.75 | 113.8219 | 32.29 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245330 | 26003H | 1232J | LP1Y-AWNP-101309-09-1 | LP1Y-AWNP-101309-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 24 | 24 | 0 | 126.9313 | 27.21 | sq ft | 6.9 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 143479 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245332 | 26003H | 1234J | LP1Y-AWNP-101309-11-1 | LP1Y-AWNP-101309-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 8" SS AWNP (315) (108) 101309 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101309 |  | TFS00D007YSPP |  | 315-AWNP | NONE | 8" | 316 SS | 46 | 46 | 0 | 174.6738 | 32.94 | sq ft | 1.54 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245336 | 26003H | 1238J | LP1Y-AWNP-101310-01-4 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 27 | 27 | 0 | 59.0298 | 27.38 | sq ft | 5.31 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145562 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245335 | 26003H | 1237J | LP1Y-AWNP-101310-01-3 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 80.115 | 18.5 | sq ft | 15.5 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143366 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245333 | 26003H | 1235J | LP1Y-AWNP-101310-01-1 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 56.6658 | 13.08 | sq ft | 8.58 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Omar Puente | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-29 | 145784
C34-S245334 | 26003H | 1236J | LP1Y-AWNP-101310-01-2 | LP1Y-AWNP-101310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 6 | 5 | 1 | 73.5471 | 21.21 | sq ft | 14.71 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian; FD: 2026-02-27; FL: Jacob Perez | 2026-02-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-28 |  | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 25%
C34-S245338 | 26003H | 1240J | LP1Y-AWNP-101310-02-2 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 6.75 | 5 | 1.75 | 41.2865 | 14.98 | sq ft | 5.98 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246957 | 26003H | 1239J-L1 | LP1Y-AWNP-101310-02-1-L1 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142856 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245337 | 26003H | 1239J | LP1Y-AWNP-101310-02-1 | LP1Y-AWNP-101310-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101310 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101310 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 11 | 1 | 42.3431 | 15.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-04-08 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-04-29 | 2026-04-30 |  | 2026-04-30 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 67%
C34-S245339 | 26003H | 1241J | LP1Y-AWNP-101314-01-1 | LP1Y-AWNP-101314-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 10" SS AWNP (315) 101314 | AWNP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101314 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 32 | 20 | 12 | 497.7848 | 78.38 | sq ft | 26.21 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144243 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246958 | 26003H | 1241JA | LP1Y-AWNP-101314-01-2 | LP1Y-AWNP-101314-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 10" SS AWNP (315) 101314 | AWNP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101314 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 10" | 316 SS | 0 | 0 | 0 | 78 | 11.28 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143971 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245341 | 26003H | 1243J | LP1Y-AWNP-102092-03-2 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4.75 | 4 | 0.75 | 16.05 | 12 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145273 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245342 | 26003H | 1244J | LP1Y-AWNP-102092-03-3 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 11.87 | 5.75 | sq ft | 1.75 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-13 | 142825 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245340 | 26003H | 1242J | LP1Y-AWNP-102092-03-1 | LP1Y-AWNP-102092-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS AWNP (315) (108) 102092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102092 |  | TFS00D006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245343 | 26003H | 1245J | LP1Y-AWNP-108094-01-1 | LP1Y-AWNP-108094-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS AWNP (315) (108) 108094 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108094 |  | TFS00E006YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 18.25 | 14 | 4.25 | 89.2888 | 34.11 | sq ft | 11.61 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245345 | 26003H | 1247J | LP1Y-AWNP-168101-08-2 | LP1Y-AWNP-168101-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS AWNP (315) (108) 168101 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-168101 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.2325 | 7.78 | sq ft | 3.78 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Omar Puente | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145079 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245344 | 26003H | 1246J | LP1Y-AWNP-168101-08-1 | LP1Y-AWNP-168101-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS AWNP (315) (108) 168101 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-168101 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.5088 | 10.94 | sq ft | 1.44 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Omar Puente | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-18 | 143007 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245346 | 26003H | 1248AB | LP1Y-BS-178304-01-1 | LP1Y-BS-178304-01 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-12 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" HAST BS (332) P 178304 | BS |  | NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178304 |  | TFS00D001YSPP |  | 332-BS | NONE | 3" | H C22 | 6.5 | 5.75 | 0.75 | 19.9192 | 25.42 | sq ft | 0.92 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245347 | 26003H | 1249J | LP1Y-DMF-062302-16-1 | LP1Y-DMF-062302-16 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Passed Production Test | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 062302 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-062302 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 78.5895 | 19.2 | sq ft | 12.2 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245349 | 26003H | 1251J | LP1Y-DMF-102102-02-2 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245352 | 26003H | 1254J | LP1Y-DMF-102102-02-5 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 21 | 21 | 0 | 157.2982 | 36.32 | sq ft | 30.32 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143879 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245348 | 26003H | 1250J | LP1Y-DMF-102102-02-1 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 26.4216 | 7.16 | sq ft | 1.66 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Roberto Tobias (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143367 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245351 | 26003H | 1253J | LP1Y-DMF-102102-02-4 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 3 | 3 | 0 | 51.4043 | 12.93 | sq ft | 8.93 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-14 | 2026-03-14 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143272 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246959 | 26003H | 1250J-L1 | LP1Y-DMF-102102-02-1-L1 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-03 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142855 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245350 | 26003H | 1252J | LP1Y-DMF-102102-02-3 | LP1Y-DMF-102102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 32.9166 | 8.66 | sq ft | 3.16 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 143027 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245353 | 26003H | 1255J | LP1Y-DMF-102103-01-1 | LP1Y-DMF-102103-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 30 | 28 | 2 | 208.9378 | 44.2 | sq ft | 13.22 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-14 |  | 2026-04-14 | 2026-04-15 |  | 2026-04-15 |  |  |  | 71% |  |  |  | 71%
C34-S245354 | 26003H | 1256J | LP1Y-DMF-102103-02-1 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 10 | 10 | 0 | 63.5378 | 15.44 | sq ft | 4.28 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Carlos Guillen | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144855 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245355 | 26003H | 1257J | LP1Y-DMF-102103-02-2 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246960 | 26003H | 1256JA | LP1Y-DMF-102103-02-3 | LP1Y-DMF-102103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102103 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102103 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144704 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245357 | 26003H | 1259J | LP1Y-DMF-102104-02-2 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 16 | 16 | 0 | 54.8928 | 13.14 | sq ft | 1.78 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 75%
C34-S245356 | 26003H | 1258J | LP1Y-DMF-102104-02-1 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245358 | 26003H | 1260J | LP1Y-DMF-102104-02-3 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 11 | 10 | 1 | 47.6 | 15 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246961 | 26003H | 1258JA | LP1Y-DMF-102104-02-4 | LP1Y-DMF-102104-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 1.5 | 1.5 | 0 | 5.61 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 145248 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245359 | 26003H | 1261J | LP1Y-DMF-102104-03-1 | LP1Y-DMF-102104-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-24 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245360 | 26003H | 1262J | LP1Y-DMF-102104-04-1 | LP1Y-DMF-102104-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 21 | 20 | 1 | 78.459 | 24.9 | sq ft | 9.9 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-02-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | 2026-04-28 |  | 67% |  | 2026-04-30 |  | 56%
C34-S245362 | 26003H | 1264J | LP1Y-DMF-102104-07-2 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245364 | 26003H | 1266J | LP1Y-DMF-102104-07-3 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian; ED: 2026-04-06; EL: Jacob Perez; FD: 2026-04-06; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245361 | 26003H | 1263J | LP1Y-DMF-102104-07-1 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-10 | released |  |  | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 18 | 18 | 0 | 71.3698 | 16.48 | sq ft | 11.98 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 144601 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245363 | 26003H | 1265J | LP1Y-DMF-102104-07-4 | LP1Y-DMF-102104-07 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102104 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102104 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245365 | 26003H | 1267J | LP1Y-DMF-102105-01-1 | LP1Y-DMF-102105-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102105 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102105 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 44.3638 | 22.42 | sq ft | 11.42 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-14 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144993 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245366 | 26003H | 1268J | LP1Y-DMF-102105-03-1 | LP1Y-DMF-102105-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102105 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102105 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245367 | 26003H | 1269J | LP1Y-DMF-102106-01-1 | LP1Y-DMF-102106-01 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 44.3325 | 21.82 | sq ft | 13.32 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-15 |  | 2026-04-14 |  | 75% |  |  |  | 63%
C34-S247104 | 26003H | 1272JA | LP1Y-DMF-102106-03-7 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.4663 | 7.87 | sq ft | 3.87 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-10 | 142622 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245372 | 26003H | 1274J | LP1Y-DMF-102106-03-5 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 17.655 | 8.69 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 100% | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-11 | 142677 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245370 | 26003H | 1272J | LP1Y-DMF-102106-03-3 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 10.8525 | 6.03 | sq ft | 0.53 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S245371 | 26003H | 1273J | LP1Y-DMF-102106-03-4 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 76.99 | 30.42 | sq ft | 26.42 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S246962 | 26003H | 1270J-L1 | LP1Y-DMF-102106-03-1-L1 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142530 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245368 | 26003H | 1270J | LP1Y-DMF-102106-03-1 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S245369 | 26003H | 1271J | LP1Y-DMF-102106-03-2 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247017 | 26003H | 1270JA | LP1Y-DMF-102106-03-6 | LP1Y-DMF-102106-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102106 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102106 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.025 | 6.85 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144768 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245373 | 26003H | 1275J | LP1Y-DMF-102108-01-1 | LP1Y-DMF-102108-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 21.4363 | 8.79 | sq ft | 7.29 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Roberto Tobias (WF) | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144659 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245374 | 26003H | 1276J | LP1Y-DMF-102108-03-1 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 16.9813 | 8.43 | sq ft | 3.93 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-07 | N/A | N/A | Aristeo Banda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-18 | 143001 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245375 | 26003H | 1277J | LP1Y-DMF-102108-03-2 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.2638 | 29.46 | sq ft | 26.46 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian; FD: 2026-03-02; FL: Jacob Perez | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-09 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 142955 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245376 | 26003H | 1278J | LP1Y-DMF-102108-03-3 | LP1Y-DMF-102108-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102108 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102108 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.2263 | 8.49 | sq ft | 3.49 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145570 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245377 | 26003H | 1279J | LP1Y-DMF-102203-01-1 | LP1Y-DMF-102203-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) 102203 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 30 | 28 | 2 | 208.9378 | 44.2 | sq ft | 13.22 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Carlos Guillen | 2026-04-16 | 2026-04-15 | 2026-04-29 | 2026-04-15 | 2026-04-16 | 2026-04-29 | 2026-04-16 |  | 2026-04-29 |  | 86% |  | 2026-04-29 |  | 86%
C34-S245378 | 26003H | 1280J | LP1Y-DMF-102203-02-1 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 10 | 10 | 0 | 63.5086 | 15.43 | sq ft | 4.28 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Montoya | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144674 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245379 | 26003H | 1281J | LP1Y-DMF-102203-02-2 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246963 | 26003H | 1280JA | LP1Y-DMF-102203-02-3 | LP1Y-DMF-102203-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 6" SS DMF (315) P 102203 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102203 |  | TFS00D006YSPP |  | 315-DMF | NONE | 6" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  |  |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% |  |  |  | 0%
C34-S245381 | 26003H | 1283J | LP1Y-DMF-102204-01-2 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 16 | 16 | 0 | 54.25 | 13 | sq ft | 1.67 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145676
C34-S245382 | 26003H | 1284J | LP1Y-DMF-102204-01-3 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 11 | 10 | 1 | 47.6025 | 14.75 | sq ft | 0.92 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245380 | 26003H | 1282J | LP1Y-DMF-102204-01-1 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246964 | 26003H | 1282JA | LP1Y-DMF-102204-01-4 | LP1Y-DMF-102204-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 1.5 | 1.5 | 0 | 5.61 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S245383 | 26003H | 1285J | LP1Y-DMF-102204-02-1 | LP1Y-DMF-102204-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 4" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245384 | 26003H | 1286J | LP1Y-DMF-102204-03-1 | LP1Y-DMF-102204-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245385 | 26003H | 1287J | LP1Y-DMF-102204-03-2 | LP1Y-DMF-102204-03 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 102204 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102204 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 11 | 1 | 35.8055 | 14.8 | sq ft | 3.3 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245386 | 26003H | 1288J | LP1Y-DMF-102205-01-1 | LP1Y-DMF-102205-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 6 | 6 | 0 | 31.9138 | 13.42 | sq ft | 10.42 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-07 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-11 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142906 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245389 | 26003H | 1291J | LP1Y-DMF-102205-03-3 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 12.705 | 6.81 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143400 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245387 | 26003H | 1289J | LP1Y-DMF-102205-03-1 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.2263 | 8.49 | sq ft | 3.49 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S245388 | 26003H | 1290J | LP1Y-DMF-102205-03-2 | LP1Y-DMF-102205-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102205 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102205 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 81.6338 | 32.26 | sq ft | 29.26 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-07 | N/A | N/A | Edgar Castaneda | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-24 | 143371 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245390 | 26003H | 1292J | LP1Y-DMF-102206-01-1 | LP1Y-DMF-102206-01 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 46.23 | 21.87 | sq ft | 14.88 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 |  | 2026-04-14 |  | 2026-04-14 |  | 71% |  |  |  | 14%
C34-S245395 | 26003H | 1297J | LP1Y-DMF-102206-03-5 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 10 | 10 | 0 | 78.9388 | 31.9 | sq ft | 27.4 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 40%
C34-S245391 | 26003H | 1293J | LP1Y-DMF-102206-03-1 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144769 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245393 | 26003H | 1295J | LP1Y-DMF-102206-03-3 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.0038 | 11.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Henrique Barahona | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144992 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245394 | 26003H | 1296J | LP1Y-DMF-102206-03-4 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.1975 | 7.01 | sq ft | 3.01 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144831 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246965 | 26003H | 1293J-L1 | LP1Y-DMF-102206-03-1-L1 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142529 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245392 | 26003H | 1294J | LP1Y-DMF-102206-03-2 | LP1Y-DMF-102206-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102206 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102206 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245397 | 26003H | 1299J | LP1Y-DMF-102211-01-2 | LP1Y-DMF-102211-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12 | 12 | 0 | 23.8738 | 12.38 | sq ft | 6.38 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144666 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245396 | 26003H | 1298J | LP1Y-DMF-102211-01-1 | LP1Y-DMF-102211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 36.2925 | 18.7 | sq ft | 9.2 | ft | 2026-02-13 |  |  |  |  | 2026-03-02 | Jacob Perez | 2026-03-02 | George Allahverdian | 2026-03-02 | Jacob Perez | 2026-03-02 | Jacob Perez | 2026-03-02 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-22 | 2026-04-14 | 2026-04-22 | 100% |  |  |  | 67%
C34-S245398 | 26003H | 1300J | LP1Y-DMF-102211-03-1 | LP1Y-DMF-102211-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS DMF (315) P 102211 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102211 |  | TFS00D006YSPP |  | 315-DMF | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-02 | Jacob Perez | 2026-03-02 | George Allahverdian | 2026-03-02 | Jacob Perez | 2026-03-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246966 | 26003H | 1301J-L1 | LP1Y-DMF-175101-01-1-L1 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143588
C34-S245399 | 26003H | 1301J | LP1Y-DMF-175101-01-1 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143333
C34-S245400 | 26003H | 1302J | LP1Y-DMF-175101-01-2 | LP1Y-DMF-175101-01 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 22 | 20 | 2 | 318.0296 | 40.92 | sq ft | 6.42 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245401 | 26003H | 1303J | LP1Y-DMF-175101-02-1 | LP1Y-DMF-175101-02 | 0 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 139.3135 | 33.35 | sq ft | 30.35 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-11 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 143876, 143877
C34-S245402 | 26003H | 1304J | LP1Y-DMF-175101-02-2 | LP1Y-DMF-175101-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 19 | 18 | 1 | 54.0284 | 29.84 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245403 | 26003H | 1305J | LP1Y-DMF-175101-03-1 | LP1Y-DMF-175101-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175101 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175101 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 3 | 6 | 32.393 | 27.12 | sq ft | 1.62 | ft | 2026-02-13 |  |  |  |  | 2026-03-03 | Jacob Perez | 2026-03-03 | George Allahverdian | 2026-03-03 | Jacob Perez | 2026-03-03 | Jacob Perez | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245404 | 26003H | 1307J | LP1Y-DMF-175102-01-1 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 6 | 6 | 0 | 26.4216 | 7.16 | sq ft | 1.66 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-19 | 143028 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246967 | 26003H | 1307J-L1 | LP1Y-DMF-175102-01-1-L1 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-14 | 142858 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245405 | 26003H | 1308J | LP1Y-DMF-175102-01-2 | LP1Y-DMF-175102-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245406 | 26003H | 1309J | LP1Y-DMF-175102-02-1 | LP1Y-DMF-175102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 9 | 0 | 61.2871 | 15.21 | sq ft | 9.71 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143746 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245407 | 26003H | 1310J | LP1Y-DMF-175102-02-2 | LP1Y-DMF-175102-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 15 | 15 | 0 | 135.7785 | 31.35 | sq ft | 26.85 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Edgar Castaneda | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143244 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245408 | 26003H | 1311J | LP1Y-DMF-175102-04-1 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 3 | 3 | 0 | 36.1365 | 9.4 | sq ft | 5.4 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-18 | Passed | No | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Henrique Barahona | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143334 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247018 | 26003H | 1311JA | LP1Y-DMF-175102-04-3 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 9 | 8 | 1 | 35.1515 | 13.15 | sq ft | 3.15 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | [6 empty] | 60% |  |  |  | 0%
C34-S245409 | 26003H | 1312J | LP1Y-DMF-175102-04-2 | LP1Y-DMF-175102-04 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D006YSPP |  | 315-DMF | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245414 | 26003H | 1317J | LP1Y-DMF-175102-06-5 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245415 | 26003H | 1318J | LP1Y-DMF-175102-06-6 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 4 | 4 | 0 | 53.2025 | 14.74 | sq ft | 0.74 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246968 | 26003H | 1313JA | LP1Y-DMF-175102-06-7 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245410 | 26003H | 1313J | LP1Y-DMF-175102-06-1 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 13 | 13 | 0 | 36.9188 | 25.78 | sq ft | 1.28 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245413 | 26003H | 1316J | LP1Y-DMF-175102-06-4 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.46 | 13.67 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245412 | 26003H | 1315J | LP1Y-DMF-175102-06-3 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245411 | 26003H | 1314J | LP1Y-DMF-175102-06-2 | LP1Y-DMF-175102-06 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245418 | 26003H | 1321J | LP1Y-DMF-175102-08-2 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Passed Production Test | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 18 | 15 | 3 | 45.3828 | 13.03 | sq ft | 4.03 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245416 | 26003H | 1319J | LP1Y-DMF-175102-08-1 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 12 | 12 | 0 | 33.97 | 12 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Carlos Guillen | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143521
C34-S245417 | 26003H | 1320J | LP1Y-DMF-175102-08-3 | LP1Y-DMF-175102-08 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" SS DMF (315) P 175102 | DMF |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175102 |  | TFS00D007YSPP |  | 315-DMF | NONE | 3" | 316 SS | 18 | 17 | 1 | 74.0532 | 21.32 | sq ft | 11.82 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245422 | 26003H | 1325J | LP1Y-ENZ-108115-01-3 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 2 | 0 | 2 | 26.1226 | 40.7 | sq ft | 37.2 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-18 | 2026-03-31 | 2026-03-18 | 2026-03-31 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245420 | 26003H | 1323J | LP1Y-ENZ-108115-01-1 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 1.5 | 0 | 1.5 | 3.5592 | 6.14 | sq ft | 1.64 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Edgar Castaneda | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145806
C34-S246970 | 26003H | 1323JA | LP1Y-ENZ-108115-01-4 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2.5 | 2 | 0.5 | 10.26 | 6.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-24 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145276
C34-S245421 | 26003H | 1324J | LP1Y-ENZ-108115-01-2 | LP1Y-ENZ-108115-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108115 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108115 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 3.9228 | 5.87 | sq ft | 2.87 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% |  |  |  | 0%
C34-S246971 | 26003H | 1326J-L1 | LP1Y-ENZ-108221-01-1-L1 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142531
C34-S245424 | 26003H | 1327J | LP1Y-ENZ-108221-01-2 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 3.4203 | 5.12 | sq ft | 2.12 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 145805
C34-S245423 | 26003H | 1326J | LP1Y-ENZ-108221-01-1 | LP1Y-ENZ-108221-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108221 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108221 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2.5 | 0 | 2.5 | 6.2377 | 8.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  | 40% |  |  |  | 40%
C34-S245428 | 26003H | 1331J | LP1Y-ENZ-162001-02-1 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 3 | 0 | 3 | 16.5108 | 27.08 | sq ft | 22.58 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 83% |  |  |  | 50%
C34-S245429 | 26003H | 1332J | LP1Y-ENZ-162001-02-2 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 6.5 | 0 | 6.5 | 30.3962 | 43.15 | sq ft | 12.65 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246973 | 26003H | 1332J-L1 | LP1Y-ENZ-162001-02-2-L1 | LP1Y-ENZ-162001-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 2 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-05 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145573
C34-S245430 | 26003H | 1333J | LP1Y-ENZ-162001-06-1 | LP1Y-ENZ-162001-06 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-02 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 4 | 0 | 4 | 27.9435 | 44.23 | sq ft | 39.23 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-01 | 2026-04-08 | 2026-04-08 | 2026-04-08 | N/A | N/A | Carlos Guillen | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | [6 empty] | 75% |  |  |  | 0%
C34-S245435 | 26003H | 1338J | LP1Y-H2SO4-013011-17-1 | LP1Y-H2SO4-013011-17 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 013011 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-013011 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 16 | 16 | 0 | 100.6067 | 23.51 | sq ft | 12.76 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144505
C34-S245439 | 26003H | 1342J | LP1Y-H2SO4-016001-02-4 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12 | 12 | 0 | 66.7288 | 27.94 | sq ft | 21.94 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143326 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245438 | 26003H | 1341J | LP1Y-H2SO4-016001-02-3 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 5 | 5 | 0 | 16.3203 | 13.07 | sq ft | 5.57 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143905 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245436 | 26003H | 1339J | LP1Y-H2SO4-016001-02-1 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 4.2977 | 6.66 | sq ft | 1.16 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Omar Puente | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 |  |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% |  |  |  | 0%
C34-S246976 | 26003H | 1339JA | LP1Y-H2SO4-016001-02-5 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-24 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145204 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245437 | 26003H | 1340J | LP1Y-H2SO4-016001-02-2 | LP1Y-H2SO4-016001-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-08 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 016001 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016001 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 6.25 | 3 | 3.25 | 13.3185 | 17.34 | sq ft | 4.34 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-08 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 |  |  | 86% |  |  |  | 0%
C34-S245440 | 26003H | 1343J | LP1Y-H2SO4-016003-02-1 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 42.9 | 18.25 | sq ft | 13.75 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143832 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245442 | 26003H | 1345J | LP1Y-H2SO4-016003-02-3 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 5.25 | 3 | 2.25 | 11.4255 | 13.9 | sq ft | 4.4 | ft | 2026-02-13 | CD: 2026-03-24; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S245441 | 26003H | 1344J | LP1Y-H2SO4-016003-02-2 | LP1Y-H2SO4-016003-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 016003 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016003 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 29.1513 | 15.47 | sq ft | 8.97 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144479, 144480 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245444 | 26003H | 1347J | LP1Y-H2SO4-016018-02-2 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 3.5 | 1 | 2.5 | 6.9158 | 12.86 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 145807
C34-S245443 | 26003H | 1346J | LP1Y-H2SO4-016018-02-1 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8.5 | 8 | 0.5 | 28.255 | 15.31 | sq ft | 7.31 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-04-29 |  | 80% |  |  |  | 0%
C34-S245445 | 26003H | 1348J | LP1Y-H2SO4-016018-02-3 | LP1Y-H2SO4-016018-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 5 | 5 | 0 | 13.0638 | 11.01 | sq ft | 1.01 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145088
C34-S245446 | 26003H | 1349J | LP1Y-H2SO4-016018-04-1 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 6.16 | 3 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Carlos Guillen | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-10 | 142593
C34-S246977 | 26003H | 1349JA | LP1Y-H2SO4-016018-04-3 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0.5 | 0 | 0.5 | 4.73 | 5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-24 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145566
C34-S245447 | 26003H | 1350J | LP1Y-H2SO4-016018-04-2 | LP1Y-H2SO4-016018-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS H2SO4 (315) P (108) 016018 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016018 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 68.66 | 24.96 | sq ft | 3.96 | ft | 2026-02-13 |  |  |  |  | 2026-03-05 | Jacob Perez | 2026-03-05 | George Allahverdian | 2026-03-05 | Jacob Perez | 2026-03-05 | Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245449 | 26003H | 1352J | LP1Y-H2SO4-100302-01-2 | LP1Y-H2SO4-100302-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 20 | 20 | 0 | 58.5758 | 19.24 | sq ft | 6.74 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-03-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144833 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245448 | 26003H | 1351J | LP1Y-H2SO4-100302-01-1 | LP1Y-H2SO4-100302-01 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 8 | 4 | 82.4739 | 18.77 | sq ft | 10.31 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143965 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245450 | 26003H | 1353J | LP1Y-H2SO4-100302-02-1 | LP1Y-H2SO4-100302-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 13.5 | 13.5 | 0 | 35.6805 | 15.62 | sq ft | 2.46 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143900 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245451 | 26003H | 1354J | LP1Y-H2SO4-100302-02-2 | LP1Y-H2SO4-100302-02 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 100302 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100302 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 23 | 17 | 6 | 80.1394 | 24.78 | sq ft | 4.83 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245455 | 26003H | 1358J | LP1Y-H2SO4-100303-01-4 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 24.4771 | 6.71 | sq ft | 2.71 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143401 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245454 | 26003H | 1357J | LP1Y-H2SO4-100303-01-3 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.0121 | 13.71 | sq ft | 1.21 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245453 | 26003H | 1356J | LP1Y-H2SO4-100303-01-2 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 10.5 | 9 | 1.5 | 37.8971 | 11.04 | sq ft | 1.54 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-03-30 | 2026-04-01 | 100% | 2026-04-02 | 2026-03-31 | 2026-04-02 | 100% | 2026-04-06 | 144173 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246979 | 26003H | 1355JA | LP1Y-H2SO4-100303-01-5 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 12.7244 | 2.94 | sq ft | 1.44 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Carlos Guillen | 2026-03-24 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143520 | [40 empty] | 2026-04-07 | 2026-04-07 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246978 | 26003H | 1355JB | LP1Y-H2SO4-100303-01-6 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 2.5 | 2.5 | 0 | 4.17 | 8 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-24 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144068 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245452 | 26003H | 1355J | LP1Y-H2SO4-100303-01-1 | LP1Y-H2SO4-100303-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 12 | 10 | 2 | 33.7266 | 13.05 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-04-07 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245456 | 26003H | 1359J | LP1Y-H2SO4-100303-02-1 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 8 | 8 | 0 | 32.6116 | 12.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144669, 144670 | [40 empty] | 2026-04-19 | 2026-04-19
C34-S245458 | 26003H | 1361J | LP1Y-H2SO4-100303-02-3 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 21 | 21 | 0 | 51.4229 | 24.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Roberto Tobias (WF) | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144223 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245457 | 26003H | 1360J | LP1Y-H2SO4-100303-02-2 | LP1Y-H2SO4-100303-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 9 | 0 | 43.1407 | 13.57 | sq ft | 2.57 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143836 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245460 | 26003H | 1363J | LP1Y-H2SO4-100303-06-2 | LP1Y-H2SO4-100303-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 15 | 15 | 0 | 63.0963 | 15.62 | sq ft | 8.63 | ft | 2026-02-13 |  |  |  |  | 2026-03-05 | Jacob Perez | 2026-03-05 | George Allahverdian | 2026-03-05 | Jacob Perez | 2026-03-05 | Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | N/A | N/A | Omar Puente | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143742 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245459 | 26003H | 1362J | LP1Y-H2SO4-100303-06-1 | LP1Y-H2SO4-100303-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS H2SO4 (315) P (108) 100303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100303 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 12 | 12 | 0 | 63.521 | 15.85 | sq ft | 11.35 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-18 | 2026-03-17 | 2026-03-17 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143245 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245462 | 26003H | 1365J | LP1Y-H2SO4-100304-01-2 | LP1Y-H2SO4-100304-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 84.6313 | 33.39 | sq ft | 30.39 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-31 | 143907 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245461 | 26003H | 1364J | LP1Y-H2SO4-100304-01-1 | LP1Y-H2SO4-100304-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.25 | 8.75 | 3.5 | 45.8038 | 22.38 | sq ft | 13.88 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-21 | 145132 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245466 | 26003H | 1369J | LP1Y-H2SO4-100304-02-4 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 13 | 13 | 0 | 45.8713 | 24.85 | sq ft | 14.35 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-28 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144558 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245465 | 26003H | 1368J | LP1Y-H2SO4-100304-02-3 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 20.695 | 14.56 | sq ft | 3.06 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144985 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245463 | 26003H | 1366J | LP1Y-H2SO4-100304-02-1 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 12.6263 | 6.7 | sq ft | 1.2 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-25 | 145561 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245464 | 26003H | 1367J | LP1Y-H2SO4-100304-02-2 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10.25 | 6 | 4.25 | 29.27 | 17.29 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-02-26; CL: Jacob Perez; DD: 2026-02-26; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 145245 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246980 | 26003H | 1366J-L1 | LP1Y-H2SO4-100304-02-1-L1 | LP1Y-H2SO4-100304-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100304 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100304 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-02 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142532 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245468 | 26003H | 1371J | LP1Y-H2SO4-100314-01-2 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8 | 8 | 0 | 32.7113 | 14.39 | sq ft | 9.89 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 143669 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245469 | 26003H | 1372J | LP1Y-H2SO4-100314-01-3 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | 2026-03-05 | 2026-03-11 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 74.6213 | 28.93 | sq ft | 27.43 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143743 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245467 | 26003H | 1370J | LP1Y-H2SO4-100314-01-1 | LP1Y-H2SO4-100314-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 20.1713 | 8.31 | sq ft | 6.81 | ft | 2026-02-13 | DD: 2026-02-26; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142940 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245470 | 26003H | 1373J | LP1Y-H2SO4-100314-02-1 | LP1Y-H2SO4-100314-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 14.8925 | 7.99 | sq ft | 2.99 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Carlos Montoya | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143749 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245471 | 26003H | 1374J | LP1Y-H2SO4-100314-02-2 | LP1Y-H2SO4-100314-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS H2SO4 (315) P (108) 100314 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100314 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8 | 8 | 0 | 47.96 | 20.17 | sq ft | 15.67 | ft | 2026-02-13 | CD: 2026-02-27; CL: Jacob Perez; DD: 2026-02-27; DL: George Allahverdian | 2026-03-02 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143673 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245475 | 26003H | 1378J | LP1Y-H2SO4-101011-02-4 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 53.2125 | 21.49 | sq ft | 18.49 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142937 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245474 | 26003H | 1377J | LP1Y-H2SO4-101011-02-3 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.8066 | 14.38 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144661 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245472 | 26003H | 1375J | LP1Y-H2SO4-101011-02-1 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 12.1303 | 13.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S245473 | 26003H | 1376J | LP1Y-H2SO4-101011-02-2 | LP1Y-H2SO4-101011-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101011 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101011 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245476 | 26003H | 1379J | LP1Y-H2SO4-101303-03-1 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 4.0773 | 6.51 | sq ft | 1.01 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Roberto Tobias (WF) | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 |  |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% |  |  |  | 0%
C34-S245478 | 26003H | 1381J | LP1Y-H2SO4-101303-03-3 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.3028 | 14.07 | sq ft | 5.07 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143904 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245479 | 26003H | 1382J | LP1Y-H2SO4-101303-03-4 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 10 | 10 | 0 | 56.925 | 23.56 | sq ft | 19.06 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142958 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245477 | 26003H | 1380J | LP1Y-H2SO4-101303-03-2 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 6.25 | 3 | 3.25 | 13.1813 | 17.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-09 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  | 2026-04-27 |  |  | 86% |  |  |  | 0%
C34-S246981 | 26003H | 1379JA | LP1Y-H2SO4-101303-03-5 | LP1Y-H2SO4-101303-03 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS H2SO4 (315) P (108) 101303 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101303 |  | TFS00D003YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-24 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145275 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S245480 | 26003H | 1383D | LP1Y-H2SO4-101516-01-1 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 2" | 2205 | 6 | 6 | 0 | 11.5345 | 12.1 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245481 | 26003H | 1384D | LP1Y-H2SO4-101516-01-2 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 1" | 2205 | 3 | 3 | 0 | 6.193 | 10.32 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245482 | 26003H | 1385D | LP1Y-H2SO4-101516-01-3 | LP1Y-H2SO4-101516-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" DUP H2SO4 (344) P (108) 101516 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101516 |  | TFS00D005YSPP |  | 344-H2SO4 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.0611 | 8.21 | sq ft | 0.21 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245485 | 26003H | 1388J | LP1Y-H2SO4-101703-03-3 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 11 | 11 | 0 | 34.1798 | 21.41 | sq ft | 10.91 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Guillen | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145613
C34-S245486 | 26003H | 1389J | LP1Y-H2SO4-101703-03-4 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.8663 | 18.33 | sq ft | 15.33 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-14 | [6 empty] | 67% |  |  |  | 0%
C34-S245483 | 26003H | 1386J | LP1Y-H2SO4-101703-03-1 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 7 | 0 | 11.9247 | 13.68 | sq ft | 0.68 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 |  |  |  | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% |  |  |  | 0%
C34-S245484 | 26003H | 1387J | LP1Y-H2SO4-101703-03-2 | LP1Y-H2SO4-101703-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 101703 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101703 |  | TFS00D005YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245487 | 26003H | 1390J | LP1Y-H2SO4-108118-02-1 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.1275 | 7.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-08 | 2026-04-08 | 2026-04-02 | 2026-04-02 | N/A | N/A | Roberto Tobias (WF) | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S245489 | 26003H | 1392J | LP1Y-H2SO4-108118-02-3 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 1 | 1 | 0 | 25.4691 | 19.36 | sq ft | 17.86 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143902, 143903
C34-S246982 | 26003H | 1390JA | LP1Y-H2SO4-108118-02-4 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-24 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145203
C34-S245488 | 26003H | 1391J | LP1Y-H2SO4-108118-02-2 | LP1Y-H2SO4-108118-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108118 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108118 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 4.25 | 2 | 2.25 | 27.0959 | 21.3 | sq ft | 3.3 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245492 | 26003H | 1395J | LP1Y-H2SO4-108220-01-3 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 1 | 1 | 0 | 25.4838 | 19.38 | sq ft | 17.88 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143238
C34-S246983 | 26003H | 1393JA | LP1Y-H2SO4-108220-01-4 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-24 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145274
C34-S245490 | 26003H | 1393J | LP1Y-H2SO4-108220-01-1 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.1422 | 7.26 | sq ft | 1.76 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S245491 | 26003H | 1394J | LP1Y-H2SO4-108220-01-2 | LP1Y-H2SO4-108220-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 1" SS H2SO4 (315) P (108) 108220 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108220 |  | TFS00E006YSPP |  | 315-H2SO4 | NONE | 1" | 316 SS | 4.25 | 2 | 2.25 | 27.1033 | 21.31 | sq ft | 3.31 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245497 | 26003H | 1400J | LP1Y-H2SO4-178101-02-1 | LP1Y-H2SO4-178101-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 6 | 6 | 0 | 105.9547 | 24.47 | sq ft | 22.97 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | N/A | N/A | Omar Puente | 2026-03-10 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143368
C34-S245498 | 26003H | 1401J | LP1Y-H2SO4-178101-02-2 | LP1Y-H2SO4-178101-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 28 | 27 | 1 | 78.0288 | 35.38 | sq ft | 6.88 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-03 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245499 | 26003H | 1402J | LP1Y-H2SO4-178101-03-1 | LP1Y-H2SO4-178101-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P 178101 | H2SO4 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.0277 | 27.03 | sq ft | 1.53 | ft | 2026-02-13 |  |  |  |  | 2026-03-03 | Jacob Perez | 2026-03-03 | George Allahverdian | 2026-03-04 | Jacob Perez | 2026-03-04 | Jacob Perez | 2026-03-04 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245500 | 26003H | 1404J | LP1Y-H2SO4-178102-03-1 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 4 | 4 | 0 | 102.3413 | 22.75 | sq ft | 17.46 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-04 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143744 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245501 | 26003H | 1405J | LP1Y-H2SO4-178102-03-2 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 11 | 11 | 0 | 53.2069 | 15.42 | sq ft | 6.02 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Carlos Montoya | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143942 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245502 | 26003H | 1406J | LP1Y-H2SO4-178102-03-3 | LP1Y-H2SO4-178102-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 14 | 13 | 1 | 44.2525 | 16.95 | sq ft | 1.25 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-03-04 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245503 | 26003H | 1407J | LP1Y-H2SO4-178102-04-1 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.675 | 2.44 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143369
C34-S245507 | 26003H | 1411J | LP1Y-H2SO4-178102-04-5 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9 | 13.83 | sq ft | 1.83 | ft | 2026-02-13 |  |  |  |  | 2026-03-18 | Jacob Perez | 2026-03-18 | George Allahverdian | 2026-03-18 | Jacob Perez | 2026-03-18 | Jacob Perez | 2026-03-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246985 | 26003H | 1407JA | LP1Y-H2SO4-178102-04-6 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-24 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144981
C34-S245506 | 26003H | 1410J | LP1Y-H2SO4-178102-04-4 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245504 | 26003H | 1408J | LP1Y-H2SO4-178102-04-2 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 9 | 0 | 35.8045 | 24.6 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245505 | 26003H | 1409J | LP1Y-H2SO4-178102-04-3 | LP1Y-H2SO4-178102-04 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245508 | 26003H | 1412J | LP1Y-H2SO4-178102-06-1 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 8 | 0 | 35.0519 | 8.62 | sq ft | 1.85 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143237 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246986 | 26003H | 1412J-L1 | LP1Y-H2SO4-178102-06-1-L1 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142534 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245509 | 26003H | 1413J | LP1Y-H2SO4-178102-06-2 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 4 | 4 | 42.3931 | 11.77 | sq ft | 2.98 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Omar Puente | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-01 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 144036 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245510 | 26003H | 1414J | LP1Y-H2SO4-178102-06-3 | LP1Y-H2SO4-178102-06 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D002YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 19.75 | 18 | 1.75 | 65.1306 | 25.23 | sq ft | 4.89 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245516 | 26003H | 1420J | LP1Y-H2SO4-178102-07-4 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245515 | 26003H | 1419J | LP1Y-H2SO4-178102-07-3 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 12 | 0 | 67.0998 | 19.9 | sq ft | 3.14 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245513 | 26003H | 1417J | LP1Y-H2SO4-178102-07-6 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 8 | 0 | 48.2281 | 11.18 | sq ft | 7.81 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-09 | Passed | No | 2026-03-09 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-11 | N/A | N/A | Roberto Tobias (WF) | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142903
C34-S245511 | 26003H | 1415J | LP1Y-H2SO4-178102-07-1 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 19 | 18 | 1 | 60.8425 | 19.55 | sq ft | 1.92 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245512 | 26003H | 1416J | LP1Y-H2SO4-178102-07-5 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 12 | 12 | 0 | 99.232 | 22.94 | sq ft | 16.12 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-23 | 143331
C34-S245514 | 26003H | 1418J | LP1Y-H2SO4-178102-07-2 | LP1Y-H2SO4-178102-07 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-25 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 4" SS H2SO4 (315) P (108) 178102 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178102 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 4" | 316 SS | 8 | 4 | 4 | 39.4931 | 9.57 | sq ft | 2.65 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 |  | 2026-04-07 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 |  |  | 50%
C34-S245518 | 26003H | 1422J | LP1Y-N2(100)-018010-15-2 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 26.0975 | 11.89 | sq ft | 7.39 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-04-02 | 143666, 144066 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246987 | 26003H | 1421J-L1 | LP1Y-N2(100)-018010-15-1-L1 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-05 | Passed | No | 2026-03-05 | 2026-03-06 | 2026-03-06 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-09 | 142535 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S245517 | 26003H | 1421J | LP1Y-N2(100)-018010-15-1 | LP1Y-N2(100)-018010-15 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 018010 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018010 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 6 | 2 | 31.24 | 13.17 | sq ft | 10.17 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Edgar Castaneda | 2026-03-30 | 2026-03-28 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143951 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246004 | 26003H | 1424J | LP1Y-N2(100)-018016-01-2 | LP1Y-N2(100)-018016-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 018016 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018016 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.8225 | 15.28 | sq ft | 12.28 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142938 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246003 | 26003H | 1423J | LP1Y-N2(100)-018016-01-1 | LP1Y-N2(100)-018016-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 018016 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018016 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246006 | 26003H | 1426J | LP1Y-N2(100)-018019-02-2 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 6 | 2 | 36.96 | 15.33 | sq ft | 12.33 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-21 | 2026-03-25 | 100% | 2026-03-25 | 2026-03-24 | 2026-03-25 | 100% | 2026-03-26 | 143524 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246005 | 26003H | 1425J | LP1Y-N2(100)-018019-02-1 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246988 | 26003H | 1425J-L1 | LP1Y-N2(100)-018019-02-1-L1 | LP1Y-N2(100)-018019-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 018019 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018019 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144646 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246007 | 26003H | 1427J | LP1Y-N2(100)-018031-02-1 | LP1Y-N2(100)-018031-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 018031 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018031 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 96.03 | 31.71 | sq ft | 17.21 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246989 | 26003H | 1427J-L1 | LP1Y-N2(100)-018031-02-1-L1 | LP1Y-N2(100)-018031-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 018031 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018031 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145579
C34-S246009 | 26003H | 1429J | LP1Y-N2(100)-018035-02-2 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.4113 | 16.64 | sq ft | 13.64 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 67%
C34-S246990 | 26003H | 1428J-L1 | LP1Y-N2(100)-018035-02-1-L1 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246008 | 26003H | 1428J | LP1Y-N2(100)-018035-02-1 | LP1Y-N2(100)-018035-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 018035 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018035 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 57.1725 | 15.66 | sq ft | 4.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246991 | 26003H | 1430J-L1 | LP1Y-N2(100)-018057-02-1-L1 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246011 | 26003H | 1431J | LP1Y-N2(100)-018057-02-2 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 69.1625 | 20.2 | sq ft | 8.7 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246010 | 26003H | 1430J | LP1Y-N2(100)-018057-02-1 | LP1Y-N2(100)-018057-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2(100) (315) E 018057 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018057 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 6.59 | 3.83 | sq ft | 2.33 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-03-06 | 2026-03-13 | Passed | No | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143233
C34-S246013 | 26003H | 1433J | LP1Y-N2(100)-180004-01-2 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 22.8388 | 10.65 | sq ft | 6.15 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143937 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246014 | 26003H | 1434J | LP1Y-N2(100)-180004-01-3 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.52 | 14.5 | sq ft | 13 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143878 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246012 | 26003H | 1432J | LP1Y-N2(100)-180004-01-1 | LP1Y-N2(100)-180004-01 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180004 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246017 | 26003H | 1437J | LP1Y-N2(100)-180005-02-3 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246016 | 26003H | 1436J | LP1Y-N2(100)-180005-02-2 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.2025 | 10.03 | sq ft | 5.53 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-04-15 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-18 | 144988 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246015 | 26003H | 1435J | LP1Y-N2(100)-180005-02-1 | LP1Y-N2(100)-180005-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180005 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180005 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.5338 | 14.51 | sq ft | 13.01 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-23 | 143269 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246020 | 26003H | 1440J | LP1Y-N2(100)-180008-02-3 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | 2026-03-13 | 2026-03-13 | released |  |  | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-13 | 2026-03-13 | Passed | No | 2026-03-13 | N/A | N/A | 2026-03-25 | 2026-03-25 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-27 | 143675 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246019 | 26003H | 1439J | LP1Y-N2(100)-180008-02-2 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 40.6313 | 15.39 | sq ft | 15.39 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-23 | 143267 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246018 | 26003H | 1438J | LP1Y-N2(100)-180008-02-1 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.1925 | 5.57 | sq ft | 2.57 | ft | 2026-02-13 | DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | [6 empty] | 50% |  |  |  | 0%
C34-S249767 | 26003H | 1439JX | LP1Y-N2(100)-180008-02-2X | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 24.42 | 9.92 | sq ft | 8.42 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143833 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246021 | 26003H | 1441J | LP1Y-N2(100)-180008-02-4 | LP1Y-N2(100)-180008-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 16.94 | 9.08 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143747 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246022 | 26003H | 1442J | LP1Y-N2(100)-180008-03-1 | LP1Y-N2(100)-180008-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246023 | 26003H | 1443J | LP1Y-N2(100)-180008-03-2 | LP1Y-N2(100)-180008-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180008 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180008 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246024 | 26003H | 1444J | LP1Y-N2(100)-180009-02-1 | LP1Y-N2(100)-180009-02 | 1 | N | PRIORITY-1 | 2026-03-11 | 2026-03-11 | released |  |  | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 80.08 | 31.67 | sq ft | 28.67 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144363 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246025 | 26003H | 1445J | LP1Y-N2(100)-180009-02-2 | LP1Y-N2(100)-180009-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.5038 | 20.46 | sq ft | 17.46 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 67%
C34-S246027 | 26003H | 1447J | LP1Y-N2(100)-180009-03-2 | LP1Y-N2(100)-180009-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246026 | 26003H | 1446J | LP1Y-N2(100)-180009-03-1 | LP1Y-N2(100)-180009-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180009 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180009 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246028 | 26003H | 1448J | LP1Y-N2(100)-180027-01-1 | LP1Y-N2(100)-180027-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E (108) 180027 | N2(100) |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.8625 | 4.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 145247 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246029 | 26003H | 1449J | LP1Y-N2(100)-180027-01-2 | LP1Y-N2(100)-180027-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E (108) 180027 | N2(100) |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 5 | 1 | 14.0545 | 17.6 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-05; CL: Jacob Perez; DD: 2026-03-05; DL: George Allahverdian | 2026-04-07 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145270 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246031 | 26003H | 1451J | LP1Y-N2(100)-180027-02-2 | LP1Y-N2(100)-180027-02 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 13 | 2 | 45.3933 | 32.81 | sq ft | 13.81 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez; FD: 2026-03-05; FL: Jacob Perez | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Roberto Tobias (WF) | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-14 | 2026-03-30 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-16 | 144867 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246030 | 26003H | 1450J | LP1Y-N2(100)-180027-02-1 | LP1Y-N2(100)-180027-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180027 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 36.9738 | 14.67 | sq ft | 13.17 | ft | 2026-02-13 | CD: 2026-03-04; CL: Jacob Perez | 2026-03-05 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-14 | 2026-03-14 | 2026-03-14 | 100% | 2026-03-14 | 142853 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246032 | 26003H | 1452J | LP1Y-N2(100)-180043-01-1 | LP1Y-N2(100)-180043-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180043 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180043 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 61.0938 | 28.71 | sq ft | 17.21 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-28 | 145666
C34-S246033 | 26003H | 1453J | LP1Y-N2(100)-180043-01-2 | LP1Y-N2(100)-180043-01 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180043 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180043 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 9 | 2 | 25.1738 | 15.67 | sq ft | 6.67 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Roberto Tobias (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 100% | 2026-04-02 | 2026-03-31 | 2026-04-02 | 100% | 2026-04-02 | 144102 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246035 | 26003H | 1455J | LP1Y-N2(100)-180045-02-2 | LP1Y-N2(100)-180045-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180045 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180045 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246034 | 26003H | 1454J | LP1Y-N2(100)-180045-02-1 | LP1Y-N2(100)-180045-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180045 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180045 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 28.745 | 14.23 | sq ft | 9.73 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | Carlos Guillen | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144703 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246037 | 26003H | 1457J | LP1Y-N2(100)-180046-02-2 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 21.0513 | 8.64 | sq ft | 7.14 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142960 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246036 | 26003H | 1456J | LP1Y-N2(100)-180046-02-1 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 43.4738 | 23.38 | sq ft | 11.88 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 86% |  |  |  | 43%
C34-S246038 | 26003H | 1458J | LP1Y-N2(100)-180046-02-3 | LP1Y-N2(100)-180046-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180046 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180046 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246039 | 26003H | 1459J | LP1Y-N2(100)-180047-02-1 | LP1Y-N2(100)-180047-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180047 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180047 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 42.58 | 23.04 | sq ft | 11.54 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | [6 empty] | 71% |  |  |  | 0%
C34-S246040 | 26003H | 1460J | LP1Y-N2(100)-180047-02-2 | LP1Y-N2(100)-180047-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180047 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180047 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246044 | 26003H | 1464J | LP1Y-N2(100)-180050-02-1 | LP1Y-N2(100)-180050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180050 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180050 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 26.1075 | 16.14 | sq ft | 6.14 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | [6 empty] | 83% |  |  |  | 0%
C34-S246045 | 26003H | 1465J | LP1Y-N2(100)-180050-02-2 | LP1Y-N2(100)-180050-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180050 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180050 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246046 | 26003H | 1466J | LP1Y-N2(100)-180087-01-1 | LP1Y-N2(100)-180087-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.25 | 8 | 4.25 | 56.5325 | 27.7 | sq ft | 15.2 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-13 | 2026-04-22 | 100% | 2026-04-22 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145281 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246047 | 26003H | 1467J | LP1Y-N2(100)-180087-04-1 | LP1Y-N2(100)-180087-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 42.4075 | 20.3 | sq ft | 11.8 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144702 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246048 | 26003H | 1468J | LP1Y-N2(100)-180087-04-2 | LP1Y-N2(100)-180087-04 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2(100) (315) E 180087 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180087 |  | TFS00D002YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 9 | 2 | 20.7325 | 13.99 | sq ft | 4.99 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Roberto Tobias (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-31 | 2026-03-30 | 2026-03-31 | 2026-03-28 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143957 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246049 | 26003H | 1469J | LP1Y-N2(100)-180088-02-1 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246050 | 26003H | 1470J | LP1Y-N2(100)-180088-02-2 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 18.7413 | 9.1 | sq ft | 4.6 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142897 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246051 | 26003H | 1471J | LP1Y-N2(100)-180088-02-3 | LP1Y-N2(100)-180088-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.7413 | 12.6 | sq ft | 9.6 | ft | 2026-02-13 |  |  |  |  | 2026-03-09 | Jacob Perez | 2026-03-09 | George Allahverdian | 2026-03-09 | Jacob Perez | 2026-03-09 | Jacob Perez | 2026-03-09 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145201 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246052 | 26003H | 1472J | LP1Y-N2(100)-180088-04-1 | LP1Y-N2(100)-180088-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 33.3538 | 19.55 | sq ft | 8.05 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Edgar Castaneda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145207 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246053 | 26003H | 1473J | LP1Y-N2(100)-180088-04-2 | LP1Y-N2(100)-180088-04 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 180088 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180088 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246992 | 26003H | 1474J-L1 | LP1Y-N2(100)-180089-01-1-L1 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez | 2026-03-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144645 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246055 | 26003H | 1475J | LP1Y-N2(100)-180089-01-2 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 24.2 | 10.5 | sq ft | 7.5 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% |  |  |  | 75%
C34-S246054 | 26003H | 1474J | LP1Y-N2(100)-180089-01-1 | LP1Y-N2(100)-180089-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2(100) (315) E 180089 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180089 |  | TFS00D006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246993 | 26003H | 1476J-L1 | LP1Y-N2(100)-180091-01-1-L1 | LP1Y-N2(100)-180091-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2(100) (315) E 180091 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180091 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246056 | 26003H | 1476J | LP1Y-N2(100)-180091-01-1 | LP1Y-N2(100)-180091-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2(100) (315) E 180091 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180091 |  | TFS00D007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 40 | 40 | 0 | 212.7328 | 91.87 | sq ft | 11.37 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246057 | 26003H | 1477J | LP1Y-N2(100)-181006-02-1 | LP1Y-N2(100)-181006-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181006 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181006 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 88.0825 | 35.36 | sq ft | 30.86 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% |  |  |  | 40%
C34-S246058 | 26003H | 1478J | LP1Y-N2(100)-181006-02-2 | LP1Y-N2(100)-181006-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181006 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181006 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 92.5173 | 53.77 | sq ft | 19.27 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246060 | 26003H | 1480J | LP1Y-N2(100)-181007-02-2 | LP1Y-N2(100)-181007-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181007 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181007 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 92.577 | 53.82 | sq ft | 19.32 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246059 | 26003H | 1479J | LP1Y-N2(100)-181007-02-1 | LP1Y-N2(100)-181007-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181007 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181007 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 91.0525 | 36.49 | sq ft | 31.99 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 80% |  |  |  | 40%
C34-S246065 | 26003H | 1485J | LP1Y-N2(100)-181010-01-5 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 59.1563 | 17.66 | sq ft | 2.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246061 | 26003H | 1481J | LP1Y-N2(100)-181010-01-1 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.0075 | 18.76 | sq ft | 15.76 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-20 | 2026-03-20 | 2026-03-20 |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% |  |  |  | 0%
C34-S246063 | 26003H | 1483J | LP1Y-N2(100)-181010-01-3 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 55.4267 | 40.67 | sq ft | 6.17 | ft | 2026-02-13 |  |  |  |  | 2026-03-06 | Jacob Perez | 2026-03-06 | George Allahverdian | 2026-03-06 | Jacob Perez | 2026-03-06 | Jacob Perez | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246064 | 26003H | 1484J | LP1Y-N2(100)-181010-01-4 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 35.3095 | 30.89 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246062 | 26003H | 1482J | LP1Y-N2(100)-181010-01-2 | LP1Y-N2(100)-181010-01 | 2 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) (108) 181010 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181010 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 31.0375 | 13.76 | sq ft | 10.76 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144771
C34-S246067 | 26003H | 1487J | LP1Y-N2(100)-181076-02-2 | LP1Y-N2(100)-181076-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181076 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181076 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 72.8313 | 27.06 | sq ft | 8.06 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246066 | 26003H | 1486J | LP1Y-N2(100)-181076-02-1 | LP1Y-N2(100)-181076-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181076 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181076 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.7163 | 10.66 | sq ft | 3.66 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S246068 | 26003H | 1488J | LP1Y-N2(100)-181077-01-1 | LP1Y-N2(100)-181077-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181077 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181077 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 82.6063 | 32.41 | sq ft | 11.91 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246069 | 26003H | 1489J | LP1Y-N2(100)-181077-01-2 | LP1Y-N2(100)-181077-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181077 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181077 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.9213 | 10.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-16 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 67% |  |  |  | 33%
C34-S246071 | 26003H | 1491J | LP1Y-N2(100)-181078-01-2 | LP1Y-N2(100)-181078-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181078 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181078 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 68.775 | 25.52 | sq ft | 6.52 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246070 | 26003H | 1490J | LP1Y-N2(100)-181078-01-1 | LP1Y-N2(100)-181078-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181078 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181078 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 44.0713 | 20.93 | sq ft | 12.43 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-03-06 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246072 | 26003H | 1492J | LP1Y-N2(100)-181082-01-1 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | 2026-04-06 | 2026-04-06 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 72.1188 | 27.98 | sq ft | 26.48 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-04-08 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 33%
C34-S246074 | 26003H | 1494J | LP1Y-N2(100)-181082-01-3 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 61.3638 | 22.71 | sq ft | 3.71 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246073 | 26003H | 1493J | LP1Y-N2(100)-181082-01-2 | LP1Y-N2(100)-181082-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181082 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181082 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 72.0663 | 32.2 | sq ft | 22.2 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255914 | 26003H | 1497JX | LP1Y-N2(100)-181090-02-4 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 43.7663 | 17.24 | sq ft | 15.74 | ft | 2026-02-13 | [12 empty] | 2026-04-15 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145568
C34-S246075 | 26003H | 1495J | LP1Y-N2(100)-181090-02-1 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 7 | 7 | 0 | 31.5545 | 27.6 | sq ft | 0.6 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246077 | 26003H | 1497J | LP1Y-N2(100)-181090-02-3 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | 2026-04-09 | 2026-04-15 | released |  |  | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 36.3725 | 15.78 | sq ft | 12.78 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-04-15 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-25 | 145564
C34-S246076 | 26003H | 1496J | LP1Y-N2(100)-181090-02-2 | LP1Y-N2(100)-181090-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181090 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 58.1669 | 43.73 | sq ft | 6.23 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246994 | 26003H | 1498J-L1 | LP1Y-N2(100)-181104-01-1-L1 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145580
C34-S246079 | 26003H | 1499J | LP1Y-N2(100)-181104-01-2 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | 2026-04-22 | 2026-04-23 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 26.4 | 11.33 | sq ft | 8.33 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-04-23 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-04-24 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  | 33% |  |  |  | 33%
C34-S246078 | 26003H | 1498J | LP1Y-N2(100)-181104-01-1 | LP1Y-N2(100)-181104-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2(100) (315) E 181104 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181104 |  | TFS00E006YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 76.04 | 26.5 | sq ft | 9.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-10 | George Allahverdian | 2026-03-10 | Jacob Perez | 2026-03-10 | Jacob Perez | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246080 | 26003H | 1500J | LP1Y-N2(100)-181105-01-1 | LP1Y-N2(100)-181105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) E 181105 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 108.4513 | 34.35 | sq ft | 3.35 | ft | 2026-02-13 |  |  |  |  | 2026-03-10 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246081 | 26003H | 1501J | LP1Y-N2(100)-181105-02-1 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 13.78 | 8.92 | sq ft | 3.42 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246082 | 26003H | 1502J | LP1Y-N2(100)-181105-02-2 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 76.8213 | 24.43 | sq ft | 9.93 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246995 | 26003H | 1501J-L1 | LP1Y-N2(100)-181105-02-1-L1 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246083 | 26003H | 1503J | LP1Y-N2(100)-181105-02-3 | LP1Y-N2(100)-181105-02 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 181105 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181105 |  | TFS00E007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 39.215 | 16.85 | sq ft | 12.35 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143748
C34-S246084 | 26003H | 1504D | LP1Y-N2-101511-01-1 | LP1Y-N2-101511-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 1" DUP N2 (344) (108) 101511 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101511 |  | TFS00D005YSPP |  | 344-N2 | NONE | 1" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14 |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246085 | 26003H | 1505D | LP1Y-N2-101511-01-2 | LP1Y-N2-101511-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 1" DUP N2 (344) (108) 101511 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101511 |  | TFS00D005YSPP |  | 344-N2 | NONE | 1" | 2205 | 5 | 5 | 0 | 10.9945 | 10.39 | sq ft | 4.39 | ft | 2026-02-13 | CD: 2026-03-09; CL: Jacob Perez; DD: 2026-03-09; DL: George Allahverdian | 2026-03-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246086 | 26003H | 1506J | LP1Y-N2-101613-01-1 | LP1Y-N2-101613-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 1" SS N2 (315) (108) 101613 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101613 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246087 | 26003H | 1507J | LP1Y-N2-101613-01-2 | LP1Y-N2-101613-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS N2 (315) (108) 101613 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101613 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 6 | 4 | 2 | 7.3519 | 11.04 | sq ft | 3.54 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% |  |  |  | 0%
C34-S246088 | 26003H | 1508J | LP1Y-N2-101713-01-1 | LP1Y-N2-101713-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 1" SS N2 (315) (108) 101713 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101713 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-10; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246089 | 26003H | 1509J | LP1Y-N2-101713-01-2 | LP1Y-N2-101713-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS N2 (315) (108) 101713 | N2 |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101713 |  | TFS00D005YSPP |  | 315-N2 | NONE | 1" | 316 SS | 6 | 4 | 2 | 7.4253 | 11.09 | sq ft | 3.59 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S246090 | 26003H | 1510J | LP1Y-N2-102112-01-1 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246996 | 26003H | 1510J-L1 | LP1Y-N2-102112-01-1-L1 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 2.38 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144090 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246997 | 26003H | 1510J-L2 | LP1Y-N2-102112-01-1-L2 | LP1Y-N2-102112-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 1" SS N2 (315) 102112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102112 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0.5 | 0 | 0.5 | 0.95 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-11 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 0%
C34-S246091 | 26003H | 1511J | LP1Y-N2-102212-01-1 | LP1Y-N2-102212-01 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 1" SS N2 (315) 102212 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102212 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246998 | 26003H | 1511J-L1 | LP1Y-N2-102212-01-1-L1 | LP1Y-N2-102212-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 1" SS N2 (315) 102212 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102212 |  | TFS00D006YSPP |  | 315-N2 | NONE | 1" | 316 SS | 0 | 0 | 0 | 2.38 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144091 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246092 | 26003H | 1512J | LP1Y-N2-180029-01-1 | LP1Y-N2-180029-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 33.75 | 31.5 | 2.25 | 71.177 | 55.51 | sq ft | 7.01 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246093 | 26003H | 1513J | LP1Y-N2-180029-01-2 | LP1Y-N2-180029-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 57.1763 | 24.91 | sq ft | 16.41 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246095 | 26003H | 1515J | LP1Y-N2-180029-02-2 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.04 | 8.58 | sq ft | 0.58 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249768 | 26003H | 1514JX | LP1Y-N2-180029-02-1X | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 35.4513 | 16.68 | sq ft | 8.18 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246096 | 26003H | 1516J | LP1Y-N2-180029-02-3 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.4536 | 29.16 | sq ft | 3.16 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246094 | 26003H | 1514J | LP1Y-N2-180029-02-1 | LP1Y-N2-180029-02 | 0 | N | PRIORITY-1 | 2026-03-06 | 2026-03-09 | released |  |  | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180029 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180029 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 2 | 2 | 0 | 29.9613 | 12.02 | sq ft | 10.52 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-30 | 2026-03-30 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143835
C34-S246098 | 26003H | 1518J | LP1Y-N2-180070-01-2 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144848 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246099 | 26003H | 1519J | LP1Y-N2-180070-01-3 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-18 | 144767, 144990 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246097 | 26003H | 1517J | LP1Y-N2-180070-01-1 | LP1Y-N2-180070-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180070 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180070 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 10 | 1 | 20.4745 | 20.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Carlos Guillen | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-23 | 2026-04-17 | 2026-04-22 | 2026-04-15 | 2026-04-22 | 100% | 2026-04-22 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145283 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246100 | 26003H | 1520J | LP1Y-N2-180072-01-1 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246101 | 26003H | 1521J | LP1Y-N2-180072-01-2 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145271 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246102 | 26003H | 1522J | LP1Y-N2-180072-01-3 | LP1Y-N2-180072-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180072 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180072 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-13 | 2026-04-17 | 100% |  | 2026-04-14 |  | 80%
C34-S246103 | 26003H | 1523J | LP1Y-N2-180073-01-1 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246104 | 26003H | 1524J | LP1Y-N2-180073-01-2 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S246105 | 26003H | 1525J | LP1Y-N2-180073-01-3 | LP1Y-N2-180073-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180073 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180073 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144772 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246106 | 26003H | 1526J | LP1Y-N2-180074-01-1 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246107 | 26003H | 1527J | LP1Y-N2-180074-01-2 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.1575 | 9.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S246108 | 26003H | 1528J | LP1Y-N2-180074-01-3 | LP1Y-N2-180074-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180074 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180074 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 19.1138 | 12.21 | sq ft | 2.21 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-05-01 | 145943, 145992
C34-S246109 | 26003H | 1529J | LP1Y-N2-180075-01-1 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246111 | 26003H | 1531J | LP1Y-N2-180075-01-3 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144774 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246110 | 26003H | 1530J | LP1Y-N2-180075-01-2 | LP1Y-N2-180075-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180075 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180075 |  | TFS00D005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145571 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246112 | 26003H | 1532J | LP1Y-N2-180076-01-1 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-10; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246113 | 26003H | 1533J | LP1Y-N2-180076-01-2 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian | 2026-03-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S246114 | 26003H | 1534J | LP1Y-N2-180076-01-3 | LP1Y-N2-180076-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS N2 (315) E 180076 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180076 |  | TFS00D006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-10; DL: George Allahverdian; ED: 2026-03-10; EL: Jacob Perez; FD: 2026-03-10; FL: Jacob Perez | 2026-03-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 |  |  |  | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% |  |  |  | 0%
C34-S246115 | 26003H | 1535J | LP1Y-N2-180094-01-1 | LP1Y-N2-180094-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 33.75 | 31.5 | 2.25 | 69.867 | 53.76 | sq ft | 9.26 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246118 | 26003H | 1538J | LP1Y-N2-180094-02-3 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 10 | 10 | 0 | 19.8 | 9.5 | sq ft | 5 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Omar Puente | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144481
C34-S246119 | 26003H | 1539J | LP1Y-N2-180094-02-4 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 52.7313 | 21.31 | sq ft | 18.31 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-16 | 142942
C34-S246120 | 26003H | 1540J | LP1Y-N2-180094-02-5 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 66.5775 | 27.22 | sq ft | 22.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-17 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-03-17 | 2026-03-17 | 2026-03-17 | 100% | 2026-03-17 | 142959
C34-S246117 | 26003H | 1537J | LP1Y-N2-180094-02-2 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8 | 8 | 0 | 44.385 | 18.81 | sq ft | 14.31 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144132
C34-S246999 | 26003H | 1536JA | LP1Y-N2-180094-02-6 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 1 | 0 | 1 | 2.22 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246116 | 26003H | 1536J | LP1Y-N2-180094-02-1 | LP1Y-N2-180094-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 | 2026-08-24 |  | LP1Y 2" SS N2 (315) E 180094 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180094 |  | TFS00D007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 11 | 0 | 33.8561 | 16.96 | sq ft | 10.46 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | [6 empty] | 67% |  |  |  | 0%
C34-S246124 | 26003H | 1544J | LP1Y-N2-180095-01-4 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.6736 | 29.24 | sq ft | 3.24 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246121 | 26003H | 1541J | LP1Y-N2-180095-01-1 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 35.1588 | 13.98 | sq ft | 12.48 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-12 | Passed | No | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145202
C34-S246123 | 26003H | 1543J | LP1Y-N2-180095-01-3 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.59 | 8.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246122 | 26003H | 1542J | LP1Y-N2-180095-01-2 | LP1Y-N2-180095-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 180095 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180095 |  | TFS00D001YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 25.895 | 13.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246126 | 26003H | 1546J | LP1Y-N2-180099-01-2 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 144909 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246127 | 26003H | 1547J | LP1Y-N2-180099-01-3 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 14.59 | 10.5 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-27 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-27 | 2026-04-14 | 2026-04-27 | 100% | 2026-04-29 | 145809
C34-S246125 | 26003H | 1545J | LP1Y-N2-180099-01-1 | LP1Y-N2-180099-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS N2 (315) E 180099 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180099 |  | TFS00D002YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 10 | 1 | 20.4745 | 20.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Carlos Guillen | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-24 | 2026-04-17 | 2026-04-23 | 2026-04-15 | 2026-04-23 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-28 | 145667
C34-S246128 | 26003H | 1548J | LP1Y-N2-181066-01-1 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246130 | 26003H | 1550J | LP1Y-N2-181066-01-3 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian; ED: 2026-03-16; EL: Jacob Perez; FD: 2026-03-16; FL: Jacob Perez | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246129 | 26003H | 1549J | LP1Y-N2-181066-01-2 | LP1Y-N2-181066-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181066 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181066 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246132 | 26003H | 1552J | LP1Y-N2-181084-01-2 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S246133 | 26003H | 1553J | LP1Y-N2-181084-01-3 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-11 | Jacob Perez | 2026-03-11 | George Allahverdian | 2026-03-11 | Jacob Perez | 2026-03-11 | Jacob Perez | 2026-03-11 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145567
C34-S246131 | 26003H | 1551J | LP1Y-N2-181084-01-1 | LP1Y-N2-181084-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181084 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181084 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246134 | 26003H | 1554J | LP1Y-N2-181117-01-1 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246136 | 26003H | 1556J | LP1Y-N2-181117-01-3 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-27 | 2026-04-22 | 2026-04-22 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145687
C34-S246135 | 26003H | 1555J | LP1Y-N2-181117-01-2 | LP1Y-N2-181117-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS N2 (315) E 181117 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181117 |  | TFS00E006YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145197
C34-S246137 | 26003H | 1557J | LP1Y-N2-181118-01-1 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246139 | 26003H | 1559J | LP1Y-N2-181118-01-3 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246138 | 26003H | 1558J | LP1Y-N2-181118-01-2 | LP1Y-N2-181118-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS N2 (315) E 181118 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181118 |  | TFS00E007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246140 | 26003H | 1560J | LP1Y-NAOH50-013012-17-1 | LP1Y-NAOH50-013012-17 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 013012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-013012 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 16 | 16 | 0 | 100.6067 | 23.51 | sq ft | 12.76 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 144279
C34-S246142 | 26003H | 1562J | LP1Y-NAOH50-016002-01-2 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 4.25 | 2 | 2.25 | 13.4682 | 16.13 | sq ft | 4.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian; ED: 2026-03-25; EL: Jacob Perez | 2026-04-09 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 0%
C34-S246141 | 26003H | 1561J | LP1Y-NAOH50-016002-01-1 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 4.7025 | 8.25 | sq ft | 1.25 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143873 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246144 | 26003H | 1564J | LP1Y-NAOH50-016002-01-4 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12 | 12 | 0 | 47.7575 | 21.43 | sq ft | 15.43 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Roberto Tobias (WF) | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145220
C34-S246143 | 26003H | 1563J | LP1Y-NAOH50-016002-01-3 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 5 | 5 | 0 | 16.1881 | 12.98 | sq ft | 5.48 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143950 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247000 | 26003H | 1561JA | LP1Y-NAOH50-016002-01-5 | LP1Y-NAOH50-016002-01 | 1 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 016002 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016002 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-24 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S246147 | 26003H | 1567J | LP1Y-NAOH50-016004-03-3 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 4.25 | 2 | 2.25 | 10.6832 | 13.13 | sq ft | 4.13 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 |  |  |  | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% |  |  |  | 0%
C34-S246145 | 26003H | 1565J | LP1Y-NAOH50-016004-03-1 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.1913 | 16.56 | sq ft | 13.56 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145601, 145602 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246146 | 26003H | 1566J | LP1Y-NAOH50-016004-03-2 | LP1Y-NAOH50-016004-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016004 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016004 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.2758 | 16.13 | sq ft | 9.63 | ft | 2026-02-13 | CD: 2026-03-11; CL: Jacob Perez; DD: 2026-03-11; DL: George Allahverdian | 2026-03-11 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 |  |  |  | 83% |  |  |  | 67%
C34-S246148 | 26003H | 1568J | LP1Y-NAOH50-016009-01-1 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 49.4138 | 24.92 | sq ft | 11.42 | ft | 2026-02-13 |  |  |  |  | 2026-03-12 | Bruno Graterol | 2026-03-12 | George Allahverdian | 2026-03-16 | Jacob Perez | 2026-03-16 | Jacob Perez | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246151 | 26003H | 1571J | LP1Y-NAOH50-016009-01-4 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.97 | 18.46 | sq ft | 16.96 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 |  |  | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 50% |  |  |  | 50%
C34-S246149 | 26003H | 1569J | LP1Y-NAOH50-016009-01-2 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.1263 | 8.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246150 | 26003H | 1570J | LP1Y-NAOH50-016009-01-3 | LP1Y-NAOH50-016009-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 016009 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016009 |  | TFS00E007YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 39.8788 | 17.69 | sq ft | 10.69 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246152 | 26003H | 1572J | LP1Y-NAOH50-100203-01-1 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 8 | 8 | 0 | 65.0289 | 14.77 | sq ft | 10.81 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144483 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247001 | 26003H | 1572J-L1 | LP1Y-NAOH50-100203-01-1-L1 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143090 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246153 | 26003H | 1573J | LP1Y-NAOH50-100203-01-2 | LP1Y-NAOH50-100203-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 20 | 20 | 0 | 72.8638 | 22.3 | sq ft | 9.29 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 144868 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246154 | 26003H | 1574J | LP1Y-NAOH50-100203-02-1 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 4 | 4 | 0 | 38.0442 | 8.41 | sq ft | 3.17 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Roberto Tobias (WF) | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143828 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S247002 | 26003H | 1574JA | LP1Y-NAOH50-100203-02-3 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143834 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246155 | 26003H | 1575J | LP1Y-NAOH50-100203-02-2 | LP1Y-NAOH50-100203-02 | 1 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 100203 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100203 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 23 | 18 | 5 | 89.6373 | 26.99 | sq ft | 6.71 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247003 | 26003H | 1576J-L1 | LP1Y-NAOH50-100204-01-1-L1 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 143587 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246156 | 26003H | 1576J | LP1Y-NAOH50-100204-01-1 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 12.0929 | 2.79 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-25 | 143474 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246158 | 26003H | 1578J | LP1Y-NAOH50-100204-01-3 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 13.5 | 12 | 1.5 | 40.738 | 11.71 | sq ft | 2.21 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian; ED: 2026-04-01; EL: Jacob Perez | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-07 | N/A | N/A | Roberto Tobias (WF) | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144359 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246159 | 26003H | 1579J | LP1Y-NAOH50-100204-01-4 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 9 | 8 | 1 | 32.967 | 13.7 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 0%
C34-S246157 | 26003H | 1577J | LP1Y-NAOH50-100204-01-2 | LP1Y-NAOH50-100204-01 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 9 | 7 | 2 | 30.4791 | 12.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-07 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 |  | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 |  | 2026-04-30 | 2026-04-29 |  |  | 80% |  |  |  | 20%
C34-S246160 | 26003H | 1580J | LP1Y-NAOH50-100204-02-1 | LP1Y-NAOH50-100204-02 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 20 | 17 | 3 | 82.3069 | 26.44 | sq ft | 8.44 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-23 | 2026-04-14 | 2026-04-23 | 2026-04-13 | 2026-04-23 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-27 | 145629
C34-S246161 | 26003H | 1581J | LP1Y-NAOH50-100204-05-1 | LP1Y-NAOH50-100204-05 | 2 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 21 | 20 | 1 | 45.6256 | 17.06 | sq ft | 2.56 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-04-29 |  | 89% |  |  |  | 0%
C34-S246162 | 26003H | 1582J | LP1Y-NAOH50-100204-06-1 | LP1Y-NAOH50-100204-06 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 56.6558 | 13.08 | sq ft | 11.58 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-20 | 2026-03-20 | 2026-03-18 | 2026-03-18 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143839 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246163 | 26003H | 1583J | LP1Y-NAOH50-100204-06-2 | LP1Y-NAOH50-100204-06 | 2 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100204 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100204 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 15 | 15 | 0 | 73.8505 | 17.05 | sq ft | 12.55 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143970 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246165 | 26003H | 1585J | LP1Y-NAOH50-100206-01-2 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 7 | 7 | 0 | 35.4588 | 18.9 | sq ft | 11.4 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Omar Puente | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144221 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246166 | 26003H | 1586J | LP1Y-NAOH50-100206-01-3 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 37.9125 | 16.95 | sq ft | 9.95 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-03-18 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145286 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246164 | 26003H | 1584J | LP1Y-NAOH50-100206-01-1 | LP1Y-NAOH50-100206-01 | 2 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 13.25 | 9 | 4.25 | 26.8538 | 19.34 | sq ft | 6.34 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Carlos Guillen | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-29 | 145810
C34-S247004 | 26003H | 1587J-L1 | LP1Y-NAOH50-100206-02-1-L1 | LP1Y-NAOH50-100206-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-19 | 2026-03-19 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143089 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246167 | 26003H | 1587J | LP1Y-NAOH50-100206-02-1 | LP1Y-NAOH50-100206-02 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 3" SS NAOH50 (315) P (108) 100206 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100206 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 8.25 | 4 | 4.25 | 31.645 | 18.1 | sq ft | 6.6 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-23 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-30 | 145907
C34-S246170 | 26003H | 1590J | LP1Y-NAOH50-100207-01-3 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 68.2 | 26.5 | sq ft | 25 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143398 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246168 | 26003H | 1588J | LP1Y-NAOH50-100207-01-1 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.4675 | 10.14 | sq ft | 7.14 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143668 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246169 | 26003H | 1589J | LP1Y-NAOH50-100207-01-2 | LP1Y-NAOH50-100207-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.8688 | 8.86 | sq ft | 5.86 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143677 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246171 | 26003H | 1591J | LP1Y-NAOH50-100207-02-1 | LP1Y-NAOH50-100207-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P (108) 100207 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100207 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 60.5425 | 26.61 | sq ft | 18.61 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-28 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-03-28 | 2026-04-06 | 100% | 2026-04-13 | 2026-03-31 | 2026-04-13 | 100% | 2026-04-13 | 144602 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246173 | 26003H | 1593J | LP1Y-NAOH50-100211-01-2 | LP1Y-NAOH50-100211-01 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P 100211 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100211 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 99.6813 | 40.43 | sq ft | 37.43 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-31 | N/A | N/A | Edgar Castaneda | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 144002 | [40 empty] | 2026-04-18 | 2026-04-18 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246172 | 26003H | 1592J | LP1Y-NAOH50-100211-01-1 | LP1Y-NAOH50-100211-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS NAOH50 (315) P 100211 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100211 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 14 | 14 | 0 | 68.695 | 28.69 | sq ft | 22.69 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143671 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246174 | 26003H | 1594J | LP1Y-NAOH50-101012-02-1 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 31.7763 | 13.37 | sq ft | 10.37 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143667 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246175 | 26003H | 1595J | LP1Y-NAOH50-101012-02-2 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 32.12 | 13.5 | sq ft | 10.5 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% |  |  |  | 33%
C34-S246176 | 26003H | 1596J | LP1Y-NAOH50-101012-02-3 | LP1Y-NAOH50-101012-02 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 11.0275 | 6.18 | sq ft | 1.68 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143451 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246178 | 26003H | 1598J | LP1Y-NAOH50-101012-03-2 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246177 | 26003H | 1597J | LP1Y-NAOH50-101012-03-1 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.7769 | 12.27 | sq ft | 0.77 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144956 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246179 | 26003H | 1599J | LP1Y-NAOH50-101012-03-3 | LP1Y-NAOH50-101012-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 1" SS NAOH50 (315) P (108) 101012 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101012 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 5 | 5 | 0 | 8.7064 | 12.54 | sq ft | 3.54 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-03-16 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144955 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246181 | 26003H | 1601J | LP1Y-NAOH50-101304-03-2 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 4.25 | 2 | 2.25 | 13.43 | 16.33 | sq ft | 4.33 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-09 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S246183 | 26003H | 1603J | LP1Y-NAOH50-101304-03-4 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 52.6488 | 21.94 | sq ft | 17.44 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 60%
C34-S246182 | 26003H | 1602J | LP1Y-NAOH50-101304-03-3 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.6319 | 14.19 | sq ft | 5.19 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% |  |  |  | 80%
C34-S246180 | 26003H | 1600J | LP1Y-NAOH50-101304-03-1 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 4 | 4 | 0 | 4.842 | 8.35 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Omar Puente | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | [6 empty] | 75% |  |  |  | 0%
C34-S247005 | 26003H | 1600JA | LP1Y-NAOH50-101304-03-5 | LP1Y-NAOH50-101304-03 | 1 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS NAOH50 (315) P (108) 101304 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101304 |  | TFS00D003YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-24 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-15 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145081 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246185 | 26003H | 1605D | LP1Y-NAOH50-101515-01-2 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.8542 | 8.78 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246184 | 26003H | 1604D | LP1Y-NAOH50-101515-01-1 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 2" | 2205 | 6 | 6 | 0 | 11.7842 | 12.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246186 | 26003H | 1606D | LP1Y-NAOH50-101515-01-3 | LP1Y-NAOH50-101515-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP NAOH50 (344) P (108) 101515 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101515 |  | TFS00D005YSPP |  | 344-NAOH50 | NONE | 1" | 2205 | 2 | 2 | 0 | 5.7588 | 8.71 | sq ft | 0.71 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246188 | 26003H | 1608J | LP1Y-NAOH50-101704-03-2 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246190 | 26003H | 1610J | LP1Y-NAOH50-101704-03-4 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 9 | 9 | 0 | 26.9375 | 14.64 | sq ft | 8.14 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145600 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246187 | 26003H | 1607J | LP1Y-NAOH50-101704-03-1 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.5566 | 12.11 | sq ft | 0.61 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144954 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246189 | 26003H | 1609J | LP1Y-NAOH50-101704-03-3 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 3 | 3 | 0 | 8.8067 | 9.86 | sq ft | 4.36 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% |  |  |  | 0%
C34-S246191 | 26003H | 1611J | LP1Y-NAOH50-101704-03-5 | LP1Y-NAOH50-101704-03 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 101704 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101704 |  | TFS00D005YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10 | 10 | 0 | 47.9875 | 20.18 | sq ft | 15.68 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 143880 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246193 | 26003H | 1613J | LP1Y-NAOH50-108121-01-2 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 6.25 | 4 | 2.25 | 27.8459 | 23.14 | sq ft | 3.64 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246194 | 26003H | 1614J | LP1Y-NAOH50-108121-01-3 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 0 | 0 | 0 | 25.9087 | 18.38 | sq ft | 18.38 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-25 | 143476
C34-S247006 | 26003H | 1612JA | LP1Y-NAOH50-108121-01-4 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-24 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S246192 | 26003H | 1612J | LP1Y-NAOH50-108121-01-1 | LP1Y-NAOH50-108121-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108121 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108121 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.2597 | 7.34 | sq ft | 1.84 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S247007 | 26003H | 1615JA | LP1Y-NAOH50-108122-01-3 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.03 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-24 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S246196 | 26003H | 1616J | LP1Y-NAOH50-108122-01-2 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 1" | 316 SS | 7.25 | 5 | 2.25 | 52.9983 | 40.97 | sq ft | 21.47 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246195 | 26003H | 1615J | LP1Y-NAOH50-108122-01-1 | LP1Y-NAOH50-108122-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS NAOH50 (315) P (108) 108122 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108122 |  | TFS00E006YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 3 | 3 | 0 | 5.3184 | 7.39 | sq ft | 1.89 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S246203 | 26003H | 1623J | LP1Y-NAOH50-178201-03-1 | LP1Y-NAOH50-178201-03 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P 178201 | NAOH50 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 9 | 3 | 6 | 32.0773 | 27.05 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247009 | 26003H | 1624J-L1 | LP1Y-NAOH50-178202-01-1-L1 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | N/A | N/A | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-19 | 143091 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246204 | 26003H | 1624J | LP1Y-NAOH50-178202-01-1 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 8 | 8 | 0 | 35.1103 | 8.64 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-23 | 143234 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246205 | 26003H | 1625J | LP1Y-NAOH50-178202-01-2 | LP1Y-NAOH50-178202-01 | 2 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 15 | 10 | 5 | 61.1127 | 20.67 | sq ft | 5.18 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246208 | 26003H | 1628J | LP1Y-NAOH50-178202-02-3 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 22.75 | 21 | 1.75 | 47.6663 | 23.43 | sq ft | 3.35 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246207 | 26003H | 1627J | LP1Y-NAOH50-178202-02-2 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 11 | 7 | 4 | 40.7305 | 12.76 | sq ft | 3.8 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Carlos Montoya | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144065 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246206 | 26003H | 1626J | LP1Y-NAOH50-178202-02-1 | LP1Y-NAOH50-178202-02 | 1 | N | PRIORITY-1 | 2026-04-02 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 3 | 0 | 3 | 33.2521 | 7.23 | sq ft | 6.3 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian; ED: 2026-03-25; EL: Jacob Perez; FD: 2026-03-25; FL: Jacob Perez | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-03-27 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144350 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246209 | 26003H | 1629J | LP1Y-NAOH50-178202-03-1 | LP1Y-NAOH50-178202-03 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D002YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 32 | 32 | 0 | 129.0575 | 31.9 | sq ft | 19.08 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Carlos Guillen | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143750 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246211 | 26003H | 1631J | LP1Y-NAOH50-178202-04-2 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 9 | 9 | 0 | 35.8045 | 24.6 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247010 | 26003H | 1630JA | LP1Y-NAOH50-178202-04-6 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | 2026-03-24 | 2026-03-24 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-24 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144278
C34-S246213 | 26003H | 1633J | LP1Y-NAOH50-178202-04-4 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246214 | 26003H | 1634J | LP1Y-NAOH50-178202-04-5 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9 | 13.83 | sq ft | 1.83 | ft | 2026-02-13 |  |  |  |  | 2026-03-18 | Jacob Perez | 2026-03-18 | George Allahverdian | 2026-03-18 | Jacob Perez | 2026-03-18 | Jacob Perez | 2026-03-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246210 | 26003H | 1630J | LP1Y-NAOH50-178202-04-1 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.675 | 2.44 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 143370
C34-S246212 | 26003H | 1632J | LP1Y-NAOH50-178202-04-3 | LP1Y-NAOH50-178202-04 | 1 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246216 | 26003H | 1636J | LP1Y-NAOH50-178202-07-2 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 8 | 4 | 4 | 39.4931 | 9.57 | sq ft | 2.65 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 |  | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 |  |  | 50%
C34-S246215 | 26003H | 1635J | LP1Y-NAOH50-178202-07-1 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 19 | 18 | 1 | 60.84 | 19.8 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246217 | 26003H | 1637J | LP1Y-NAOH50-178202-07-3 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 12 | 12 | 0 | 67.0998 | 19.9 | sq ft | 3.14 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246219 | 26003H | 1639J | LP1Y-NAOH50-178202-07-5 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 12 | 12 | 0 | 70.8228 | 17.34 | sq ft | 11.45 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143676
C34-S246218 | 26003H | 1638J | LP1Y-NAOH50-178202-07-4 | LP1Y-NAOH50-178202-07 | 1 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 4" SS NAOH50 (315) P (108) 178202 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178202 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 4" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-03-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251751 | 26003H | 1640J-L1 | LP1Y-PV-100210-01-1-L1 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-27 | 143670 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246222 | 26003H | 1642J | LP1Y-PV-100210-01-3 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 4 | 4 | 0 | 34.9628 | 8.34 | sq ft | 5.45 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143936 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246220 | 26003H | 1640J | LP1Y-PV-100210-01-1 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 8 | 8 | 0 | 27.0167 | 6.91 | sq ft | 0.42 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143899 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246221 | 26003H | 1641J | LP1Y-PV-100210-01-2 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 12 | 12 | 0 | 32.4467 | 10.51 | sq ft | 0.42 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Carlos Montoya | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143837 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246223 | 26003H | 1643J | LP1Y-PV-100210-01-4 | LP1Y-PV-100210-01 | 2 | N | PRIORITY-1 | 2026-03-31 | 2026-03-31 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 4" SS PV (315) (108) 100210 | PV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100210 |  | TFS00D002YSPP |  | 315-PV | NONE | 4" | 316 SS | 12 | 8 | 4 | 23.7494 | 5.84 | sq ft | 3.27 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | Ramiro Gonzalez | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146038
C34-S247012 | 26003H | 1644J-L1 | LP1Y-PV-100306-01-1-L1 | LP1Y-PV-100306-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS PV (315) P (108) 100306 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100306 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144866 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246224 | 26003H | 1644J | LP1Y-PV-100306-01-1 | LP1Y-PV-100306-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS PV (315) P (108) 100306 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100306 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 11.525 | 7.94 | sq ft | 0.94 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145080 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S246227 | 26003H | 1647J | LP1Y-PV-101062-01-1 | LP1Y-PV-101062-01 | 2 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101062 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246228 | 26003H | 1648J | LP1Y-PV-101062-01-2 | LP1Y-PV-101062-01 | 2 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101062 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.4406 | 13.81 | sq ft | 1.31 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145912
C34-S246229 | 26003H | 1649J | LP1Y-PV-101063-01-1 | LP1Y-PV-101063-01 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246230 | 26003H | 1650J | LP1Y-PV-101063-01-2 | LP1Y-PV-101063-01 | 1 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.4406 | 13.81 | sq ft | 1.31 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145911
C34-S246233 | 26003H | 1653J | LP1Y-PV-101063-03-3 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246232 | 26003H | 1652J | LP1Y-PV-101063-03-2 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 16 | 16 | 0 | 78.2702 | 19.32 | sq ft | 11.6 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Henrique Barahona | 2026-03-24 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-26 | 143612 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S246231 | 26003H | 1651J | LP1Y-PV-101063-03-1 | LP1Y-PV-101063-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PV (315) (108) 101063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101063 |  | TFS00D005YSPP |  | 315-PV | NONE | 4" | 316 SS | 8 | 8 | 0 | 52.085 | 12 | sq ft | 8.5 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-03-16 | 2026-03-16 | Passed | No | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-19 | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143752 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246234 | 26003H | 1654J | LP1Y-PV-101065-01-1 | LP1Y-PV-101065-01 | 1 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101065 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101065 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246235 | 26003H | 1655J | LP1Y-PV-101065-01-2 | LP1Y-PV-101065-01 | 1 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101065 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101065 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 12 | 8 | 4 | 33.4406 | 13.81 | sq ft | 1.31 | ft | 2026-02-13 | CD: 2026-03-12; CL: Bruno Graterol; DD: 2026-03-12; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 2026-04-28 |  |  | 83% |  |  |  | 0%
C34-S246236 | 26003H | 1656D | LP1Y-PV-101510-01-1 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 21 | 21 | 0 | 116.9636 | 30.11 | sq ft | 20.11 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247013 | 26003H | 1656D-L1 | LP1Y-PV-101510-01-1-L1 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246237 | 26003H | 1657D | LP1Y-PV-101510-01-2 | LP1Y-PV-101510-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 18 | 18 | 0 | 69.1227 | 17.02 | sq ft | 8.52 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250444 | 26003H | 1660JA | LP1Y-PV-101518-01-1A | LP1Y-PV-101518-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 4 | 4 | 0 | 8.6027 | 13.33 | sq ft | 2.33 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144444 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251749 | 26003H | 1663JX | LP1Y-PV-101612-01-2X | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 3 | 3 | 0 | 39.5388 | 9.13 | sq ft | 7.63 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Carlos Montoya | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144705 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246242 | 26003H | 1662J | LP1Y-PV-101612-01-1 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 15 | 15 | 0 | 101.2593 | 25.43 | sq ft | 19.43 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144409 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246244 | 26003H | 1664J | LP1Y-PV-101612-01-3 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 32.3528 | 8.53 | sq ft | 3.03 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 144001 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S246243 | 26003H | 1663J | LP1Y-PV-101612-01-2 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | 2026-03-12 | 2026-03-23 | released |  |  | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 3 | 3 | 0 | 54.9193 | 12.68 | sq ft | 11.18 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Carlos Montoya | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 144547 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247014 | 26003H | 1662JA | LP1Y-PV-101612-01-4 | LP1Y-PV-101612-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-07 | 144216 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247019 | 26003H | 1667JA | LP1Y-PV-101617-01-3 | LP1Y-PV-101617-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 3 | 3 | 0 | 6.215 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144364 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247211 | 26003H | 1673J | LP1Y-PV-101712-01-5 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 32.4655 | 8.55 | sq ft | 3.05 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143621 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S247209 | 26003H | 1671J | LP1Y-PV-101712-01-3 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 179.7 | 41.5 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; ED: 2026-03-18; EL: Jacob Perez; FD: 2026-03-18; FL: Jacob Perez | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | N/A | N/A | Roberto Tobias (WF) | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% |  |  |  | 0%
C34-S247210 | 26003H | 1672J | LP1Y-PV-101712-01-4 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 3 | 3 | 0 | 129.4264 | 29.89 | sq ft | 29.89 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | Roberto Tobias (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% |  |  |  | 0%
C34-S247207 | 26003H | 1669J | LP1Y-PV-101712-01-1 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-23 | 143274 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S247208 | 26003H | 1670J | LP1Y-PV-101712-01-2 | LP1Y-PV-101712-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 15 | 15 | 0 | 113.3697 | 28.22 | sq ft | 22.22 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145210
C34-S247213 | 26003H | 1675J | LP1Y-PV-101712-02-2 | LP1Y-PV-101712-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247212 | 26003H | 1674J | LP1Y-PV-101712-02-1 | LP1Y-PV-101712-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101712 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101712 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247214 | 26003H | 1676J | LP1Y-PV-101717-01-1 | LP1Y-PV-101717-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 24 | 24 | 0 | 84.5375 | 18.07 | sq ft | 5.54 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian; ED: 2026-04-01; EL: Jacob Perez | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Henrique Barahona | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144354 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247217 | 26003H | 1679J | LP1Y-PV-102061-01-1 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 37.84 | 15.67 | sq ft | 12.67 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S247218 | 26003H | 1680J | LP1Y-PV-102061-01-2 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 56.8838 | 22.21 | sq ft | 20.71 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144411 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247219 | 26003H | 1681J | LP1Y-PV-102061-01-3 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247220 | 26003H | 1682J | LP1Y-PV-102061-01-4 | LP1Y-PV-102061-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102061 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 22.3713 | 15.35 | sq ft | 1.85 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145179 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247221 | 26003H | 1683J | LP1Y-PV-102062-01-1 | LP1Y-PV-102062-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247222 | 26003H | 1684J | LP1Y-PV-102062-01-2 | LP1Y-PV-102062-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 22.1788 | 15.28 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-18 | 144987 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247224 | 26003H | 1686J | LP1Y-PV-102062-02-2 | LP1Y-PV-102062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 16 | 14 | 2 | 51.745 | 22.94 | sq ft | 16.94 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-09 | 2026-04-15 | 100% |  | 2026-04-10 |  | 88%
C34-S247223 | 26003H | 1685J | LP1Y-PV-102062-02-1 | LP1Y-PV-102062-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PV (315) 102062 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102062 |  | TFS00D006YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 54.4638 | 21.96 | sq ft | 18.96 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144508 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247225 | 26003H | 1687J | LP1Y-PV-108061-01-1 | LP1Y-PV-108061-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 12 | 12 | 0 | 39.7788 | 17.73 | sq ft | 11.73 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Roberto Tobias (WF) | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | [6 empty] | 67% |  |  |  | 0%
C34-S247226 | 26003H | 1688J | LP1Y-PV-108061-01-2 | LP1Y-PV-108061-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 39.4213 | 15.6 | sq ft | 14.1 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Montoya | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 50%
C34-S247227 | 26003H | 1689J | LP1Y-PV-108061-02-1 | LP1Y-PV-108061-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.8163 | 7.04 | sq ft | 5.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144226
C34-S247229 | 26003H | 1691J | LP1Y-PV-108061-04-2 | LP1Y-PV-108061-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 8 | 8 | 0 | 68.1625 | 21.07 | sq ft | 5.57 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247228 | 26003H | 1690J | LP1Y-PV-108061-04-1 | LP1Y-PV-108061-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108061 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 22.6563 | 14.12 | sq ft | 2.12 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S247230 | 26003H | 1692J | LP1Y-PV-108062-01-1 | LP1Y-PV-108062-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9963 | 13.87 | sq ft | 1.87 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  | 2026-04-29 | 2026-04-29 | 2026-04-27 |  |  | 80% |  |  |  | 20%
C34-S247231 | 26003H | 1693J | LP1Y-PV-108062-01-2 | LP1Y-PV-108062-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.0288 | 21.4 | sq ft | 5.9 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247233 | 26003H | 1695J | LP1Y-PV-108062-02-2 | LP1Y-PV-108062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 48.07 | 19.54 | sq ft | 16.54 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Henrique Barahona | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 67%
C34-S247232 | 26003H | 1694J | LP1Y-PV-108062-02-1 | LP1Y-PV-108062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 108062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108062 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 39.2425 | 15.53 | sq ft | 14.03 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  | N/A | N/A | Omar Puente | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | [6 empty] | 50% |  |  |  | 0%
C34-S247237 | 26003H | 1699J | LP1Y-PV-109061-02-4 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 22.11 | 9.71 | sq ft | 6.71 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-06 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144463
C34-S247234 | 26003H | 1696J | LP1Y-PV-109061-02-1 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 85.0713 | 32.22 | sq ft | 32.22 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247235 | 26003H | 1697J | LP1Y-PV-109061-02-2 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 110.1288 | 34.98 | sq ft | 3.98 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247238 | 26003H | 1700J | LP1Y-PV-109061-02-5 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 8 | 8 | 0 | 54.6288 | 15.36 | sq ft | 2.36 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247236 | 26003H | 1698J | LP1Y-PV-109061-02-3 | LP1Y-PV-109061-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 27.8025 | 11.2 | sq ft | 9.7 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247240 | 26003H | 1702J | LP1Y-PV-109061-03-2 | LP1Y-PV-109061-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 29.27 | 17.29 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247239 | 26003H | 1701J | LP1Y-PV-109061-03-1 | LP1Y-PV-109061-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109061 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 22.1 | 10.29 | sq ft | 4.79 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247241 | 26003H | 1703AB | LP1Y-PV-109062-01-1 | LP1Y-PV-109062-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 14.25 | 13.5 | 0.75 | 42.56 | 23.92 | sq ft | 7.92 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247244 | 26003H | 1706AB | LP1Y-PV-109062-02-3 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | 2026-04-06 | 2026-04-14 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 0 | 0 | 0 | 43.45 | 16.46 | sq ft | 16.46 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-01 | Passed | No | 2026-05-01 | N/A | N/A |  |  | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S247245 | 26003H | 1707AB | LP1Y-PV-109062-02-4 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 10.25 | 9.5 | 0.75 | 44.9388 | 24.15 | sq ft | 9.65 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247243 | 26003H | 1705AB | LP1Y-PV-109062-02-2 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | 2026-04-06 | 2026-04-14 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 4 | 4 | 0 | 31.3088 | 13.19 | sq ft | 10.19 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247242 | 26003H | 1704AB | LP1Y-PV-109062-02-1 | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 8 | 8 | 0 | 59.1013 | 23.89 | sq ft | 8.39 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256295 | 26003H | 1706ABA | LP1Y-PV-109062-02-3X | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  | 0 | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 9.5 | 8 | 1.5 | 87.6973 | 35.39 | sq ft | 19.89 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256294 | 26003H | 1705ABA | LP1Y-PV-109062-02-2X | LP1Y-PV-109062-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 |  | 0 | LP1Y 2" HAST PV (332) (108) 109062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109062 |  | TFS00E007YSPP |  | 332-PV | NONE | 2" | H C22 | 4 | 4 | 0 | 59.18 | 23.08 | sq ft | 21.58 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247246 | 26003H | 1708J | LP1Y-PV-109112-01-1 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247247 | 26003H | 1709J | LP1Y-PV-109112-01-2 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 18 | 18 | 0 | 73.28 | 26.58 | sq ft | 4.08 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247248 | 26003H | 1710J | LP1Y-PV-109112-01-3 | LP1Y-PV-109112-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS PV (315) (108) 109112 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109112 |  | TFS00E007YSPP |  | 315-PV | NONE | 2" | 316 SS | 11 | 11 | 0 | 35.3095 | 30.89 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247249 | 26003H | 1711J | LP1Y-PV-121006-01-1 | LP1Y-PV-121006-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 121006 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121006 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 16 | 16 | 0 | 122.2663 | 38.87 | sq ft | 8.87 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247250 | 26003H | 1712J | LP1Y-PV-121006-02-1 | LP1Y-PV-121006-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PV (315) (108) 121006 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121006 |  | TFS00E006YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 107.03 | 40.54 | sq ft | 40.54 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S247252 | 26003H | 1714J | LP1Y-PVP-102109-01-2 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247254 | 26003H | 1716J | LP1Y-PVP-102109-01-4 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 64.8863 | 27.24 | sq ft | 21.24 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 145246 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247251 | 26003H | 1713J | LP1Y-PVP-102109-01-1 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144644 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247253 | 26003H | 1715J | LP1Y-PVP-102109-01-3 | LP1Y-PVP-102109-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.4788 | 10.32 | sq ft | 8.82 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 50%
C34-S247257 | 26003H | 1719J | LP1Y-PVP-102111-01-1 | LP1Y-PVP-102111-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 3" SS PVP (315) P 102111 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102111 |  | TFS00D006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144449 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247258 | 26003H | 1720J | LP1Y-PVP-102111-01-2 | LP1Y-PVP-102111-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 3" SS PVP (315) P 102111 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102111 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247260 | 26003H | 1722J | LP1Y-PVP-102202-01-2 | LP1Y-PVP-102202-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102202 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102202 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247259 | 26003H | 1721J | LP1Y-PVP-102202-01-1 | LP1Y-PVP-102202-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102202 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102202 |  | TFS00D006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144450 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247261 | 26003H | 1723J | LP1Y-PVP-102209-01-1 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144643 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247264 | 26003H | 1726J | LP1Y-PVP-102209-01-4 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 10 | 10 | 0 | 66 | 27 | sq ft | 22.5 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Roberto Tobias (WF) | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | [6 empty] | 60% |  |  |  | 0%
C34-S247263 | 26003H | 1725J | LP1Y-PVP-102209-01-3 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 25.4788 | 10.32 | sq ft | 8.82 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S247262 | 26003H | 1724J | LP1Y-PVP-102209-01-2 | LP1Y-PVP-102209-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PVP (315) P 102209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102209 |  | TFS00D006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247265 | 26003H | 1727J | LP1Y-PVP-108129-01-1 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144468
C34-S247266 | 26003H | 1728J | LP1Y-PVP-108129-01-2 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 12.0888 | 8.15 | sq ft | 1.15 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145909
C34-S247268 | 26003H | 1730J | LP1Y-PVP-108129-01-4 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 34.0245 | 28.93 | sq ft | 1.93 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247267 | 26003H | 1729J | LP1Y-PVP-108129-01-3 | LP1Y-PVP-108129-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108129 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108129 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 59.16 | 18.33 | sq ft | 2.83 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247269 | 26003H | 1731J | LP1Y-PVP-108231-01-1 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144834
C34-S247270 | 26003H | 1732J | LP1Y-PVP-108231-01-2 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 12.1025 | 8.16 | sq ft | 1.16 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145910, 145941
C34-S247272 | 26003H | 1734J | LP1Y-PVP-108231-01-4 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 34.5595 | 29.06 | sq ft | 2.06 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247271 | 26003H | 1733J | LP1Y-PVP-108231-01-3 | LP1Y-PVP-108231-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PVP (315) P (108) 108231 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108231 |  | TFS00E006YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 58.83 | 18.21 | sq ft | 2.71 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247275 | 26003H | 1737AB | LP1Y-PVP-109213-01-3 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 2" | H C22 | 2 | 2 | 0 | 14.5 | 8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247274 | 26003H | 1736AB | LP1Y-PVP-109213-01-2 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 2" | H C22 | 12 | 12 | 0 | 28.4 | 16.25 | sq ft | 3.75 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247273 | 26003H | 1735AB | LP1Y-PVP-109213-01-1 | LP1Y-PVP-109213-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST PVP (332) P (108) 109213 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109213 |  | TFS00E007YSPP |  | 332-PVP | NONE | 3" | H C22 | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247276 | 26003H | 1738J | LP1Y-PVP-176001-04-1 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S247279 | 26003H | 1741J | LP1Y-PVP-176001-04-4 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 57.4475 | 23.09 | sq ft | 20.09 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247277 | 26003H | 1739J | LP1Y-PVP-176001-04-2 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 14.25 | 10 | 4.25 | 31.2425 | 16.86 | sq ft | 8.36 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247278 | 26003H | 1740J | LP1Y-PVP-176001-04-3 | LP1Y-PVP-176001-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.3688 | 6.11 | sq ft | 4.61 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247280 | 26003H | 1742J | LP1Y-PWP-014002-01-1 | LP1Y-PWP-014002-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247281 | 26003H | 1743J | LP1Y-PWP-014002-01-2 | LP1Y-PWP-014002-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247282 | 26003H | 1744J | LP1Y-PWP-014002-07-1 | LP1Y-PWP-014002-07 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 18 | 18 | 0 | 117.4188 | 23.99 | sq ft | 6.6 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | Henrique Barahona | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144241 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247283 | 26003H | 1745J | LP1Y-PWP-014002-07-2 | LP1Y-PWP-014002-07 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 24 | 24 | 0 | 104.3328 | 21 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144351 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247284 | 26003H | 1746J | LP1Y-PWP-014002-08-1 | LP1Y-PWP-014002-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 33 | 20 | 13 | 218.5816 | 50.39 | sq ft | 16.83 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146036
C34-S247290 | 26003H | 1752J | LP1Y-PWP-014002-11-2 | LP1Y-PWP-014002-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 24 | 24 | 0 | 181.8969 | 36.92 | sq ft | 16.01 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 75%
C34-S247289 | 26003H | 1751J | LP1Y-PWP-014002-11-1 | LP1Y-PWP-014002-11 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 34 | 32 | 2 | 184.6747 | 41.47 | sq ft | 12.32 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Guillen | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144835 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247297 | 26003H | 1759J | LP1Y-PWP-014002-13-2 | LP1Y-PWP-014002-13 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247296 | 26003H | 1758J | LP1Y-PWP-014002-13-1 | LP1Y-PWP-014002-13 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247298 | 26003H | 1760J | LP1Y-PWP-014002-14-1 | LP1Y-PWP-014002-14 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247299 | 26003H | 1761J | LP1Y-PWP-014002-14-2 | LP1Y-PWP-014002-14 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247300 | 26003H | 1762J | LP1Y-PWP-014002-15-1 | LP1Y-PWP-014002-15 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 014002 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247301 | 26003H | 1763J | LP1Y-PWP-014003-01-1 | LP1Y-PWP-014003-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014003 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014003 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247302 | 26003H | 1764J | LP1Y-PWP-014003-01-2 | LP1Y-PWP-014003-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 014003 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014003 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247307 | 26003H | 1769J | LP1Y-PWP-036047-09-2 | LP1Y-PWP-036047-09 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 036047 | PWP |  | 113 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036047 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247306 | 26003H | 1768J | LP1Y-PWP-036047-09-1 | LP1Y-PWP-036047-09 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 036047 | PWP |  | 112 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036047 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247308 | 26003H | 1770J | LP1Y-PWP-036049-01-1 | LP1Y-PWP-036049-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 036049 | PWP |  | 114 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036049 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247309 | 26003H | 1771J | LP1Y-PWP-036049-01-2 | LP1Y-PWP-036049-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 036049 | PWP |  | 115 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036049 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247310 | 26003H | 1772J | LP1Y-PWP-101025-01-1 | LP1Y-PWP-101025-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 116 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 20 | 20 | 0 | 127.2542 | 29.21 | sq ft | 17.51 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Roberto Tobias (WF) | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 80% |  |  |  | 80%
C34-S247311 | 26003H | 1773J | LP1Y-PWP-101025-01-2 | LP1Y-PWP-101025-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 117 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247313 | 26003H | 1775J | LP1Y-PWP-101025-03-2 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 119 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.3411 | 7.83 | sq ft | 1.19 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 144127 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247315 | 26003H | 1777J | LP1Y-PWP-101025-03-4 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 16 | 16 | 0 | 41.3961 | 11.43 | sq ft | 5.03 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144540 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247312 | 26003H | 1774J | LP1Y-PWP-101025-03-1 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 118 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-07 | 144217 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247316 | 26003H | 1778J | LP1Y-PWP-101025-03-5 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 12 | 12 | 0 | 121.9934 | 27.81 | sq ft | 20.18 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Carlos Montoya | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% |  |  |  | 67%
C34-S247314 | 26003H | 1776J | LP1Y-PWP-101025-03-3 | LP1Y-PWP-101025-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101025 | PWP |  | 120 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101025 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247320 | 26003H | 1782J | LP1Y-PWP-101604-01-4 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 18 | 18 | 0 | 61.7859 | 14.28 | sq ft | 1.21 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 144003 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247318 | 26003H | 1780J | LP1Y-PWP-101604-01-2 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 6 | 6 | 0 | 42.6703 | 8.38 | sq ft | 0.93 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Edgar Castaneda | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144070 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247317 | 26003H | 1779J | LP1Y-PWP-101604-01-1 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-08 | 144311 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247319 | 26003H | 1781J | LP1Y-PWP-101604-01-3 | LP1Y-PWP-101604-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 18 | 16 | 2 | 114.7034 | 26.91 | sq ft | 7.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-01 | Jacob Perez | 2026-04-01 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144959 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247325 | 26003H | 1787J | LP1Y-PWP-101606-01-2 | LP1Y-PWP-101606-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 16 | 14 | 2 | 146.7575 | 31.48 | sq ft | 7.54 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-14 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144849 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247324 | 26003H | 1786J | LP1Y-PWP-101606-01-1 | LP1Y-PWP-101606-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 15 | 14 | 1 | 81.825 | 20.18 | sq ft | 1.38 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-28 | N/A | N/A | Omar Puente | 2026-05-01 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  |  |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% |  |  |  | 0%
C34-S247328 | 26003H | 1790J | LP1Y-PWP-101606-02-3 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 30 | 30 | 0 | 198.6484 | 39.71 | sq ft | 15.34 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Edgar Castaneda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144854 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247327 | 26003H | 1789J | LP1Y-PWP-101606-02-2 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 45 | 44 | 1 | 150.1656 | 39.71 | sq ft | 9.78 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-28 |  | 2026-04-28 | 2026-04-29 |  | 2026-04-29 | 2026-05-01 |  |  | 90% |  |  |  | 50%
C34-S247326 | 26003H | 1788J | LP1Y-PWP-101606-02-1 | LP1Y-PWP-101606-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 30 | 30 | 0 | 227.7594 | 45.34 | sq ft | 18.47 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144766 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247331 | 26003H | 1793J | LP1Y-PWP-101606-03-3 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 21 | 18 | 3 | 103.9126 | 21.09 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | N/A | N/A | Aristeo Banda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-09 | 144344 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247330 | 26003H | 1792J | LP1Y-PWP-101606-03-2 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247329 | 26003H | 1791J | LP1Y-PWP-101606-03-1 | LP1Y-PWP-101606-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101606 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101606 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144673 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247332 | 26003H | 1794J | LP1Y-PWP-101607-01-1 | LP1Y-PWP-101607-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 12 | 12 | 0 | 46.4673 | 10.73 | sq ft | 7.73 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144366 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247333 | 26003H | 1795J | LP1Y-PWP-101607-03-1 | LP1Y-PWP-101607-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247334 | 26003H | 1796J | LP1Y-PWP-101607-03-2 | LP1Y-PWP-101607-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 9 | 9 | 0 | 74.7251 | 17.26 | sq ft | 14.26 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144675 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247335 | 26003H | 1797J | LP1Y-PWP-101607-04-1 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-07 | 144218 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247338 | 26003H | 1800J | LP1Y-PWP-101607-04-4 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 6 | 5 | 1 | 26.8022 | 11.22 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145913
C34-S247337 | 26003H | 1799J | LP1Y-PWP-101607-04-3 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 9 | 8 | 1 | 38.9884 | 15.09 | sq ft | 2.59 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-28 |  | 2026-04-28 |  |  |  | 2026-04-28 |  |  | 80% |  |  |  | 0%
C34-S247336 | 26003H | 1798J | LP1Y-PWP-101607-04-2 | LP1Y-PWP-101607-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101607 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101607 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 6 | 6 | 0 | 25.9931 | 7.06 | sq ft | 1.56 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144400 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247339 | 26003H | 1801J | LP1Y-PWP-101609-01-1 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-07 | 144219 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247341 | 26003H | 1803J | LP1Y-PWP-101609-01-3 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247340 | 26003H | 1802J | LP1Y-PWP-101609-01-2 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.2242 | 7.81 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144130 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247343 | 26003H | 1805J | LP1Y-PWP-101609-01-5 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 12 | 12 | 0 | 96.2809 | 22.31 | sq ft | 15.59 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144451 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247342 | 26003H | 1804J | LP1Y-PWP-101609-01-4 | LP1Y-PWP-101609-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101609 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101609 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 16 | 16 | 0 | 42.8278 | 11.74 | sq ft | 5.28 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144367 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247345 | 26003H | 1807J | LP1Y-PWP-101702-03-2 | LP1Y-PWP-101702-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247344 | 26003H | 1806J | LP1Y-PWP-101702-03-1 | LP1Y-PWP-101702-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 24 | 24 | 0 | 215.0281 | 43.33 | sq ft | 19.57 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-01 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144515 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S255915 | 26003H | 1815J-L1 | LP1Y-PWP-101705-01-3-L1 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 |  |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-16 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145011 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S256297 | 26003H | 1814JA | LP1Y-PWP-101705-01-4 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  | 0 | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.5 | 9.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez | 2026-04-20 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247352 | 26003H | 1814J | LP1Y-PWP-101705-01-2 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 18 | 16 | 2 | 96.2034 | 23.21 | sq ft | 9.01 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-10 | 2026-04-13 | 2026-04-10 | 2026-04-14 | 2026-04-24 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145563 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247351 | 26003H | 1813J | LP1Y-PWP-101705-01-1 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 70.9625 | 14.42 | sq ft | 2.79 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144382 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247353 | 26003H | 1815J | LP1Y-PWP-101705-01-3 | LP1Y-PWP-101705-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 6 | 6 | 0 | 43.3484 | 8.51 | sq ft | 1.01 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144383 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247358 | 26003H | 1820D | LP1Y-PWP-101706-02-2 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 22 | 22 | 0 | 91.2106 | 21.56 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247357 | 26003H | 1819D | LP1Y-PWP-101706-02-1 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 36.75 | 32 | 4.75 | 177.0263 | 44.66 | sq ft | 11.98 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian; ED: 2026-04-06; EL: Jacob Perez; FD: 2026-04-06; FL: Jacob Perez | 2026-04-06 | 2026-04-23 | Passed | No | 2026-04-23 |  |  | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247359 | 26003H | 1821D | LP1Y-PWP-101706-02-3 | LP1Y-PWP-101706-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 36 | 36 | 0 | 188.4328 | 38.3 | sq ft | 13.06 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-01 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247360 | 26003H | 1822D | LP1Y-PWP-101706-06-1 | LP1Y-PWP-101706-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 2" | 2205 | 6 | 6 | 0 | 10.88 | 6.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247367 | 26003H | 1829D | LP1Y-PWP-101706-08-1 | LP1Y-PWP-101706-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247368 | 26003H | 1830D | LP1Y-PWP-101706-08-2 | LP1Y-PWP-101706-08 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247369 | 26003H | 1831D | LP1Y-PWP-101706-09-1 | LP1Y-PWP-101706-09 | 0 | N | PRIORITY-1 | 2026-04-06 | 2026-04-14 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 36 | 36 | 0 | 137.0109 | 29.73 | sq ft | 6.8 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-05-02 | 2026-05-02 | 2026-05-01 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256298 | 26003H | 1831DA | LP1Y-PWP-101706-09-3 | LP1Y-PWP-101706-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 |  | 0 | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 14 | 12 | 2 | 79.6981 | 16.23 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez | 2026-04-20 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247370 | 26003H | 1832D | LP1Y-PWP-101706-09-2 | LP1Y-PWP-101706-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 15 | 14 | 1 | 121.8803 | 28.18 | sq ft | 5.43 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247375 | 26003H | 1837J | LP1Y-PWP-101707-01-1 | LP1Y-PWP-101707-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247376 | 26003H | 1838J | LP1Y-PWP-101707-03-1 | LP1Y-PWP-101707-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 15 | 15 | 0 | 78.2256 | 18.06 | sq ft | 13.56 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144352 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247377 | 26003H | 1839J | LP1Y-PWP-101707-03-2 | LP1Y-PWP-101707-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 4" | 316 SS | 30 | 29 | 1 | 51.4545 | 29.6 | sq ft | 3.04 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 |  | 2026-04-30 |  | 2026-04-29 |  | 73% |  |  |  | 55%
C34-S247379 | 26003H | 1841J | LP1Y-PWP-101707-04-2 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 6 | 6 | 0 | 25.948 | 7.05 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144360 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247380 | 26003H | 1842J | LP1Y-PWP-101707-04-3 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 9 | 8 | 1 | 31.2981 | 13.31 | sq ft | 0.81 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-28 |  | 2026-04-28 |  |  |  | 2026-04-28 |  |  | 80% |  |  |  | 0%
C34-S247381 | 26003H | 1843J | LP1Y-PWP-101707-04-4 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 3 | 3 | 0 | 22.064 | 6.15 | sq ft | 2.15 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144353 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247378 | 26003H | 1840J | LP1Y-PWP-101707-04-1 | LP1Y-PWP-101707-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS PWP (315) (108) 101707 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101707 |  | TFS00D005YSPP |  | 315-PWP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-08 | 144308 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247383 | 26003H | 1845J | LP1Y-PWP-101716-01-2 | LP1Y-PWP-101716-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 24 | 24 | 0 | 117.2359 | 24.88 | sq ft | 3.38 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144166 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247382 | 26003H | 1844J | LP1Y-PWP-101716-01-1 | LP1Y-PWP-101716-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 16 | 14 | 2 | 146.8059 | 31.48 | sq ft | 7.55 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-13 | 2026-04-15 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-14 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144829 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247385 | 26003H | 1847J | LP1Y-PWP-101716-02-2 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247387 | 26003H | 1849J | LP1Y-PWP-101716-02-4 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 15 | 14 | 1 | 81.7741 | 20.42 | sq ft | 1.12 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247386 | 26003H | 1848J | LP1Y-PWP-101716-02-3 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 21 | 18 | 3 | 103.9126 | 21.09 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 144320 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247384 | 26003H | 1846J | LP1Y-PWP-101716-02-1 | LP1Y-PWP-101716-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101716 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101716 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144365 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247388 | 26003H | 1850J | LP1Y-PWP-102072-01-1 | LP1Y-PWP-102072-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PWP (315) P (108) 102072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102072 |  | TFS00D006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247389 | 26003H | 1851J | LP1Y-PWP-102072-02-1 | LP1Y-PWP-102072-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS PWP (315) (108) 102072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102072 |  | TFS00D006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247392 | 26003H | 1854J | LP1Y-PWP-108074-01-3 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.675 | 16.81 | sq ft | 2.81 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247391 | 26003H | 1853J | LP1Y-PWP-108074-01-2 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.96 | 6.54 | sq ft | 2.54 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-25 | 2026-04-25 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145848
C34-S247390 | 26003H | 1852J | LP1Y-PWP-108074-01-1 | LP1Y-PWP-108074-01 | 0 | N | PRIORITY-1 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 13.75 | 10.75 | 3 | 82.91 | 33.5 | sq ft | 9.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-04-18 | Jacob Perez | 2026-04-18 | Jacob Perez | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247393 | 26003H | 1855J | LP1Y-PWP-108074-04-1 | LP1Y-PWP-108074-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 19.04 | 12.75 | sq ft | 0.75 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | 2026-04-29 | 2026-04-29 | 2026-04-28 |  |  | 80% |  |  |  | 20%
C34-S247394 | 26003H | 1856J | LP1Y-PWP-108074-04-2 | LP1Y-PWP-108074-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 22 | 22 | 0 | 122.435 | 40.85 | sq ft | 5.35 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247395 | 26003H | 1857J | LP1Y-PWP-108074-05-1 | LP1Y-PWP-108074-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS PWP (315) (108) 108074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108074 |  | TFS00E006YSPP |  | 315-PWP | NONE | 2" | 316 SS | 12 | 12 | 0 | 64.0913 | 21.18 | sq ft | 4.18 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247398 | 26003H | 1860J | LP1Y-PWP-850051-01-3 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 8 | 8 | 0 | 27.7888 | 12.53 | sq ft | 8.03 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-08 | N/A | N/A | Omar Puente | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144462 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247396 | 26003H | 1858J | LP1Y-PWP-850051-01-1 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247397 | 26003H | 1859J | LP1Y-PWP-850051-01-2 | LP1Y-PWP-850051-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00D005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247399 | 26003H | 1861J | LP1Y-RV-015007-01-1 | LP1Y-RV-015007-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D003YSPP |  | 315-RV | NONE | 4" | 316 SS | 23 | 23 | 0 | 90.5278 | 24.74 | sq ft | 12.28 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144657 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247400 | 26003H | 1862J | LP1Y-RV-015008-01-1 | LP1Y-RV-015008-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D003YSPP |  | 315-RV | NONE | 4" | 316 SS | 23 | 23 | 0 | 90.7908 | 24.79 | sq ft | 12.33 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | N/A | N/A | Henrique Barahona | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144385 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247402 | 26003H | 1864J | LP1Y-RV-017083-01-2 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247403 | 26003H | 1865J | LP1Y-RV-017083-01-3 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247401 | 26003H | 1863J | LP1Y-RV-017083-01-1 | LP1Y-RV-017083-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS RV (36) 017083 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017083 |  | TFS00D007YSPP |  | 36-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247404 | 26003H | 1866J | LP1Y-RV-100208-01-1 | LP1Y-RV-100208-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100208 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100208 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144865 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247405 | 26003H | 1867J | LP1Y-RV-100208-01-2 | LP1Y-RV-100208-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100208 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100208 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 7 | 5 | 2 | 12.18 | 10.08 | sq ft | 2.58 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Guillen | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-15 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144850 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247406 | 26003H | 1868J | LP1Y-RV-100212-01-1 | LP1Y-RV-100212-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100212 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100212 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 17.25 | 15 | 2.25 | 36.1213 | 23.52 | sq ft | 9.02 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-10 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 144886 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247407 | 26003H | 1869J | LP1Y-RV-100308-01-1 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-16 | [9 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143972 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247409 | 26003H | 1871J | LP1Y-RV-100308-01-3 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 12 | 12 | 0 | 49.3 | 12.8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 143874 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S247408 | 26003H | 1870J | LP1Y-RV-100308-01-2 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 5 | 4 | 1 | 30.4591 | 7.69 | sq ft | 1.74 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Montoya | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144672 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247411 | 26003H | 1873J | LP1Y-RV-100308-01-5 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-03-31 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 15 | 12 | 3 | 115.1238 | 27.7 | sq ft | 19.13 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-08 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-08 | 2026-04-09 | 100% | 2026-04-10 | 144452 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247410 | 26003H | 1872J | LP1Y-RV-100308-01-4 | LP1Y-RV-100308-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100308 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100308 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 16 | 16 | 0 | 56.0773 | 13.98 | sq ft | 4.82 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144285 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247413 | 26003H | 1875J | LP1Y-RV-100313-01-2 | LP1Y-RV-100313-01 | 0 | N | PRIORITY-1 | 2026-03-26 | 2026-03-26 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100313 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100313 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 9 | 7 | 2 | 15.0538 | 11.84 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Edgar Castaneda | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144069 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247412 | 26003H | 1874J | LP1Y-RV-100313-01-1 | LP1Y-RV-100313-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100313 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100313 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144864 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247415 | 26003H | 1877J | LP1Y-RV-100316-01-2 | LP1Y-RV-100316-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100316 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100316 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 11.25 | 9 | 2.25 | 29.15 | 20.21 | sq ft | 7.21 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-14 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-16 | 2026-04-21 | 100% | 2026-04-21 | 145196 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247414 | 26003H | 1876J | LP1Y-RV-100316-01-1 | LP1Y-RV-100316-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS RV (315) P (108) 100316 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100316 |  | TFS00D002YSPP |  | 315-RV | NONE | 2" | 316 SS | 6 | 6 | 0 | 16.8988 | 7.73 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | N/A | N/A | Omar Puente | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-03-27 | 143674 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S247416 | 26003H | 1878J | LP1Y-RV-100317-01-1 | LP1Y-RV-100317-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 18 | 12 | 6 | 122.4225 | 28.12 | sq ft | 20.92 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Henrique Barahona | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 100% | 2026-04-09 | 2026-04-06 | 2026-04-09 | 100% | 2026-04-10 | 144453 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S256299 | 26003H | 1879JA | LP1Y-RV-100317-04-1A | LP1Y-RV-100317-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 |  | 0 | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 4 | 4 | 0 | 61.435 | 14 | sq ft | 10.17 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145280 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247418 | 26003H | 1880J | LP1Y-RV-100317-04-2 | LP1Y-RV-100317-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 4 | 4 | 0 | 67.8047 | 15.36 | sq ft | 11.3 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144077 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247417 | 26003H | 1879J | LP1Y-RV-100317-04-1 | LP1Y-RV-100317-04 | 0 | N | PRIORITY-1 | 2026-03-25 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 4" SS RV (315) (108) 100317 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100317 |  | TFS00D002YSPP |  | 315-RV | NONE | 4" | 316 SS | 8 | 8 | 0 | 150.523 | 33.06 | sq ft | 26.05 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144559 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247419 | 26003H | 1881J | LP1Y-RV-100410-01-1 | LP1Y-RV-100410-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS RV (315) (108) 100410 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100410 |  | TFS00D003YSPP |  | 315-RV | NONE | 2" | 316 SS | 7 | 7 | 0 | 17.9413 | 12.27 | sq ft | 4.77 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 75%
C34-S247420 | 26003H | 1882J | LP1Y-RV-101007-01-1 | LP1Y-RV-101007-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 12 | 12 | 0 | 43.8917 | 11.11 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | N/A | N/A | Roberto Tobias (WF) | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144403 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247421 | 26003H | 1883J | LP1Y-RV-101007-01-2 | LP1Y-RV-101007-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 101007 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101007 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247423 | 26003H | 1885J | LP1Y-RV-101008-01-2 | LP1Y-RV-101008-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247422 | 26003H | 1884J | LP1Y-RV-101008-01-1 | LP1Y-RV-101008-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 101008 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101008 |  | TFS00D005YSPP |  | 315-RV | NONE | 4" | 316 SS | 12 | 12 | 0 | 43.5995 | 11.04 | sq ft | 6.2 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144362 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247424 | 26003H | 1886J | LP1Y-RV-101017-01-1 | LP1Y-RV-101017-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS RV (315) (108) 101017 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101017 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 21.75 | 19 | 2.75 | 67.5238 | 37.05 | sq ft | 18.55 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-29 |  | 2026-04-29 |  |  |  | 75% |  |  |  | 8%
C34-S247425 | 26003H | 1887J | LP1Y-RV-101017-03-1 | LP1Y-RV-101017-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS RV (315) (108) 101017 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101017 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 12 | 12 | 0 | 46.9975 | 19.8 | sq ft | 15.3 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | [6 empty] | 67% |  |  |  | 0%
C34-S247426 | 26003H | 1888D | LP1Y-RV-101517-01-1 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 12 | 12 | 0 | 41.9925 | 10.7 | sq ft | 5.92 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-20 | Passed | No | 2026-04-20 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247427 | 26003H | 1889D | LP1Y-RV-101517-01-2 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 4 | 4 | 0 | 69.0453 | 15.04 | sq ft | 8.7 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-20 | Passed | No | 2026-04-20 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247428 | 26003H | 1890D | LP1Y-RV-101517-01-3 | LP1Y-RV-101517-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 4" DUP RV (344) (108) 101517 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101517 |  | TFS00D005YSPP |  | 344-RV | NONE | 4" | 2205 | 22 | 21 | 1 | 53.2872 | 20.46 | sq ft | 2.22 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247430 | 26003H | 1892J | LP1Y-RV-101718-01-2 | LP1Y-RV-101718-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS RV (315) (108) 101718 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101718 |  | TFS00D005YSPP |  | 315-RV | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247429 | 26003H | 1891J | LP1Y-RV-101718-01-1 | LP1Y-RV-101718-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS RV (315) (108) 101718 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101718 |  | TFS00D005YSPP |  | 315-RV | NONE | 2" | 316 SS | 4.75 | 4 | 0.75 | 15.3638 | 9.42 | sq ft | 0.42 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-30 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145272 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247438 | 26003H | 1900J | LP1Y-RV-102107-01-2 | LP1Y-RV-102107-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS RV (315) P 102107 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102107 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247437 | 26003H | 1899J | LP1Y-RV-102107-01-1 | LP1Y-RV-102107-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS RV (315) P 102107 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102107 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-20 | [9 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144648 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247439 | 26003H | 1901J | LP1Y-RV-102207-01-1 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02 |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247442 | 26003H | 1904J | LP1Y-RV-102207-01-4 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02 |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247443 | 26003H | 1905J | LP1Y-RV-102207-01-5 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02 |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247441 | 26003H | 1903J | LP1Y-RV-102207-01-3 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0% |  |  |  | 0%
C34-S247440 | 26003H | 1902J | LP1Y-RV-102207-01-2 | LP1Y-RV-102207-01 | 0 | N | PRIORITY-1 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102207 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102207 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 55.7531 | 20.08 | sq ft | 1.32 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247444 | 26003H | 1906J | LP1Y-RV-102224-01-1 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-20 | [9 empty] | 100% |  |  |  | 100% | 2026-04-14 | 144647 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247446 | 26003H | 1908J | LP1Y-RV-102224-01-3 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 3 | 3 | 0 | 10.0213 | 8.6 | sq ft | 2.6 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144978 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247445 | 26003H | 1907J | LP1Y-RV-102224-01-2 | LP1Y-RV-102224-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS RV (315) P 102224 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102224 |  | TFS00D006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247451 | 26003H | 1913J | LP1Y-RV-108125-01-6 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 24 | 24 | 0 | 186.7844 | 37.29 | sq ft | 17.72 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 75%
C34-S247447 | 26003H | 1909J | LP1Y-RV-108125-01-1 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-27 | 2026-04-27 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146072
C34-S256229 | 26003H | 1912J-L1 | LP1Y-RV-108125-01-5-L1 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-17 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-27 | 2026-04-27 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146071
C34-S247450 | 26003H | 1912J | LP1Y-RV-108125-01-5 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 112.3891 | 23.47 | sq ft | 8.54 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 80%
C34-S247449 | 26003H | 1911J | LP1Y-RV-108125-01-3 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-27 | 2026-04-27 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247448 | 26003H | 1910J | LP1Y-RV-108125-01-2 | LP1Y-RV-108125-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108125 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108125 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 58.175 | 20.55 | sq ft | 1.58 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247452 | 26003H | 1914J | LP1Y-RV-108134-01-1 | LP1Y-RV-108134-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 3" SS RV (315) P (108) 108134 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108134 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 15 | 15 | 0 | 292.9152 | 22.02 | sq ft | 2.52 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247453 | 26003H | 1915J | LP1Y-RV-108136-01-1 | LP1Y-RV-108136-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108136 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108136 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 13 | 13 | 0 | 65.52 | 24.87 | sq ft | 3.38 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247455 | 26003H | 1917J | LP1Y-RV-108138-01-2 | LP1Y-RV-108138-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108138 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108138 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 7 | 7 | 0 | 20.2275 | 13.8 | sq ft | 6.3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | [6 empty] | 75% |  |  |  | 0%
C34-S247454 | 26003H | 1916J | LP1Y-RV-108138-01-1 | LP1Y-RV-108138-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108138 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108138 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 10 | 10 | 0 | 59.0288 | 17.03 | sq ft | 4.03 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247457 | 26003H | 1919J | LP1Y-RV-108227-01-2 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 58.2719 | 20.57 | sq ft | 1.59 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255916 | 26003H | 1921J-L1 | LP1Y-RV-108227-01-5-L1 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-16 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-27 | 2026-04-27 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146073
C34-S247456 | 26003H | 1918J | LP1Y-RV-108227-01-1 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-27 | 2026-04-27 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146074
C34-S247459 | 26003H | 1921J | LP1Y-RV-108227-01-5 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 112.3406 | 23.46 | sq ft | 8.53 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-30 | 145946
C34-S247458 | 26003H | 1920J | LP1Y-RV-108227-01-3 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 144869
C34-S247460 | 26003H | 1922J | LP1Y-RV-108227-01-6 | LP1Y-RV-108227-01 | 0 | N | PRIORITY-1 | 2026-04-16 | 2026-04-22 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 6" SS RV (315) (108) 108227 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108227 |  | TFS00E006YSPP |  | 315-RV | NONE | 6" | 316 SS | 24 | 24 | 0 | 244.9094 | 48.54 | sq ft | 23.97 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-22 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-04-14 | 2026-04-14 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | [6 empty] | 50% |  |  |  | 0%
C34-S247711 | 26003H | 1923J | LP1Y-RV-108234-01-1 | LP1Y-RV-108234-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108234 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108234 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145575
C34-S247712 | 26003H | 1924J | LP1Y-RV-108234-01-2 | LP1Y-RV-108234-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108234 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108234 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 11 | 11 | 0 | 57.9263 | 20.74 | sq ft | 3.24 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247713 | 26003H | 1925J | LP1Y-RV-108236-01-1 | LP1Y-RV-108236-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 3" SS RV (315) P (108) 108236 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108236 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145577
C34-S247714 | 26003H | 1926J | LP1Y-RV-108236-01-2 | LP1Y-RV-108236-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 3" SS RV (315) P (108) 108236 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108236 |  | TFS00E006YSPP |  | 315-RV | NONE | 3" | 316 SS | 12 | 12 | 0 | 282.3302 | 18.52 | sq ft | 3.02 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247715 | 26003H | 1927J | LP1Y-RV-108238-01-1 | LP1Y-RV-108238-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108238 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108238 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 14 | 14 | 0 | 65.56 | 20.17 | sq ft | 5.67 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247716 | 26003H | 1928J | LP1Y-RV-108238-01-2 | LP1Y-RV-108238-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS RV (315) P (108) 108238 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108238 |  | TFS00E006YSPP |  | 315-RV | NONE | 2" | 316 SS | 7 | 7 | 0 | 22.8675 | 14.8 | sq ft | 7.3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Henrique Barahona | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-23 | 145267, 145278
C34-S247721 | 26003H | 1933J | LP1Y-RV-109107-01-5 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 12 | 12 | 0 | 152.118 | 34.26 | sq ft | 25.55 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247722 | 26003H | 1934J | LP1Y-RV-109107-01-6 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 4 | 4 | 0 | 61.435 | 14 | sq ft | 10.17 | ft | 2026-02-13 |  |  |  |  | 2026-04-09 | Jacob Perez | 2026-04-09 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247718 | 26003H | 1930J | LP1Y-RV-109107-01-2 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 5.5 | 4 | 1.5 | 39.722 | 17.74 | sq ft | 1.79 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247717 | 26003H | 1929J | LP1Y-RV-109107-01-1 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S247719 | 26003H | 1931J | LP1Y-RV-109107-01-3 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 8 | 8 | 0 | 44.9 | 11 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144286
C34-S247720 | 26003H | 1932J | LP1Y-RV-109107-01-4 | LP1Y-RV-109107-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109107 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 20 | 20 | 0 | 72.7905 | 17.56 | sq ft | 7.8 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247723 | 26003H | 1935J | LP1Y-RV-109121-01-1 | LP1Y-RV-109121-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS RV (315) (108) 109121 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109121 |  | TFS00E007YSPP |  | 315-RV | NONE | 2" | 316 SS | 21.25 | 19 | 2.25 | 77.9075 | 32.68 | sq ft | 8.18 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247728 | 26003H | 1940AB | LP1Y-RV-109211-01-1 | LP1Y-RV-109211-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST RV (332) P (108) 109211 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109211 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 16.25 | 15.5 | 0.75 | 54.0125 | 32.53 | sq ft | 6.03 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-07 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247730 | 26003H | 1942AB | LP1Y-RV-109214-01-2 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 4 | 4 | 0 | 13.8913 | 7.18 | sq ft | 1.68 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247729 | 26003H | 1941AB | LP1Y-RV-109214-01-1 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 3" | H C22 | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247731 | 26003H | 1943AB | LP1Y-RV-109214-01-3 | LP1Y-RV-109214-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST RV (332) P (108) 109214 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109214 |  | TFS00E007YSPP |  | 332-RV | NONE | 2" | H C22 | 5 | 5 | 0 | 12.5275 | 10.8 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247733 | 26003H | 1945J | LP1Y-RV-162310-01-2 | LP1Y-RV-162310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS RV (315) P (108) 162310 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162310 |  | TFS00E006YSPP |  | 315-RV | NONE | 1" | 316 SS | 2 | 2 | 0 | 10.4517 | 11.03 | sq ft | 5.53 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S247732 | 26003H | 1944J | LP1Y-RV-162310-01-1 | LP1Y-RV-162310-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS RV (315) P (108) 162310 | RV |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162310 |  | TFS00E006YSPP |  | 315-RV | NONE | 1" | 316 SS | 2 | 2 | 0 | 7.9542 | 6.94 | sq ft | 5.44 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 0%
C34-S247734 | 26003H | 1946J | LP1Y-RV-180096-01-1 | LP1Y-RV-180096-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS RV (315) 180096 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180096 |  | TFS00D007YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247735 | 26003H | 1947J | LP1Y-RV-180097-01-1 | LP1Y-RV-180097-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS RV (315) 180097 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180097 |  | TFS00D007YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247736 | 26003H | 1948C | LP1Y-S(130)-018009-01-1 | LP1Y-S(130)-018009-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018009 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018009 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247737 | 26003H | 1949C | LP1Y-S(130)-018009-01-2 | LP1Y-S(130)-018009-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018009 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018009 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 9 | 0 | 9 | 32.9314 | 42.96 | sq ft | 2.46 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-31 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247739 | 26003H | 1951C | LP1Y-S(130)-018013-01-2 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 21.2789 | 6 | 15.2789 | 112.4496 | 26.3 | sq ft | 20.29 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247740 | 26003H | 1952C | LP1Y-S(130)-018013-01-3 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 16.75 | 16 | 0.75 | 42.036 | 27.49 | sq ft | 3.49 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247738 | 26003H | 1950C | LP1Y-S(130)-018013-01-1 | LP1Y-S(130)-018013-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018013 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018013 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 14 | 14 | 0 | 72.0193 | 24.64 | sq ft | 18.64 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247741 | 26003H | 1953C | LP1Y-S(130)-018062-14-1 | LP1Y-S(130)-018062-14 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018062 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018062 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 27.4034 | 10.69 | sq ft | 6.19 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247742 | 26003H | 1954C | LP1Y-S(130)-018062-14-2 | LP1Y-S(130)-018062-14 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018062 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018062 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 8.75 | 8 | 0.75 | 44.8696 | 24.79 | sq ft | 6.79 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247743 | 26003H | 1955C | LP1Y-S(130)-018070-03-1 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 20.75 | 18 | 2.75 | 62.0644 | 32.69 | sq ft | 10.19 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247745 | 26003H | 1957C | LP1Y-S(130)-018070-03-3 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 13.6394 | 6 | 7.6394 | 61.9312 | 16.4 | sq ft | 11.1 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247744 | 26003H | 1956C | LP1Y-S(130)-018070-03-2 | LP1Y-S(130)-018070-03 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 15.6394 | 8 | 7.6394 | 46.8687 | 12.65 | sq ft | 5.85 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247747 | 26003H | 1959C | LP1Y-S(130)-018070-04-2 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 21.2789 | 6 | 15.2789 | 119.7243 | 26.48 | sq ft | 21.64 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247748 | 26003H | 1960C | LP1Y-S(130)-018070-04-3 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 19.2789 | 4 | 15.2789 | 113.9507 | 24.94 | sq ft | 21.84 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247746 | 26003H | 1958C | LP1Y-S(130)-018070-04-1 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 54.9305 | 18.23 | sq ft | 13.73 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247749 | 26003H | 1961C | LP1Y-S(130)-018070-04-4 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 40.7381 | 14 | 26.7381 | 214.0034 | 49.26 | sq ft | 38.68 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247750 | 26003H | 1962C | LP1Y-S(130)-018070-04-5 | LP1Y-S(130)-018070-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018070 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018070 |  | TFS00E007YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.961 | 24.49 | sq ft | 1.99 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247751 | 26003H | 1963C | LP1Y-S(130)-018071-04-1 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 13.6394 | 6 | 7.6394 | 48.644 | 11.78 | sq ft | 7.98 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247752 | 26003H | 1964C | LP1Y-S(130)-018071-04-2 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 36.9183 | 14 | 22.9183 | 149.3941 | 34.46 | sq ft | 24.56 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247753 | 26003H | 1965C | LP1Y-S(130)-018071-04-3 | LP1Y-S(130)-018071-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 16.75 | 16 | 0.75 | 40.9524 | 27.2 | sq ft | 3.2 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247757 | 26003H | 1969C | LP1Y-S(130)-018071-05-4 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 47.2883 | 16.14 | sq ft | 11.64 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247756 | 26003H | 1968C | LP1Y-S(130)-018071-05-3 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 15.6394 | 8 | 7.6394 | 40.1304 | 10.51 | sq ft | 5.21 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247754 | 26003H | 1966C | LP1Y-S(130)-018071-05-1 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 17.75 | 14 | 3.75 | 59.75 | 31.22 | sq ft | 10.22 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247755 | 26003H | 1967C | LP1Y-S(130)-018071-05-2 | LP1Y-S(130)-018071-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018071 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018071 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 13.6394 | 6 | 7.6394 | 48.3484 | 11.99 | sq ft | 6.69 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247758 | 26003H | 1970C | LP1Y-S(130)-018076-02-1 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 8 | 2 | 29.1477 | 10.33 | sq ft | 7.33 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247761 | 26003H | 1973C | LP1Y-S(130)-018076-02-4 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 51.9206 | 15.29 | sq ft | 13.79 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247759 | 26003H | 1971C | LP1Y-S(130)-018076-02-2 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 10.75 | 10 | 0.75 | 44.643 | 26.01 | sq ft | 6.51 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247760 | 26003H | 1972C | LP1Y-S(130)-018076-02-3 | LP1Y-S(130)-018076-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 42.3953 | 16.16 | sq ft | 8.66 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247764 | 26003H | 1976C | LP1Y-S(130)-018076-04-3 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 33.7823 | 24.17 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247762 | 26003H | 1974C | LP1Y-S(130)-018076-04-1 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 101.2716 | 28.81 | sq ft | 27.31 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247763 | 26003H | 1975C | LP1Y-S(130)-018076-04-2 | LP1Y-S(130)-018076-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 2" CS S(130) (2) (103) 018076 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018076 |  | TFS00D006YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 30.0544 | 11.71 | sq ft | 5.71 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247765 | 26003H | 1977C | LP1Y-S(130)-018077-04-1 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 20.7646 | 8.79 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247766 | 26003H | 1978C | LP1Y-S(130)-018077-04-2 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 68.3646 | 19.79 | sq ft | 18.29 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247767 | 26003H | 1979C | LP1Y-S(130)-018077-04-3 | LP1Y-S(130)-018077-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 44.2013 | 16.65 | sq ft | 9.15 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247768 | 26003H | 1980C | LP1Y-S(130)-018077-05-1 | LP1Y-S(130)-018077-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 22.75 | 20 | 2.75 | 63.9084 | 33.19 | sq ft | 10.69 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247769 | 26003H | 1981C | LP1Y-S(130)-018077-06-1 | LP1Y-S(130)-018077-06 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 74.0708 | 22.42 | sq ft | 19.42 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247770 | 26003H | 1982C | LP1Y-S(130)-018077-06-2 | LP1Y-S(130)-018077-06 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 16 | 14 | 2 | 44.7144 | 17.09 | sq ft | 11.09 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247771 | 26003H | 1983C | LP1Y-S(130)-018077-07-1 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 52.4771 | 18.54 | sq ft | 12.54 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247772 | 26003H | 1984C | LP1Y-S(130)-018077-07-2 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 52.8258 | 16.89 | sq ft | 12.39 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247773 | 26003H | 1985C | LP1Y-S(130)-018077-07-3 | LP1Y-S(130)-018077-07 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018077 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.5998 | 24.4 | sq ft | 1.9 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247774 | 26003H | 1986C | LP1Y-S(130)-018078-01-1 | LP1Y-S(130)-018078-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 45.0948 | 16.9 | sq ft | 9.4 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247775 | 26003H | 1987C | LP1Y-S(130)-018078-01-2 | LP1Y-S(130)-018078-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 72.0208 | 22.92 | sq ft | 18.42 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247777 | 26003H | 1989C | LP1Y-S(130)-018078-04-5 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 18.2479 | 10.96 | sq ft | 1.96 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247779 | 26003H | 1991C | LP1Y-S(130)-018078-04-3 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 25.7169 | 9.46 | sq ft | 4.96 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247780 | 26003H | 1992C | LP1Y-S(130)-018078-04-4 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 36.3868 | 24.89 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247778 | 26003H | 1990C | LP1Y-S(130)-018078-04-2 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 182.256 | 50.99 | sq ft | 49.49 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247781 | 26003H | 1993C | LP1Y-S(130)-018078-04-6 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6.25 | 4 | 2.25 | 30.9315 | 19.73 | sq ft | 2.73 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247776 | 26003H | 1988C | LP1Y-S(130)-018078-04-1 | LP1Y-S(130)-018078-04 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018078 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018078 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 103.9773 | 31.67 | sq ft | 27.17 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247783 | 26003H | 1995C | LP1Y-S(130)-018079-05-2 | LP1Y-S(130)-018079-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 29.6245 | 10.24 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247782 | 26003H | 1994C | LP1Y-S(130)-018079-05-1 | LP1Y-S(130)-018079-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 39.868 | 11.98 | sq ft | 10.48 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | N/A | N/A | Guillermo Plasencia | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 2026-04-24 | 143928, 145582
C34-S247785 | 26003H | 1997C | LP1Y-S(130)-018079-08-2 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 10.75 | 10 | 0.75 | 38.9224 | 24.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247786 | 26003H | 1998C | LP1Y-S(130)-018079-08-3 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 44.7495 | 15.74 | sq ft | 9.74 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247787 | 26003H | 1999C | LP1Y-S(130)-018079-08-4 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 29.1523 | 11.17 | sq ft | 6.67 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247784 | 26003H | 1996C | LP1Y-S(130)-018079-08-1 | LP1Y-S(130)-018079-08 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 27.8375 | 9.75 | sq ft | 6.75 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | N/A | N/A | Ricardo Salinas Saldana | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-24 | 143929, 145583
C34-S247789 | 26003H | 2001C | LP1Y-S(130)-018079-10-2 | LP1Y-S(130)-018079-10 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 97.9654 | 29.18 | sq ft | 26.18 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247788 | 26003H | 2000C | LP1Y-S(130)-018079-10-1 | LP1Y-S(130)-018079-10 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 56.7776 | 19.8 | sq ft | 13.8 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247790 | 26003H | 2002C | LP1Y-S(130)-018079-11-1 | LP1Y-S(130)-018079-11 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 18.2047 | 6.34 | sq ft | 3.34 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Ricardo Salinas Saldana | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 0% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-24 | 143927, 145584
C34-S247791 | 26003H | 2003C | LP1Y-S(130)-018079-11-2 | LP1Y-S(130)-018079-11 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018079 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018079 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 33.7633 | 24.17 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247794 | 26003H | 2006C | LP1Y-S(130)-018082-02-3 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247792 | 26003H | 2004C | LP1Y-S(130)-018082-02-1 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247793 | 26003H | 2005C | LP1Y-S(130)-018082-02-2 | LP1Y-S(130)-018082-02 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 2" CS S(130) (2) (103) 018082 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018082 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247797 | 26003H | 2009C | LP1Y-S(130)-018101-02-3 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247796 | 26003H | 2008C | LP1Y-S(130)-018101-02-2 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247795 | 26003H | 2007C | LP1Y-S(130)-018101-02-1 | LP1Y-S(130)-018101-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018101 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018101 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247801 | 26003H | 2013C | LP1Y-S(130)-018103-02-4 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247798 | 26003H | 2010C | LP1Y-S(130)-018103-02-1 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247800 | 26003H | 2012C | LP1Y-S(130)-018103-02-3 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247799 | 26003H | 2011C | LP1Y-S(130)-018103-02-2 | LP1Y-S(130)-018103-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018103 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 8.8284 | 4.22 | sq ft | 1.72 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247802 | 26003H | 2014C | LP1Y-S(130)-018105-02-1 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247803 | 26003H | 2015C | LP1Y-S(130)-018105-02-2 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247804 | 26003H | 2016C | LP1Y-S(130)-018105-02-3 | LP1Y-S(130)-018105-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018105 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247807 | 26003H | 2019C | LP1Y-S(130)-018107-02-3 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247805 | 26003H | 2017C | LP1Y-S(130)-018107-02-1 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247806 | 26003H | 2018C | LP1Y-S(130)-018107-02-2 | LP1Y-S(130)-018107-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018107 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247809 | 26003H | 2021C | LP1Y-S(130)-018109-02-2 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247810 | 26003H | 2022C | LP1Y-S(130)-018109-02-3 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247808 | 26003H | 2020C | LP1Y-S(130)-018109-02-1 | LP1Y-S(130)-018109-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018109 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018109 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247812 | 26003H | 2024C | LP1Y-S(130)-018131-01-2 | LP1Y-S(130)-018131-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.3717 | 24.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247811 | 26003H | 2023C | LP1Y-S(130)-018131-01-1 | LP1Y-S(130)-018131-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 17.0466 | 7.31 | sq ft | 2.81 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Ricardo Salinas Saldana | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 0% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-24 | 143926, 145585
C34-S247813 | 26003H | 2025C | LP1Y-S(130)-018131-02-1 | LP1Y-S(130)-018131-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 45.3872 | 15.62 | sq ft | 11.12 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-03-28 | 2026-03-28 | 2026-03-27 | 2026-03-27 | N/A | N/A | Hayden Whitton | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-24 | 144026, 145586
C34-S247814 | 26003H | 2026C | LP1Y-S(130)-018131-02-2 | LP1Y-S(130)-018131-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" CS S(130) (2) (103) 018131 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018131 |  | TFS00D002YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 98.0018 | 27.91 | sq ft | 26.41 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247817 | 26003H | 2029C | LP1Y-S(130)-018132-01-3 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 36.0826 | 24.8 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247816 | 26003H | 2028C | LP1Y-S(130)-018132-01-2 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 25.606 | 10.49 | sq ft | 4.49 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247815 | 26003H | 2027C | LP1Y-S(130)-018132-01-1 | LP1Y-S(130)-018132-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 2" CS S(130) (2) (103) 018132 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018132 |  | TFS00D003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 175.3393 | 50.16 | sq ft | 47.16 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-30 | George Allahverdian | 2026-03-31 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247818 | 26003H | 2030C | LP1Y-S(130)-018134-01-1 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 48.8398 | 15.42 | sq ft | 12.42 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247819 | 26003H | 2031C | LP1Y-S(130)-018134-01-2 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 34.1172 | 13.59 | sq ft | 7.59 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247820 | 26003H | 2032C | LP1Y-S(130)-018134-01-3 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 46.5174 | 16.22 | sq ft | 10.22 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247821 | 26003H | 2033C | LP1Y-S(130)-018134-01-4 | LP1Y-S(130)-018134-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018134 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018134 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.5998 | 24.4 | sq ft | 1.9 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247825 | 26003H | 2037C | LP1Y-S(130)-018135-01-4 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.5998 | 24.4 | sq ft | 1.9 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247823 | 26003H | 2035C | LP1Y-S(130)-018135-01-2 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 28.0276 | 9.8 | sq ft | 6.8 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247824 | 26003H | 2036C | LP1Y-S(130)-018135-01-3 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 40.7352 | 13.58 | sq ft | 9.08 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247822 | 26003H | 2034C | LP1Y-S(130)-018135-01-1 | LP1Y-S(130)-018135-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018135 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018135 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 76.7323 | 23.15 | sq ft | 20.15 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247826 | 26003H | 2038C | LP1Y-S(130)-018136-01-1 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 53.5016 | 16.78 | sq ft | 13.78 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247828 | 26003H | 2040C | LP1Y-S(130)-018136-01-3 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.5998 | 24.4 | sq ft | 1.9 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247827 | 26003H | 2039C | LP1Y-S(130)-018136-01-2 | LP1Y-S(130)-018136-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 018136 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018136 |  | TFS00D005YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 52.8068 | 16.89 | sq ft | 12.39 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247829 | 26003H | 2041C | LP1Y-S(130)-018137-01-1 | LP1Y-S(130)-018137-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 15.3563 | 6.63 | sq ft | 2.13 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247830 | 26003H | 2042C | LP1Y-S(130)-018137-01-2 | LP1Y-S(130)-018137-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.3146 | 24.32 | sq ft | 1.82 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247831 | 26003H | 2043C | LP1Y-S(130)-018137-02-1 | LP1Y-S(130)-018137-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 34.5578 | 4 | 30.5578 | 192.2347 | 39.04 | sq ft | 34.34 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247832 | 26003H | 2044C | LP1Y-S(130)-018137-02-2 | LP1Y-S(130)-018137-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P016 | 2026-06-08 |  | LP1Y 2" CS S(130) (2) (103) 018137 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018137 |  | TFS00E006YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 86.5417 | 25.83 | sq ft | 22.83 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247835 | 26003H | 2047C | LP1Y-S(130)-018143-02-3 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247833 | 26003H | 2045C | LP1Y-S(130)-018143-02-1 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 2.3167 | 2.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0% |  |  |  | 0%
C34-S247834 | 26003H | 2046C | LP1Y-S(130)-018143-02-2 | LP1Y-S(130)-018143-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018143 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018143 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 3 | 0 | 3 | 7.2826 | 5.01 | sq ft | 2.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247836 | 26003H | 2048C | LP1Y-S(130)-018145-02-1 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 2.2257 | 2.29 | sq ft | 0.79 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0% |  |  |  | 0%
C34-S247837 | 26003H | 2049C | LP1Y-S(130)-018145-02-2 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 3 | 0 | 3 | 6.3025 | 4.5 | sq ft | 2 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247838 | 26003H | 2050C | LP1Y-S(130)-018145-02-3 | LP1Y-S(130)-018145-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 018145 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018145 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247839 | 26003H | 2051C | LP1Y-S(130)-018152-01-1 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247840 | 26003H | 2052C | LP1Y-S(130)-018152-01-2 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247842 | 26003H | 2054C | LP1Y-S(130)-018152-01-4 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247843 | 26003H | 2055C | LP1Y-S(130)-018152-01-5 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 3 | 0 | 3 | 6.9921 | 5.1 | sq ft | 2.1 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247844 | 26003H | 2056C | LP1Y-S(130)-018152-01-6 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247841 | 26003H | 2053C | LP1Y-S(130)-018152-01-3 | LP1Y-S(130)-018152-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018152 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018152 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247846 | 26003H | 2058C | LP1Y-S(130)-018158-01-2 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247845 | 26003H | 2057C | LP1Y-S(130)-018158-01-1 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 13.1466 | 15.22 | sq ft | 2.22 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247847 | 26003H | 2059C | LP1Y-S(130)-018158-01-3 | LP1Y-S(130)-018158-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" CS S(130) (2) (103) 018158 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018158 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247848 | 26003H | 2060C | LP1Y-S(130)-018160-02-1 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247850 | 26003H | 2062C | LP1Y-S(130)-018160-02-3 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247849 | 26003H | 2061C | LP1Y-S(130)-018160-02-2 | LP1Y-S(130)-018160-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P036 | 2026-08-24 |  | LP1Y 1" CS S(130) (2) (103) 018160 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018160 |  | TFS00D007YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247851 | 26003H | 2063C | LP1Y-S(130)-034046-01-1 | LP1Y-S(130)-034046-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 034046 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034046 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 12.413 | 11.52 | sq ft | 7.02 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0% |  |  |  | 0%
C34-S247852 | 26003H | 2064C | LP1Y-S(130)-034046-01-2 | LP1Y-S(130)-034046-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 034046 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034046 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 12 | 0 | 12 | 46.0234 | 57.28 | sq ft | 5.28 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247853 | 26003H | 2065C | LP1Y-S(130)-034058-02-1 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 20.7245 | 6.74 | sq ft | 5.24 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247854 | 26003H | 2066C | LP1Y-S(130)-034058-02-2 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 34.469 | 10.51 | sq ft | 9.01 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247855 | 26003H | 2067C | LP1Y-S(130)-034058-02-3 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 2" | CS | 19.25 | 14 | 5.25 | 85.4504 | 46.06 | sq ft | 15.56 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247856 | 26003H | 2068C | LP1Y-S(130)-034058-02-4 | LP1Y-S(130)-034058-02 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" CS S(130) (2) (103) 034058 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034058 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 2" | CS | 11.75 | 8 | 3.75 | 37.1397 | 23.91 | sq ft | 4.41 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247859 | 26003H | 2071C | LP1Y-S(130)-034103-02-3 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-24 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-24 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-24 | 144370, 145587
C34-S247857 | 26003H | 2069C | LP1Y-S(130)-034103-02-1 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% |  |  |  | 0%
C34-S247858 | 26003H | 2070C | LP1Y-S(130)-034103-02-2 | LP1Y-S(130)-034103-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034103 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034103 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 4 | 0 | 4 | 10.9659 | 4.97 | sq ft | 2.47 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  | 2026-04-01 |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247861 | 26003H | 2073C | LP1Y-S(130)-034105-02-2 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  | 2026-04-01 |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247862 | 26003H | 2074C | LP1Y-S(130)-034105-02-3 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-24 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-24 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-24 | 144371, 145588
C34-S247860 | 26003H | 2072C | LP1Y-S(130)-034105-02-1 | LP1Y-S(130)-034105-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034105 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034105 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% |  |  |  | 0%
C34-S247864 | 26003H | 2076C | LP1Y-S(130)-034107-02-2 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 4 | 0 | 4 | 8.3722 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247865 | 26003H | 2077C | LP1Y-S(130)-034107-02-3 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-24 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-04-24 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-24 | 144369, 145589
C34-S247863 | 26003H | 2075C | LP1Y-S(130)-034107-02-1 | LP1Y-S(130)-034107-02 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS S(130) (2) (103) 034107 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034107 |  | TFS00D001YSPP |  | 2-S(130) | P-4 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% |  |  |  | 0%
C34-S247866 | 26003H | 2078C | LP1Y-S(130)-034180-01-1 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 3 | 0 | 3 | 4.775 | 5.15 | sq ft | 2.15 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 0% |  |  |  | 0%
C34-S247867 | 26003H | 2079C | LP1Y-S(130)-034180-01-2 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 9.3373 | 7.54 | sq ft | 3.54 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-22; EL: Jacob Perez; FD: 2026-04-22; FL: Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247868 | 26003H | 2080C | LP1Y-S(130)-034180-01-3 | LP1Y-S(130)-034180-01 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" CS S(130) (2) (103) 034180 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034180 |  | TFS00D001YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247869 | 26003H | 2081J | LP1Y-S(130)-165115-01-1 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Edgar Castaneda | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144280 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247871 | 26003H | 2083J | LP1Y-S(130)-165115-01-3 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.8594 | 2.85 | sq ft | 2.35 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145269 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247870 | 26003H | 2082J | LP1Y-S(130)-165115-01-2 | LP1Y-S(130)-165115-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165115 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165115 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 4.813 | 7.32 | sq ft | 2.82 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Edgar Castaneda | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144067 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247874 | 26003H | 2086J | LP1Y-S(130)-165116-01-3 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.8667 | 2.86 | sq ft | 2.36 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-25 | 145565 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S247872 | 26003H | 2084J | LP1Y-S(130)-165116-01-1 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143935 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247873 | 26003H | 2085J | LP1Y-S(130)-165116-01-2 | LP1Y-S(130)-165116-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 1" SS S(130) (315) (103) 165116 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165116 |  | TFS00D002YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 4.7542 | 7.28 | sq ft | 2.78 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143969 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247876 | 26003H | 2088J | LP1Y-S(130)-165215-01-2 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 5.6208 | 7.89 | sq ft | 3.39 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Henrique Barahona | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 0%
C34-S247877 | 26003H | 2089J | LP1Y-S(130)-165215-01-3 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.125 | 2.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146050
C34-S247875 | 26003H | 2087J | LP1Y-S(130)-165215-01-1 | LP1Y-S(130)-165215-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165215 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165215 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Roberto Tobias (WF) | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 0%
C34-S247880 | 26003H | 2092J | LP1Y-S(130)-165216-01-3 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.125 | 2.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247879 | 26003H | 2091J | LP1Y-S(130)-165216-01-2 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 4.9341 | 7.53 | sq ft | 3.03 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144283 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247878 | 26003H | 2090J | LP1Y-S(130)-165216-01-1 | LP1Y-S(130)-165216-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 1" SS S(130) (315) (103) 165216 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165216 |  | TFS00D003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-30 | George Allahverdian | 2026-03-31 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Omar Puente | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144460 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S247881 | 26003H | 2093J | LP1Y-S(130)-165315-01-1 | LP1Y-S(130)-165315-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165315 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165315 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Roberto Tobias (WF) | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S247882 | 26003H | 2094J | LP1Y-S(130)-165315-01-2 | LP1Y-S(130)-165315-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165315 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165315 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 9.1056 | 10.48 | sq ft | 5.48 | ft | 2026-02-13 |  |  |  |  | 2026-04-01 | Jacob Perez | 2026-04-01 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-06 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | [6 empty] | 86% |  |  |  | 0%
C34-S247884 | 26003H | 2096J | LP1Y-S(130)-165316-01-2 | LP1Y-S(130)-165316-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165316 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165316 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 9.135 | 10.5 | sq ft | 5.5 | ft | 2026-02-13 |  |  |  |  | 2026-04-01 | Jacob Perez | 2026-04-01 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-06 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | [6 empty] | 86% |  |  |  | 0%
C34-S247883 | 26003H | 2095J | LP1Y-S(130)-165316-01-1 | LP1Y-S(130)-165316-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165316 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165316 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144459 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247886 | 26003H | 2098J | LP1Y-S(130)-165317-01-2 | LP1Y-S(130)-165317-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165317 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165317 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S247885 | 26003H | 2097J | LP1Y-S(130)-165317-01-1 | LP1Y-S(130)-165317-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165317 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165317 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 9.2011 | 10.55 | sq ft | 5.55 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | [6 empty] | 86% |  |  |  | 0%
C34-S247888 | 26003H | 2100J | LP1Y-S(130)-165318-01-2 | LP1Y-S(130)-165318-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165318 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165318 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  |  |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% |  |  |  | 0%
C34-S247887 | 26003H | 2099J | LP1Y-S(130)-165318-01-1 | LP1Y-S(130)-165318-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165318 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165318 |  | TFS00D005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 8.7091 | 10.2 | sq ft | 5.2 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | [6 empty] | 86% |  |  |  | 0%
C34-S247889 | 26003H | 2101J | LP1Y-S(130)-165405-01-1 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S247890 | 26003H | 2102J | LP1Y-S(130)-165405-01-2 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 6.5461 | 8.55 | sq ft | 4.05 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% |  |  |  | 0%
C34-S247891 | 26003H | 2103J | LP1Y-S(130)-165405-01-3 | LP1Y-S(130)-165405-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 1" SS S(130) (315) (103) 165405 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165405 |  | TFS00D006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.1764 | 2.37 | sq ft | 1.87 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% |  |  |  | 0%
C34-S247892 | 26003H | 2104J | LP1Y-S(130)-165705-01-1 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247897 | 26003H | 2109J | LP1Y-S(130)-165705-01-3 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247894 | 26003H | 2106J | LP1Y-S(130)-165705-01-4 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247895 | 26003H | 2107J | LP1Y-S(130)-165705-01-5 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247896 | 26003H | 2108J | LP1Y-S(130)-165705-01-6 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247893 | 26003H | 2105J | LP1Y-S(130)-165705-01-2 | LP1Y-S(130)-165705-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P036 | 2026-08-24 |  | LP1Y 1" SS S(130) (315) (103) 165705 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165705 |  | TFS00D007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 8 | 8 | 0 | 8.9463 | 14.12 | sq ft | 5.13 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247904 | 26003H | 2116J | LP1Y-S(130)-165805-01-3 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 28.2138 | 20.88 | sq ft | 19.88 | ft | 2026-02-13 |  |  |  |  | 2026-03-19 | Jacob Perez | 2026-03-19 | George Allahverdian | 2026-03-19 | Jacob Perez | 2026-03-19 | Jacob Perez | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | Carlos Montoya | 2026-03-26 | 2026-03-25 | 2026-03-25 | 2026-03-25 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% |  |  |  | 0%
C34-S247899 | 26003H | 2111J | LP1Y-S(130)-165805-01-2 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 6 | 6 | 0 | 5.9638 | 10.71 | sq ft | 3.21 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-24 | 143452, 143461
C34-S247900 | 26003H | 2112J | LP1Y-S(130)-165805-01-4 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 8.1167 | 8.36 | sq ft | 5.36 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143898
C34-S247901 | 26003H | 2113J | LP1Y-S(130)-165805-01-5 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 2 | 2 | 0 | 11.6188 | 9.54 | sq ft | 8.04 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-23 | N/A | N/A | Henrique Barahona | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% |  |  |  | 50%
C34-S247898 | 26003H | 2110J | LP1Y-S(130)-165805-01-1 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 28.2138 | 20.88 | sq ft | 19.88 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | Carlos Montoya | 2026-03-26 | 2026-03-25 | 2026-03-25 | 2026-03-25 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% |  |  |  | 0%
C34-S247903 | 26003H | 2115J | LP1Y-S(130)-165805-01-7 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 2.2731 | 1.73 | sq ft | 1.23 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247902 | 26003H | 2114J | LP1Y-S(130)-165805-01-6 | LP1Y-S(130)-165805-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 165805 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165805 |  | TFS00D001YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 9.2412 | 10.46 | sq ft | 5.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | N/A | N/A | Henrique Barahona | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% |  |  |  | 75%
C34-S247905 | 26003H | 2117J | LP1Y-S(130)-166205-01-1 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | N/A | N/A | Omar Puente | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S247907 | 26003H | 2119J | LP1Y-S(130)-166205-01-3 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 2 | 2 | 0 | 2.7073 | 3.34 | sq ft | 1.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247906 | 26003H | 2118J | LP1Y-S(130)-166205-01-2 | LP1Y-S(130)-166205-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166205 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166205 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 6 | 6 | 0 | 7.2878 | 9.07 | sq ft | 4.57 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-21 | 2026-04-21 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | [6 empty] | 83% |  |  |  | 0%
C34-S247910 | 26003H | 2122J | LP1Y-S(130)-166206-01-3 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 2 | 2 | 0 | 2.7073 | 3.34 | sq ft | 1.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247909 | 26003H | 2121J | LP1Y-S(130)-166206-01-2 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 6 | 6 | 0 | 6.223 | 8.32 | sq ft | 3.82 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-21 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | [6 empty] | 83% |  |  |  | 0%
C34-S247908 | 26003H | 2120J | LP1Y-S(130)-166206-01-1 | LP1Y-S(130)-166206-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS S(130) (315) (103) 166206 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166206 |  | TFS00E006YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S247911 | 26003H | 2123J | LP1Y-S(130)-166308-01-1 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247913 | 26003H | 2125J | LP1Y-S(130)-166308-01-3 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.4408 | 2.56 | sq ft | 2.06 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian; ED: 2026-04-08; EL: Jacob Perez; FD: 2026-04-08; FL: Jacob Perez | 2026-04-09 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247912 | 26003H | 2124J | LP1Y-S(130)-166308-01-2 | LP1Y-S(130)-166308-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166308 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166308 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 4.5927 | 7.16 | sq ft | 2.66 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247915 | 26003H | 2127J | LP1Y-S(130)-166309-01-2 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 4.3127 | 5.66 | sq ft | 2.66 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247916 | 26003H | 2128J | LP1Y-S(130)-166309-01-3 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.125 | 2.33 | sq ft | 1.83 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-07 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247914 | 26003H | 2126J | LP1Y-S(130)-166309-01-1 | LP1Y-S(130)-166309-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 1" SS S(130) (315) (103) 166309 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166309 |  | TFS00E007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247917 | 26003H | 2129C | LP1Y-SC-018102-01-1 | LP1Y-SC-018102-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018102 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018102 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247918 | 26003H | 2130C | LP1Y-SC-018104-01-1 | LP1Y-SC-018104-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018104 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018104 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247919 | 26003H | 2131C | LP1Y-SC-018106-01-1 | LP1Y-SC-018106-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018106 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018106 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247920 | 26003H | 2132C | LP1Y-SC-018108-01-1 | LP1Y-SC-018108-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018108 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018108 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247921 | 26003H | 2133C | LP1Y-SC-018110-01-1 | LP1Y-SC-018110-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018110 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018110 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247922 | 26003H | 2134C | LP1Y-SC-018144-01-1 | LP1Y-SC-018144-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 0.75" CS SC (2) (101) 018144 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018144 |  | TFS00D001YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 6.5188 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-03 | 2026-04-03 | 2026-04-03 | 100%
C34-S247923 | 26003H | 2135C | LP1Y-SC-018146-01-1 | LP1Y-SC-018146-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 0.75" CS SC (2) (101) 018146 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018146 |  | TFS00D001YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 6.5341 | 5.47 | sq ft | 3.97 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-01 | 2026-04-01 | 2026-04-01 |  |  |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% |  |  |  | 0%
C34-S247924 | 26003H | 2136C | LP1Y-SC-018153-01-1 | LP1Y-SC-018153-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS SC (2) (101) 018153 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018153 |  | TFS00D007YSPP |  | 2-SC | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247925 | 26003H | 2137C | LP1Y-SC-018159-01-1 | LP1Y-SC-018159-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 0.75" CS SC (2) (101) 018159 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018159 |  | TFS00D007YSPP |  | 2-SC | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247926 | 26003H | 2138C | LP1Y-SC-018161-01-1 | LP1Y-SC-018161-01 | 0 | N | PRIORITY-1 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P036 | 2026-08-24 |  | LP1Y 1" CS SC (2) (101) 018161 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018161 |  | TFS00D007YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247927 | 26003H | 2139C | LP1Y-SC-034104-01-1 | LP1Y-SC-034104-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS SC (2) (101) 034104 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034104 |  | TFS00D001YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.4101 | 5.38 | sq ft | 3.88 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247928 | 26003H | 2140C | LP1Y-SC-034106-01-1 | LP1Y-SC-034106-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS SC (2) (101) 034106 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034106 |  | TFS00D001YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247929 | 26003H | 2141C | LP1Y-SC-034108-01-1 | LP1Y-SC-034108-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 1" CS SC (2) (101) 034108 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034108 |  | TFS00D001YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247930 | 26003H | 2142C | LP1Y-SC-034181-01-1 | LP1Y-SC-034181-01 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P018 | 2026-06-15 |  | LP1Y 0.75" CS SC (2) (101) 034181 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-034181 |  | TFS00D001YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 6.9092 | 5.72 | sq ft | 4.22 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jorge Hernandez | 2026-04-06 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-03 | 2026-04-03 | 2026-04-03 | 100%
C34-S247931 | 26003H | 2143J | LP1Y-SRACNP-011010-04-1 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 | 86 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-20 | [9 empty] | 100% |  |  |  | 100% | 2026-04-09 | 144386
C34-S247932 | 26003H | 2144J | LP1Y-SRACNP-011010-04-2 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 | 86 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 18 | 18 | 0 | 56.7006 | 17.87 | sq ft | 7.06 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 40% |  |  |  | 20%
C34-S247933 | 26003H | 2145J | LP1Y-SRACNP-011010-04-3 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 | 86 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 33.1684 | 8.81 | sq ft | 4.34 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Carlos Guillen | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144506
C34-S247934 | 26003H | 2146J | LP1Y-SRACNP-011010-04-4 | LP1Y-SRACNP-011010-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 011010 | SRACNP |  | 108 | 86 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011010 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 109.78 | 25.2 | sq ft | 18 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | N/A | N/A | Henrique Barahona | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144512
C34-S247936 | 26003H | 2148J | LP1Y-SRACNP-108006-01-2 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7538 | 7.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-05-02 | 2026-05-02 | 2026-05-02 | 100%
C34-S247938 | 26003H | 2150J | LP1Y-SRACNP-108006-01-4 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.41 | 6.79 | sq ft | 3.79 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Roberto Tobias (WF) | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144482
C34-S247935 | 26003H | 2147J | LP1Y-SRACNP-108006-01-1 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145578
C34-S247937 | 26003H | 2149J | LP1Y-SRACNP-108006-01-3 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 64.78 | 19.79 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247939 | 26003H | 2151J | LP1Y-SRACNP-108006-01-5 | LP1Y-SRACNP-108006-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 77.66 | 30.75 | sq ft | 27.75 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 75% |  |  |  | 75%
C34-S247940 | 26003H | 2152J | LP1Y-SRACNP-108006-03-1 | LP1Y-SRACNP-108006-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 12 | 12 | 0 | 70.5 | 22.62 | sq ft | 5.63 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247941 | 26003H | 2153J | LP1Y-SRACNP-108006-03-2 | LP1Y-SRACNP-108006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108006 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108006 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.2738 | 7.8 | sq ft | 3.8 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145598
C34-S247942 | 26003H | 2154J | LP1Y-SRACNP-108009-01-1 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145576
C34-S247944 | 26003H | 2156J | LP1Y-SRACNP-108009-01-3 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 52.5525 | 12.1 | sq ft | 8.58 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-02 | 2026-04-02 | 2026-04-01 | 2026-04-02 | N/A | N/A | Roberto Tobias (WF) | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144464
C34-S247943 | 26003H | 2155J | LP1Y-SRACNP-108009-01-2 | LP1Y-SRACNP-108009-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108009 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108009 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 34.6706 | 8.27 | sq ft | 5.4 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145682
C34-S247945 | 26003H | 2157J | LP1Y-SRACNP-108102-01-1 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145572
C34-S247948 | 26003H | 2160J | LP1Y-SRACNP-108102-01-4 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 16 | 16 | 0 | 465.8336 | 22.93 | sq ft | 3.78 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247947 | 26003H | 2159J | LP1Y-SRACNP-108102-01-3 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 33.9197 | 9.96 | sq ft | 1.47 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144405
C34-S247946 | 26003H | 2158J | LP1Y-SRACNP-108102-01-2 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.6917 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144220
C34-S247949 | 26003H | 2161J | LP1Y-SRACNP-108102-01-5 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 25 | 22 | 3 | 128.0275 | 39.44 | sq ft | 8.4 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247950 | 26003H | 2162J | LP1Y-SRACNP-108102-01-6 | LP1Y-SRACNP-108102-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108102 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108102 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 16 | 16 | 0 | 65.7645 | 16.64 | sq ft | 9.37 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 75% |  |  |  | 50%
C34-S247953 | 26003H | 2165J | LP1Y-SRACNP-108103-01-3 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 420 | 12 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247951 | 26003H | 2163J | LP1Y-SRACNP-108103-01-1 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144853
C34-S247952 | 26003H | 2164J | LP1Y-SRACNP-108103-01-2 | LP1Y-SRACNP-108103-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 16 | 16 | 0 | 97.6241 | 26.74 | sq ft | 14.49 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-17 | N/A | N/A | Omar Puente | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145680
C34-S247958 | 26003H | 2170J | LP1Y-SRACNP-108103-02-5 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 20 | 20 | 0 | 468.7847 | 23.56 | sq ft | 4.3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247957 | 26003H | 2169J | LP1Y-SRACNP-108103-02-4 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 16.3092 | 5.21 | sq ft | 1.34 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144484
C34-S247955 | 26003H | 2167J | LP1Y-SRACNP-108103-02-2 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.6352 | 8.32 | sq ft | 3.1 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144401
C34-S247954 | 26003H | 2166J | LP1Y-SRACNP-108103-02-1 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144237
C34-S247956 | 26003H | 2168J | LP1Y-SRACNP-108103-02-3 | LP1Y-SRACNP-108103-02 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108103 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108103 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 25 | 24 | 1 | 82.8552 | 31.52 | sq ft | 5.99 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247965 | 26003H | 2177J | LP1Y-SRACNP-108104-07-2 | LP1Y-SRACNP-108104-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 46 | 46 | 0 | 547.5334 | 47.01 | sq ft | 14.51 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247964 | 26003H | 2176J | LP1Y-SRACNP-108104-07-1 | LP1Y-SRACNP-108104-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 30 | 30 | 0 | 92.3888 | 36.09 | sq ft | 8.42 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247966 | 26003H | 2178J | LP1Y-SRACNP-108104-08-1 | LP1Y-SRACNP-108104-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 24.25 | 22 | 2.25 | 44.0888 | 29.86 | sq ft | 7.36 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | [6 empty] | 79% |  |  |  | 0%
C34-S247967 | 26003H | 2179J | LP1Y-SRACNP-108104-08-2 | LP1Y-SRACNP-108104-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 112.44 | 34.21 | sq ft | 4.71 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247970 | 26003H | 2182J | LP1Y-SRACNP-108104-09-3 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 24.86 | 10.08 | sq ft | 8.58 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144507
C34-S247968 | 26003H | 2180J | LP1Y-SRACNP-108104-09-1 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.1225 | 12.57 | sq ft | 7.07 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 67% |  |  |  | 0%
C34-S247969 | 26003H | 2181J | LP1Y-SRACNP-108104-09-2 | LP1Y-SRACNP-108104-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 34 | 34 | 0 | 56.8505 | 33.18 | sq ft | 5.37 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% |  |  |  | 85%
C34-S247972 | 26003H | 2184J | LP1Y-SRACNP-108105-01-2 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 8.9873 | 2.78 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144276
C34-S247971 | 26003H | 2183J | LP1Y-SRACNP-108105-01-1 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146060
C34-S247973 | 26003H | 2185J | LP1Y-SRACNP-108105-01-3 | LP1Y-SRACNP-108105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108105 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108105 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 35 | 30 | 5 | 485.117 | 40.59 | sq ft | 5.95 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247976 | 26003H | 2188J | LP1Y-SRACNP-108106-03-1 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146070
C34-S247977 | 26003H | 2189J | LP1Y-SRACNP-108106-03-2 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 18.9293 | 5.43 | sq ft | 1.43 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145085
C34-S247979 | 26003H | 2191J | LP1Y-SRACNP-108106-03-4 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 30.0469 | 8.02 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145677
C34-S247980 | 26003H | 2192J | LP1Y-SRACNP-108106-03-5 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 18.75 | 18 | 0.75 | 74.5247 | 20.81 | sq ft | 7.39 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247978 | 26003H | 2190J | LP1Y-SRACNP-108106-03-3 | LP1Y-SRACNP-108106-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 10 | 9 | 1 | 24.0025 | 12.35 | sq ft | 1.25 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255917 | 26003H | 2193J-L1 | LP1Y-SRACNP-108106-04-1-L1 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146061
C34-S247981 | 26003H | 2193J | LP1Y-SRACNP-108106-04-1 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 24 | 24 | 0 | 61.5134 | 15.41 | sq ft | 2.18 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144314
C34-S247982 | 26003H | 2194J | LP1Y-SRACNP-108106-04-2 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 70.4358 | 16.19 | sq ft | 8.16 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | [6 empty] | 67% |  |  |  | 0%
C34-S247983 | 26003H | 2195J | LP1Y-SRACNP-108106-04-3 | LP1Y-SRACNP-108106-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 90.1742 | 21.01 | sq ft | 14.51 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 67% |  |  |  | 67%
C34-S247984 | 26003H | 2196J | LP1Y-SRACNP-108111-02-1 | LP1Y-SRACNP-108111-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.25 | 6 | 4.25 | 66.7038 | 22.3 | sq ft | 6.8 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249494 | 26003H | 2197J | LP1Y-SRACNP-108111-03-1 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.75 | 10 | 0.75 | 22.2788 | 15.03 | sq ft | 1.53 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-24 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 |  | 2026-04-28 |  | 2026-04-27 |  | 83% |  |  |  | 17%
C34-S249495 | 26003H | 2198J | LP1Y-SRACNP-108111-03-2 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 46.08 | 19.38 | sq ft | 13.88 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145730
C34-S249496 | 26003H | 2199J | LP1Y-SRACNP-108111-03-3 | LP1Y-SRACNP-108111-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108111 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108111 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.6025 | 15.2 | sq ft | 12.2 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 67% |  |  |  | 0%
C34-S249497 | 26003H | 2200J | LP1Y-SRACNP-108119-01-1 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 37.4138 | 15.51 | sq ft | 12.51 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 145021
C34-S249499 | 26003H | 2202J | LP1Y-SRACNP-108119-01-3 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.9463 | 6.54 | sq ft | 2.54 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S249498 | 26003H | 2201J | LP1Y-SRACNP-108119-01-2 | LP1Y-SRACNP-108119-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.6488 | 13.82 | sq ft | 6.82 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 145022
C34-S249503 | 26003H | 2206J | LP1Y-SRACNP-108119-03-3 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 81.73 | 32.29 | sq ft | 29.29 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 0%
C34-S249501 | 26003H | 2204J | LP1Y-SRACNP-108119-03-2 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 20 | 20 | 0 | 82.85 | 30.87 | sq ft | 6.88 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249502 | 26003H | 2205J | LP1Y-SRACNP-108119-03-4 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 75.0575 | 28.64 | sq ft | 3.64 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249500 | 26003H | 2203J | LP1Y-SRACNP-108119-03-1 | LP1Y-SRACNP-108119-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108119 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108119 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 14 | 14 | 0 | 39.8925 | 18.36 | sq ft | 9.86 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-24 | N/A | N/A | Edgar Castaneda | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 71%
C34-S249505 | 26003H | 2208J | LP1Y-SRACNP-108135-01-2 | LP1Y-SRACNP-108135-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.9963 | 8.79 | sq ft | 3.79 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 145849
C34-S249504 | 26003H | 2207J | LP1Y-SRACNP-108135-01-1 | LP1Y-SRACNP-108135-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.3175 | 6.47 | sq ft | 4.97 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S249509 | 26003H | 2212J | LP1Y-SRACNP-108203-01-1 | LP1Y-SRACNP-108203-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 6" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144225
C34-S249510 | 26003H | 2213J | LP1Y-SRACNP-108203-01-2 | LP1Y-SRACNP-108203-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 6" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 20 | 20 | 0 | 520.3122 | 39.31 | sq ft | 14.97 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249512 | 26003H | 2215J | LP1Y-SRACNP-108203-02-2 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.5767 | 8.31 | sq ft | 3.09 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144288
C34-S249511 | 26003H | 2214J | LP1Y-SRACNP-108203-02-1 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144228
C34-S249513 | 26003H | 2216J | LP1Y-SRACNP-108203-02-3 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 25 | 24 | 1 | 86.6536 | 32.34 | sq ft | 6.67 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249514 | 26003H | 2217J | LP1Y-SRACNP-108203-02-4 | LP1Y-SRACNP-108203-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108203 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108203 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 36 | 36 | 0 | 489.5059 | 29.71 | sq ft | 6.43 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249520 | 26003H | 2223J | LP1Y-SRACNP-108204-02-1 | LP1Y-SRACNP-108204-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 39.25 | 36 | 3.25 | 566.1116 | 65.2 | sq ft | 11.32 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249521 | 26003H | 2224J | LP1Y-SRACNP-108204-02-2 | LP1Y-SRACNP-108204-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 18.5938 | 8.3 | sq ft | 4.3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 0%
C34-S249522 | 26003H | 2225J | LP1Y-SRACNP-108204-03-1 | LP1Y-SRACNP-108204-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 39.0138 | 22.71 | sq ft | 8.71 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-24 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-01 | 2026-04-29 | 2026-04-29 |  |  |  | 78% |  |  |  | 67%
C34-S249523 | 26003H | 2226J | LP1Y-SRACNP-108204-05-1 | LP1Y-SRACNP-108204-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 43.81 | 20.29 | sq ft | 14.79 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | [6 empty] | 60% |  |  |  | 0%
C34-S249525 | 26003H | 2228J | LP1Y-SRACNP-108205-02-2 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 15.9706 | 4.27 | sq ft | 2.06 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144557
C34-S249526 | 26003H | 2229J | LP1Y-SRACNP-108205-02-3 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 31 | 26 | 5 | 478.0753 | 39.09 | sq ft | 4.7 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249524 | 26003H | 2227J | LP1Y-SRACNP-108205-02-1 | LP1Y-SRACNP-108205-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108205 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108205 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146067
C34-S249531 | 26003H | 2234J | LP1Y-SRACNP-108206-02-3 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 10 | 9 | 1 | 28.3269 | 13.27 | sq ft | 2.02 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249530 | 26003H | 2233J | LP1Y-SRACNP-108206-02-2 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 18.8842 | 5.42 | sq ft | 1.42 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144402
C34-S249533 | 26003H | 2236J | LP1Y-SRACNP-108206-02-5 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 18.75 | 18 | 0.75 | 86.0369 | 23.27 | sq ft | 9.44 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-27 | 2026-04-27 | 2026-05-01 | 2026-04-27 | 2026-04-28 |  | 2026-04-28 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 67%
C34-S249532 | 26003H | 2235J | LP1Y-SRACNP-108206-02-4 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 32.6181 | 8.58 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145683
C34-S249529 | 26003H | 2232J | LP1Y-SRACNP-108206-02-1 | LP1Y-SRACNP-108206-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146069
C34-S249536 | 26003H | 2239J | LP1Y-SRACNP-108206-03-3 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 52.9045 | 12.44 | sq ft | 5.04 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145726
C34-S249535 | 26003H | 2238J | LP1Y-SRACNP-108206-03-2 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 45.9213 | 10.95 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144404
C34-S249534 | 26003H | 2237J | LP1Y-SRACNP-108206-03-1 | LP1Y-SRACNP-108206-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146068
C34-S249537 | 26003H | 2240J | LP1Y-SRACNP-108213-01-1 | LP1Y-SRACNP-108213-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.25 | 6 | 4.25 | 66.9375 | 22.39 | sq ft | 6.89 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249538 | 26003H | 2241J | LP1Y-SRACNP-108213-02-1 | LP1Y-SRACNP-108213-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.75 | 10 | 0.75 | 22.65 | 15.17 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-30 | 145904
C34-S249539 | 26003H | 2242J | LP1Y-SRACNP-108213-02-2 | LP1Y-SRACNP-108213-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108213 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108213 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 76.6463 | 24.29 | sq ft | 8.79 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249541 | 26003H | 2244J | LP1Y-SRACNP-108219-02-2 | LP1Y-SRACNP-108219-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 48.8213 | 13.15 | sq ft | 4.13 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Omar Puente | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145678
C34-S249540 | 26003H | 2243J | LP1Y-SRACNP-108219-02-1 | LP1Y-SRACNP-108219-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 37 | 34 | 3 | 153.9809 | 47.34 | sq ft | 14.33 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249542 | 26003H | 2245J | LP1Y-SRACNP-108219-04-1 | LP1Y-SRACNP-108219-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.7209 | 7.91 | sq ft | 1.26 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez | 2026-04-21 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-30 | 145906
C34-S256537 | 26003H | 2245J-L1 | LP1Y-SRACNP-108219-04-1-L1 | LP1Y-SRACNP-108219-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-21 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146076
C34-S249543 | 26003H | 2246J | LP1Y-SRACNP-108219-04-2 | LP1Y-SRACNP-108219-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108219 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108219 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 28 | 28 | 0 | 489.6728 | 30.74 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249546 | 26003H | 2249J | LP1Y-SRACNP-108235-02-1 | LP1Y-SRACNP-108235-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 38.0463 | 15.74 | sq ft | 12.74 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 75% |  |  |  | 50%
C34-S249547 | 26003H | 2250J | LP1Y-SRACNP-108235-02-2 | LP1Y-SRACNP-108235-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 27.1288 | 12.28 | sq ft | 7.78 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 80% |  |  |  | 60%
C34-S249549 | 26003H | 2252J | LP1Y-SRACNP-108248-01-2 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7538 | 7.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-05-02 | 2026-05-02 | 2026-05-02 | 100%
C34-S249548 | 26003H | 2251J | LP1Y-SRACNP-108248-01-1 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146065
C34-S249550 | 26003H | 2253J | LP1Y-SRACNP-108248-01-3 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 12 | 12 | 0 | 76.99 | 25.08 | sq ft | 8.08 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249551 | 26003H | 2254J | LP1Y-SRACNP-108248-01-4 | LP1Y-SRACNP-108248-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108248 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108248 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 78.54 | 31.75 | sq ft | 27.25 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 80% |  |  |  | 40%
C34-S249552 | 26003H | 2255J | LP1Y-STORM-100408-01-1 | LP1Y-STORM-100408-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORM (315) 100408 | STORM |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100408 |  | TFS00D003YSPP |  | 315-STORM | NONE | 4" | 316 SS | 0 | 0 | 0 | 16.5 | 3.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144089 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249553 | 26003H | 2256J | LP1Y-STORM-100408-01-2 | LP1Y-STORM-100408-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORM (315) 100408 | STORM |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100408 |  | TFS00D003YSPP |  | 315-STORM | NONE | 4" | 316 SS | 12 | 12 | 0 | 58.355 | 16 | sq ft | 8.83 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144514 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249555 | 26003H | 2258J | LP1Y-STORM-100409-01-2 | LP1Y-STORM-100409-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORM (315) (108) 100409 | STORM |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100409 |  | TFS00D003YSPP |  | 315-STORM | NONE | 3" | 316 SS | 6 | 6 | 0 | 28.353 | 6.55 | sq ft | 5.05 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Edgar Castaneda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144832 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249554 | 26003H | 2257J | LP1Y-STORM-100409-01-1 | LP1Y-STORM-100409-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORM (315) (108) 100409 | STORM |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100409 |  | TFS00D003YSPP |  | 315-STORM | NONE | 3" | 316 SS | 0 | 0 | 0 | 11.5 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144087, 144088 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249556 | 26003H | 2259J | LP1Y-STORMP-015002-12-1 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 20 | 16 | 4 | 48.0696 | 18.96 | sq ft | 2.96 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 |  |  | 88% |  |  |  | 0%
C34-S249557 | 26003H | 2260J | LP1Y-STORMP-015002-12-2 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 12 | 12 | 0 | 44.539 | 12.4 | sq ft | 2.9 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-20 | 145050 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249558 | 26003H | 2261J | LP1Y-STORMP-015002-12-3 | LP1Y-STORMP-015002-12 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 18 | 18 | 0 | 81.594 | 19.9 | sq ft | 11.4 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144454 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249562 | 26003H | 2265J | LP1Y-STORMP-015002-25-4 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 9 | 6 | 3 | 36.388 | 9.8 | sq ft | 1.3 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144242 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249559 | 26003H | 2262J | LP1Y-STORMP-015002-25-1 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 9 | 9 | 0 | 46.8086 | 11.86 | sq ft | 6.36 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Montoya | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% |  |  |  | 67%
C34-S249560 | 26003H | 2263J | LP1Y-STORMP-015002-25-2 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 15 | 14 | 1 | 56.7357 | 17.07 | sq ft | 8.07 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-05-01 | 100% |  | 2026-05-01 |  | 86%
C34-S249561 | 26003H | 2264J | LP1Y-STORMP-015002-25-3 | LP1Y-STORMP-015002-25 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 015002 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015002 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 8.75 | 7 | 1.75 | 32.4911 | 16.36 | sq ft | 3.86 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-30 | 145908
C34-S249563 | 26003H | 2266J | LP1Y-STORMP-037007-04-1 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 15.0488 | 9.98 | sq ft | 1.98 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-20 |  |  | 75%
C34-S249564 | 26003H | 2267J | LP1Y-STORMP-037007-04-2 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.6388 | 14.19 | sq ft | 7.19 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-30 | George Allahverdian | 2026-03-31 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 50%
C34-S249565 | 26003H | 2268J | LP1Y-STORMP-037007-04-3 | LP1Y-STORMP-037007-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 33.1925 | 13.91 | sq ft | 10.91 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 144871 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249567 | 26003H | 2270J | LP1Y-STORMP-100402-01-2 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 8 | 8 | 0 | 29.2067 | 7.11 | sq ft | 4.42 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-30 | George Allahverdian | 2026-03-31 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Roberto Tobias (WF) | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% |  |  |  | 50%
C34-S249566 | 26003H | 2269J | LP1Y-STORMP-100402-01-1 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 0 | 0 | 0 | 16.5 | 3.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144086 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249568 | 26003H | 2271J | LP1Y-STORMP-100402-01-3 | LP1Y-STORMP-100402-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 23 | 20 | 3 | 32.7686 | 14.66 | sq ft | 1.61 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Henrique Barahona | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 144851 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249572 | 26003H | 2275J | LP1Y-STORMP-100402-02-4 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 15 | 12 | 3 | 44.5518 | 11.81 | sq ft | 3.1 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 144129 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249569 | 26003H | 2272J | LP1Y-STORMP-100402-02-1 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143964 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249570 | 26003H | 2273J | LP1Y-STORMP-100402-02-2 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.4014 | 8.27 | sq ft | 3.06 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144408 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249571 | 26003H | 2274J | LP1Y-STORMP-100402-02-3 | LP1Y-STORMP-100402-02 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100402 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100402 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 11 | 10 | 1 | 38.4728 | 13.39 | sq ft | 2.11 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249578 | 26003H | 2281J | LP1Y-STORMP-100403-02-1 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 15 | 12 | 3 | 67.1782 | 16.57 | sq ft | 9.57 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Carlos Guillen | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 |  | 2026-04-16 |  | 2026-04-15 |  | 80% |  |  |  | 60%
C34-S249580 | 26003H | 2283J | LP1Y-STORMP-100403-02-3 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 6 | 5 | 1 | 21.3603 | 9.95 | sq ft | 1.45 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249579 | 26003H | 2282J | LP1Y-STORMP-100403-02-2 | LP1Y-STORMP-100403-02 | 0 | N | PRIORITY-1 | 2026-04-08 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 18 | 17 | 1 | 58.5059 | 19.59 | sq ft | 4.09 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-28 |  | 2026-04-28 | 2026-04-30 |  | 2026-04-30 |  |  |  | 63% |  |  |  | 38%
C34-S249581 | 26003H | 2284J | LP1Y-STORMP-100403-04-1 | LP1Y-STORMP-100403-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249582 | 26003H | 2285J | LP1Y-STORMP-100403-04-2 | LP1Y-STORMP-100403-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P036 | 2026-08-24 |  | LP1Y 3" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 12 | 12 | 0 | 37.3869 | 9.69 | sq ft | 2.69 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249585 | 26003H | 2288J | LP1Y-STORMP-100403-05-3 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 8 | 8 | 0 | 36.4861 | 10.63 | sq ft | 4.36 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144313 | [40 empty] | 2026-04-20 | 2026-04-20 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249583 | 26003H | 2286J | LP1Y-STORMP-100403-05-1 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 26 | 22 | 4 | 89.2105 | 25.96 | sq ft | 8.46 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-22 | 145219 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249586 | 26003H | 2289J | LP1Y-STORMP-100403-05-4 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 19 | 19 | 0 | 77.5801 | 21.6 | sq ft | 12.09 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144700 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249584 | 26003H | 2287J | LP1Y-STORMP-100403-05-2 | LP1Y-STORMP-100403-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 7 | 6 | 1 | 75.1409 | 20.96 | sq ft | 12.26 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249589 | 26003H | 2292J | LP1Y-STORMP-100406-01-3 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 14 | 12 | 2 | 35.7225 | 16.2 | sq ft | 10.2 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-06 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-07 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-07 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-07 | 2026-04-09 | 100% | 2026-04-10 | 144412 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249587 | 26003H | 2290J | LP1Y-STORMP-100406-01-1 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | 2026-04-14 | 2026-04-14 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 12.25 | 7 | 5.25 | 36.6925 | 17.03 | sq ft | 2.53 | ft | 2026-02-13 | CD: 2026-04-02; CL: Shannon Carpenter; DD: 2026-04-03; DL: George Allahverdian | 2026-04-14 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 |  |  | 86% |  |  |  | 0%
C34-S249588 | 26003H | 2291J | LP1Y-STORMP-100406-01-2 | LP1Y-STORMP-100406-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS STORMP (315) (308) 100406 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 3" | 316 SS | 12.25 | 10 | 2.25 | 31.535 | 17.56 | sq ft | 6.56 | ft | 2026-02-13 |  |  |  |  | 2026-04-02 | Shannon Carpenter | 2026-04-03 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Carlos Guillen | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 |  | 2026-04-14 |  | 2026-04-29 |  | 75% |  |  |  | 38%
C34-S249591 | 26003H | 2294J | LP1Y-STORMP-165104-02-1 | LP1Y-STORMP-165104-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.8513 | 11.97 | sq ft | 6.47 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Carlos Guillen | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-23 | 145268 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249593 | 26003H | 2296J | LP1Y-STORMP-165104-03-2 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 29.04 | 12.33 | sq ft | 9.33 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144284 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249592 | 26003H | 2295J | LP1Y-STORMP-165104-03-1 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 47.85 | 19.46 | sq ft | 16.46 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144560 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249594 | 26003H | 2297J | LP1Y-STORMP-165104-03-3 | LP1Y-STORMP-165104-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165104 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 8 | 2 | 49.5725 | 21.45 | sq ft | 16.95 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-06 | 2026-04-02 | 2026-04-06 | 2026-04-01 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-06 | 2026-04-07 | 100% | 2026-04-07 | 144222 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249595 | 26003H | 2298J | LP1Y-STORMP-165114-02-1 | LP1Y-STORMP-165114-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 27.1013 | 11.6 | sq ft | 8.6 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143952 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249596 | 26003H | 2299J | LP1Y-STORMP-165114-02-2 | LP1Y-STORMP-165114-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 30.1125 | 12.07 | sq ft | 10.57 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-30 | 143827 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S249597 | 26003H | 2300J | LP1Y-STORMP-165114-05-1 | LP1Y-STORMP-165114-05 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 25.11 | 13.21 | sq ft | 7.71 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-15 | 2026-04-16 | 100% | 2026-04-23 | 2026-04-15 | 2026-04-23 | 100% | 2026-04-23 | 145285 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249598 | 26003H | 2301J | LP1Y-STORMP-165114-06-1 | LP1Y-STORMP-165114-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 52.03 | 25.04 | sq ft | 15.54 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145087 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249599 | 26003H | 2302J | LP1Y-STORMP-165114-06-2 | LP1Y-STORMP-165114-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS STORMP (315) (108) 165114 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165114 |  | TFS00D002YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 47.6988 | 19.4 | sq ft | 16.4 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143933 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249603 | 26003H | 2306J | LP1Y-STORMP-165204-01-4 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 11 | 7 | 4 | 28.9545 | 24.16 | sq ft | 5.66 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  |  | 2026-04-22 |  | 89% |  |  |  | 0%
C34-S249600 | 26003H | 2303J | LP1Y-STORMP-165204-01-1 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143974 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249602 | 26003H | 2305J | LP1Y-STORMP-165204-01-3 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 5.75 | 3.5 | 2.25 | 21.445 | 14.94 | sq ft | 4.94 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S249604 | 26003H | 2307J | LP1Y-STORMP-165204-01-5 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 49.2388 | 20.65 | sq ft | 16.15 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Carlos Guillen | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 60%
C34-S249601 | 26003H | 2304J | LP1Y-STORMP-165204-01-2 | LP1Y-STORMP-165204-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 |  |  |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% |  |  |  | 0%
C34-S249607 | 26003H | 2310J | LP1Y-STORMP-165204-04-3 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 45.2925 | 19.16 | sq ft | 14.66 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Aristeo Banda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 145277 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249606 | 26003H | 2309J | LP1Y-STORMP-165204-04-2 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.63 | 7.08 | sq ft | 1.58 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 0%
C34-S249605 | 26003H | 2308J | LP1Y-STORMP-165204-04-1 | LP1Y-STORMP-165204-04 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165204 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165204 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 15.0488 | 9.98 | sq ft | 1.98 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Ramiro Gonzalez | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  | 2026-04-23 | 2026-04-23 | 2026-04-15 |  |  | 75% |  |  |  | 25%
C34-S249608 | 26003H | 2311J | LP1Y-STORMP-165214-01-1 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145009 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249609 | 26003H | 2312J | LP1Y-STORMP-165214-01-2 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 4.4954 | 5.74 | sq ft | 0.24 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% |  |  |  | 0%
C34-S249612 | 26003H | 2315J | LP1Y-STORMP-165214-01-5 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 41.9513 | 17.22 | sq ft | 14.22 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Henrique Barahona | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% |  |  |  | 75%
C34-S249611 | 26003H | 2314J | LP1Y-STORMP-165214-01-4 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 11 | 8 | 3 | 23.405 | 17.23 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | 2026-04-17 |  | 88% |  |  |  | 50%
C34-S249610 | 26003H | 2313J | LP1Y-STORMP-165214-01-3 | LP1Y-STORMP-165214-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS STORMP (315) (108) 165214 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165214 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 9.75 | 6.5 | 3.25 | 20.812 | 20.44 | sq ft | 3.44 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% |  |  |  | 0%
C34-S249613 | 26003H | 2316J | LP1Y-STORMP-165304-01-2 | LP1Y-STORMP-165304-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 41.6625 | 21.11 | sq ft | 11.61 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-24 | 2026-04-27 | Passed | No | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249614 | 26003H | 2317J | LP1Y-STORMP-165304-01-1 | LP1Y-STORMP-165304-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249617 | 26003H | 2320J | LP1Y-STORMP-165304-03-3 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249616 | 26003H | 2319J | LP1Y-STORMP-165304-03-2 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S249615 | 26003H | 2318J | LP1Y-STORMP-165304-03-1 | LP1Y-STORMP-165304-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165304 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165304 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145004 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249618 | 26003H | 2321J | LP1Y-STORMP-165314-01-1 | LP1Y-STORMP-165314-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249619 | 26003H | 2322J | LP1Y-STORMP-165314-01-2 | LP1Y-STORMP-165314-01 | 0 | N | PRIORITY-1 | 2026-04-23 | 2026-04-23 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.25 | 8 | 4.25 | 33.195 | 17.6 | sq ft | 9.1 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-23 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-24 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 |  | 2026-04-28 |  | 88% |  |  |  | 63%
C34-S249622 | 26003H | 2325J | LP1Y-STORMP-165314-03-3 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249621 | 26003H | 2324J | LP1Y-STORMP-165314-03-2 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145815, 145816
C34-S249620 | 26003H | 2323J | LP1Y-STORMP-165314-03-1 | LP1Y-STORMP-165314-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165314 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165314 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145007 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249625 | 26003H | 2328J | LP1Y-STORMP-165324-01-3 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249623 | 26003H | 2326J | LP1Y-STORMP-165324-01-1 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145008 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249624 | 26003H | 2327J | LP1Y-STORMP-165324-01-2 | LP1Y-STORMP-165324-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S249628 | 26003H | 2331J | LP1Y-STORMP-165324-02-3 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249627 | 26003H | 2330J | LP1Y-STORMP-165324-02-2 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 49.5725 | 21.36 | sq ft | 14.36 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | [6 empty] | 80% |  |  |  | 0%
C34-S249626 | 26003H | 2329J | LP1Y-STORMP-165324-02-1 | LP1Y-STORMP-165324-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165324 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165324 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249632 | 26003H | 2335J | LP1Y-STORMP-165334-02-4 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249629 | 26003H | 2332J | LP1Y-STORMP-165334-02-1 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 43.3813 | 18.43 | sq ft | 13.93 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145198 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249633 | 26003H | 2336J | LP1Y-STORMP-165334-02-5 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 30.9513 | 13.06 | sq ft | 10.06 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% |  |  |  | 67%
C34-S249630 | 26003H | 2333J | LP1Y-STORMP-165334-02-2 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 26.3588 | 11.32 | sq ft | 8.32 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144410 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249631 | 26003H | 2334J | LP1Y-STORMP-165334-02-3 | LP1Y-STORMP-165334-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10.75 | 10 | 0.75 | 30.2263 | 18.04 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  |  | 2026-04-21 |  | 83% |  |  |  | 0%
C34-S249636 | 26003H | 2339J | LP1Y-STORMP-165334-06-3 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-31 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249634 | 26003H | 2337J | LP1Y-STORMP-165334-06-1 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian; ED: 2026-04-17; EL: Jacob Perez | 2026-04-21 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146075
C34-S249635 | 26003H | 2338J | LP1Y-STORMP-165334-06-2 | LP1Y-STORMP-165334-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165334 | STORMP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165334 |  | TFS00D005YSPP |  | 315-STORMP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-03-31 | George Allahverdian | 2026-04-02 | Jacob Perez | 2026-04-02 | Jacob Perez | 2026-04-02 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S249638 | 26003H | 2341J | LP1Y-STORMP-165404-01-2 | LP1Y-STORMP-165404-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS STORMP (315) (108) 165404 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165404 |  | TFS00D006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249637 | 26003H | 2340J | LP1Y-STORMP-165404-01-1 | LP1Y-STORMP-165404-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS STORMP (315) (108) 165404 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165404 |  | TFS00D006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 44.6325 | 17.57 | sq ft | 16.07 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144660 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249639 | 26003H | 2342J | LP1Y-STORMP-165704-02-1 | LP1Y-STORMP-165704-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS STORMP (315) (108) 165704 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165704 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249640 | 26003H | 2343J | LP1Y-STORMP-165704-02-2 | LP1Y-STORMP-165704-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS STORMP (315) (108) 165704 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165704 |  | TFS00D007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249641 | 26003H | 2344J | LP1Y-STORMP-165804-02-1 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 28.875 | 11.6 | sq ft | 10.1 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144664
C34-S249643 | 26003H | 2346J | LP1Y-STORMP-165804-02-3 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.6325 | 10.11 | sq ft | 4.61 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249642 | 26003H | 2345J | LP1Y-STORMP-165804-02-2 | LP1Y-STORMP-165804-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 165804 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165804 |  | TFS00D001YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 63.1463 | 22.2 | sq ft | 2.7 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249645 | 26003H | 2348J | LP1Y-STORMP-166204-02-2 | LP1Y-STORMP-166204-02 | 0 | N | PRIORITY-1 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS STORMP (315) (108) 166204 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166204 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 11.5 | 10.75 | 0.75 | 71.3988 | 25.44 | sq ft | 6.94 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-18 | Jacob Perez | 2026-04-18 | Jacob Perez | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249644 | 26003H | 2347J | LP1Y-STORMP-166204-02-1 | LP1Y-STORMP-166204-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS STORMP (315) (108) 166204 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166204 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 14 | 14 | 0 | 50.4488 | 21.78 | sq ft | 15.78 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-05-02 | 2026-05-02 | 2026-05-02 |  |  |  | 57% |  |  |  | 43%
C34-S249647 | 26003H | 2350J | LP1Y-STORMP-166214-04-2 | LP1Y-STORMP-166214-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 34.54 | 15.08 | sq ft | 10.58 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 60% |  |  |  | 60%
C34-S249646 | 26003H | 2349J | LP1Y-STORMP-166214-04-1 | LP1Y-STORMP-166214-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 48.9088 | 20.53 | sq ft | 16.03 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | [6 empty] | 75% |  |  |  | 0%
C34-S249648 | 26003H | 2351J | LP1Y-STORMP-166214-06-1 | LP1Y-STORMP-166214-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS STORMP (315) (108) 166214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166214 |  | TFS00E006YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 60.6263 | 19.33 | sq ft | 5.33 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249649 | 26003H | 2352J | LP1Y-STORMP-166304-01-1 | LP1Y-STORMP-166304-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 166304 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166304 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.655 | 12.19 | sq ft | 9.19 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144509
C34-S249650 | 26003H | 2353J | LP1Y-STORMP-166304-01-2 | LP1Y-STORMP-166304-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 166304 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166304 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 72.9738 | 25.34 | sq ft | 8.34 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249651 | 26003H | 2354J | LP1Y-STORMP-166306-03-1 | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | 2026-04-06 | 2026-04-14 | released |  |  | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 66.715 | 26.6 | sq ft | 23.6 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256300 | 26003H | 2354JA | LP1Y-STORMP-166306-03-1X | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 |  | 0 | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 41.635 | 17.1 | sq ft | 14.1 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256301 | 26003H | 2355JA | LP1Y-STORMP-166306-03-2X | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 |  | 0 | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 82.6813 | 29.02 | sq ft | 12.02 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249652 | 26003H | 2355J | LP1Y-STORMP-166306-03-2 | LP1Y-STORMP-166306-03 | 0 | N | PRIORITY-1 | 2026-04-06 | 2026-04-14 | released |  |  | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS STORMP (315) (108) 166306 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166306 |  | TFS00E007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.0163 | 29.37 | sq ft | 26.37 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249653 | 26003H | 2356J | LP1Y-SW-165102-01-1 | LP1Y-SW-165102-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS SW (315) E 165102 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165102 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 3 | 3 | 0 | 9.0219 | 8.27 | sq ft | 2.27 | ft | 2026-02-13 |  |  |  |  | 2026-03-27 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-07 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145287
C34-S249654 | 26003H | 2357J | LP1Y-SW-165102-01-2 | LP1Y-SW-165102-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SW (315) E 165102 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165102 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.1163 | 6.04 | sq ft | 4.04 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Roberto Tobias (WF) | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144312 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249656 | 26003H | 2359J | LP1Y-SW-165112-01-2 | LP1Y-SW-165112-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SW (315) 165112 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165112 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.2363 | 5.04 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144358 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249655 | 26003H | 2358J | LP1Y-SW-165112-01-1 | LP1Y-SW-165112-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SW (315) 165112 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165112 |  | TFS00D002YSPP |  | 315-SW | NONE | 2" | 316 SS | 7 | 5 | 2 | 11.4769 | 11.14 | sq ft | 2.14 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-07 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145282, 145289 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249657 | 26003H | 2360J | LP1Y-SW-165402-01-1 | LP1Y-SW-165402-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS SW (315) 165402 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165402 |  | TFS00D006YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-05 | George Allahverdian | 2026-04-05 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249658 | 26003H | 2361J | LP1Y-SW-165702-01-1 | LP1Y-SW-165702-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SW (315) 165702 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165702 |  | TFS00D007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249659 | 26003H | 2362J | LP1Y-SW-165702-01-2 | LP1Y-SW-165702-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SW (315) 165702 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165702 |  | TFS00D007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249662 | 26003H | 2365J | LP1Y-SW-165802-01-3 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 8 | 8 | 0 | 33.71 | 14.13 | sq ft | 10.63 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144671
C34-S249660 | 26003H | 2363J | LP1Y-SW-165802-01-1 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 9.5 | 9.5 | 0 | 62.8988 | 21.61 | sq ft | 4.11 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249661 | 26003H | 2364J | LP1Y-SW-165802-01-2 | LP1Y-SW-165802-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS SW (315) 165802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165802 |  | TFS00D001YSPP |  | 315-SW | NONE | 2" | 316 SS | 2 | 2 | 0 | 35.64 | 14.17 | sq ft | 12.67 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Carlos Montoya | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144665
C34-S249663 | 26003H | 2366J | LP1Y-SW-166202-01-1 | LP1Y-SW-166202-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SW (315) 166202 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166202 |  | TFS00E006YSPP |  | 315-SW | NONE | 2" | 316 SS | 14 | 14 | 0 | 67.8429 | 25.87 | sq ft | 6.37 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249664 | 26003H | 2367J | LP1Y-SW-166212-01-1 | LP1Y-SW-166212-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SW (315) 166212 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166212 |  | TFS00E006YSPP |  | 315-SW | NONE | 2" | 316 SS | 14 | 14 | 0 | 69.0169 | 26.71 | sq ft | 7.21 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249665 | 26003H | 2368J | LP1Y-SW-166302-01-1 | LP1Y-SW-166302-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS SW (315) 166302 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166302 |  | TFS00E007YSPP |  | 315-SW | NONE | 2" | 316 SS | 12.5 | 12.5 | 0 | 67.9304 | 25.93 | sq ft | 6.43 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249666 | 26003H | 2369J | LP1Y-SW-166307-01-1 | LP1Y-SW-166307-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS SW (315) 166307 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166307 |  | TFS00E007YSPP |  | 315-SW | NONE | 2" | 316 SS | 11 | 11 | 0 | 67.0652 | 24.25 | sq ft | 6.25 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249673 | 26003H | 2376D | LP1Y-SWP-014001-07-1 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 36 | 36 | 0 | 130.6656 | 28.51 | sq ft | 6.11 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-01 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249675 | 26003H | 2378D | LP1Y-SWP-014001-07-3 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 23 | 22 | 1 | 77.1325 | 22.55 | sq ft | 2.42 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-20 | Passed | No | 2026-04-20 |  |  | 2026-05-01 |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249676 | 26003H | 2379D | LP1Y-SWP-014001-07-4 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 91.6125 | 19.93 | sq ft | 0.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249677 | 26003H | 2380D | LP1Y-SWP-014001-07-5 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 116.1547 | 23.17 | sq ft | 7.65 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249674 | 26003H | 2377D | LP1Y-SWP-014001-07-2 | LP1Y-SWP-014001-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 75.2731 | 19.07 | sq ft | 1.98 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-20 | Passed | No | 2026-04-20 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249678 | 26003H | 2381D | LP1Y-SWP-014001-08-1 | LP1Y-SWP-014001-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 45 | 32 | 13 | 245.6456 | 71.31 | sq ft | 15.11 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249683 | 26003H | 2386D | LP1Y-SWP-014001-11-2 | LP1Y-SWP-014001-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 28 | 26 | 2 | 134.1059 | 31.68 | sq ft | 6.88 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249682 | 26003H | 2385D | LP1Y-SWP-014001-11-1 | LP1Y-SWP-014001-11 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 206.1328 | 42.1 | sq ft | 20.39 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249687 | 26003H | 2390D | LP1Y-SWP-014001-13-2 | LP1Y-SWP-014001-13 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.385 | 19 | sq ft | 0.5 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249686 | 26003H | 2389D | LP1Y-SWP-014001-13-1 | LP1Y-SWP-014001-13 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.54 | 11.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249691 | 26003H | 2394D | LP1Y-SWP-014001-15-1 | LP1Y-SWP-014001-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.5692 | 19.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 | 2026-04-23 | Passed | No | 2026-04-23 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249692 | 26003H | 2395D | LP1Y-SWP-014001-15-2 | LP1Y-SWP-014001-15 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.32 | 11.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249693 | 26003H | 2396D | LP1Y-SWP-014001-16-1 | LP1Y-SWP-014001-16 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.5692 | 19.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249694 | 26003H | 2397D | LP1Y-SWP-014001-16-2 | LP1Y-SWP-014001-16 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.32 | 11.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249696 | 26003H | 2399D | LP1Y-SWP-014001-17-2 | LP1Y-SWP-014001-17 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.5692 | 19.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-23 | Passed | No | 2026-04-23 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249695 | 26003H | 2398D | LP1Y-SWP-014001-17-1 | LP1Y-SWP-014001-17 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.32 | 11.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249697 | 26003H | 2400D | LP1Y-SWP-014001-18-1 | LP1Y-SWP-014001-18 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.32 | 11.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249698 | 26003H | 2401D | LP1Y-SWP-014001-18-2 | LP1Y-SWP-014001-18 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.5692 | 19.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-23 | Passed | No | 2026-04-23 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249700 | 26003H | 2403D | LP1Y-SWP-014001-19-2 | LP1Y-SWP-014001-19 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.25 | 10.25 | 0 | 20.5692 | 19.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-23 | Passed | No | 2026-04-23 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249699 | 26003H | 2402D | LP1Y-SWP-014001-19-1 | LP1Y-SWP-014001-19 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 6 | 6 | 0 | 21.32 | 11.25 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249704 | 26003H | 2407D | LP1Y-SWP-014001-21-1 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 15.5 | 15.5 | 0 | 23.91 | 20.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-23 | Passed | No | 2026-04-23 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249705 | 26003H | 2408D | LP1Y-SWP-014001-21-2 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 4 | 4 | 0 | 16.15 | 8.63 | sq ft | 0.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249706 | 26003H | 2409D | LP1Y-SWP-014001-21-3 | LP1Y-SWP-014001-21 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 2" | 2205 | 10.75 | 10.75 | 0 | 23.3938 | 18.55 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249707 | 26003H | 2410D | LP1Y-SWP-014001-22-1 | LP1Y-SWP-014001-22 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 28 | 26 | 2 | 187.7934 | 43.46 | sq ft | 11.92 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-23 | Passed | No | 2026-04-23 |  |  | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249708 | 26003H | 2411D | LP1Y-SWP-014001-23-1 | LP1Y-SWP-014001-23 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 4 | 4 | 0 | 24.0777 | 5.42 | sq ft | 0.68 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-20 | Passed | No | 2026-04-20 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249709 | 26003H | 2412D | LP1Y-SWP-014001-23-2 | LP1Y-SWP-014001-23 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 12.5 | 11.5 | 1 | 32.0542 | 16.61 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249716 | 26003H | 2419J | LP1Y-SWP-100411-01-3 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 41.1288 | 21.28 | sq ft | 11.28 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-24 |  | 2026-04-24 |  | 2026-04-15 |  | 78% |  |  |  | 44%
C34-S249718 | 26003H | 2421J | LP1Y-SWP-100411-01-5 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144862 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249715 | 26003H | 2418J | LP1Y-SWP-100411-01-2 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 34.5163 | 15.66 | sq ft | 8.66 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 80%
C34-S249717 | 26003H | 2420J | LP1Y-SWP-100411-01-4 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6.75 | 4 | 2.75 | 29.425 | 15.81 | sq ft | 7.81 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-16 | 2026-05-01 | 2026-05-01 | 100% | 2026-04-24 |  |  | 75%
C34-S249714 | 26003H | 2417J | LP1Y-SWP-100411-01-1 | LP1Y-SWP-100411-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 2" SS SWP (315) (108) 100411 | SWP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100411 |  | TFS00D003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 16.2725 | 10.45 | sq ft | 2.45 | ft | 2026-02-13 |  |  |  |  | 2026-03-31 | Jacob Perez | 2026-03-31 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 |  |  |  | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% |  |  |  | 0%
C34-S249721 | 26003H | 2424J | LP1Y-SWP-101026-01-3 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 24 | 24 | 0 | 104.8469 | 22.62 | sq ft | 5.84 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 75%
C34-S249719 | 26003H | 2422J | LP1Y-SWP-101026-01-1 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 21 | 20 | 1 | 110.8469 | 26.24 | sq ft | 6.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-28 | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-04-30 |  | 2026-04-30 | [6 empty] | 67% |  |  |  | 0%
C34-S249720 | 26003H | 2423J | LP1Y-SWP-101026-01-2 | LP1Y-SWP-101026-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS SWP (315) (108) 101026 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101026 |  | TFS00D005YSPP |  | 315-SWP | NONE | 6" | 316 SS | 18 | 18 | 0 | 349.7766 | 68.84 | sq ft | 35.24 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144513 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249722 | 26003H | 2425D | LP1Y-SWP-101505-01-1 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 89.2719 | 17.97 | sq ft | 4.76 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-02 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249725 | 26003H | 2428D | LP1Y-SWP-101505-01-4 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-20 | 2026-04-20 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-20 | 145032 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249723 | 26003H | 2426D | LP1Y-SWP-101505-01-2 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 24 | 22 | 2 | 115.2144 | 28.64 | sq ft | 6.8 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-23 | Passed | No | 2026-04-23 |  |  | 2026-05-01 |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249724 | 26003H | 2427D | LP1Y-SWP-101505-01-3 | LP1Y-SWP-101505-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 6 | 6 | 0 | 43.2031 | 8.48 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 | 2026-05-02 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249740 | 26003H | 2443D | LP1Y-SWP-101509-01-2 | LP1Y-SWP-101509-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 9 | 9 | 0 | 44.9338 | 10.38 | sq ft | 7.38 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-09 | N/A | N/A | Edgar Castaneda | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | [6 empty] | 67% |  |  |  | 0%
C34-S249739 | 26003H | 2442D | LP1Y-SWP-101509-01-1 | LP1Y-SWP-101509-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 15 | 15 | 0 | 65.2641 | 17.51 | sq ft | 10.91 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249742 | 26003H | 2445D | LP1Y-SWP-101509-03-2 | LP1Y-SWP-101509-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 101509 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 39 | 38 | 1 | 85.0903 | 38.68 | sq ft | 6.11 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249741 | 26003H | 2444D | LP1Y-SWP-101509-03-1 | LP1Y-SWP-101509-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 101509 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 9 | 9 | 0 | 53.0074 | 12.24 | sq ft | 9.24 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249748 | 26003H | 2451J | LP1Y-SWP-102082-01-1 | LP1Y-SWP-102082-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 102082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102082 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249749 | 26003H | 2452J | LP1Y-SWP-102082-01-2 | LP1Y-SWP-102082-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 102082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102082 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 10.1788 | 5.11 | sq ft | 1.11 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145086, 145131 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249750 | 26003H | 2453J | LP1Y-SWP-108084-01-1 | LP1Y-SWP-108084-01 | 0 | N | PRIORITY-1 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 108084 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108084 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 17.75 | 14.75 | 3 | 95.5363 | 39.54 | sq ft | 11.54 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-18 | Jacob Perez | 2026-04-18 | Jacob Perez | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249752 | 26003H | 2455J | LP1Y-SWP-109022-10-2 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1" | 316 SS | 2 | 2 | 0 | 5.6633 | 8.64 | sq ft | 0.64 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Omar Puente | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 0%
C34-S249751 | 26003H | 2454J | LP1Y-SWP-109022-10-1 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1" | 316 SS | 4 | 4 | 0 | 19.1033 | 19.47 | sq ft | 9.97 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249753 | 26003H | 2456J | LP1Y-SWP-109022-10-3 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 9 | 9 | 0 | 21.1313 | 14.14 | sq ft | 5.14 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249754 | 26003H | 2457J | LP1Y-SWP-109022-10-4 | LP1Y-SWP-109022-10 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 109022 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109022 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 43.175 | 17.02 | sq ft | 15.52 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249757 | 26003H | 2460J | LP1Y-SWP-165103-02-3 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 2 | 2 | 34.045 | 13.56 | sq ft | 12.06 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Edgar Castaneda | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 144028 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249756 | 26003H | 2459J | LP1Y-SWP-165103-02-2 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 30.2775 | 12.8 | sq ft | 9.8 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144281 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249755 | 26003H | 2458J | LP1Y-SWP-165103-02-1 | LP1Y-SWP-165103-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 46.0075 | 18.76 | sq ft | 15.76 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143956 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249758 | 26003H | 2461J | LP1Y-SWP-165103-03-1 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143896 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249759 | 26003H | 2462J | LP1Y-SWP-165103-03-2 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 144104 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249761 | 26003H | 2464J | LP1Y-SWP-165103-03-4 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 41.595 | 23.1 | sq ft | 11.6 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Edgar Castaneda | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-14 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-16 | 2026-04-21 | 100% | 2026-04-22 | 145206 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249760 | 26003H | 2463J | LP1Y-SWP-165103-03-3 | LP1Y-SWP-165103-03 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165103 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14 | 9.5 | 4.5 | 25.292 | 25.29 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-07 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145610
C34-S256302 | 26003H | 2465JA | LP1Y-SWP-165113-02-1A | LP1Y-SWP-165113-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 |  | 0 | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 22.7288 | 9.28 | sq ft | 7.78 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145850
C34-S249833 | 26003H | 2465J | LP1Y-SWP-165113-02-1 | LP1Y-SWP-165113-02 | 0 | N | PRIORITY-1 | 2026-03-25 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 28.16 | 11.33 | sq ft | 9.83 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144356, 144357 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249835 | 26003H | 2467J | LP1Y-SWP-165113-05-2 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-26 | Jacob Perez | 2026-03-26 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | Omar Puente | 2026-03-30 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 144103 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249834 | 26003H | 2466J | LP1Y-SWP-165113-05-1 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143895 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249836 | 26003H | 2468J | LP1Y-SWP-165113-05-3 | LP1Y-SWP-165113-05 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 20.25 | 13.5 | 6.75 | 44.227 | 37.81 | sq ft | 9.81 | ft | 2026-02-13 |  |  |  |  | 2026-03-26 | Jacob Perez | 2026-03-26 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-07 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-27 | 145612
C34-S249838 | 26003H | 2470J | LP1Y-SWP-165113-06-2 | LP1Y-SWP-165113-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 52.03 | 25.04 | sq ft | 15.54 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144991 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249837 | 26003H | 2469J | LP1Y-SWP-165113-06-1 | LP1Y-SWP-165113-06 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS SWP (315) (108) 165113 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165113 |  | TFS00D002YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 48.2525 | 20.95 | sq ft | 16.45 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-27 | 2026-03-27 | N/A | N/A | Edgar Castaneda | 2026-03-28 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143932 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249841 | 26003H | 2473J | LP1Y-SWP-165403-01-3 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-05 | George Allahverdian | 2026-04-05 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249839 | 26003H | 2471J | LP1Y-SWP-165403-01-1 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-20 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145006 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249840 | 26003H | 2472J | LP1Y-SWP-165403-01-2 | LP1Y-SWP-165403-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S249843 | 26003H | 2475J | LP1Y-SWP-165403-02-2 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.5213 | 12.81 | sq ft | 9.81 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | N/A | N/A | Roberto Tobias (WF) | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% |  |  |  | 33%
C34-S249844 | 26003H | 2476J | LP1Y-SWP-165403-02-3 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 51.5213 | 20.18 | sq ft | 18.68 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% |  |  |  | 50%
C34-S249842 | 26003H | 2474J | LP1Y-SWP-165403-02-1 | LP1Y-SWP-165403-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS SWP (315) (108) 165403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165403 |  | TFS00D006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 14.2 | 11.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Omar Puente | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-30 | 2026-04-29 | 2026-04-30 | 100%
C34-S249845 | 26003H | 2477J | LP1Y-SWP-165703-02-1 | LP1Y-SWP-165703-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249846 | 26003H | 2478J | LP1Y-SWP-165703-02-2 | LP1Y-SWP-165703-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249847 | 26003H | 2479J | LP1Y-SWP-165703-03-1 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249848 | 26003H | 2480J | LP1Y-SWP-165703-03-2 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249849 | 26003H | 2481J | LP1Y-SWP-165703-03-3 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249850 | 26003H | 2482J | LP1Y-SWP-165703-03-4 | LP1Y-SWP-165703-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS SWP (315) (108) 165703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165703 |  | TFS00D007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 9.25 | 7 | 2.25 | 33.9816 | 27.34 | sq ft | 3.34 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249852 | 26003H | 2484J | LP1Y-SWP-165803-02-2 | LP1Y-SWP-165803-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.0225 | 7.32 | sq ft | 3.32 | ft | 2026-02-13 |  |  |  |  | 2026-03-26 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249851 | 26003H | 2483J | LP1Y-SWP-165803-02-1 | LP1Y-SWP-165803-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 90.715 | 33.31 | sq ft | 12.31 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249854 | 26003H | 2486J | LP1Y-SWP-165803-04-2 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249853 | 26003H | 2485J | LP1Y-SWP-165803-04-1 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249855 | 26003H | 2487J | LP1Y-SWP-165803-04-3 | LP1Y-SWP-165803-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 165803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165803 |  | TFS00D001YSPP |  | 315-SWP | NONE | 2" | 316 SS | 21 | 16.5 | 4.5 | 96.2283 | 51.06 | sq ft | 7.06 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249856 | 26003H | 2488J | LP1Y-SWP-166203-01-1 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146062
C34-S249857 | 26003H | 2489J | LP1Y-SWP-166203-01-2 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249858 | 26003H | 2490J | LP1Y-SWP-166203-01-3 | LP1Y-SWP-166203-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 34 | 29.5 | 4.5 | 98.8279 | 55.82 | sq ft | 7.32 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249860 | 26003H | 2492J | LP1Y-SWP-166203-02-2 | LP1Y-SWP-166203-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 11.5 | 10.75 | 0.75 | 74.5525 | 26.66 | sq ft | 8.16 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249859 | 26003H | 2491J | LP1Y-SWP-166203-02-1 | LP1Y-SWP-166203-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166203 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166203 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14 | 14 | 0 | 50.8888 | 21.94 | sq ft | 15.94 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  | 71% |  |  |  | 57%
C34-S249862 | 26003H | 2494J | LP1Y-SWP-166213-02-2 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249863 | 26003H | 2495J | LP1Y-SWP-166213-02-3 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 29.5 | 25 | 4.5 | 97.0774 | 52.48 | sq ft | 6.98 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249861 | 26003H | 2493J | LP1Y-SWP-166213-02-1 | LP1Y-SWP-166213-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146066
C34-S249864 | 26003H | 2496J | LP1Y-SWP-166213-03-1 | LP1Y-SWP-166213-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 75.9988 | 25.82 | sq ft | 10.32 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249865 | 26003H | 2497J | LP1Y-SWP-166213-03-2 | LP1Y-SWP-166213-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SWP (315) (108) 166213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166213 |  | TFS00E006YSPP |  | 315-SWP | NONE | 2" | 316 SS | 12 | 12 | 0 | 58.3 | 24.75 | sq ft | 18.75 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | [6 empty] | 67% |  |  |  | 0%
C34-S249869 | 26003H | 2501J | LP1Y-SWP-166303-01-4 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.5488 | 13.19 | sq ft | 8.69 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-06 | N/A | N/A | Omar Puente | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 |  |  |  | 75% |  |  |  | 50%
C34-S249866 | 26003H | 2498J | LP1Y-SWP-166303-01-1 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249868 | 26003H | 2500J | LP1Y-SWP-166303-01-3 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 30.25 | 23.5 | 6.75 | 161.7308 | 72.35 | sq ft | 14.35 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249867 | 26003H | 2499J | LP1Y-SWP-166303-01-2 | LP1Y-SWP-166303-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166303 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166303 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249870 | 26003H | 2502J | LP1Y-SWP-166305-03-1 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249871 | 26003H | 2503J | LP1Y-SWP-166305-03-2 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249874 | 26003H | 2506J | LP1Y-SWP-166305-03-5 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 58.3963 | 22.79 | sq ft | 21.29 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249875 | 26003H | 2507J | LP1Y-SWP-166305-03-6 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 68.365 | 27.9 | sq ft | 23.4 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249873 | 26003H | 2505J | LP1Y-SWP-166305-03-4 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14 | 14 | 0 | 76.165 | 32.19 | sq ft | 26.19 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249872 | 26003H | 2504J | LP1Y-SWP-166305-03-3 | LP1Y-SWP-166305-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS SWP (315) (108) 166305 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166305 |  | TFS00E007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 30.25 | 23.5 | 6.75 | 148.7233 | 67.43 | sq ft | 9.43 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249877 | 26003H | 2509AB | LP1Y-TFA-010025-03-2 | LP1Y-TFA-010025-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 20.8863 | 9.91 | sq ft | 5.41 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249876 | 26003H | 2508AB | LP1Y-TFA-010025-03-1 | LP1Y-TFA-010025-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 4 | 4 | 0 | 18.1363 | 7.54 | sq ft | 6.04 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249890 | 26003H | 2522AB | LP1Y-TFA-109205-03-2 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 26.5 | 25 | 1.5 | 97.0313 | 51.64 | sq ft | 6.14 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian; ED: 2026-04-24; EL: Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249891 | 26003H | 2523AB | LP1Y-TFA-109205-03-3 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 6 | 6 | 0 | 70.015 | 27.44 | sq ft | 14.44 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249889 | 26003H | 2521AB | LP1Y-TFA-109205-03-1 | LP1Y-TFA-109205-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 4 | 4 | 0 | 16.5488 | 8.78 | sq ft | 0.78 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249892 | 26003H | 2524AB | LP1Y-TFA-109205-04-1 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 9 | 8 | 1 | 34.1055 | 14.3 | sq ft | 1.3 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249893 | 26003H | 2525AB | LP1Y-TFA-109205-04-2 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 14 | 14 | 0 | 54.5403 | 18.53 | sq ft | 3.53 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249894 | 26003H | 2526AB | LP1Y-TFA-109205-04-3 | LP1Y-TFA-109205-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 9 | 9 | 0 | 28.6357 | 11.32 | sq ft | 2.32 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249896 | 26003H | 2528AB | LP1Y-TFA-109205-05-2 | LP1Y-TFA-109205-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 17.215 | 8.52 | sq ft | 4.02 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249895 | 26003H | 2527AB | LP1Y-TFA-109205-05-1 | LP1Y-TFA-109205-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 4 | 4 | 0 | 16.3763 | 6.87 | sq ft | 5.37 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249915 | 26003H | 2547AB | LP1Y-TFA-109215-01-1 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 4.75 | 4.75 | 0 | 12.1125 | 10.11 | sq ft | 2.61 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249916 | 26003H | 2548AB | LP1Y-TFA-109215-01-2 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 10 | 10 | 0 | 16.0325 | 8.07 | sq ft | 3.57 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249917 | 26003H | 2549AB | LP1Y-TFA-109215-01-3 | LP1Y-TFA-109215-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 10 | 10 | 0 | 65.5875 | 26.84 | sq ft | 22.34 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249918 | 26003H | 2550AB | LP1Y-TFA-109215-03-1 | LP1Y-TFA-109215-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 109215 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109215 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 2 | 2 | 0 | 20.6113 | 8.47 | sq ft | 6.97 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249926 | 26003H | 2558C | LP1Y-TWRP-109313-05-1 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | P-3 | 3" | CS | 3 | 3 | 0 | 123.4375 | 17.13 | sq ft | 15.63 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249927 | 26003H | 2559C | LP1Y-TWRP-109313-05-2 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | P-3 | 3" | CS | 12 | 12 | 0 | 63.6514 | 11.29 | sq ft | 6.29 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249928 | 26003H | 2560C | LP1Y-TWRP-109313-05-3 | LP1Y-TWRP-109313-05 | 0 | N | PRIORITY-1 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" CS TWRP (6) (108) 109313 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-109313 |  | TFS00E007YSPP |  | 6-TWRP | P-3 | 1 1/2" | CS | 1.5 | 0 | 1.5 | 14.105 | 4.13 | sq ft | 3.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249931 | 26003H | 2563C | LP1Y-TWSP-017020-05-3 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | P-4 | 1 1/2" | CS | 1.5 | 0 | 1.5 | 14.105 | 4.13 | sq ft | 3.63 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249929 | 26003H | 2561C | LP1Y-TWSP-017020-05-1 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | P-4 | 3" | CS | 3 | 3 | 0 | 129.1225 | 17.88 | sq ft | 16.38 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249930 | 26003H | 2562C | LP1Y-TWSP-017020-05-2 | LP1Y-TWSP-017020-05 | 0 | N | PRIORITY-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" CS TWSP (6) (108) 017020 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017020 |  | TFS00E007YSPP |  | 6-TWSP | P-4 | 3" | CS | 12 | 12 | 0 | 56.703 | 10.37 | sq ft | 5.37 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian; ED: 2026-04-08; EL: Jacob Perez; FD: 2026-04-08; FL: Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249932 | 26003H | 2564J | LP1Y-WFO-017003-03-1 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249936 | 26003H | 2568J | LP1Y-WFO-017003-03-5 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249937 | 26003H | 2569J | LP1Y-WFO-017003-03-6 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249933 | 26003H | 2565J | LP1Y-WFO-017003-03-2 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249934 | 26003H | 2566J | LP1Y-WFO-017003-03-3 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249935 | 26003H | 2567J | LP1Y-WFO-017003-03-4 | LP1Y-WFO-017003-03 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) 017003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017003 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249942 | 26003H | 2574J | LP1Y-WFO-017004-05-5 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S249944 | 26003H | 2576J | LP1Y-WFO-017004-05-7 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249939 | 26003H | 2571J | LP1Y-WFO-017004-05-2 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.71 | 2.54 | sq ft | 2.54 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144425 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249941 | 26003H | 2573J | LP1Y-WFO-017004-05-4 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 28.7513 | 10.89 | sq ft | 10.89 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144751 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249938 | 26003H | 2570J | LP1Y-WFO-017004-05-3 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 30.03 | 11.38 | sq ft | 11.38 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144423 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249940 | 26003H | 2572J | LP1Y-WFO-017004-05-1 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 21.6425 | 8.2 | sq ft | 8.2 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S249943 | 26003H | 2575J | LP1Y-WFO-017004-05-6 | LP1Y-WFO-017004-05 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 017004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017004 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.9575 | 2.64 | sq ft | 2.64 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144758 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249947 | 26003H | 2579J | LP1Y-WFO-017007-19-3 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 23.045 | 8.73 | sq ft | 8.73 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144296 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249948 | 26003H | 2580J | LP1Y-WFO-017007-19-4 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.0125 | 2.66 | sq ft | 2.66 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144305 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249945 | 26003H | 2577J | LP1Y-WFO-017007-19-1 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.48 | 7 | sq ft | 7 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144258 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249946 | 26003H | 2578J | LP1Y-WFO-017007-19-2 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.8025 | 2.2 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144257 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249949 | 26003H | 2581J | LP1Y-WFO-017007-19-5 | LP1Y-WFO-017007-19 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.5513 | 1.72 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144256 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249950 | 26003H | 2582J | LP1Y-WFO-017007-20-1 | LP1Y-WFO-017007-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D007YSPP |  | 36-WFO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249951 | 26003H | 2583J | LP1Y-WFO-017007-20-2 | LP1Y-WFO-017007-20 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D007YSPP |  | 36-WFO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249953 | 26003H | 2585J | LP1Y-WFO-017007-57-2 | LP1Y-WFO-017007-57 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146040
C34-S249952 | 26003H | 2584J | LP1Y-WFO-017007-57-1 | LP1Y-WFO-017007-57 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.66 | 8.58 | sq ft | 8.58 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144297 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249955 | 26003H | 2587J | LP1Y-WFO-017007-58-2 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.8163 | 2.2 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144255 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249954 | 26003H | 2586J | LP1Y-WFO-017007-58-1 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 45.3888 | 17.19 | sq ft | 17.19 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144289 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S249956 | 26003H | 2588J | LP1Y-WFO-017007-58-3 | LP1Y-WFO-017007-58 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 017007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249957 | 26003H | 2589J | LP1Y-WFO-017008-08-1 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 46.5713 | 17.64 | sq ft | 17.64 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144762 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249959 | 26003H | 2591J | LP1Y-WFO-017008-08-3 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.3588 | 1.65 | sq ft | 1.65 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S249958 | 26003H | 2590J | LP1Y-WFO-017008-08-2 | LP1Y-WFO-017008-08 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249961 | 26003H | 2593J | LP1Y-WFO-017008-09-2 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 34.925 | 13.23 | sq ft | 13.23 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144416 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249960 | 26003H | 2592J | LP1Y-WFO-017008-09-1 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.64 | 1 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144737 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249963 | 26003H | 2595J | LP1Y-WFO-017008-09-4 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 23.3338 | 8.84 | sq ft | 8.84 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144743 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249962 | 26003H | 2594J | LP1Y-WFO-017008-09-3 | LP1Y-WFO-017008-09 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.47 | 3.21 | sq ft | 3.21 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S249965 | 26003H | 2597J | LP1Y-WFO-017008-10-2 | LP1Y-WFO-017008-10 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249964 | 26003H | 2596J | LP1Y-WFO-017008-10-1 | LP1Y-WFO-017008-10 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 24.035 | 9.1 | sq ft | 9.1 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144750 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249972 | 26003H | 2604J | LP1Y-WFO-017009-07-7 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.74 | 1.42 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249973 | 26003H | 2605J | LP1Y-WFO-017009-07-8 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249966 | 26003H | 2598J | LP1Y-WFO-017009-07-1 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6438 | 1.38 | sq ft | 1.38 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249969 | 26003H | 2601J | LP1Y-WFO-017009-07-4 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.405 | 11.9 | sq ft | 11.9 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249970 | 26003H | 2602J | LP1Y-WFO-017009-07-5 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.5938 | 7.42 | sq ft | 7.42 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249971 | 26003H | 2603J | LP1Y-WFO-017009-07-6 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.67 | 4.04 | sq ft | 4.04 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249967 | 26003H | 2599J | LP1Y-WFO-017009-07-2 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1725 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249968 | 26003H | 2600J | LP1Y-WFO-017009-07-3 | LP1Y-WFO-017009-07 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.7475 | 2.18 | sq ft | 2.18 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249974 | 26003H | 2606J | LP1Y-WFO-017009-08-1 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 21.0375 | 7.97 | sq ft | 7.97 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249977 | 26003H | 2609J | LP1Y-WFO-017009-08-4 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249975 | 26003H | 2607J | LP1Y-WFO-017009-08-2 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2413 | 0.85 | sq ft | 0.85 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249976 | 26003H | 2608J | LP1Y-WFO-017009-08-3 | LP1Y-WFO-017009-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.24 | 3.5 | sq ft | 3.5 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249982 | 26003H | 2614J | LP1Y-WFO-017009-09-5 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.4625 | 6.61 | sq ft | 6.61 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249978 | 26003H | 2610J | LP1Y-WFO-017009-09-1 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.2 | 5 | sq ft | 5 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249980 | 26003H | 2612J | LP1Y-WFO-017009-09-3 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.1088 | 2.69 | sq ft | 2.69 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249981 | 26003H | 2613J | LP1Y-WFO-017009-09-4 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249979 | 26003H | 2611J | LP1Y-WFO-017009-09-2 | LP1Y-WFO-017009-09 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 017009 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017009 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.0413 | 8.35 | sq ft | 8.35 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249983 | 26003H | 2615J | LP1Y-WFO-017038-02-1 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249984 | 26003H | 2616J | LP1Y-WFO-017038-02-2 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249987 | 26003H | 2619J | LP1Y-WFO-017038-02-5 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249988 | 26003H | 2620J | LP1Y-WFO-017038-02-6 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249990 | 26003H | 2622J | LP1Y-WFO-017038-02-8 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.59 | 8.58 | sq ft | 3.08 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249989 | 26003H | 2621J | LP1Y-WFO-017038-02-7 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249985 | 26003H | 2617J | LP1Y-WFO-017038-02-3 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249986 | 26003H | 2618J | LP1Y-WFO-017038-02-4 | LP1Y-WFO-017038-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 017038 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017038 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249993 | 26003H | 2625J | LP1Y-WFO-017049-06-3 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 32.395 | 12.27 | sq ft | 12.27 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-18 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S249991 | 26003H | 2623J | LP1Y-WFO-017049-06-1 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 35.31 | 13.38 | sq ft | 13.38 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S249992 | 26003H | 2624J | LP1Y-WFO-017049-06-2 | LP1Y-WFO-017049-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.4725 | 2.07 | sq ft | 2.07 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146033
C34-S249994 | 26003H | 2626J | LP1Y-WFO-017049-07-1 | LP1Y-WFO-017049-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.9525 | 4.91 | sq ft | 4.91 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S249995 | 26003H | 2627J | LP1Y-WFO-017049-07-2 | LP1Y-WFO-017049-07 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 017049 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017049 |  | TFS00E006YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250000 | 26003H | 2632J | LP1Y-WFO-017052-04-5 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249998 | 26003H | 2630J | LP1Y-WFO-017052-04-3 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.7863 | 3.33 | sq ft | 3.33 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250001 | 26003H | 2633J | LP1Y-WFO-017052-04-6 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249999 | 26003H | 2631J | LP1Y-WFO-017052-04-4 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.5438 | 0.96 | sq ft | 0.96 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249997 | 26003H | 2629J | LP1Y-WFO-017052-04-2 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.315 | 2.77 | sq ft | 2.77 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250002 | 26003H | 2634J | LP1Y-WFO-017052-04-7 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250003 | 26003H | 2635J | LP1Y-WFO-017052-04-8 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 34.925 | 13.23 | sq ft | 13.23 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249996 | 26003H | 2628J | LP1Y-WFO-017052-04-1 | LP1Y-WFO-017052-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) (108) 017052 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017052 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 29.7025 | 18.28 | sq ft | 2.78 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian; ED: 2026-04-08; EL: Jacob Perez; FD: 2026-04-08; FL: Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250004 | 26003H | 2636J | LP1Y-WFO-017060-14-1 | LP1Y-WFO-017060-14 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.8725 | 12.07 | sq ft | 12.07 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143976 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250005 | 26003H | 2637J | LP1Y-WFO-017060-14-2 | LP1Y-WFO-017060-14 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez | 2026-04-07 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250007 | 26003H | 2639J | LP1Y-WFO-017060-15-2 | LP1Y-WFO-017060-15 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.51 | 5.88 | sq ft | 5.88 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143914, 143915 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250006 | 26003H | 2638J | LP1Y-WFO-017060-15-1 | LP1Y-WFO-017060-15 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 0 | 6 | 39.1188 | 14.82 | sq ft | 14.82 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143938 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250011 | 26003H | 2643J | LP1Y-WFO-017060-16-4 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.475 | 0.94 | sq ft | 0.94 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | N/A | N/A | 2026-03-30 | 2026-03-30 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143913 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250008 | 26003H | 2640J | LP1Y-WFO-017060-16-1 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 0 | 6 | 48.125 | 18.23 | sq ft | 18.23 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-08 | 2026-04-08 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 144546 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250012 | 26003H | 2644J | LP1Y-WFO-017060-16-5 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9638 | 1.88 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144190 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250009 | 26003H | 2641J | LP1Y-WFO-017060-16-2 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.38 | 6.58 | sq ft | 6.58 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144177 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250010 | 26003H | 2642J | LP1Y-WFO-017060-16-3 | LP1Y-WFO-017060-16 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 017060 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017060 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250014 | 26003H | 2646J | LP1Y-WFO-033053-06-2 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 25.3825 | 9.61 | sq ft | 9.61 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144294
C34-S250017 | 26003H | 2649J | LP1Y-WFO-033053-06-5 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250016 | 26003H | 2648J | LP1Y-WFO-033053-06-4 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.3013 | 2.77 | sq ft | 2.77 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144254
C34-S250015 | 26003H | 2647J | LP1Y-WFO-033053-06-3 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 4.75 | 0 | 4.75 | 23.88 | 9.42 | sq ft | 8.92 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250018 | 26003H | 2650J | LP1Y-WFO-033053-06-6 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 7.75 | 0 | 7.75 | 17.155 | 13.73 | sq ft | 0.73 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250013 | 26003H | 2645J | LP1Y-WFO-033053-06-1 | LP1Y-WFO-033053-06 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 033053 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033053 |  | TFS00D001YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 32.285 | 12.23 | sq ft | 12.23 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144290
C34-S250019 | 26003H | 2651J | LP1Y-WFO-033060-04-1 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250020 | 26003H | 2652J | LP1Y-WFO-033060-04-2 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250021 | 26003H | 2653J | LP1Y-WFO-033060-04-3 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250026 | 26003H | 2658J | LP1Y-WFO-033060-04-8 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.59 | 8.58 | sq ft | 3.08 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250022 | 26003H | 2654J | LP1Y-WFO-033060-04-4 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250023 | 26003H | 2655J | LP1Y-WFO-033060-04-5 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250024 | 26003H | 2656J | LP1Y-WFO-033060-04-6 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250025 | 26003H | 2657J | LP1Y-WFO-033060-04-7 | LP1Y-WFO-033060-04 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WFO (36) (108) 033060 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033060 |  | TFS00D007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250030 | 26003H | 2662J | LP1Y-WFO-100109-02-4 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.29 | 1.63 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143920 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250028 | 26003H | 2660J | LP1Y-WFO-100109-02-2 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143912 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250029 | 26003H | 2661J | LP1Y-WFO-100109-02-3 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250027 | 26003H | 2659J | LP1Y-WFO-100109-02-1 | LP1Y-WFO-100109-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100109 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100109 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146045
C34-S250034 | 26003H | 2666J | LP1Y-WFO-100209-02-4 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.29 | 1.63 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143921 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250032 | 26003H | 2664J | LP1Y-WFO-100209-02-2 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143919 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250033 | 26003H | 2665J | LP1Y-WFO-100209-02-3 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250031 | 26003H | 2663J | LP1Y-WFO-100209-02-1 | LP1Y-WFO-100209-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100209 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100209 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146047
C34-S250037 | 26003H | 2669J | LP1Y-WFO-100309-02-3 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250038 | 26003H | 2670J | LP1Y-WFO-100309-02-4 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6713 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143910 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250036 | 26003H | 2668J | LP1Y-WFO-100309-02-2 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.7638 | 1.05 | sq ft | 1.05 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143911 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250035 | 26003H | 2667J | LP1Y-WFO-100309-02-1 | LP1Y-WFO-100309-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 100309 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100309 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146043
C34-S250041 | 26003H | 2673J | LP1Y-WFO-101111-02-3 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.895 | 1.85 | sq ft | 1.85 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144252 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250040 | 26003H | 2672J | LP1Y-WFO-101111-02-2 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1313 | 0.81 | sq ft | 0.81 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144253 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250042 | 26003H | 2674J | LP1Y-WFO-101111-02-4 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250039 | 26003H | 2671J | LP1Y-WFO-101111-02-1 | LP1Y-WFO-101111-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101111 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101111 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 146011
C34-S250043 | 26003H | 2675J | LP1Y-WFO-101311-02-1 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146044
C34-S250046 | 26003H | 2678J | LP1Y-WFO-101311-02-4 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250044 | 26003H | 2676J | LP1Y-WFO-101311-02-2 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3513 | 0.89 | sq ft | 0.89 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144251 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250045 | 26003H | 2677J | LP1Y-WFO-101311-02-3 | LP1Y-WFO-101311-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 101311 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101311 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7713 | 1.81 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144250 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250047 | 26003H | 2679J | LP1Y-WFO-101513-02-1 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250048 | 26003H | 2680J | LP1Y-WFO-101513-02-2 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.6125 | 0.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144760 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250049 | 26003H | 2681J | LP1Y-WFO-101513-02-3 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9775 | 1.89 | sq ft | 1.89 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250050 | 26003H | 2682J | LP1Y-WFO-101513-02-4 | LP1Y-WFO-101513-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101513 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101513 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250053 | 26003H | 2685J | LP1Y-WFO-101610-02-3 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.06 | 1.92 | sq ft | 1.92 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250054 | 26003H | 2686J | LP1Y-WFO-101610-02-4 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250051 | 26003H | 2683J | LP1Y-WFO-101610-02-1 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250052 | 26003H | 2684J | LP1Y-WFO-101610-02-2 | LP1Y-WFO-101610-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101610 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2688 | 0.86 | sq ft | 0.86 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250057 | 26003H | 2689J | LP1Y-WFO-101710-02-3 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.8538 | 1.84 | sq ft | 1.84 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250058 | 26003H | 2690J | LP1Y-WFO-101710-02-4 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250055 | 26003H | 2687J | LP1Y-WFO-101710-02-1 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250056 | 26003H | 2688J | LP1Y-WFO-101710-02-2 | LP1Y-WFO-101710-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 101710 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101710 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3513 | 0.89 | sq ft | 0.89 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250061 | 26003H | 2693J | LP1Y-WFO-102110-02-3 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250062 | 26003H | 2694J | LP1Y-WFO-102110-02-4 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.85 | 1.46 | sq ft | 1.46 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250060 | 26003H | 2692J | LP1Y-WFO-102110-02-2 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250059 | 26003H | 2691J | LP1Y-WFO-102110-02-1 | LP1Y-WFO-102110-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102110 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250064 | 26003H | 2696J | LP1Y-WFO-102210-02-2 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250063 | 26003H | 2695J | LP1Y-WFO-102210-02-1 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146049
C34-S250065 | 26003H | 2697J | LP1Y-WFO-102210-02-3 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250066 | 26003H | 2698J | LP1Y-WFO-102210-02-4 | LP1Y-WFO-102210-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 102210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102210 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.85 | 1.46 | sq ft | 1.46 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250068 | 26003H | 2700J | LP1Y-WFO-108123-02-2 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3513 | 0.89 | sq ft | 0.89 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250069 | 26003H | 2701J | LP1Y-WFO-108123-02-3 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.0563 | 1.54 | sq ft | 1.54 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250071 | 26003H | 2703J | LP1Y-WFO-108123-02-5 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146016
C34-S250067 | 26003H | 2699J | LP1Y-WFO-108123-02-1 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 5 | 2 | 3 | 6.5675 | 4.56 | sq ft | 1.56 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256230 | 26003H | 2699J-L1 | LP1Y-WFO-108123-02-1-L1 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 3 | 3 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-17 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146063
C34-S250070 | 26003H | 2702J | LP1Y-WFO-108123-02-4 | LP1Y-WFO-108123-02 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108123 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108123 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250075 | 26003H | 2707J | LP1Y-WFO-108224-02-4 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250072 | 26003H | 2704J | LP1Y-WFO-108224-02-1 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 5 | 2 | 3 | 6.5748 | 4.57 | sq ft | 1.57 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250073 | 26003H | 2705J | LP1Y-WFO-108224-02-2 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3513 | 0.89 | sq ft | 0.89 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146022
C34-S256231 | 26003H | 2704J-L1 | LP1Y-WFO-108224-02-1-L1 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 |  |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 3 | 3 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-17 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-23 | 2026-04-23 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 100% |  |  |  | 100% | 2026-05-02 | 146064
C34-S250076 | 26003H | 2708J | LP1Y-WFO-108224-02-5 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.7738 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250074 | 26003H | 2706J | LP1Y-WFO-108224-02-3 | LP1Y-WFO-108224-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 108224 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108224 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.905 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-04-21 | Passed | No | 2026-04-21 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146026
C34-S250080 | 26003H | 2712J | LP1Y-WFO-109110-02-4 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250078 | 26003H | 2710J | LP1Y-WFO-109110-02-2 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250079 | 26003H | 2711J | LP1Y-WFO-109110-02-3 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.3213 | 2.02 | sq ft | 2.02 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250077 | 26003H | 2709J | LP1Y-WFO-109110-02-1 | LP1Y-WFO-109110-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109110 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250084 | 26003H | 2716J | LP1Y-WFO-109210-02-4 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250085 | 26003H | 2717J | LP1Y-WFO-109210-02-5 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250083 | 26003H | 2715J | LP1Y-WFO-109210-02-3 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9775 | 1.89 | sq ft | 1.89 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250081 | 26003H | 2713J | LP1Y-WFO-109210-02-1 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250082 | 26003H | 2714J | LP1Y-WFO-109210-02-2 | LP1Y-WFO-109210-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 109210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109210 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250089 | 26003H | 2721J | LP1Y-WFO-195001-03-4 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.225 | 1.98 | sq ft | 1.98 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144249 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250086 | 26003H | 2718J | LP1Y-WFO-195001-03-1 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 32.4913 | 12.31 | sq ft | 12.31 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144292 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250087 | 26003H | 2719J | LP1Y-WFO-195001-03-2 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.5325 | 3.99 | sq ft | 3.99 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144300 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250088 | 26003H | 2720J | LP1Y-WFO-195001-03-3 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.0688 | 4.19 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144299 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250090 | 26003H | 2722J | LP1Y-WFO-195001-03-5 | LP1Y-WFO-195001-03 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-18 |  | LP1Y 2" SS WFO (36) 195001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195001 |  | TFS00D003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250093 | 26003H | 2725J | LP1Y-WFO-195003-03-3 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.1925 | 8.41 | sq ft | 8.41 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144746 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250091 | 26003H | 2723J | LP1Y-WFO-195003-03-1 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.5775 | 8.55 | sq ft | 8.55 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144421 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250092 | 26003H | 2724J | LP1Y-WFO-195003-03-2 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.0763 | 0.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144748 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250094 | 26003H | 2726J | LP1Y-WFO-195003-03-4 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250095 | 26003H | 2727J | LP1Y-WFO-195003-03-5 | LP1Y-WFO-195003-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195003 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.73 | 1.79 | sq ft | 1.79 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250097 | 26003H | 2729J | LP1Y-WFO-195004-03-2 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250096 | 26003H | 2728J | LP1Y-WFO-195004-03-1 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 45.21 | 17.13 | sq ft | 17.13 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144763 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250098 | 26003H | 2730J | LP1Y-WFO-195004-03-3 | LP1Y-WFO-195004-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 195004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195004 |  | TFS00D005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.4 | 1.67 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250105 | 26003H | 2737J | LP1Y-WFO-195007-03-7 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250100 | 26003H | 2732J | LP1Y-WFO-195007-03-2 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 42.24 | 16 | sq ft | 16 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144413 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250099 | 26003H | 2731J | LP1Y-WFO-195007-03-1 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.8713 | 2.22 | sq ft | 2.22 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250101 | 26003H | 2733J | LP1Y-WFO-195007-03-3 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 23.9388 | 9.07 | sq ft | 9.07 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-09 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144741 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250102 | 26003H | 2734J | LP1Y-WFO-195007-03-4 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.37 | 2.79 | sq ft | 2.79 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250104 | 26003H | 2736J | LP1Y-WFO-195007-03-6 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6988 | 1.4 | sq ft | 1.4 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250103 | 26003H | 2735J | LP1Y-WFO-195007-03-5 | LP1Y-WFO-195007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195007 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-08 | Passed | No | 2026-04-08 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250106 | 26003H | 2738J | LP1Y-WFO-195008-03-1 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.2525 | 1.99 | sq ft | 1.99 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144742 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250110 | 26003H | 2742J | LP1Y-WFO-195008-03-5 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144424 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250108 | 26003H | 2740J | LP1Y-WFO-195008-03-3 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.7838 | 8.63 | sq ft | 8.63 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144749 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250111 | 26003H | 2743J | LP1Y-WFO-195008-03-6 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.7125 | 1.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144759 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250109 | 26003H | 2741J | LP1Y-WFO-195008-03-4 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.37 | 2.79 | sq ft | 2.79 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250112 | 26003H | 2744J | LP1Y-WFO-195008-03-7 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250107 | 26003H | 2739J | LP1Y-WFO-195008-03-2 | LP1Y-WFO-195008-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-06-01 |  | LP1Y 2" SS WFO (36) 195008 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195008 |  | TFS00D006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 42.24 | 16 | sq ft | 16 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-04; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144765 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250117 | 26003H | 2749J | LP1Y-WFO-195027-03-5 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7438 | 1.8 | sq ft | 1.8 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144187 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250116 | 26003H | 2748J | LP1Y-WFO-195027-03-4 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian; ED: 2026-03-26; EL: Jacob Perez; FD: 2026-03-26; FL: Jacob Perez | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | N/A | N/A | 2026-03-30 | 2026-03-30 | N/A | N/A | NO FITTER | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143917 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250114 | 26003H | 2746J | LP1Y-WFO-195027-03-2 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.315 | 6.94 | sq ft | 6.94 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144175 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250115 | 26003H | 2747J | LP1Y-WFO-195027-03-3 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250113 | 26003H | 2745J | LP1Y-WFO-195027-03-1 | LP1Y-WFO-195027-03 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195027 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 0 | 6 | 49.1425 | 18.61 | sq ft | 18.61 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 144907 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250120 | 26003H | 2752J | LP1Y-WFO-195028-03-3 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250121 | 26003H | 2753J | LP1Y-WFO-195028-03-4 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.4613 | 0.93 | sq ft | 0.93 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian; ED: 2026-03-26; EL: Jacob Perez; FD: 2026-03-26; FL: Jacob Perez | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | N/A | N/A | 2026-03-30 | 2026-03-30 | N/A | N/A | NO FITTER | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143916 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250119 | 26003H | 2751J | LP1Y-WFO-195028-03-2 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.82 | 6.75 | sq ft | 6.75 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144176 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250122 | 26003H | 2754J | LP1Y-WFO-195028-03-5 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.5925 | 1.74 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144188 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250118 | 26003H | 2750J | LP1Y-WFO-195028-03-1 | LP1Y-WFO-195028-03 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-04-02 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WFO (36) 195028 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195028 |  | TFS00D002YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 0 | 6 | 48.125 | 18.23 | sq ft | 18.23 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-11 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 144908 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250123 | 26003H | 2755J | LP1Y-WFO-195029-02-1 | LP1Y-WFO-195029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 0.75" SS WFO (36) 195029 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195029 |  | TFS00D007YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 19.7332 | 18.32 | sq ft | 3.82 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250124 | 26003H | 2756J | LP1Y-WFO-195030-02-1 | LP1Y-WFO-195030-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 0.75" SS WFO (36) 195030 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-195030 |  | TFS00D001YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 20.9023 | 19.68 | sq ft | 5.18 | ft | 2026-02-13 |  |  |  |  | 2026-03-26 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250126 | 26003H | 2758J | LP1Y-WFO-196006-03-2 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 26.675 | 10.1 | sq ft | 10.1 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250125 | 26003H | 2757J | LP1Y-WFO-196006-03-1 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250127 | 26003H | 2759J | LP1Y-WFO-196006-03-3 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250128 | 26003H | 2760J | LP1Y-WFO-196006-03-4 | LP1Y-WFO-196006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196006 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196006 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.6238 | 2.13 | sq ft | 2.13 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146030
C34-S250130 | 26003H | 2762J | LP1Y-WFO-196007-03-2 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.7863 | 19.99 | sq ft | 19.99 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250131 | 26003H | 2763J | LP1Y-WFO-196007-03-3 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.7288 | 8.61 | sq ft | 8.61 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250133 | 26003H | 2765J | LP1Y-WFO-196007-03-5 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.83 | 2.21 | sq ft | 2.21 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146025
C34-S250132 | 26003H | 2764J | LP1Y-WFO-196007-03-4 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250129 | 26003H | 2761J | LP1Y-WFO-196007-03-1 | LP1Y-WFO-196007-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WFO (36) 196007 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196007 |  | TFS00E006YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.675 | 5.94 | sq ft | 5.94 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250134 | 26003H | 2766J | LP1Y-WFO-196010-03-1 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.5738 | 4.01 | sq ft | 4.01 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250135 | 26003H | 2767J | LP1Y-WFO-196010-03-2 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.6113 | 11.97 | sq ft | 11.97 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250139 | 26003H | 2771J | LP1Y-WFO-196010-03-6 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WNP (36) 017008 | WNP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017008 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250138 | 26003H | 2770J | LP1Y-WFO-196010-03-5 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.8225 | 1.45 | sq ft | 1.45 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250136 | 26003H | 2768J | LP1Y-WFO-196010-03-3 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.815 | 0.69 | sq ft | 0.69 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250137 | 26003H | 2769J | LP1Y-WFO-196010-03-4 | LP1Y-WFO-196010-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WFO (36) 196010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196010 |  | TFS00E007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.9763 | 4.54 | sq ft | 4.54 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250142 | 26003H | 2772J | LP1Y-WPC-017029-02-1 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250143 | 26003H | 2773J | LP1Y-WPC-017029-02-2 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250144 | 26003H | 2774J | LP1Y-WPC-017029-02-3 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250145 | 26003H | 2775J | LP1Y-WPC-017029-02-4 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250146 | 26003H | 2776J | LP1Y-WPC-017029-02-5 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250147 | 26003H | 2777J | LP1Y-WPC-017029-02-6 | LP1Y-WPC-017029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 017029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017029 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250155 | 26003H | 2785J | LP1Y-WPC-017041-03-8 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250149 | 26003H | 2779J | LP1Y-WPC-017041-03-2 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.1075 | 1.18 | sq ft | 1.18 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250148 | 26003H | 2778J | LP1Y-WPC-017041-03-1 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.815 | 0.69 | sq ft | 0.69 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144428
C34-S250152 | 26003H | 2782J | LP1Y-WPC-017041-03-5 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250154 | 26003H | 2784J | LP1Y-WPC-017041-03-7 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9638 | 1.88 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250153 | 26003H | 2783J | LP1Y-WPC-017041-03-6 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2725 | 1.24 | sq ft | 1.24 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250150 | 26003H | 2780J | LP1Y-WPC-017041-03-3 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.39 | 2.04 | sq ft | 2.04 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250151 | 26003H | 2781J | LP1Y-WPC-017041-03-4 | LP1Y-WPC-017041-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017041 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017041 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.1538 | 7.26 | sq ft | 7.26 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 0% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 0% | 2026-04-15 | 144738
C34-S250158 | 26003H | 2788J | LP1Y-WPC-017042-03-3 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.62 | 1.75 | sq ft | 1.75 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250161 | 26003H | 2791J | LP1Y-WPC-017042-03-6 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250156 | 26003H | 2786J | LP1Y-WPC-017042-03-1 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 20.9825 | 7.95 | sq ft | 7.95 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250157 | 26003H | 2787J | LP1Y-WPC-017042-03-2 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250160 | 26003H | 2790J | LP1Y-WPC-017042-03-5 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.09 | 0.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-09 | [9 empty] | 0% |  |  |  | 0%
C34-S250159 | 26003H | 2789J | LP1Y-WPC-017042-03-4 | LP1Y-WPC-017042-03 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 017042 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017042 |  | TFS00D006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 6.25 | 0 | 6.25 | 20.1263 | 13.2 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250172 | 26003H | 2802J | LP1Y-WPC-017050-02-11 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250171 | 26003H | 2801J | LP1Y-WPC-017050-02-10 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.85 | 1.46 | sq ft | 1.46 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146029
C34-S250169 | 26003H | 2799J | LP1Y-WPC-017050-02-8 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.7263 | 1.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146027
C34-S250170 | 26003H | 2800J | LP1Y-WPC-017050-02-9 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 2.25 | 0 | 2.25 | 20.3325 | 13.28 | sq ft | 2.28 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250166 | 26003H | 2796J | LP1Y-WPC-017050-02-5 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.0313 | 4.56 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250165 | 26003H | 2795J | LP1Y-WPC-017050-02-4 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.145 | 0.81 | sq ft | 0.81 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146021
C34-S250168 | 26003H | 2798J | LP1Y-WPC-017050-02-7 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250162 | 26003H | 2792J | LP1Y-WPC-017050-02-1 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.92 | 3 | sq ft | 3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-07 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250163 | 26003H | 2793J | LP1Y-WPC-017050-02-2 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.4975 | 3.22 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250164 | 26003H | 2794J | LP1Y-WPC-017050-02-3 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.5013 | 3.6 | sq ft | 3.6 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250167 | 26003H | 2797J | LP1Y-WPC-017050-02-6 | LP1Y-WPC-017050-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 017050 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017050 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.5063 | 5.49 | sq ft | 5.49 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-24 | [9 empty] | 0% |  |  |  | 0%
C34-S250173 | 26003H | 2803J | LP1Y-WPC-017051-01-1 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.8888 | 2.61 | sq ft | 2.61 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250179 | 26003H | 2809J | LP1Y-WPC-017051-01-7 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250178 | 26003H | 2808J | LP1Y-WPC-017051-01-6 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3.75 | 0 | 3.75 | 19.315 | 12.9 | sq ft | 1.9 | ft | 2026-02-13 |  |  |  |  | 2026-04-08 | Jacob Perez | 2026-04-08 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250175 | 26003H | 2805J | LP1Y-WPC-017051-01-3 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.6088 | 4.78 | sq ft | 4.78 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250176 | 26003H | 2806J | LP1Y-WPC-017051-01-4 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250174 | 26003H | 2804J | LP1Y-WPC-017051-01-2 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.83 | 2.21 | sq ft | 2.21 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250177 | 26003H | 2807J | LP1Y-WPC-017051-01-5 | LP1Y-WPC-017051-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 017051 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017051 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9638 | 1.88 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250186 | 26003H | 2816J | LP1Y-WPC-017061-08-7 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 5.5 | 0 | 5.5 | 4.0938 | 2.34 | sq ft | 1.34 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145284 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250187 | 26003H | 2817J | LP1Y-WPC-017061-08-8 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146041
C34-S250184 | 26003H | 2814J | LP1Y-WPC-017061-08-5 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.6963 | 2.54 | sq ft | 2.54 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143715 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250183 | 26003H | 2813J | LP1Y-WPC-017061-08-4 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | 2026-03-26 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250185 | 26003H | 2815J | LP1Y-WPC-017061-08-6 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.4863 | 2.08 | sq ft | 2.08 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143714 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250182 | 26003H | 2812J | LP1Y-WPC-017061-08-3 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.0863 | 4.58 | sq ft | 4.58 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143722 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250180 | 26003H | 2810J | LP1Y-WPC-017061-08-1 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.805 | 5.23 | sq ft | 5.23 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143726 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250181 | 26003H | 2811J | LP1Y-WPC-017061-08-2 | LP1Y-WPC-017061-08 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017061 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017061 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.3688 | 5.44 | sq ft | 5.44 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143710 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250188 | 26003H | 2818J | LP1Y-WPC-017064-05-1 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250189 | 26003H | 2819J | LP1Y-WPC-017064-05-2 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250190 | 26003H | 2820J | LP1Y-WPC-017064-05-3 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250191 | 26003H | 2821J | LP1Y-WPC-017064-05-4 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250192 | 26003H | 2822J | LP1Y-WPC-017064-05-5 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250193 | 26003H | 2823J | LP1Y-WPC-017064-05-6 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250194 | 26003H | 2824J | LP1Y-WPC-017064-05-7 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250195 | 26003H | 2825J | LP1Y-WPC-017064-05-8 | LP1Y-WPC-017064-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 4" SS WPC (36) (108) 017064 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017064 |  | TFS00D007YSPP |  | 36-WPC | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250205 | 26003H | 2835J | LP1Y-WPC-017071-01-10 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 30.0163 | 11.37 | sq ft | 11.37 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144291 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250196 | 26003H | 2826J | LP1Y-WPC-017071-01-1 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146039
C34-S250204 | 26003H | 2834J | LP1Y-WPC-017071-01-9 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.6713 | 5.56 | sq ft | 5.56 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144298 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250209 | 26003H | 2839J | LP1Y-WPC-017071-01-14 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.515 | 3.6 | sq ft | 3.6 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144304 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250206 | 26003H | 2836J | LP1Y-WPC-017071-01-11 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-09 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250202 | 26003H | 2832J | LP1Y-WPC-017071-01-7 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 18.2013 | 7.68 | sq ft | 6.68 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-29 | 2026-04-29 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250199 | 26003H | 2829J | LP1Y-WPC-017071-01-4 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 28.5863 | 10.83 | sq ft | 10.83 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144293 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250198 | 26003H | 2828J | LP1Y-WPC-017071-01-3 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.13 | 3.46 | sq ft | 3.46 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144306 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250200 | 26003H | 2830J | LP1Y-WPC-017071-01-5 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 26.3863 | 9.99 | sq ft | 9.99 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144295 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250201 | 26003H | 2831J | LP1Y-WPC-017071-01-6 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.05 | 2.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144248 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250197 | 26003H | 2827J | LP1Y-WPC-017071-01-2 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250203 | 26003H | 2833J | LP1Y-WPC-017071-01-8 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.1713 | 3.47 | sq ft | 3.47 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144307 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250210 | 26003H | 2840J | LP1Y-WPC-017071-01-15 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250208 | 26003H | 2838J | LP1Y-WPC-017071-01-13 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1588 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144247 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250207 | 26003H | 2837J | LP1Y-WPC-017071-01-12 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.58 | 3.25 | sq ft | 3.25 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144303 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250211 | 26003H | 2841J | LP1Y-WPC-017071-01-16 | LP1Y-WPC-017071-01 | 0 | N | PRIORITY-1 | 2026-04-10 | 2026-04-10 | released |  |  | Passed Visual Inspection | P012 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017071 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017071 |  | TFS00D004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; CL: Shannon Carpenter; DD: 2026-04-03; DL: George Allahverdian | 2026-04-10 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146051
C34-S250217 | 26003H | 2847J | LP1Y-WPC-033054-02-6 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 6.25 | 0 | 6.25 | 17.8025 | 12.32 | sq ft | 1.32 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250214 | 26003H | 2844J | LP1Y-WPC-033054-02-3 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.8475 | 2.59 | sq ft | 2.59 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143716
C34-S250218 | 26003H | 2848J | LP1Y-WPC-033054-02-7 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250212 | 26003H | 2842J | LP1Y-WPC-033054-02-1 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.0275 | 8.34 | sq ft | 8.34 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143728
C34-S250213 | 26003H | 2843J | LP1Y-WPC-033054-02-2 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7713 | 1.81 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143717
C34-S250215 | 26003H | 2845J | LP1Y-WPC-033054-02-4 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.545 | 2.48 | sq ft | 2.48 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-03-19 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143721
C34-S250216 | 26003H | 2846J | LP1Y-WPC-033054-02-5 | LP1Y-WPC-033054-02 | 0 | N | PRIORITY-1 | 2026-03-25 |  | active | client | cancelled | On Hold/Cancelled | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 033054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033054 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250219 | 26003H | 2849J | LP1Y-WPC-194002-01-1 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250220 | 26003H | 2850J | LP1Y-WPC-194002-01-2 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2825 | 0.86 | sq ft | 0.86 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143918 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250222 | 26003H | 2852J | LP1Y-WPC-194002-01-4 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.8513 | 2.97 | sq ft | 2.97 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143923 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250221 | 26003H | 2851J | LP1Y-WPC-194002-01-3 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143908, 143909 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250223 | 26003H | 2853J | LP1Y-WPC-194002-01-5 | LP1Y-WPC-194002-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146042
C34-S250225 | 26003H | 2855J | LP1Y-WPC-194002-02-2 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146048
C34-S250224 | 26003H | 2854J | LP1Y-WPC-194002-02-1 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.2425 | 2.36 | sq ft | 2.36 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-03-26 | 2026-03-27 | Passed | No | 2026-03-27 | N/A | N/A | 2026-03-28 | 2026-03-28 | N/A | N/A | NO FITTER | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 143922 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250226 | 26003H | 2856J | LP1Y-WPC-194002-02-3 | LP1Y-WPC-194002-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194002 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194002 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 11.25 | 0 | 11.25 | 18.9794 | 16.06 | sq ft | 6.06 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-26; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250227 | 26003H | 2857J | LP1Y-WPC-194003-01-1 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 20.4463 | 7.74 | sq ft | 7.74 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143711 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250228 | 26003H | 2858J | LP1Y-WPC-194003-01-2 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 25.2588 | 9.57 | sq ft | 9.57 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143712 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250233 | 26003H | 2863J | LP1Y-WPC-194003-01-7 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.8113 | 4.47 | sq ft | 4.47 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143723 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250231 | 26003H | 2861J | LP1Y-WPC-194003-01-5 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 53.36 | 21 | sq ft | 20 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-04-07 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-21 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145290 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250230 | 26003H | 2860J | LP1Y-WPC-194003-01-4 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.4325 | 3.57 | sq ft | 3.57 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143709 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250229 | 26003H | 2859J | LP1Y-WPC-194003-01-3 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.2013 | 2.35 | sq ft | 2.35 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143713 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250232 | 26003H | 2862J | LP1Y-WPC-194003-01-6 | LP1Y-WPC-194003-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 4 | 0 | 4 | 4.5513 | 1.72 | sq ft | 1.72 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian | 2026-03-25 | 2026-03-26 | Passed | No | 2026-03-26 | N/A | N/A | 2026-03-26 | 2026-03-26 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143719 | [40 empty] | 2026-04-08 | 2026-04-08 |  | 1001-0 | 2026-04-09 | JA Harris Trucking Inc.
C34-S250234 | 26003H | 2864J | LP1Y-WPC-194003-02-1 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.5088 | 4.36 | sq ft | 4.36 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144180 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250239 | 26003H | 2869J | LP1Y-WPC-194003-02-6 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | 2026-04-02 | 2026-04-07 | released |  |  | Released to Production | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 1" | 316 SS | 12.625 | 0 | 12.625 | 25.9517 | 21.29 | sq ft | 8.79 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-07 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250237 | 26003H | 2867J | LP1Y-WPC-194003-02-4 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.3038 | 1.63 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144184 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250238 | 26003H | 2868J | LP1Y-WPC-194003-02-5 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146046
C34-S250236 | 26003H | 2866J | LP1Y-WPC-194003-02-3 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.8775 | 1.47 | sq ft | 1.47 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144186 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250235 | 26003H | 2865J | LP1Y-WPC-194003-02-2 | LP1Y-WPC-194003-02 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P011 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 194003 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194003 |  | TFS00D002YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250245 | 26003H | 2875J | LP1Y-WPC-194006-01-6 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250241 | 26003H | 2871J | LP1Y-WPC-194006-01-2 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.8225 | 5.61 | sq ft | 5.61 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250242 | 26003H | 2872J | LP1Y-WPC-194006-01-3 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.0463 | 6.08 | sq ft | 6.08 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144414
C34-S250240 | 26003H | 2870J | LP1Y-WPC-194006-01-1 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.2563 | 2.37 | sq ft | 2.37 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144431
C34-S250244 | 26003H | 2874J | LP1Y-WPC-194006-01-5 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.05 | 2.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250243 | 26003H | 2873J | LP1Y-WPC-194006-01-4 | LP1Y-WPC-194006-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250248 | 26003H | 2878J | LP1Y-WPC-194006-04-3 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6025 | 1.36 | sq ft | 1.36 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250247 | 26003H | 2877J | LP1Y-WPC-194006-04-2 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.2213 | 1.6 | sq ft | 1.6 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250246 | 26003H | 2876J | LP1Y-WPC-194006-04-1 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.545 | 2.48 | sq ft | 2.48 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250255 | 26003H | 2885J | LP1Y-WPC-194006-04-10 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250253 | 26003H | 2883J | LP1Y-WPC-194006-04-8 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250254 | 26003H | 2884J | LP1Y-WPC-194006-04-9 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 5.6719 | 5.6 | sq ft | 2.6 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  |  |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% |  |  |  | 0%
C34-S250249 | 26003H | 2879J | LP1Y-WPC-194006-04-4 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.12 | 3.83 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144430 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250252 | 26003H | 2882J | LP1Y-WPC-194006-04-7 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 4.4825 | 1.7 | sq ft | 1.7 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250250 | 26003H | 2880J | LP1Y-WPC-194006-04-5 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250251 | 26003H | 2881J | LP1Y-WPC-194006-04-6 | LP1Y-WPC-194006-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194006 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194006 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6575 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-30 | 145947
C34-S250262 | 26003H | 2892J | LP1Y-WPC-194007-01-7 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 4.4895 | 4.77 | sq ft | 1.77 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | N/A | N/A | Aristeo Banda | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  |  |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% |  |  |  | 0%
C34-S250263 | 26003H | 2893J | LP1Y-WPC-194007-01-8 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250257 | 26003H | 2887J | LP1Y-WPC-194007-01-2 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.575 | 1.35 | sq ft | 1.35 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250256 | 26003H | 2886J | LP1Y-WPC-194007-01-1 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.475 | 5.1 | sq ft | 5.1 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144754 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250258 | 26003H | 2888J | LP1Y-WPC-194007-01-3 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250261 | 26003H | 2891J | LP1Y-WPC-194007-01-6 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250260 | 26003H | 2890J | LP1Y-WPC-194007-01-5 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.905 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250259 | 26003H | 2889J | LP1Y-WPC-194007-01-4 | LP1Y-WPC-194007-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194007 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194007 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6575 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250267 | 26003H | 2897J | LP1Y-WPC-194008-01-4 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6575 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250271 | 26003H | 2901J | LP1Y-WPC-194008-01-8 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250264 | 26003H | 2894J | LP1Y-WPC-194008-01-1 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.3275 | 1.26 | sq ft | 1.26 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144744 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250265 | 26003H | 2895J | LP1Y-WPC-194008-01-2 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.19 | 1.21 | sq ft | 1.21 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250266 | 26003H | 2896J | LP1Y-WPC-194008-01-3 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | 2026-04-01 |  | active | client | cancelled | On Hold/Cancelled | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250268 | 26003H | 2898J | LP1Y-WPC-194008-01-5 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 3.905 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144427 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250269 | 26003H | 2899J | LP1Y-WPC-194008-01-6 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250270 | 26003H | 2900J | LP1Y-WPC-194008-01-7 | LP1Y-WPC-194008-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194008 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194008 |  | TFS00D005YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 4.4895 | 4.77 | sq ft | 1.77 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250274 | 26003H | 2904J | LP1Y-WPC-194012-01-3 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.925 | 0.73 | sq ft | 0.73 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250273 | 26003H | 2903J | LP1Y-WPC-194012-01-2 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250275 | 26003H | 2905J | LP1Y-WPC-194012-01-4 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250272 | 26003H | 2902J | LP1Y-WPC-194012-01-1 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250277 | 26003H | 2907J | LP1Y-WPC-194012-01-6 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250278 | 26003H | 2908J | LP1Y-WPC-194012-01-7 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250276 | 26003H | 2906J | LP1Y-WPC-194012-01-5 | LP1Y-WPC-194012-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194012 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.7612 | 2.18 | sq ft | 2.18 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250285 | 26003H | 2915J | LP1Y-WPC-194013-01-7 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250288 | 26003H | 2918J | LP1Y-WPC-194013-01-10 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.7612 | 2.18 | sq ft | 2.18 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250281 | 26003H | 2911J | LP1Y-WPC-194013-01-3 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250282 | 26003H | 2912J | LP1Y-WPC-194013-01-4 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.2113 | 1.97 | sq ft | 1.97 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250280 | 26003H | 2910J | LP1Y-WPC-194013-01-2 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8975 | 0.72 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144426
C34-S250279 | 26003H | 2909J | LP1Y-WPC-194013-01-1 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250287 | 26003H | 2917J | LP1Y-WPC-194013-01-9 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.6213 | 7.43 | sq ft | 7.43 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144415
C34-S250286 | 26003H | 2916J | LP1Y-WPC-194013-01-8 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 30.2363 | 11.45 | sq ft | 11.45 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144419
C34-S250284 | 26003H | 2914J | LP1Y-WPC-194013-01-6 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.1263 | 7.24 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S250283 | 26003H | 2913J | LP1Y-WPC-194013-01-5 | LP1Y-WPC-194013-01 | 0 | N | PRIORITY-1 | 2026-04-16 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.7775 | 1.05 | sq ft | 1.05 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 0% | 2026-04-10 | 144432
C34-S250290 | 26003H | 2920J | LP1Y-WPC-194013-02-2 | LP1Y-WPC-194013-02 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256303 | 26003H | 2920JA | LP1Y-WPC-194013-02-3 | LP1Y-WPC-194013-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 |  | 0 | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 2.5 | 0 | 2.5 | 2.98 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250289 | 26003H | 2919J | LP1Y-WPC-194013-02-1 | LP1Y-WPC-194013-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 2" SS WPC (36) (108) 194013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194013 |  | TFS00D006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S250295 | 26003H | 2925J | LP1Y-WPC-194027-01-5 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250297 | 26003H | 2927J | LP1Y-WPC-194027-01-7 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250301 | 26003H | 2931J | LP1Y-WPC-194027-01-11 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250294 | 26003H | 2924J | LP1Y-WPC-194027-01-4 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250296 | 26003H | 2926J | LP1Y-WPC-194027-01-6 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250298 | 26003H | 2928J | LP1Y-WPC-194027-01-8 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250299 | 26003H | 2929J | LP1Y-WPC-194027-01-9 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250300 | 26003H | 2930J | LP1Y-WPC-194027-01-10 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250291 | 26003H | 2921J | LP1Y-WPC-194027-01-1 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250292 | 26003H | 2922J | LP1Y-WPC-194027-01-2 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250293 | 26003H | 2923J | LP1Y-WPC-194027-01-3 | LP1Y-WPC-194027-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250302 | 26003H | 2932J | LP1Y-WPC-194027-02-1 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250303 | 26003H | 2933J | LP1Y-WPC-194027-02-2 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250304 | 26003H | 2934J | LP1Y-WPC-194027-02-3 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250305 | 26003H | 2935J | LP1Y-WPC-194027-02-4 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250306 | 26003H | 2936J | LP1Y-WPC-194027-02-5 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250307 | 26003H | 2937J | LP1Y-WPC-194027-02-6 | LP1Y-WPC-194027-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194027 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194027 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250308 | 26003H | 2938J | LP1Y-WPC-194028-01-1 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250309 | 26003H | 2939J | LP1Y-WPC-194028-01-2 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250310 | 26003H | 2940J | LP1Y-WPC-194028-01-3 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250311 | 26003H | 2941J | LP1Y-WPC-194028-01-4 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250312 | 26003H | 2942J | LP1Y-WPC-194028-01-5 | LP1Y-WPC-194028-01 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 2" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250316 | 26003H | 2946J | LP1Y-WPC-194028-02-4 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 7.5 | 0 | 7.5 | 11.7525 | 8.31 | sq ft | 2.81 | ft | 2026-02-13 | DD: 2026-03-29; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250313 | 26003H | 2943J | LP1Y-WPC-194028-02-1 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250314 | 26003H | 2944J | LP1Y-WPC-194028-02-2 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250315 | 26003H | 2945J | LP1Y-WPC-194028-02-3 | LP1Y-WPC-194028-02 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 1.25" SS WPC (36) (108) 194028 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194028 |  | TFS00D007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250321 | 26003H | 2951J | LP1Y-WPC-194029-01-5 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 5.7673 | 5.67 | sq ft | 2.67 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Henrique Barahona | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144447
C34-S250317 | 26003H | 2947J | LP1Y-WPC-194029-01-1 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.27 | 2.38 | sq ft | 2.38 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144246
C34-S250319 | 26003H | 2949J | LP1Y-WPC-194029-01-3 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.6125 | 0.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-16 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144245
C34-S250320 | 26003H | 2950J | LP1Y-WPC-194029-01-4 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250318 | 26003H | 2948J | LP1Y-WPC-194029-01-2 | LP1Y-WPC-194029-01 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250326 | 26003H | 2956J | LP1Y-WPC-194029-02-5 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 7.5 | 0 | 7.5 | 11.7525 | 8.31 | sq ft | 2.81 | ft | 2026-02-13 | DD: 2026-03-29; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250323 | 26003H | 2953J | LP1Y-WPC-194029-02-2 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3.75 | 0 | 3.75 | 19.46 | 12.17 | sq ft | 9.17 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Henrique Barahona | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 144604
C34-S250322 | 26003H | 2952J | LP1Y-WPC-194029-02-1 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 10.25 | 0 | 10.25 | 47.24 | 33.08 | sq ft | 14.58 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250324 | 26003H | 2954J | LP1Y-WPC-194029-02-3 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3.75 | 0 | 3.75 | 16.835 | 10.71 | sq ft | 7.71 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Henrique Barahona | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 144603
C34-S250325 | 26003H | 2955J | LP1Y-WPC-194029-02-4 | LP1Y-WPC-194029-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 1.25" SS WPC (36) (108) 194029 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194029 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3.5 | 0 | 3.5 | 10.4681 | 6.1 | sq ft | 4.6 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250331 | 26003H | 2961J | LP1Y-WPC-194030-01-5 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.8925 | 7.16 | sq ft | 7.16 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143727
C34-S250329 | 26003H | 2959J | LP1Y-WPC-194030-01-3 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2 | 0.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143718
C34-S250330 | 26003H | 2960J | LP1Y-WPC-194030-01-4 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2313 | 1.22 | sq ft | 1.22 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143720
C34-S250328 | 26003H | 2958J | LP1Y-WPC-194030-01-2 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.8263 | 5.99 | sq ft | 5.99 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143724
C34-S250327 | 26003H | 2957J | LP1Y-WPC-194030-01-1 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.4963 | 5.87 | sq ft | 5.87 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18 | 2026-03-18 | 2026-03-20 | Passed | No | 2026-03-20 | N/A | N/A | 2026-03-23 | 2026-03-23 | N/A | N/A | NO FITTER | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-03-28 | 143725
C34-S250332 | 26003H | 2962J | LP1Y-WPC-194030-01-6 | LP1Y-WPC-194030-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian | 2026-03-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250333 | 26003H | 2963J | LP1Y-WPC-194030-02-1 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.025 | 1.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 144244
C34-S250334 | 26003H | 2964J | LP1Y-WPC-194030-02-2 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | 2026-03-31 |  | active | client | cancelled | On Hold/Cancelled | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250336 | 26003H | 2966J | LP1Y-WPC-194030-02-4 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250337 | 26003H | 2967J | LP1Y-WPC-194030-02-5 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 37.5269 | 28.44 | sq ft | 8.44 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250335 | 26003H | 2965J | LP1Y-WPC-194030-02-3 | LP1Y-WPC-194030-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194030 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194030 |  | TFS00D001YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 10.505 | 3.98 | sq ft | 3.98 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | N/A | N/A | 2026-04-02 | 2026-04-02 | N/A | N/A | NO FITTER | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144301, 144302
C34-S250338 | 26003H | 2968J | LP1Y-WPC-194105-01-1 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.4213 | 2.43 | sq ft | 2.43 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146023
C34-S250341 | 26003H | 2971J | LP1Y-WPC-194105-01-4 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250342 | 26003H | 2972J | LP1Y-WPC-194105-01-5 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.7125 | 1.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146031
C34-S250343 | 26003H | 2973J | LP1Y-WPC-194105-01-6 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A |  |  | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 100% |  |  |  | 0%
C34-S250339 | 26003H | 2969J | LP1Y-WPC-194105-01-2 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.96 | 1.5 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250340 | 26003H | 2970J | LP1Y-WPC-194105-01-3 | LP1Y-WPC-194105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.6063 | 5.91 | sq ft | 5.91 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250348 | 26003H | 2978J | LP1Y-WPC-194105-04-5 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250349 | 26003H | 2979J | LP1Y-WPC-194105-04-6 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 2.09 | 0.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146019
C34-S250352 | 26003H | 2982J | LP1Y-WPC-194105-04-9 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 10 | 0 | 10 | 31.0644 | 22.96 | sq ft | 5.96 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250347 | 26003H | 2977J | LP1Y-WPC-194105-04-4 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.1738 | 2.34 | sq ft | 2.34 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146024
C34-S250351 | 26003H | 2981J | LP1Y-WPC-194105-04-8 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 3.858 | 4.32 | sq ft | 1.32 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-05-02 | 2026-05-02 | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250344 | 26003H | 2974J | LP1Y-WPC-194105-04-1 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2313 | 1.22 | sq ft | 1.22 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250350 | 26003H | 2980J | LP1Y-WPC-194105-04-7 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250345 | 26003H | 2975J | LP1Y-WPC-194105-04-2 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.8937 | 4.51 | sq ft | 4.51 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250346 | 26003H | 2976J | LP1Y-WPC-194105-04-3 | LP1Y-WPC-194105-04 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194105 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194105 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.985 | 6.81 | sq ft | 6.81 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250353 | 26003H | 2983J | LP1Y-WPC-194106-01-1 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.9425 | 1.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146028
C34-S250356 | 26003H | 2986J | LP1Y-WPC-194106-01-4 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250358 | 26003H | 2988J | LP1Y-WPC-194106-01-6 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8563 | 0.7 | sq ft | 0.7 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146020
C34-S250354 | 26003H | 2984J | LP1Y-WPC-194106-01-2 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.0775 | 2.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250355 | 26003H | 2985J | LP1Y-WPC-194106-01-3 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.6263 | 5.16 | sq ft | 5.16 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250359 | 26003H | 2989J | LP1Y-WPC-194106-01-7 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 4.0288 | 1.53 | sq ft | 1.53 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146032
C34-S250360 | 26003H | 2990J | LP1Y-WPC-194106-01-8 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250361 | 26003H | 2991J | LP1Y-WPC-194106-01-9 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 34.7216 | 27.33 | sq ft | 7.33 | ft | 2026-02-13 |  |  |  |  | 2026-04-06 | Jacob Perez | 2026-04-06 | George Allahverdian | 2026-04-08 | Jacob Perez | 2026-04-08 | Jacob Perez | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250357 | 26003H | 2987J | LP1Y-WPC-194106-01-5 | LP1Y-WPC-194106-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS WPC (36) (108) 194106 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194106 |  | TFS00E006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1175 | 0.8 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-08 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146017
C34-S250362 | 26003H | 2992J | LP1Y-WPC-194109-01-1 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.5688 | 2.11 | sq ft | 2.11 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250363 | 26003H | 2993J | LP1Y-WPC-194109-01-2 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250364 | 26003H | 2994J | LP1Y-WPC-194109-01-3 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250365 | 26003H | 2995J | LP1Y-WPC-194109-01-4 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.4225 | 3.95 | sq ft | 3.95 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250366 | 26003H | 2996J | LP1Y-WPC-194109-01-5 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250367 | 26003H | 2997J | LP1Y-WPC-194109-01-6 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250368 | 26003H | 2998J | LP1Y-WPC-194109-01-7 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250369 | 26003H | 2999J | LP1Y-WPC-194109-01-8 | LP1Y-WPC-194109-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194109 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194109 |  | TFS00E007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 33.8166 | 26.74 | sq ft | 6.74 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250373 | 26003H | 3003J | LP1Y-WPC-194111-01-4 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 1 | 0 | 1 | 5.0917 | 5.19 | sq ft | 2.19 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250370 | 26003H | 3000J | LP1Y-WPC-194111-01-1 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1175 | 0.8 | sq ft | 0.8 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250372 | 26003H | 3002J | LP1Y-WPC-194111-01-3 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250371 | 26003H | 3001J | LP1Y-WPC-194111-01-2 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | 2026-04-08 |  | active | client | cancelled | On Hold/Cancelled | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250374 | 26003H | 3004J | LP1Y-WPC-194111-01-5 | LP1Y-WPC-194111-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WPC (36) (108) 194111 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194111 |  | TFS00E007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 10 | 0 | 10 | 31.7863 | 23.36 | sq ft | 6.36 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250378 | 26003H | 3008J | LP1Y-WTFAP-014006-03-4 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 8 | 8 | 0 | 48.9734 | 11.01 | sq ft | 1.51 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250380 | 26003H | 3010J | LP1Y-WTFAP-014006-03-6 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 16 | 16 | 0 | 94.2236 | 22.73 | sq ft | 14.44 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250381 | 26003H | 3011J | LP1Y-WTFAP-014006-03-7 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 12 | 12 | 0 | 121.1169 | 27.62 | sq ft | 20.02 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250375 | 26003H | 3005J | LP1Y-WTFAP-014006-03-1 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-08 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250379 | 26003H | 3009J | LP1Y-WTFAP-014006-03-5 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 29 | 26 | 3 | 115.7463 | 37.4 | sq ft | 5.94 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250376 | 26003H | 3006J | LP1Y-WTFAP-014006-03-2 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 8 | 8 | 0 | 36.1914 | 8.87 | sq ft | 2.06 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144361
C34-S250377 | 26003H | 3007J | LP1Y-WTFAP-014006-03-3 | LP1Y-WTFAP-014006-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 014006 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014006 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 16 | 16 | 0 | 53.8363 | 15.35 | sq ft | 0.63 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-02 | N/A | N/A | Aristeo Banda | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144287
C34-S250383 | 26003H | 3013J | LP1Y-WTFAP-109103-01-2 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 8 | 8 | 0 | 23.1958 | 8.75 | sq ft | 2.75 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian; ED: 2026-03-30; EL: Jacob Perez; FD: 2026-03-31; FL: Jacob Perez | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-07 | N/A | N/A | Roberto Tobias (WF) | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144654
C34-S250382 | 26003H | 3012J | LP1Y-WTFAP-109103-01-1 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144224
C34-S250384 | 26003H | 3014J | LP1Y-WTFAP-109103-01-3 | LP1Y-WTFAP-109103-01 | 0 | N | PRIORITY-1 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 30 | 29 | 1 | 585.7318 | 48.18 | sq ft | 10.68 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250386 | 26003H | 3016J | LP1Y-WTFAP-109103-02-2 | LP1Y-WTFAP-109103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 16 | 16 | 0 | 104.3076 | 28.01 | sq ft | 19.51 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250385 | 26003H | 3015J | LP1Y-WTFAP-109103-02-1 | LP1Y-WTFAP-109103-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 4" SS WTFAP (315) (108) 109103 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109103 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 4" | 316 SS | 16 | 16 | 0 | 82.1452 | 20.77 | sq ft | 10.77 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-13 | 144600
C34-S250387 | 26003H | 3017J | LP1Y-WTFAP-109105-01-1 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 3 | 3 | 0 | 20.5981 | 5.81 | sq ft | 1.81 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Carlos Montoya | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-10 | 144384, 144448
C34-S250389 | 26003H | 3019J | LP1Y-WTFAP-109105-01-3 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 27 | 25 | 2 | 315.6443 | 35.79 | sq ft | 5.79 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250388 | 26003H | 3018J | LP1Y-WTFAP-109105-01-2 | LP1Y-WTFAP-109105-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 9 | 8 | 1 | 36.7307 | 14.82 | sq ft | 1.82 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250390 | 26003H | 3020J | LP1Y-WTFAP-109105-02-1 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4 | 4 | 0 | 15.875 | 8.52 | sq ft | 0.52 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250392 | 26003H | 3022J | LP1Y-WTFAP-109105-02-3 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 10.75 | 10 | 0.75 | 88.8738 | 34.88 | sq ft | 8.38 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250391 | 26003H | 3021J | LP1Y-WTFAP-109105-02-2 | LP1Y-WTFAP-109105-02 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 24.25 | 22 | 2.25 | 130.2075 | 44.51 | sq ft | 8.01 | ft | 2026-02-13 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250396 | 26003H | 3026J | LP1Y-WTFAP-109105-05-4 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 3 | 3 | 0 | 19.25 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-08 | Jacob Perez | 2026-04-08 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250393 | 26003H | 3023J | LP1Y-WTFAP-109105-05-1 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 3 | 3 | 0 | 5.36 | 8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 144282
C34-S250394 | 26003H | 3024J | LP1Y-WTFAP-109105-05-2 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 11 | 10 | 1 | 68.9586 | 26.26 | sq ft | 10.26 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250395 | 26003H | 3025J | LP1Y-WTFAP-109105-05-3 | LP1Y-WTFAP-109105-05 | 0 | N | PRIORITY-1 | [5 empty] | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 6 | 6 | 0 | 35.3747 | 9.22 | sq ft | 3.72 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144355
C34-S250397 | 26003H | 3027J | LP1Y-WTFAP-109116-01-1 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250398 | 26003H | 3028J | LP1Y-WTFAP-109116-01-2 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 12.25 | 10 | 2.25 | 64.6175 | 23.93 | sq ft | 2.43 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250399 | 26003H | 3029J | LP1Y-WTFAP-109116-01-3 | LP1Y-WTFAP-109116-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 46.4263 | 23.2 | sq ft | 12.2 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250402 | 26003H | 3032J | LP1Y-WTFAP-109116-03-3 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4 | 4 | 0 | 26.4138 | 11.34 | sq ft | 8.34 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250400 | 26003H | 3030J | LP1Y-WTFAP-109116-03-1 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 14.5 | 10 | 4.5 | 75.235 | 29.81 | sq ft | 6.31 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250401 | 26003H | 3031J | LP1Y-WTFAP-109116-03-2 | LP1Y-WTFAP-109116-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109116 | WTFAP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109116 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 13.1788 | 9.28 | sq ft | 1.28 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250408 | 26003H | 3038J | LP1Y-WTFAP-109208-01-6 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.3188 | 13.78 | sq ft | 9.28 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250405 | 26003H | 3035J | LP1Y-WTFAP-109208-01-3 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 16.25 | 14 | 2.25 | 76.3413 | 27.85 | sq ft | 2.35 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250404 | 26003H | 3034J | LP1Y-WTFAP-109208-01-2 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 6 | 6 | 0 | 22.8583 | 6.33 | sq ft | 0.83 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250409 | 26003H | 3039J | LP1Y-WTFAP-109208-01-7 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4 | 4 | 0 | 56.5538 | 22.09 | sq ft | 20.59 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250406 | 26003H | 3036J | LP1Y-WTFAP-109208-01-4 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 14.485 | 9.77 | sq ft | 1.77 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250407 | 26003H | 3037J | LP1Y-WTFAP-109208-01-5 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 6 | 6 | 0 | 24.5575 | 10.64 | sq ft | 7.64 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250403 | 26003H | 3033J | LP1Y-WTFAP-109208-01-1 | LP1Y-WTFAP-109208-01 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 3" SS WTFAP (315) (108) 109208 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250410 | 26003H | 3040J | LP1Y-WTFAP-109208-03-1 | LP1Y-WTFAP-109208-03 | 0 | N | PRIORITY-1 | [5 empty] | Passed Production Test | P017 | 2026-06-15 |  | LP1Y 2" SS WTFAP (315) (108) 109208 | WTFAP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109208 |  | TFS00E007YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.1188 | 8.03 | sq ft | 2.53 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-03-31 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250411 | 26003H | 3041D | LP1Y-WV-061046-30-1 | LP1Y-WV-061046-30 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 061046 | WV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-061046 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250412 | 26003H | 3042D | LP1Y-WV-061046-30-2 | LP1Y-WV-061046-30 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 061046 | WV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-061046 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 15 | 15 | 0 | 69.979 | 18.4 | sq ft | 9.9 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250414 | 26003H | 3044J | LP1Y-WV-100407-01-2 | LP1Y-WV-100407-01 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-03-31 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS WV (315) (108) 100407 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100407 |  | TFS00D003YSPP |  | 315-WV | NONE | 4" | 316 SS | 12 | 8 | 4 | 14.1244 | 4.64 | sq ft | 0.77 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | [11 empty] | 0% |  |  |  | 0%
C34-S250413 | 26003H | 3043J | LP1Y-WV-100407-01-1 | LP1Y-WV-100407-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS WV (315) (108) 100407 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100407 |  | TFS00D003YSPP |  | 315-WV | NONE | 4" | 316 SS | 0 | 0 | 0 | 16.5 | 3.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-02 | 144085 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250419 | 26003H | 3049D | LP1Y-WV-101015-01-5 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 9 | 9 | 0 | 90.286 | 20.85 | sq ft | 17.85 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-08 | Passed | No | 2026-04-08 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250418 | 26003H | 3048D | LP1Y-WV-101015-01-4 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 18 | 18 | 0 | 77.1512 | 18.87 | sq ft | 10.37 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250415 | 26003H | 3045D | LP1Y-WV-101015-01-1 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-20 | 2026-04-20 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-17 | [9 empty] | 100% |  |  |  | 100% | 2026-04-20 | 145031 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S250417 | 26003H | 3047D | LP1Y-WV-101015-01-3 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 6 | 6 | 0 | 29.5368 | 8.93 | sq ft | 0.93 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250416 | 26003H | 3046D | LP1Y-WV-101015-01-2 | LP1Y-WV-101015-01 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101015 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101015 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 9 | 9 | 0 | 28.3159 | 7.59 | sq ft | 2.09 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez | 2026-03-27 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250422 | 26003H | 3052J | LP1Y-WV-101113-01-3 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 12 | 12 | 0 | 186.0133 | 26.13 | sq ft | 5.33 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Guillen | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 144076 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250420 | 26003H | 3050J | LP1Y-WV-101113-01-1 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 82 | 13.26 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143975 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250421 | 26003H | 3051J | LP1Y-WV-101113-01-2 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 24 | 24 | 0 | 262.489 | 36.88 | sq ft | 8.49 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-26 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | Henrique Barahona | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | 2026-04-07 | 144240 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250423 | 26003H | 3053J | LP1Y-WV-101113-01-4 | LP1Y-WV-101113-01 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-03-31 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101113 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101113 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 48 | 36 | 12 | 224.7817 | 32.14 | sq ft | 2.14 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-06 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 |  |  | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2026-04-30 |  | 2026-04-30 |  |  |  | 50% |  |  |  | 50%
C34-S250427 | 26003H | 3057J | LP1Y-WV-101313-01-4 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | 2026-03-31 | 2026-03-31 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 48 | 36 | 12 | 226.1676 | 32.33 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-06 | 2026-04-22 | Passed | No | 2026-04-22 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 |  |  | Edgar Castaneda | 2026-04-29 | 2026-04-29 |  | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-04-30 |  |  |  | 50% |  | 2026-05-01 |  | 75%
C34-S250424 | 26003H | 3054J | LP1Y-WV-101313-01-1 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 0 | 0 | 0 | 82 | 13.26 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-03-31 | 143973 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250426 | 26003H | 3056J | LP1Y-WV-101313-01-3 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 24 | 24 | 0 | 248.0002 | 34.85 | sq ft | 7.9 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | N/A | N/A | Aristeo Banda | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-06 | 144131 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250425 | 26003H | 3055J | LP1Y-WV-101313-01-2 | LP1Y-WV-101313-01 | 0 | N | PRIORITY-1 | 2026-03-30 | 2026-03-30 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 12" SS WV (315) (108) 101313 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101313 |  | TFS00D003YSPP |  | 315-WV | NONE | 12" | 316 SS | 12 | 12 | 0 | 200.7541 | 28.21 | sq ft | 5.94 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-03-30 | 2026-03-30 | Passed | No | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | N/A | N/A | Carlos Montoya | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 143967 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S250430 | 26003H | 3060D | LP1Y-WV-101615-03-3 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 18 | 18 | 0 | 68.1078 | 16.78 | sq ft | 8.28 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250428 | 26003H | 3058D | LP1Y-WV-101615-03-1 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 6 | 6 | 0 | 66.0425 | 15.25 | sq ft | 12.25 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250429 | 26003H | 3059D | LP1Y-WV-101615-03-2 | LP1Y-WV-101615-03 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 101615 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101615 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 9 | 9 | 0 | 41.8216 | 9.66 | sq ft | 6.66 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250432 | 26003H | 3062J | LP1Y-WV-101616-01-2 | LP1Y-WV-101616-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS WV (315) (108) 101616 | WV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101616 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250431 | 26003H | 3061J | LP1Y-WV-101616-01-1 | LP1Y-WV-101616-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS WV (315) (108) 101616 | WV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101616 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-08 | 144310 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250434 | 26003H | 3064J | LP1Y-WV-101715-01-2 | LP1Y-WV-101715-01 | 0 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 3" SS WV (315) (108) 101715 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101715 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250433 | 26003H | 3063J | LP1Y-WV-101715-01-1 | LP1Y-WV-101715-01 | 0 | N | PRIORITY-1 | [5 empty] | Shipped | P014 | 2026-06-15 |  | LP1Y 3" SS WV (315) (108) 101715 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101715 |  | TFS00D005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | 2026-04-07 | 2026-04-07 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-08 | 144309 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250440 | 26003H | 3070D | LP1Y-WV-175013-05-4 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Production | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 15 | 14 | 1 | 74.3349 | 24.49 | sq ft | 10.99 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250437 | 26003H | 3067D | LP1Y-WV-175013-05-1 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250439 | 26003H | 3069D | LP1Y-WV-175013-05-3 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | In Engineering | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250438 | 26003H | 3068D | LP1Y-WV-175013-05-2 | LP1Y-WV-175013-05 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 3 | 3 | 0 | 27.6764 | 6.39 | sq ft | 4.89 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian | 2026-03-30 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-21 | 2026-04-21 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250442 | 26003H | 3072D | LP1Y-WV-175013-06-2 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 12 | 12 | 0 | 63.8098 | 14.73 | sq ft | 11.73 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250443 | 26003H | 3073D | LP1Y-WV-175013-06-3 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 12 | 12 | 0 | 94.2827 | 21.77 | sq ft | 17.27 | ft | 2026-02-13 | CD: 2026-04-02; DD: 2026-04-03; DL: George Allahverdian | 2026-04-06 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250441 | 26003H | 3071D | LP1Y-WV-175013-06-1 | LP1Y-WV-175013-06 | 0 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D005YSPP |  | 344-WV | NONE | 3" | 2205 | 15 | 15 | 0 | 44.6311 | 11.36 | sq ft | 2.86 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-03-27 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254589 | 26003H | 3575J | LP1Y-WPC-017072-01-12 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254595 | 26003H | 3581J | LP1Y-WPC-017072-01-9 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 32.6563 | 12.37 | sq ft | 12.37 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144417 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254596 | 26003H | 3582J | LP1Y-WPC-017072-01-13 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.3163 | 4.29 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144755 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254598 | 26003H | 3584J | LP1Y-WPC-017072-01-10 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254597 | 26003H | 3583J | LP1Y-WPC-017072-01-14 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1588 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S254591 | 26003H | 3577J | LP1Y-WPC-017072-01-5 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.7138 | 2.92 | sq ft | 2.92 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144433 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254585 | 26003H | 3571J | LP1Y-WPC-017072-01-1 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254587 | 26003H | 3573J | LP1Y-WPC-017072-01-3 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 27.5963 | 10.45 | sq ft | 10.45 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144747 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254588 | 26003H | 3574J | LP1Y-WPC-017072-01-11 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.515 | 3.6 | sq ft | 3.6 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144756 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254586 | 26003H | 3572J | LP1Y-WPC-017072-01-2 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.13 | 3.46 | sq ft | 3.46 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144429 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254592 | 26003H | 3578J | LP1Y-WPC-017072-01-6 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.8675 | 6.01 | sq ft | 6.01 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144735 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254593 | 26003H | 3579J | LP1Y-WPC-017072-01-7 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.5313 | 2.47 | sq ft | 2.47 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144757 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254594 | 26003H | 3580J | LP1Y-WPC-017072-01-8 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | [5 empty] | Shipped | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.935 | 4.52 | sq ft | 4.52 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144761 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254590 | 26003H | 3576J | LP1Y-WPC-017072-01-4 | LP1Y-WPC-017072-01 | 2 | N | PRIORITY-1 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P015 | 2026-05-18 |  | LP1Y 2" SS WPC (36) (108) 017072 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017072 |  | TFS00E001YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254603 | 26003H | 3589J | LP1Y-WPC-017073-01-12 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | 2026-04-10 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-07; CL: Shannon Carpenter; DD: 2026-04-07; DL: George Allahverdian | 2026-04-10 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254604 | 26003H | 3590J | LP1Y-WPC-017073-01-4 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.31 | 5.04 | sq ft | 5.04 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144740 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254606 | 26003H | 3592J | LP1Y-WPC-017073-01-6 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | 2026-04-14 | 2026-04-14 | released |  |  | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 23.4813 | 9.68 | sq ft | 8.68 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-14 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-29 | 2026-04-29 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254605 | 26003H | 3591J | LP1Y-WPC-017073-01-5 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.3113 | 2.39 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144434 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254601 | 26003H | 3587J | LP1Y-WPC-017073-01-3 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 43.6563 | 16.54 | sq ft | 16.54 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144764 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254602 | 26003H | 3588J | LP1Y-WPC-017073-01-11 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.705 | 4.81 | sq ft | 4.81 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S254600 | 26003H | 3586J | LP1Y-WPC-017073-01-2 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.32 | 4.67 | sq ft | 4.67 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144736 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254607 | 26003H | 3593J | LP1Y-WPC-017073-01-7 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.8113 | 4.47 | sq ft | 4.47 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144739 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254599 | 26003H | 3585J | LP1Y-WPC-017073-01-1 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 0 | 2 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254608 | 26003H | 3594J | LP1Y-WPC-017073-01-8 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.935 | 4.52 | sq ft | 4.52 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144752 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254611 | 26003H | 3597J | LP1Y-WPC-017073-01-14 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1588 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-08 | [9 empty] | 0% |  |  |  | 0%
C34-S254612 | 26003H | 3598J | LP1Y-WPC-017073-01-10 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | 2026-04-14 | 2026-04-14 | released |  |  | Released to Fabrication | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-14 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254610 | 26003H | 3596J | LP1Y-WPC-017073-01-13 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.3163 | 4.29 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144753 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254609 | 26003H | 3595J | LP1Y-WPC-017073-01-9 | LP1Y-WPC-017073-01 | 1 | N | PRIORITY-1 | [5 empty] | Shipped | P013 | 2026-05-11 |  | LP1Y 2" SS WPC (36) (108) 017073 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017073 |  | TFS00E004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 27.3763 | 10.37 | sq ft | 10.37 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-06 | 2026-04-06 | Passed | No | 2026-04-06 | N/A | N/A | 2026-04-09 | 2026-04-09 | N/A | N/A | NO FITTER | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-15 | 144745 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S250639 | 26003H | 3074J | LP1Y-ACN-011012-02-1 | LP1Y-ACN-011012-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 | 2026-07-27 |  | LP1Y 4" SS ACN (315) P (108) 011012 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 |  |  |  |  | 2026-04-28 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250640 | 26003H | 3075J | LP1Y-ACN-011014-02-1 | LP1Y-ACN-011014-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS ACN (315) P (108) 011014 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-011014 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 34.8425 | 13.86 | sq ft | 12.36 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250641 | 26003H | 3076J | LP1Y-ACN-063302-07-1 | LP1Y-ACN-063302-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 063302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-063302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 78.8602 | 19.27 | sq ft | 12.27 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250643 | 26003H | 3078J | LP1Y-ACN-107012-04-2 | LP1Y-ACN-107012-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 4" SS ACN (315) P (108) 107012 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 4 | 4 | 0 | 27.2198 | 6.68 | sq ft | 4.07 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258536 | 26003H | 3077JA | LP1Y-ACN-107012-04-3 | LP1Y-ACN-107012-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 |  |  | LP1Y 4" SS ACN (315) P (108) 107012 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 4 | 4 | 58.893 | 13.46 | sq ft | 9.71 | ft | 2026-01-20 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250642 | 26003H | 3077J | LP1Y-ACN-107012-04-1 | LP1Y-ACN-107012-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P025 | 2026-07-27 |  | LP1Y 4" SS ACN (315) P (108) 107012 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107012 |  | TFS00E015YSPP |  | 315-ACN | NONE | 4" | 316 SS | 3 | 2 | 1 | 104.8684 | 26.46 | sq ft | 18.34 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250647 | 26003H | 3082J | LP1Y-ACN-107102-02-4 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.0212 | 5.6 | sq ft | 4.1 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250646 | 26003H | 3081J | LP1Y-ACN-107102-02-3 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 62.7313 | 18.35 | sq ft | 4.35 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250644 | 26003H | 3079J | LP1Y-ACN-107102-02-1 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250645 | 26003H | 3080J | LP1Y-ACN-107102-02-2 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250649 | 26003H | 3084J | LP1Y-ACN-107102-02-6 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 5.5 | 3.42 | sq ft | 0.42 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250648 | 26003H | 3083J | LP1Y-ACN-107102-02-5 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 32.9213 | 14.47 | sq ft | 11.47 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250650 | 26003H | 3085J | LP1Y-ACN-107102-02-7 | LP1Y-ACN-107102-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107102 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107102 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.1713 | 9.27 | sq ft | 6.27 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250652 | 26003H | 3087J | LP1Y-ACN-107103-01-2 | LP1Y-ACN-107103-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 20 | 20 | 0 | 495.4763 | 34 | sq ft | 10.54 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250651 | 26003H | 3086J | LP1Y-ACN-107103-01-1 | LP1Y-ACN-107103-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250655 | 26003H | 3090J | LP1Y-ACN-107103-02-3 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 31.6041 | 7.89 | sq ft | 1.24 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250654 | 26003H | 3089J | LP1Y-ACN-107103-02-2 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.2553 | 8.24 | sq ft | 3.03 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250656 | 26003H | 3091J | LP1Y-ACN-107103-02-4 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 24 | 23 | 1 | 502.6608 | 42.45 | sq ft | 6.56 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250653 | 26003H | 3088J | LP1Y-ACN-107103-02-1 | LP1Y-ACN-107103-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107103 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107103 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250665 | 26003H | 3100J | LP1Y-ACN-107105-02-3 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 59.06 | 16.96 | sq ft | 2.96 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250663 | 26003H | 3098J | LP1Y-ACN-107105-02-1 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 30 | 30 | 0 | 367.4284 | 44.18 | sq ft | 9.68 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250664 | 26003H | 3099J | LP1Y-ACN-107105-02-2 | LP1Y-ACN-107105-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 285.8483 | 19.33 | sq ft | 3.83 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250666 | 26003H | 3101J | LP1Y-ACN-107105-03-1 | LP1Y-ACN-107105-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 55.9793 | 12.93 | sq ft | 11.43 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250667 | 26003H | 3102J | LP1Y-ACN-107105-03-2 | LP1Y-ACN-107105-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 21 | 20 | 1 | 49.9716 | 20.66 | sq ft | 4.66 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250670 | 26003H | 3105J | LP1Y-ACN-107105-05-3 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 291.1511 | 21.61 | sq ft | 3.61 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250669 | 26003H | 3104J | LP1Y-ACN-107105-05-2 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 26.7824 | 7.24 | sq ft | 1.74 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250671 | 26003H | 3106J | LP1Y-ACN-107105-05-4 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 38.3967 | 9.92 | sq ft | 4.42 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250668 | 26003H | 3103J | LP1Y-ACN-107105-05-1 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250673 | 26003H | 3108J | LP1Y-ACN-107105-05-6 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 114.5019 | 26.44 | sq ft | 24.94 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250672 | 26003H | 3107J | LP1Y-ACN-107105-05-5 | LP1Y-ACN-107105-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 25.2458 | 5.83 | sq ft | 2.83 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250677 | 26003H | 3112J | LP1Y-ACN-107106-01-4 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 21.25 | 13 | sq ft | 3.5 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250674 | 26003H | 3109J | LP1Y-ACN-107106-01-1 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 17.25 | 15 | 2.25 | 80.42 | 29.75 | sq ft | 2.75 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250675 | 26003H | 3110J | LP1Y-ACN-107106-01-2 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 15.8438 | 7.92 | sq ft | 2.42 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250676 | 26003H | 3111J | LP1Y-ACN-107106-01-3 | LP1Y-ACN-107106-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107106 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107106 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 26.4588 | 11.28 | sq ft | 7.28 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250678 | 26003H | 3113J | LP1Y-ACN-107116-01-1 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 65.7894 | 15.19 | sq ft | 13.69 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250680 | 26003H | 3115J | LP1Y-ACN-107116-01-3 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 11 | 1 | 64.8977 | 20.02 | sq ft | 10.02 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250679 | 26003H | 3114J | LP1Y-ACN-107116-01-2 | LP1Y-ACN-107116-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107116 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107116 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 44.9155 | 11.55 | sq ft | 7.05 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250682 | 26003H | 3117J | LP1Y-ACN-107117-01-2 | LP1Y-ACN-107117-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 35.1788 | 18.28 | sq ft | 8.78 | ft | 2026-01-20 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250681 | 26003H | 3116J | LP1Y-ACN-107117-01-1 | LP1Y-ACN-107117-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 37.62 | 14.92 | sq ft | 13.42 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250683 | 26003H | 3118J | LP1Y-ACN-107117-04-1 | LP1Y-ACN-107117-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107117 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107117 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 79.9863 | 27.99 | sq ft | 10.99 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250690 | 26003H | 3125J | LP1Y-ACN-107202-02-7 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 19.25 | 7.96 | sq ft | 6.46 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250686 | 26003H | 3121J | LP1Y-ACN-107202-02-3 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 62.7313 | 18.35 | sq ft | 4.35 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250684 | 26003H | 3119J | LP1Y-ACN-107202-02-1 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250685 | 26003H | 3120J | LP1Y-ACN-107202-02-2 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.0288 | 7.23 | sq ft | 1.73 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250687 | 26003H | 3122J | LP1Y-ACN-107202-02-4 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.0212 | 5.6 | sq ft | 4.1 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250688 | 26003H | 3123J | LP1Y-ACN-107202-02-5 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 33.8013 | 15.47 | sq ft | 10.97 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250689 | 26003H | 3124J | LP1Y-ACN-107202-02-6 | LP1Y-ACN-107202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107202 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107202 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 4.62 | 2.42 | sq ft | 0.92 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250691 | 26003H | 3126J | LP1Y-ACN-107203-01-1 | LP1Y-ACN-107203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250692 | 26003H | 3127J | LP1Y-ACN-107203-01-2 | LP1Y-ACN-107203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 20 | 20 | 0 | 495.4763 | 34 | sq ft | 10.54 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250693 | 26003H | 3128J | LP1Y-ACN-107203-02-1 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250694 | 26003H | 3129J | LP1Y-ACN-107203-02-2 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 8 | 8 | 0 | 37.1978 | 10.14 | sq ft | 2.61 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250695 | 26003H | 3130J | LP1Y-ACN-107203-02-3 | LP1Y-ACN-107203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107203 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107203 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 36 | 35 | 1 | 528.1873 | 49.04 | sq ft | 6.71 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250702 | 26003H | 3137J | LP1Y-ACN-107204-02-1 | LP1Y-ACN-107204-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 50 | 50 | 0 | 727.9958 | 83.82 | sq ft | 19.82 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250703 | 26003H | 3138J | LP1Y-ACN-107204-03-1 | LP1Y-ACN-107204-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 17 | 1 | 78.9526 | 23.26 | sq ft | 11.76 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250704 | 26003H | 3139J | LP1Y-ACN-107204-05-1 | LP1Y-ACN-107204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 76.8718 | 18.93 | sq ft | 14.43 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250706 | 26003H | 3141J | LP1Y-ACN-107206-01-2 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 57.605 | 19.44 | sq ft | 1.44 | ft | 2026-01-20 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250707 | 26003H | 3142J | LP1Y-ACN-107206-01-3 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8 | 8 | 0 | 41.0513 | 18.72 | sq ft | 9.22 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250708 | 26003H | 3143J | LP1Y-ACN-107206-01-4 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 22.13 | 13.33 | sq ft | 3.83 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250705 | 26003H | 3140J | LP1Y-ACN-107206-01-1 | LP1Y-ACN-107206-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107206 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107206 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250709 | 26003H | 3144J | LP1Y-ACN-107216-01-1 | LP1Y-ACN-107216-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107216 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107216 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 20.25 | 18 | 2.25 | 55.1238 | 29.17 | sq ft | 15.17 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250710 | 26003H | 3145J | LP1Y-ACN-107216-04-1 | LP1Y-ACN-107216-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107216 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107216 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 81.4163 | 29.2 | sq ft | 10.7 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250711 | 26003H | 3146J | LP1Y-ACN-107217-01-1 | LP1Y-ACN-107217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107217 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107217 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 14 | 1 | 72.638 | 21.8 | sq ft | 10.3 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250712 | 26003H | 3147J | LP1Y-ACN-107217-01-2 | LP1Y-ACN-107217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107217 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107217 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 11 | 9 | 2 | 85.627 | 20.78 | sq ft | 17.78 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256304 | 26003H | 3148JA | LP1Y-ACN-107302-01-2 | LP1Y-ACN-107302-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 2" SS ACN (315) P (108) 107302 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107302 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 37.475 | 19.15 | sq ft | 9.65 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250713 | 26003H | 3148J | LP1Y-ACN-107302-01-1 | LP1Y-ACN-107302-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-06 | 2026-04-14 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107302 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107302 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 32.34 | 13.58 | sq ft | 10.58 | ft | 2026-01-20 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-18 | Jacob Perez | 2026-04-18 | Jacob Perez | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250714 | 26003H | 3149J | LP1Y-ACN-107302-03-1 | LP1Y-ACN-107302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 107302 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107302 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 77.4425 | 27.7 | sq ft | 9.2 | ft | 2026-01-20 |  |  |  |  | 2026-04-09 | Jacob Perez | 2026-04-09 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250716 | 26003H | 3151J | LP1Y-ACN-107303-01-2 | LP1Y-ACN-107303-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 20 | 20 | 0 | 495.4763 | 34 | sq ft | 10.54 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250715 | 26003H | 3150J | LP1Y-ACN-107303-01-1 | LP1Y-ACN-107303-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250718 | 26003H | 3153J | LP1Y-ACN-107303-02-2 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.2553 | 8.24 | sq ft | 3.03 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250717 | 26003H | 3152J | LP1Y-ACN-107303-02-1 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250719 | 26003H | 3154J | LP1Y-ACN-107303-02-3 | LP1Y-ACN-107303-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P (108) 107303 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107303 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 36 | 35 | 1 | 531.4598 | 49.74 | sq ft | 7.3 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250725 | 26003H | 3160J | LP1Y-ACN-107305-02-1 | LP1Y-ACN-107305-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-09 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 53 | 53 | 0 | 744.7569 | 87.78 | sq ft | 23.78 | ft | 2026-01-20 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256305 | 26003H | 3160JX | LP1Y-ACN-107305-02-2 | LP1Y-ACN-107305-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 8 | 8 | 0 | 52.0484 | 15.84 | sq ft | 7.34 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250726 | 26003H | 3161J | LP1Y-ACN-107305-03-1 | LP1Y-ACN-107305-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 17 | 1 | 81.0048 | 23.73 | sq ft | 12.23 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250727 | 26003H | 3162J | LP1Y-ACN-107305-04-1 | LP1Y-ACN-107305-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 63.0198 | 15.73 | sq ft | 12.73 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250728 | 26003H | 3163J | LP1Y-ACN-107306-01-1 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250729 | 26003H | 3164J | LP1Y-ACN-107306-01-2 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 57.0963 | 19.24 | sq ft | 1.24 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250730 | 26003H | 3165J | LP1Y-ACN-107306-01-3 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8 | 8 | 0 | 40.7763 | 18.62 | sq ft | 9.12 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250731 | 26003H | 3166J | LP1Y-ACN-107306-01-4 | LP1Y-ACN-107306-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107306 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107306 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 21.25 | 13 | sq ft | 3.5 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250732 | 26003H | 3167J | LP1Y-ACN-107308-01-1 | LP1Y-ACN-107308-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107308 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107308 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 29 | 26 | 3 | 156.3294 | 42.13 | sq ft | 27.63 | ft | 2026-01-20 | CD: 2026-04-16; CL: Jacob Perez; ED: 2026-04-17; EL: Jacob Perez; FD: 2026-04-17; FL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250741 | 26003H | 3176J | LP1Y-ACN-107405-03-1 | LP1Y-ACN-107405-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 53 | 53 | 0 | 717.9442 | 79.47 | sq ft | 11.67 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250742 | 26003H | 3177J | LP1Y-ACN-107405-04-1 | LP1Y-ACN-107405-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 70 | 68 | 2 | 1433.7345 | 88.74 | sq ft | 18.37 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250743 | 26003H | 3178J | LP1Y-ACN-107405-04-2 | LP1Y-ACN-107405-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 28 | 28 | 0 | 96.6075 | 24.1 | sq ft | 14.08 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250744 | 26003H | 3179J | LP1Y-ACN-107405-06-1 | LP1Y-ACN-107405-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS ACN (315) P 107405 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 28 | 26 | 2 | 241.3122 | 50.35 | sq ft | 16.53 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250745 | 26003H | 3180J | LP1Y-ACN-107407-01-1 | LP1Y-ACN-107407-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-09 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 14 | 1 | 75.2234 | 21.34 | sq ft | 13.84 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256306 | 26003H | 3180JX | LP1Y-ACN-107407-01-2 | LP1Y-ACN-107407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 62.9078 | 14.53 | sq ft | 11.53 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250749 | 26003H | 3184J | LP1Y-ACN-107407-03-4 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-09 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 88.1967 | 21.42 | sq ft | 14.42 | ft | 2026-01-20 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256307 | 26003H | 3184JX | LP1Y-ACN-107407-03-5 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 146.0623 | 33.73 | sq ft | 29.23 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250746 | 26003H | 3181J | LP1Y-ACN-107407-03-1 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.0066 | 10.66 | sq ft | 1.16 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250748 | 26003H | 3183J | LP1Y-ACN-107407-03-3 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 38.292 | 10.95 | sq ft | 1.45 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250747 | 26003H | 3182J | LP1Y-ACN-107407-03-2 | LP1Y-ACN-107407-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 107407 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107407 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 17 | 1 | 297.9691 | 27.16 | sq ft | 3.16 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250752 | 26003H | 3187J | LP1Y-ACN-107411-01-3 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-09 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 95.9772 | 23.22 | sq ft | 16.22 | ft | 2026-01-20 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250751 | 26003H | 3186J | LP1Y-ACN-107411-01-2 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 14 | 1 | 51.3294 | 17.94 | sq ft | 3.94 | ft | 2026-01-20 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250750 | 26003H | 3185J | LP1Y-ACN-107411-01-1 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 35.5101 | 9.26 | sq ft | 3.76 | ft | 2026-01-20 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256308 | 26003H | 3187JX | LP1Y-ACN-107411-01-4 | LP1Y-ACN-107411-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 3" SS ACN (315) P (108) 107411 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107411 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 63.6921 | 14.71 | sq ft | 13.21 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250753 | 26003H | 3188J | LP1Y-ACN-107416-01-1 | LP1Y-ACN-107416-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 107416 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107416 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 73.775 | 34.23 | sq ft | 21.73 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250754 | 26003H | 3189J | LP1Y-ACN-107416-04-1 | LP1Y-ACN-107416-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 107416 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107416 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 80.3438 | 28.13 | sq ft | 11.13 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250755 | 26003H | 3190J | LP1Y-ACN-107422-01-1 | LP1Y-ACN-107422-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 24.5988 | 9.98 | sq ft | 8.48 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250756 | 26003H | 3191J | LP1Y-ACN-107422-01-2 | LP1Y-ACN-107422-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 34.98 | 13.92 | sq ft | 12.42 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256309 | 26003H | 3192JA | LP1Y-ACN-107422-03-2 | LP1Y-ACN-107422-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 45.7188 | 18.65 | sq ft | 15.65 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256310 | 26003H | 3192JB | LP1Y-ACN-107422-03-3 | LP1Y-ACN-107422-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 0 | 2 | 66.0413 | 25.02 | sq ft | 25.02 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250757 | 26003H | 3192J | LP1Y-ACN-107422-03-1 | LP1Y-ACN-107422-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-06 | 2026-04-14 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 107422 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107422 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 14.75 | 14 | 0.75 | 44.1938 | 21.09 | sq ft | 11.59 | ft | 2026-01-20 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250758 | 26003H | 3193J | LP1Y-ACN-111002-05-1 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 36.2849 | 10.49 | sq ft | 0.99 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250759 | 26003H | 3194J | LP1Y-ACN-111002-05-2 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 18 | 0 | 299.2298 | 23.48 | sq ft | 3.98 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250760 | 26003H | 3195J | LP1Y-ACN-111002-05-3 | LP1Y-ACN-111002-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 27 | 27 | 0 | 158.9526 | 37.76 | sq ft | 27.76 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250761 | 26003H | 3196J | LP1Y-ACN-111002-06-1 | LP1Y-ACN-111002-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111002 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111002 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 321.9279 | 27.79 | sq ft | 14.79 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250762 | 26003H | 3197J | LP1Y-ACN-111003-03-1 | LP1Y-ACN-111003-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 319.6007 | 26.07 | sq ft | 14.57 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250763 | 26003H | 3198J | LP1Y-ACN-111003-06-1 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 31.3975 | 7.25 | sq ft | 5.75 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250766 | 26003H | 3201J | LP1Y-ACN-111003-06-4 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 15 | 15 | 0 | 77.02 | 27.08 | sq ft | 2.58 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250764 | 26003H | 3199J | LP1Y-ACN-111003-06-2 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 52.3133 | 12.08 | sq ft | 7.58 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250765 | 26003H | 3200J | LP1Y-ACN-111003-06-3 | LP1Y-ACN-111003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 11 | 1 | 296.8284 | 25.84 | sq ft | 7.34 | ft | 2026-01-20 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250767 | 26003H | 3202J | LP1Y-ACN-111003-07-1 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250770 | 26003H | 3205J | LP1Y-ACN-111003-07-4 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.1325 | 7.16 | sq ft | 5.66 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250771 | 26003H | 3206J | LP1Y-ACN-111003-07-5 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10 | 10 | 0 | 61.1488 | 20.73 | sq ft | 2.23 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250768 | 26003H | 3203J | LP1Y-ACN-111003-07-2 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 12.8738 | 6.8 | sq ft | 1.3 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250769 | 26003H | 3204J | LP1Y-ACN-111003-07-3 | LP1Y-ACN-111003-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACN (315) P 111003 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111003 |  | TFS00E009YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.9088 | 16.9 | sq ft | 2.9 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250772 | 26003H | 3207J | LP1Y-ACN-111203-01-1 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250773 | 26003H | 3208J | LP1Y-ACN-111203-01-2 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 12 | 12 | 0 | 46.7834 | 15.86 | sq ft | 5.43 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250774 | 26003H | 3209J | LP1Y-ACN-111203-01-3 | LP1Y-ACN-111203-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 4 | 4 | 0 | 483.0541 | 25.49 | sq ft | 11.24 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250775 | 26003H | 3210J | LP1Y-ACN-111203-02-1 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250776 | 26003H | 3211J | LP1Y-ACN-111203-02-2 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 4 | 4 | 0 | 42.2809 | 9.31 | sq ft | 3.93 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250777 | 26003H | 3212J | LP1Y-ACN-111203-02-3 | LP1Y-ACN-111203-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 111203 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111203 |  | TFS00E010YSPP |  | 315-ACN | NONE | 4" | 316 SS | 40 | 39 | 1 | 531.6352 | 49.77 | sq ft | 7.33 | ft | 2026-01-20 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250778 | 26003H | 3213J | LP1Y-ACN-111205-03-1 | LP1Y-ACN-111205-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 48 | 46 | 2 | 1092.2445 | 75.95 | sq ft | 8.95 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250779 | 26003H | 3214J | LP1Y-ACN-111205-03-2 | LP1Y-ACN-111205-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 18 | 0 | 323.0241 | 28.91 | sq ft | 12.91 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250780 | 26003H | 3215J | LP1Y-ACN-111205-04-1 | LP1Y-ACN-111205-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 24 | 23 | 1 | 55.6442 | 21.67 | sq ft | 5.17 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250781 | 26003H | 3216J | LP1Y-ACN-111205-05-1 | LP1Y-ACN-111205-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 297.3323 | 24.98 | sq ft | 4.98 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250782 | 26003H | 3217J | LP1Y-ACN-111205-06-1 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.3448 | 10.73 | sq ft | 1.23 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250783 | 26003H | 3218J | LP1Y-ACN-111205-06-2 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.9142 | 13.92 | sq ft | 1.42 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250784 | 26003H | 3219J | LP1Y-ACN-111205-06-3 | LP1Y-ACN-111205-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 11 | 11 | 0 | 47.0675 | 15.75 | sq ft | 4.75 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250786 | 26003H | 3221J | LP1Y-ACN-111205-07-2 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 24.5191 | 5.66 | sq ft | 4.16 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250785 | 26003H | 3220J | LP1Y-ACN-111205-07-1 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250787 | 26003H | 3222J | LP1Y-ACN-111205-07-3 | LP1Y-ACN-111205-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 111205 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111205 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 14 | 13 | 1 | 88.339 | 31.79 | sq ft | 11.79 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250788 | 26003H | 3223J | LP1Y-ACN-111207-01-1 | LP1Y-ACN-111207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 79.1613 | 27.68 | sq ft | 10.68 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250789 | 26003H | 3224J | LP1Y-ACN-111207-01-2 | LP1Y-ACN-111207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.11 | 18.04 | sq ft | 15.04 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250790 | 26003H | 3225J | LP1Y-ACN-111207-03-1 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.6863 | 7.95 | sq ft | 3.95 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250791 | 26003H | 3226J | LP1Y-ACN-111207-03-2 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10 | 10 | 0 | 52.2775 | 21.8 | sq ft | 17.3 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250792 | 26003H | 3227J | LP1Y-ACN-111207-03-3 | LP1Y-ACN-111207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.52 | 23.5 | sq ft | 20.5 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-22; EL: Jacob Perez; FD: 2026-04-22; FL: Jacob Perez | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250795 | 26003H | 3230J | LP1Y-ACN-111207-04-3 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10 | 10 | 0 | 23.3963 | 12.7 | sq ft | 1.7 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250793 | 26003H | 3228J | LP1Y-ACN-111207-04-1 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250794 | 26003H | 3229J | LP1Y-ACN-111207-04-2 | LP1Y-ACN-111207-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111207 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111207 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 69.1488 | 26.4 | sq ft | 2.9 | ft | 2026-01-20 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250797 | 26003H | 3232J | LP1Y-ACN-111211-01-2 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10.75 | 10 | 0.75 | 34.8738 | 19.8 | sq ft | 6.3 | ft | 2026-01-20 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250796 | 26003H | 3231J | LP1Y-ACN-111211-01-1 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 57.2725 | 16.28 | sq ft | 2.28 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250798 | 26003H | 3233J | LP1Y-ACN-111211-01-3 | LP1Y-ACN-111211-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.31 | 18.21 | sq ft | 16.71 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250799 | 26003H | 3234J | LP1Y-ACN-111211-03-1 | LP1Y-ACN-111211-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111211 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111211 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 19 | 16 | 3 | 80.8188 | 34.32 | sq ft | 9.32 | ft | 2026-01-20 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250800 | 26003H | 3235J | LP1Y-ACN-111212-01-1 | LP1Y-ACN-111212-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10 | 10 | 0 | 36.7813 | 15.93 | sq ft | 11.43 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250802 | 26003H | 3237J | LP1Y-ACN-111212-03-2 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10 | 10 | 0 | 56.905 | 24.9 | sq ft | 20.4 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250801 | 26003H | 3236J | LP1Y-ACN-111212-03-1 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.405 | 8.56 | sq ft | 3.56 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250803 | 26003H | 3238J | LP1Y-ACN-111212-03-3 | LP1Y-ACN-111212-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P 111212 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111212 |  | TFS00E010YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 90.2 | 35.5 | sq ft | 32.5 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250805 | 26003H | 3240J | LP1Y-ACN-177301-01-2 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250806 | 26003H | 3241J | LP1Y-ACN-177301-01-3 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 19 | 17 | 2 | 316.1808 | 40.48 | sq ft | 5.98 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250804 | 26003H | 3239J | LP1Y-ACN-177301-01-1 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250807 | 26003H | 3242J | LP1Y-ACN-177301-01-4 | LP1Y-ACN-177301-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 131.9121 | 30.46 | sq ft | 28.96 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250809 | 26003H | 3244J | LP1Y-ACN-177301-02-2 | LP1Y-ACN-177301-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 128.0776 | 30.76 | sq ft | 29.26 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250808 | 26003H | 3243J | LP1Y-ACN-177301-02-1 | LP1Y-ACN-177301-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 28 | 27 | 1 | 324.2177 | 37.52 | sq ft | 7.02 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250810 | 26003H | 3245J | LP1Y-ACN-177301-03-1 | LP1Y-ACN-177301-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177301 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177301 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 3 | 6 | 32.4381 | 27.13 | sq ft | 1.63 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250812 | 26003H | 3247J | LP1Y-ACN-177302-02-2 | LP1Y-ACN-177302-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 172.5835 | 39.85 | sq ft | 35.35 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250811 | 26003H | 3246J | LP1Y-ACN-177302-02-1 | LP1Y-ACN-177302-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 12 | 12 | 0 | 310.3173 | 24.98 | sq ft | 9.48 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250813 | 26003H | 3248J | LP1Y-ACN-177302-03-1 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250814 | 26003H | 3249J | LP1Y-ACN-177302-03-2 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 6 | 6 | 0 | 29.3984 | 7.84 | sq ft | 2.34 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250816 | 26003H | 3251J | LP1Y-ACN-177302-03-4 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 8 | 1 | 41.1308 | 15.58 | sq ft | 3.08 | ft | 2026-01-20 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250815 | 26003H | 3250J | LP1Y-ACN-177302-03-3 | LP1Y-ACN-177302-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E010YSPP |  | 315-ACN | NONE | 3" | 316 SS | 15 | 15 | 0 | 296.3206 | 22.81 | sq ft | 3.31 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250817 | 26003H | 3252J | LP1Y-ACN-177302-04-1 | LP1Y-ACN-177302-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-14 | 2026-04-15 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 21 | 20 | 1 | 87.2653 | 28.53 | sq ft | 11.03 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250818 | 26003H | 3253J | LP1Y-ACN-177302-04-2 | LP1Y-ACN-177302-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 3" | 316 SS | 18 | 15 | 3 | 88.928 | 25.54 | sq ft | 4.04 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250823 | 26003H | 3258J | LP1Y-ACN-177302-05-5 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.24 | 13.58 | sq ft | 1.58 | ft | 2026-01-20 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250820 | 26003H | 3255J | LP1Y-ACN-177302-05-2 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 13 | 13 | 0 | 38.885 | 26.52 | sq ft | 2.02 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250819 | 26003H | 3254J | LP1Y-ACN-177302-05-1 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250821 | 26003H | 3256J | LP1Y-ACN-177302-05-3 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250822 | 26003H | 3257J | LP1Y-ACN-177302-05-4 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250824 | 26003H | 3259J | LP1Y-ACN-177302-05-6 | LP1Y-ACN-177302-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS ACN (315) P 177302 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177302 |  | TFS00E016YSPP |  | 315-ACN | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.9238 | 9.3 | sq ft | 1.3 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250826 | 26003H | 3261J | LP1Y-ACN-850013-04-2 | LP1Y-ACN-850013-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 48.785 | 18.48 | sq ft | 18.48 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258537 | 26003H | 3261JA | LP1Y-ACN-850013-04-3 | LP1Y-ACN-850013-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-30; CL: Jacob Perez; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250825 | 26003H | 3260J | LP1Y-ACN-850013-04-1 | LP1Y-ACN-850013-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E015YSPP |  | 315-ACN | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 70.635 | 33.44 | sq ft | 23.44 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250831 | 26003H | 3266J | LP1Y-ACN-850013-06-1 | LP1Y-ACN-850013-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.9588 | 10.73 | sq ft | 1.23 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250832 | 26003H | 3267J | LP1Y-ACN-850013-06-2 | LP1Y-ACN-850013-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 28 | 28 | 0 | 127.0025 | 47.36 | sq ft | 24.36 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250833 | 26003H | 3268J | LP1Y-ACNDMSO-010027-04-1 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 59.75 | 57 | 2.75 | 890.359 | 79.4 | sq ft | 16.9 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250835 | 26003H | 3270J | LP1Y-ACNDMSO-010027-04-3 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 12 | 12 | 0 | 65.7769 | 15.19 | sq ft | 10.69 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250834 | 26003H | 3269J | LP1Y-ACNDMSO-010027-04-2 | LP1Y-ACNDMSO-010027-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 010027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 28.5559 | 6.59 | sq ft | 5.09 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250836 | 26003H | 3271J | LP1Y-ACNDMSO-110001-01-1 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 16 | 14 | 2 | 29.0125 | 13.66 | sq ft | 7.66 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250837 | 26003H | 3272J | LP1Y-ACNDMSO-110001-01-2 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 12.75 | 12 | 0.75 | 46.41 | 24.17 | sq ft | 10.67 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250838 | 26003H | 3273J | LP1Y-ACNDMSO-110001-01-3 | LP1Y-ACNDMSO-110001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 4.83 | sq ft | 0.83 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250839 | 26003H | 3274J | LP1Y-ACNDMSO-110001-03-1 | LP1Y-ACNDMSO-110001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110001 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110001 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 9.75 | 6 | 3.75 | 63.1863 | 22.54 | sq ft | 5.04 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250840 | 26003H | 3275J | LP1Y-ACNDMSO-110005-01-1 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 33.605 | 13.4 | sq ft | 11.9 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250841 | 26003H | 3276J | LP1Y-ACNDMSO-110005-01-2 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 23.585 | 14.85 | sq ft | 2.85 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250842 | 26003H | 3277J | LP1Y-ACNDMSO-110005-01-3 | LP1Y-ACNDMSO-110005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 4.83 | sq ft | 0.83 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250843 | 26003H | 3278J | LP1Y-ACNDMSO-110005-03-1 | LP1Y-ACNDMSO-110005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110005 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110005 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 9.75 | 6 | 3.75 | 63.1863 | 22.54 | sq ft | 5.04 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250847 | 26003H | 3282J | LP1Y-ACNDMSO-110027-01-4 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 28 | 27 | 1 | 314.2717 | 33.17 | sq ft | 3.17 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250846 | 26003H | 3281J | LP1Y-ACNDMSO-110027-01-3 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 46.5348 | 11.08 | sq ft | 3.9 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250845 | 26003H | 3280J | LP1Y-ACNDMSO-110027-01-2 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 4 | 4 | 0 | 10.2145 | 3.04 | sq ft | 1.04 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250844 | 26003H | 3279J | LP1Y-ACNDMSO-110027-01-1 | LP1Y-ACNDMSO-110027-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110027 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110027 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250850 | 26003H | 3285J | LP1Y-ACNDMSO-110603-01-3 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 12 | 11 | 1 | 490.0914 | 37.52 | sq ft | 9.29 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250848 | 26003H | 3283J | LP1Y-ACNDMSO-110603-01-1 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250849 | 26003H | 3284J | LP1Y-ACNDMSO-110603-01-2 | LP1Y-ACNDMSO-110603-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 31.093 | 12.51 | sq ft | 2.63 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250853 | 26003H | 3288J | LP1Y-ACNDMSO-110603-02-3 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | DD: 2026-05-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250854 | 26003H | 3289J | LP1Y-ACNDMSO-110603-02-4 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | DD: 2026-05-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250851 | 26003H | 3286J | LP1Y-ACNDMSO-110603-02-1 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | DD: 2026-05-04; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250852 | 26003H | 3287J | LP1Y-ACNDMSO-110603-02-2 | LP1Y-ACNDMSO-110603-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110603 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110603 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250855 | 26003H | 3290J | LP1Y-ACNDMSO-110604-03-1 | LP1Y-ACNDMSO-110604-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 33.0213 | 7.63 | sq ft | 6.13 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250856 | 26003H | 3291J | LP1Y-ACNDMSO-110604-03-2 | LP1Y-ACNDMSO-110604-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 54.8066 | 12.66 | sq ft | 11.16 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250858 | 26003H | 3293J | LP1Y-ACNDMSO-110604-04-2 | LP1Y-ACNDMSO-110604-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 9 | 9 | 0 | 337.2139 | 30.14 | sq ft | 18.64 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250857 | 26003H | 3292J | LP1Y-ACNDMSO-110604-04-1 | LP1Y-ACNDMSO-110604-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 42 | 40 | 2 | 585.7641 | 53.41 | sq ft | 8.91 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250859 | 26003H | 3294J | LP1Y-ACNDMSO-110604-05-1 | LP1Y-ACNDMSO-110604-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 37 | 37 | 0 | 589.2724 | 58.85 | sq ft | 10.15 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250861 | 26003H | 3296J | LP1Y-ACNDMSO-110604-06-2 | LP1Y-ACNDMSO-110604-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 30 | 30 | 0 | 89.0644 | 25.92 | sq ft | 8.44 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250860 | 26003H | 3295J | LP1Y-ACNDMSO-110604-06-1 | LP1Y-ACNDMSO-110604-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 11 | 10 | 1 | 55.4916 | 16.44 | sq ft | 2.32 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250865 | 26003H | 3300J | LP1Y-ACNDMSO-110604-07-4 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.25 | 13 | sq ft | 1.67 | ft | 2026-01-20 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250862 | 26003H | 3297J | LP1Y-ACNDMSO-110604-07-1 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 1.5 | 1.5 | 0 | 5.61 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250864 | 26003H | 3299J | LP1Y-ACNDMSO-110604-07-3 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 16 | 15 | 1 | 64.237 | 25.4 | sq ft | 3.85 | ft | 2026-01-20 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250863 | 26003H | 3298J | LP1Y-ACNDMSO-110604-07-2 | LP1Y-ACNDMSO-110604-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110604 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110604 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 4 | 4 | 0 | 10.01 | 3 | sq ft | 1 | ft | 2026-01-20 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250866 | 26003H | 3301J | LP1Y-ACNDMSO-110605-01-1 | LP1Y-ACNDMSO-110605-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 39.3688 | 19.28 | sq ft | 12.28 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250868 | 26003H | 3303J | LP1Y-ACNDMSO-110605-03-2 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 10.77 | 6 | sq ft | 0.5 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250869 | 26003H | 3304J | LP1Y-ACNDMSO-110605-03-3 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 64.5425 | 25.11 | sq ft | 23.61 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250867 | 26003H | 3302J | LP1Y-ACNDMSO-110605-03-1 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 26.5413 | 11.31 | sq ft | 7.31 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256781 | 26003H | 3304J-L1 | LP1Y-ACNDMSO-110605-03-3-L1 | LP1Y-ACNDMSO-110605-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 |  |  | LP1Y 2" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | [12 empty] | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250872 | 26003H | 3307J | LP1Y-ACNDMSO-110605-04-3 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.6288 | 8.15 | sq ft | 2.15 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250870 | 26003H | 3305J | LP1Y-ACNDMSO-110605-04-1 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250871 | 26003H | 3306J | LP1Y-ACNDMSO-110605-04-2 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 24.5948 | 6.73 | sq ft | 1.23 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250873 | 26003H | 3308J | LP1Y-ACNDMSO-110605-04-4 | LP1Y-ACNDMSO-110605-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110605 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110605 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 61.2763 | 21.49 | sq ft | 1.99 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250874 | 26003H | 3309J | LP1Y-ACNDMSO-110610-01-1 | LP1Y-ACNDMSO-110610-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 12 | 12 | 0 | 86.5563 | 34.79 | sq ft | 30.29 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250876 | 26003H | 3311J | LP1Y-ACNDMSO-110610-02-2 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 10.7113 | 4.72 | sq ft | 3.22 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250875 | 26003H | 3310J | LP1Y-ACNDMSO-110610-02-1 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0.75 | 0 | 0.75 | 7 | 5 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250877 | 26003H | 3312J | LP1Y-ACNDMSO-110610-02-3 | LP1Y-ACNDMSO-110610-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110610 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110610 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 14 | 14 | 0 | 57.6263 | 24.49 | sq ft | 18.49 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250879 | 26003H | 3314J | LP1Y-ACNDMSO-110803-01-2 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 72.0364 | 16.64 | sq ft | 15.14 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250880 | 26003H | 3315J | LP1Y-ACNDMSO-110803-01-3 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 22 | 22 | 0 | 297.3009 | 24.84 | sq ft | 4.84 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250878 | 26003H | 3313J | LP1Y-ACNDMSO-110803-01-1 | LP1Y-ACNDMSO-110803-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 4" | 316 SS | 4 | 4 | 0 | 22.53 | 7 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250881 | 26003H | 3316J | LP1Y-ACNDMSO-110803-02-1 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250882 | 26003H | 3317J | LP1Y-ACNDMSO-110803-02-2 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.6975 | 8.18 | sq ft | 2.18 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250883 | 26003H | 3318J | LP1Y-ACNDMSO-110803-02-3 | LP1Y-ACNDMSO-110803-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110803 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110803 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 28 | 27 | 1 | 339.8793 | 45.08 | sq ft | 8.08 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250884 | 26003H | 3319J | LP1Y-ACNDMSO-110805-01-1 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 5.36 | 8 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250885 | 26003H | 3320J | LP1Y-ACNDMSO-110805-01-2 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 9.9279 | 2.29 | sq ft | 0.79 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250886 | 26003H | 3321J | LP1Y-ACNDMSO-110805-01-3 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 10 | 9 | 1 | 48.77 | 22.5 | sq ft | 2 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250887 | 26003H | 3322J | LP1Y-ACNDMSO-110805-01-4 | LP1Y-ACNDMSO-110805-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 9 | 9 | 0 | 39.9834 | 11.34 | sq ft | 1.84 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251147 | 26003H | 3323J | LP1Y-ACNDMSO-110805-02-1 | LP1Y-ACNDMSO-110805-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 9 | 8 | 1 | 40.6121 | 15.46 | sq ft | 2.96 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251148 | 26003H | 3324J | LP1Y-ACNDMSO-110805-02-2 | LP1Y-ACNDMSO-110805-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 21 | 21 | 0 | 348.6239 | 39.38 | sq ft | 5.38 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251149 | 26003H | 3325J | LP1Y-ACNDMSO-110805-03-1 | LP1Y-ACNDMSO-110805-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 3" | 316 SS | 16 | 16 | 0 | 73.0425 | 27.07 | sq ft | 5.07 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251150 | 26003H | 3326J | LP1Y-ACNDMSO-110805-03-2 | LP1Y-ACNDMSO-110805-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 88.9263 | 34.29 | sq ft | 11.79 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251151 | 26003H | 3327J | LP1Y-ACNDMSO-110805-05-1 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 8 | 8 | 0 | 47.9763 | 22.41 | sq ft | 13.91 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251153 | 26003H | 3329J | LP1Y-ACNDMSO-110805-05-3 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.585 | 5.81 | sq ft | 4.31 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251152 | 26003H | 3328J | LP1Y-ACNDMSO-110805-05-2 | LP1Y-ACNDMSO-110805-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 58.2075 | 23.3 | sq ft | 19.3 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251154 | 26003H | 3330J | LP1Y-ACNDMSO-110805-06-1 | LP1Y-ACNDMSO-110805-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 111.8488 | 33.98 | sq ft | 4.48 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251155 | 26003H | 3331J | LP1Y-ACNDMSO-110805-07-1 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251156 | 26003H | 3332J | LP1Y-ACNDMSO-110805-07-2 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.1625 | 6.91 | sq ft | 1.41 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251157 | 26003H | 3333J | LP1Y-ACNDMSO-110805-07-3 | LP1Y-ACNDMSO-110805-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110805 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110805 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 62.03 | 18.08 | sq ft | 4.08 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251158 | 26003H | 3334J | LP1Y-ACNDMSO-110810-01-1 | LP1Y-ACNDMSO-110810-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 55.2225 | 25.28 | sq ft | 18.28 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251159 | 26003H | 3335J | LP1Y-ACNDMSO-110810-03-1 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.65 | 11.38 | sq ft | 1.88 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251161 | 26003H | 3337J | LP1Y-ACNDMSO-110810-03-3 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.9825 | 14.78 | sq ft | 8.78 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251162 | 26003H | 3338J | LP1Y-ACNDMSO-110810-03-4 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 52.58 | 21.25 | sq ft | 18.25 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251160 | 26003H | 3336J | LP1Y-ACNDMSO-110810-03-2 | LP1Y-ACNDMSO-110810-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.7925 | 7.61 | sq ft | 3.61 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251163 | 26003H | 3339J | LP1Y-ACNDMSO-110810-04-1 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251164 | 26003H | 3340J | LP1Y-ACNDMSO-110810-04-2 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.1625 | 6.91 | sq ft | 1.41 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251165 | 26003H | 3341J | LP1Y-ACNDMSO-110810-04-3 | LP1Y-ACNDMSO-110810-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110810 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110810 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 67.0688 | 24.28 | sq ft | 2.28 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251167 | 26003H | 3343J | LP1Y-ACNDMSO-110813-01-2 | LP1Y-ACNDMSO-110813-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 8 | 8 | 0 | 74.7863 | 29.66 | sq ft | 26.66 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251166 | 26003H | 3342J | LP1Y-ACNDMSO-110813-01-1 | LP1Y-ACNDMSO-110813-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 10 | 10 | 0 | 30.5113 | 13.56 | sq ft | 9.06 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251169 | 26003H | 3345J | LP1Y-ACNDMSO-110813-02-2 | LP1Y-ACNDMSO-110813-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.81 | 16.79 | sq ft | 13.79 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251168 | 26003H | 3344J | LP1Y-ACNDMSO-110813-02-1 | LP1Y-ACNDMSO-110813-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS ACNDMSO (315) P (108) 110813 | ACNDMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110813 |  | TFS00E009YSPP |  | 315-ACNDMSO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.8312 | 8.72 | sq ft | 3.72 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251178 | 26003H | 3354J | LP1Y-AF-162003-04-3 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 1.5 | 0 | 1.5 | 10.6315 | 17.49 | sq ft | 14.49 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144458 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251176 | 26003H | 3352J | LP1Y-AF-162003-04-1 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 3 | 0 | 3 | 8.0221 | 14.46 | sq ft | 1.96 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145686
C34-S251177 | 26003H | 3353J | LP1Y-AF-162003-04-2 | LP1Y-AF-162003-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 3.5 | 0 | 3.5 | 14.5046 | 24.93 | sq ft | 13.93 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Omar Puente | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | [6 empty] | 86% |  |  |  | 0%
C34-S251181 | 26003H | 3357J | LP1Y-AF-162003-05-3 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-24 | 2026-04-24 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 1 | 0 | 1 | 27.0521 | 40.46 | sq ft | 39.96 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | 2026-04-21 | 2026-04-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251179 | 26003H | 3355J | LP1Y-AF-162003-05-1 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-23 | 2026-04-23 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 1.5 | 0 | 1.5 | 16.8026 | 25.97 | sq ft | 23.97 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251180 | 26003H | 3356J | LP1Y-AF-162003-05-2 | LP1Y-AF-162003-05 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-24 | 2026-04-24 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 1 | 0 | 1 | 27.0521 | 40.46 | sq ft | 39.96 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | 2026-04-21 | 2026-04-21 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251182 | 26003H | 3358J | LP1Y-AF-162003-06-1 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 1 | 0 | 1 | 8.0115 | 12.77 | sq ft | 11.27 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Henrique Barahona | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 |  |  |  | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% |  |  |  | 0%
C34-S251184 | 26003H | 3360J | LP1Y-AF-162003-06-3 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-02 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 2 | 0 | 2 | 15.168 | 24.27 | sq ft | 21.27 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-02 | 2026-04-02 | Passed | No | 2026-04-02 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Omar Puente | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 144407 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251183 | 26003H | 3359J | LP1Y-AF-162003-06-2 | LP1Y-AF-162003-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 0.5" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 2 | 0 | 2 | 7.8078 | 14.09 | sq ft | 9.59 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-03-31 | Passed | No | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | N/A | N/A | Edgar Castaneda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144457 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251188 | 26003H | 3364J | LP1Y-AI(100)-019025-02-1 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-14 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-15 | 2026-04-15 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S251189 | 26003H | 3365J | LP1Y-AI(100)-019025-02-2 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-15 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 5 | 5 | 0 | 84.9273 | 34.79 | sq ft | 31.79 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% |  |  |  | 33%
C34-S251190 | 26003H | 3366J | LP1Y-AI(100)-019025-02-3 | LP1Y-AI(100)-019025-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-15 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AI(100) (315) 019025 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019025 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 18.25 | 16 | 2.25 | 126.9042 | 59.67 | sq ft | 43.17 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-23 |  | 2026-04-23 | 2026-04-27 | 2026-04-21 | 2026-04-27 | 100% |  |  |  | 33%
C34-S251191 | 26003H | 3367J | LP1Y-AI(100)-019062-02-1 | LP1Y-AI(100)-019062-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS AI(100) (315) 019062 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019062 |  | TFS00E015YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 24.1863 | 10.49 | sq ft | 7.49 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251192 | 26003H | 3368J | LP1Y-AI(100)-019062-02-2 | LP1Y-AI(100)-019062-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS AI(100) (315) 019062 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019062 |  | TFS00E015YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 15 | 15 | 0 | 64.4663 | 31.49 | sq ft | 14.99 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251193 | 26003H | 3369J | LP1Y-AI(100)-019064-02-1 | LP1Y-AI(100)-019064-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS AI(100) (315) 019064 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019064 |  | TFS00E016YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 17 | 17 | 0 | 60.0525 | 30.49 | sq ft | 12.49 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251194 | 26003H | 3370J | LP1Y-AI(100)-190023-01-1 | LP1Y-AI(100)-190023-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AI(100) (315) 190023 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-190023 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144863 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251195 | 26003H | 3371J | LP1Y-AI(100)-190023-01-2 | LP1Y-AI(100)-190023-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AI(100) (315) 190023 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-190023 |  | TFS00E003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 32.375 | 15.6 | sq ft | 11.1 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 60% |  |  |  | 20%
C34-S251196 | 26003H | 3372J | LP1Y-AI(100)-199005-01-1 | LP1Y-AI(100)-199005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251197 | 26003H | 3373J | LP1Y-AI(100)-199005-01-2 | LP1Y-AI(100)-199005-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251199 | 26003H | 3375J | LP1Y-AI(100)-199005-02-2 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251198 | 26003H | 3374J | LP1Y-AI(100)-199005-02-1 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251200 | 26003H | 3376J | LP1Y-AI(100)-199005-02-3 | LP1Y-AI(100)-199005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251203 | 26003H | 3379J | LP1Y-AI(100)-199005-03-3 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251201 | 26003H | 3377J | LP1Y-AI(100)-199005-03-1 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251202 | 26003H | 3378J | LP1Y-AI(100)-199005-03-2 | LP1Y-AI(100)-199005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199005 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199005 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251204 | 26003H | 3380J | LP1Y-AI(100)-199006-02-1 | LP1Y-AI(100)-199006-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251205 | 26003H | 3381J | LP1Y-AI(100)-199006-02-2 | LP1Y-AI(100)-199006-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251207 | 26003H | 3383J | LP1Y-AI(100)-199006-05-2 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251206 | 26003H | 3382J | LP1Y-AI(100)-199006-05-1 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251208 | 26003H | 3384J | LP1Y-AI(100)-199006-05-3 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251209 | 26003H | 3385J | LP1Y-AI(100)-199006-05-4 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251210 | 26003H | 3386J | LP1Y-AI(100)-199006-05-5 | LP1Y-AI(100)-199006-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P027 | 2026-08-03 |  | LP1Y 3" SS AI(100) (315) 199006 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199006 |  | TFS00E014YSPP |  | 315-AI(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-19; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251211 | 26003H | 3387J | LP1Y-APL(100)-019005-02-1 | LP1Y-APL(100)-019005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 6 | 6 | 0 | 41.4332 | 9.57 | sq ft | 8.07 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-19; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251212 | 26003H | 3388J | LP1Y-APL(100)-019005-02-2 | LP1Y-APL(100)-019005-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 18 | 18 | 0 | 581.8595 | 40.95 | sq ft | 16.45 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-19; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251214 | 26003H | 3390J | LP1Y-APL(100)-019005-03-2 | LP1Y-APL(100)-019005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251213 | 26003H | 3389J | LP1Y-APL(100)-019005-03-1 | LP1Y-APL(100)-019005-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 019005 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019005 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 27 | 24 | 3 | 324.9461 | 28.36 | sq ft | 8.36 | ft | 2026-01-20 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-19 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251215 | 26003H | 3391J | LP1Y-APL(100)-019048-01-1 | LP1Y-APL(100)-019048-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.01 | 9.29 | sq ft | 6.29 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251216 | 26003H | 3392J | LP1Y-APL(100)-019048-01-2 | LP1Y-APL(100)-019048-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 11 | 2.75 | 8.25 | 46.4426 | 40.75 | sq ft | 7.75 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251217 | 26003H | 3393J | LP1Y-APL(100)-019048-02-1 | LP1Y-APL(100)-019048-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.845 | 14.35 | sq ft | 9.85 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251218 | 26003H | 3394J | LP1Y-APL(100)-019048-04-1 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 7.0253 | 8.8 | sq ft | 4.3 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251219 | 26003H | 3395J | LP1Y-APL(100)-019048-04-2 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.3042 | 6.46 | sq ft | 1.46 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251220 | 26003H | 3396J | LP1Y-APL(100)-019048-04-3 | LP1Y-APL(100)-019048-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 019048 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019048 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.7336 | 4.21 | sq ft | 1.71 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251221 | 26003H | 3397J | LP1Y-APL(100)-019049-01-1 | LP1Y-APL(100)-019049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.5938 | 13.88 | sq ft | 9.38 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251222 | 26003H | 3398J | LP1Y-APL(100)-019049-01-2 | LP1Y-APL(100)-019049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 31.735 | 13.35 | sq ft | 10.35 | ft | 2026-01-20 |  |  |  |  | 2026-04-09 | Jacob Perez | 2026-04-09 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251223 | 26003H | 3399J | LP1Y-APL(100)-019049-02-1 | LP1Y-APL(100)-019049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 0 | 9 | 38.2889 | 37.66 | sq ft | 4.66 | ft | 2026-01-20 |  |  |  |  | 2026-04-09 | Jacob Perez | 2026-04-09 | George Allahverdian | 2026-04-10 | Jacob Perez | 2026-04-10 | Jacob Perez | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251224 | 26003H | 3400J | LP1Y-APL(100)-019049-04-1 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 6.9805 | 8.74 | sq ft | 4.24 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251225 | 26003H | 3401J | LP1Y-APL(100)-019049-04-2 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.3445 | 6.51 | sq ft | 1.51 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251226 | 26003H | 3402J | LP1Y-APL(100)-019049-04-3 | LP1Y-APL(100)-019049-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 0.75" SS APL(100) (315) 019049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019049 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.7381 | 4.22 | sq ft | 1.72 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251231 | 26003H | 3407J | LP1Y-APL(100)-019077-02-5 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.145 | 15.98 | sq ft | 12.48 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 67% |  |  |  | 0%
C34-S251229 | 26003H | 3405J | LP1Y-APL(100)-019077-02-3 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 28 | 22 | 6 | 102.2338 | 51.17 | sq ft | 29.67 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-13 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 |  | 2026-04-15 |  | 2026-04-14 |  | 64% |  |  |  | 7%
C34-S251230 | 26003H | 3406J | LP1Y-APL(100)-019077-02-4 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 57.3238 | 23.71 | sq ft | 19.21 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Edgar Castaneda | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-09 | 144348, 144349 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251227 | 26003H | 3403J | LP1Y-APL(100)-019077-02-1 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-14 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-15 | 2026-04-15 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% |  |  |  | 0%
C34-S251228 | 26003H | 3404J | LP1Y-APL(100)-019077-02-2 | LP1Y-APL(100)-019077-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-14 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S251232 | 26003H | 3408J | LP1Y-APL(100)-019077-03-1 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 6.34 | 9.5 | sq ft | 4.5 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251234 | 26003H | 3410J | LP1Y-APL(100)-019077-03-3 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 1.5 | 0 | 1.5 | 1.67 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251233 | 26003H | 3409J | LP1Y-APL(100)-019077-03-2 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.3618 | 8.43 | sq ft | 3.43 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251235 | 26003H | 3411J | LP1Y-APL(100)-019077-03-4 | LP1Y-APL(100)-019077-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 5.25 | 0 | 5.25 | 7.6001 | 14.35 | sq ft | 2.85 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251236 | 26003H | 3412J | LP1Y-APL(100)-019077-04-1 | LP1Y-APL(100)-019077-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 019077 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019077 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.0965 | 6.14 | sq ft | 3.14 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S251237 | 26003H | 3413J | LP1Y-APL(100)-019078-04-1 | LP1Y-APL(100)-019078-04 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-06 | 2026-04-14 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 019078 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 8 | 2 | 66.9763 | 26.7 | sq ft | 23.7 | ft | 2026-01-20 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256312 | 26003H | 3413JA | LP1Y-APL(100)-019078-04-2 | LP1Y-APL(100)-019078-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 |  | 0 | LP1Y 2" SS APL(100) (315) 019078 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 27.7838 | 11.3 | sq ft | 7.8 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251238 | 26003H | 3414J | LP1Y-APL(100)-019078-05-1 | LP1Y-APL(100)-019078-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 14.25 | 0 | 14.25 | 47.8411 | 50.34 | sq ft | 13.84 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251239 | 26003H | 3415J | LP1Y-APL(100)-019078-06-1 | LP1Y-APL(100)-019078-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.359 | 5.01 | sq ft | 2.01 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251240 | 26003H | 3416J | LP1Y-APL(100)-019078-06-2 | LP1Y-APL(100)-019078-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019078 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019078 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 6.9403 | 9.05 | sq ft | 2.55 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251242 | 26003H | 3418J | LP1Y-APL(100)-019081-04-2 | LP1Y-APL(100)-019081-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 41.6488 | 17.78 | sq ft | 13.28 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251241 | 26003H | 3417J | LP1Y-APL(100)-019081-04-1 | LP1Y-APL(100)-019081-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 34.045 | 15.56 | sq ft | 9.56 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251243 | 26003H | 3419J | LP1Y-APL(100)-019081-05-1 | LP1Y-APL(100)-019081-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 0 | 9 | 37.178 | 36.37 | sq ft | 3.37 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251246 | 26003H | 3422J | LP1Y-APL(100)-019081-06-3 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251245 | 26003H | 3421J | LP1Y-APL(100)-019081-06-2 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6.75 | 0 | 6.75 | 8.2353 | 10.8 | sq ft | 3.8 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-14 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251244 | 26003H | 3420J | LP1Y-APL(100)-019081-06-1 | LP1Y-APL(100)-019081-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 0.75" SS APL(100) (315) 019081 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019081 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 8.4721 | 10.48 | sq ft | 5.98 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-14 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251247 | 26003H | 3423J | LP1Y-APL(100)-019082-04-1 | LP1Y-APL(100)-019082-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 35.2 | 14.67 | sq ft | 11.67 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251248 | 26003H | 3424J | LP1Y-APL(100)-019082-04-2 | LP1Y-APL(100)-019082-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 42.5288 | 18.78 | sq ft | 12.78 | ft | 2026-01-20 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251249 | 26003H | 3425J | LP1Y-APL(100)-019082-05-1 | LP1Y-APL(100)-019082-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 9 | 0 | 9 | 38.5089 | 38.16 | sq ft | 4.66 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251250 | 26003H | 3426J | LP1Y-APL(100)-019082-06-1 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 8.4721 | 10.48 | sq ft | 5.98 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251251 | 26003H | 3427J | LP1Y-APL(100)-019082-06-2 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4475 | 6.63 | sq ft | 1.63 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251252 | 26003H | 3428J | LP1Y-APL(100)-019082-06-3 | LP1Y-APL(100)-019082-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 0.75" SS APL(100) (315) 019082 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019082 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 3.55 | 4 | sq ft | 1.5 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251255 | 26003H | 3431J | LP1Y-APL(100)-019083-03-3 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 9.75 | 0 | 9.75 | 24.5167 | 27.83 | sq ft | 4.33 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251253 | 26003H | 3429J | LP1Y-APL(100)-019083-03-1 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.9475 | 12.68 | sq ft | 9.68 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251254 | 26003H | 3430J | LP1Y-APL(100)-019083-03-2 | LP1Y-APL(100)-019083-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019083 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 5.5 | 4.75 | 0.75 | 25.1342 | 16.14 | sq ft | 11.14 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251256 | 26003H | 3432J | LP1Y-APL(100)-019083-04-1 | LP1Y-APL(100)-019083-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 019083 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 8.5853 | 11.3 | sq ft | 5.3 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251257 | 26003H | 3433J | LP1Y-APL(100)-019083-04-2 | LP1Y-APL(100)-019083-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 019083 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019083 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 8.25 | 0 | 8.25 | 21.6444 | 20.16 | sq ft | 3.66 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251258 | 26003H | 3434J | LP1Y-APL(100)-019084-02-1 | LP1Y-APL(100)-019084-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019084 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019084 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 71.9263 | 28.58 | sq ft | 25.58 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251259 | 26003H | 3435J | LP1Y-APL(100)-019084-02-2 | LP1Y-APL(100)-019084-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 019084 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019084 |  | TFS00E015YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 66.162 | 32.83 | sq ft | 15.83 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251260 | 26003H | 3436J | LP1Y-APL(100)-019085-02-1 | LP1Y-APL(100)-019085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS APL(100) (315) 019085 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019085 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 66.1238 | 26.38 | sq ft | 23.38 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251261 | 26003H | 3437J | LP1Y-APL(100)-019085-02-2 | LP1Y-APL(100)-019085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS APL(100) (315) 019085 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-019085 |  | TFS00E016YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 63.742 | 31.91 | sq ft | 14.91 | ft | 2026-01-20 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251263 | 26003H | 3439J | LP1Y-APL(100)-198049-01-2 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 1 | 1 | 0 | 15.3714 | 12.2 | sq ft | 10.7 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | N/A | N/A | Carlos Montoya | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144663 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251264 | 26003H | 3440J | LP1Y-APL(100)-198049-01-3 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 6 | 3.75 | 2.25 | 15.3162 | 18.52 | sq ft | 8.52 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  |  | 2026-04-24 |  | 86% |  |  |  | 0%
C34-S251262 | 26003H | 3438J | LP1Y-APL(100)-198049-01-1 | LP1Y-APL(100)-198049-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 4 | 3 | 1 | 17.8377 | 16.83 | sq ft | 11.83 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  |  | 2026-04-27 |  | 75% |  |  |  | 0%
C34-S251265 | 26003H | 3441J | LP1Y-APL(100)-198049-02-1 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 4.5859 | 5.89 | sq ft | 1.89 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251266 | 26003H | 3442J | LP1Y-APL(100)-198049-02-2 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 4.7219 | 5.78 | sq ft | 0.78 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251267 | 26003H | 3443J | LP1Y-APL(100)-198049-02-3 | LP1Y-APL(100)-198049-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.7699 | 6.65 | sq ft | 2.65 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251268 | 26003H | 3444J | LP1Y-APL(100)-198049-03-1 | LP1Y-APL(100)-198049-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 0.75" SS APL(100) (315) 198049 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198049 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.1054 | 6.15 | sq ft | 3.15 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S251269 | 26003H | 3445J | LP1Y-APL(100)-198085-02-1 | LP1Y-APL(100)-198085-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 198085 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198085 |  | TFS00E005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 35.5338 | 16.05 | sq ft | 9.05 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251270 | 26003H | 3446J | LP1Y-APL(100)-198089-02-1 | LP1Y-APL(100)-198089-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS APL(100) (315) 198089 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198089 |  | TFS00E009YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 21.8663 | 9.54 | sq ft | 5.54 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-10; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251272 | 26003H | 3448J | LP1Y-APL(100)-198090-02-2 | LP1Y-APL(100)-198090-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 198090 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198090 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 21.5163 | 12.08 | sq ft | 5.08 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251271 | 26003H | 3447J | LP1Y-APL(100)-198090-02-1 | LP1Y-APL(100)-198090-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS APL(100) (315) 198090 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198090 |  | TFS00E010YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 27.995 | 11.94 | sq ft | 8.94 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251273 | 26003H | 3449J | LP1Y-APL(100)-198091-02-1 | LP1Y-APL(100)-198091-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198091 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198091 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.2563 | 11.58 | sq ft | 7.58 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251276 | 26003H | 3452J | LP1Y-APL(100)-198092-03-3 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 60.9263 | 24.41 | sq ft | 21.41 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251275 | 26003H | 3451J | LP1Y-APL(100)-198092-03-2 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 23.65 | 10.29 | sq ft | 7.29 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251274 | 26003H | 3450J | LP1Y-APL(100)-198092-03-1 | LP1Y-APL(100)-198092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 39.545 | 16.98 | sq ft | 12.48 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251277 | 26003H | 3453J | LP1Y-APL(100)-198092-04-1 | LP1Y-APL(100)-198092-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8.5 | 4.75 | 3.75 | 15.81 | 17.98 | sq ft | 6.48 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251278 | 26003H | 3454J | LP1Y-APL(100)-198092-04-2 | LP1Y-APL(100)-198092-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 6 | 0 | 6 | 34.1108 | 30.29 | sq ft | 5.79 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251281 | 26003H | 3457J | LP1Y-APL(100)-198092-05-3 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 3 | 0 | 3 | 4.2084 | 4.77 | sq ft | 2.27 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251280 | 26003H | 3456J | LP1Y-APL(100)-198092-05-2 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 5.4301 | 6.85 | sq ft | 1.35 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251279 | 26003H | 3455J | LP1Y-APL(100)-198092-05-1 | LP1Y-APL(100)-198092-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 0.75" SS APL(100) (315) 198092 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198092 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 4.5 | 0 | 4.5 | 8.1496 | 10.1 | sq ft | 5.6 | ft | 2026-01-20 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251282 | 26003H | 3458J | LP1Y-APL(100)-198093-02-1 | LP1Y-APL(100)-198093-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS APL(100) (315) 198093 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198093 |  | TFS00E011YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.5725 | 11.7 | sq ft | 7.7 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251283 | 26003H | 3459J | LP1Y-APL(100)-198112-01-1 | LP1Y-APL(100)-198112-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 198112 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198112 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 26.1938 | 11.26 | sq ft | 8.26 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 |  |  |  | 50% |  |  |  | 50%
C34-S251284 | 26003H | 3460J | LP1Y-APL(100)-198112-01-2 | LP1Y-APL(100)-198112-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS APL(100) (315) 198112 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-198112 |  | TFS00E003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 26.9538 | 12.8 | sq ft | 5.8 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145174 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S251285 | 26003H | 3461J | LP1Y-APL(100)-199001-01-1 | LP1Y-APL(100)-199001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251286 | 26003H | 3462J | LP1Y-APL(100)-199001-01-2 | LP1Y-APL(100)-199001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251287 | 26003H | 3463J | LP1Y-APL(100)-199001-02-1 | LP1Y-APL(100)-199001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251288 | 26003H | 3464J | LP1Y-APL(100)-199001-03-1 | LP1Y-APL(100)-199001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251289 | 26003H | 3465J | LP1Y-APL(100)-199001-03-2 | LP1Y-APL(100)-199001-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251290 | 26003H | 3466J | LP1Y-APL(100)-199001-04-1 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251291 | 26003H | 3467J | LP1Y-APL(100)-199001-04-2 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251292 | 26003H | 3468J | LP1Y-APL(100)-199001-04-3 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251293 | 26003H | 3469J | LP1Y-APL(100)-199001-04-4 | LP1Y-APL(100)-199001-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 3" SS APL(100) (315) 199001 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199001 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251294 | 26003H | 3470J | LP1Y-APL(100)-199010-02-1 | LP1Y-APL(100)-199010-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS APL(100) (315) 199010 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199010 |  | TFS00E014YSPP |  | 315-APL(100) | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251297 | 26003H | 3473J | LP1Y-AW-199014-01-3 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251296 | 26003H | 3472J | LP1Y-AW-199014-01-2 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251298 | 26003H | 3474J | LP1Y-AW-199014-01-4 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251295 | 26003H | 3471J | LP1Y-AW-199014-01-1 | LP1Y-AW-199014-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | In Engineering | P027 | 2026-08-03 |  | LP1Y 2" SS AW (315) (108) 199014 | AW |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199014 |  | TFS00E014YSPP |  | 315-AW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251300 | 26003H | 3476J | LP1Y-AWNP-015009-03-2 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251301 | 26003H | 3477J | LP1Y-AWNP-015009-03-3 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251302 | 26003H | 3478J | LP1Y-AWNP-015009-03-4 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251299 | 26003H | 3475J | LP1Y-AWNP-015009-03-1 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258538 | 26003H | 3478JX | LP1Y-AWNP-015009-03-5 | LP1Y-AWNP-015009-03 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-30 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS AWNP (315) (108) 015009 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-015009 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251303 | 26003H | 3479J | LP1Y-AWNP-107093-04-1 | LP1Y-AWNP-107093-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS AWNP (315) (108) 107093 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107093 |  | TFS00E005YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 94.0875 | 35.26 | sq ft | 14.26 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251304 | 26003H | 3480J | LP1Y-AWNP-107093-04-2 | LP1Y-AWNP-107093-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS AWNP (315) (108) 107093 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107093 |  | TFS00E005YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 26.985 | 17.4 | sq ft | 1.4 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251306 | 26003H | 3482J | LP1Y-AWNP-110094-04-2 | LP1Y-AWNP-110094-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS AWNP (315) (108) 110094 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110094 |  | TFS00E009YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 14.75 | 14 | 0.75 | 92.9263 | 35.12 | sq ft | 11.62 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251305 | 26003H | 3481J | LP1Y-AWNP-110094-04-1 | LP1Y-AWNP-110094-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS AWNP (315) (108) 110094 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110094 |  | TFS00E009YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 19.3325 | 9.32 | sq ft | 4.82 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251307 | 26003H | 3483J | LP1Y-AWNP-111092-02-1 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.2463 | 13.08 | sq ft | 8.58 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251308 | 26003H | 3484J | LP1Y-AWNP-111092-02-2 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 67.3538 | 23.13 | sq ft | 5.13 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251309 | 26003H | 3485J | LP1Y-AWNP-111092-02-3 | LP1Y-AWNP-111092-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P023 | 2026-07-20 |  | LP1Y 2" SS AWNP (315) (108) 111092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111092 |  | TFS00E010YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 27.04 | 17.42 | sq ft | 1.42 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251312 | 26003H | 3488J | LP1Y-AWNP-112092-03-3 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 28.25 | 17.88 | sq ft | 1.88 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251310 | 26003H | 3486J | LP1Y-AWNP-112092-03-1 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 51.2875 | 21.43 | sq ft | 16.93 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251311 | 26003H | 3487J | LP1Y-AWNP-112092-03-2 | LP1Y-AWNP-112092-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112092 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112092 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 61.8675 | 21.05 | sq ft | 3.05 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251314 | 26003H | 3490J | LP1Y-AWNP-112202-01-2 | LP1Y-AWNP-112202-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 6" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 20 | 20 | 0 | 521.8316 | 39.64 | sq ft | 15.24 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251313 | 26003H | 3489J | LP1Y-AWNP-112202-01-1 | LP1Y-AWNP-112202-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 6" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251316 | 26003H | 3492J | LP1Y-AWNP-112202-02-2 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.6059 | 8.31 | sq ft | 3.09 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251315 | 26003H | 3491J | LP1Y-AWNP-112202-02-1 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251317 | 26003H | 3493J | LP1Y-AWNP-112202-02-3 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 32.8725 | 7.3 | sq ft | 2.25 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251318 | 26003H | 3494J | LP1Y-AWNP-112202-02-4 | LP1Y-AWNP-112202-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112202 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112202 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 22 | 21 | 1 | 317.2707 | 39.7 | sq ft | 5.14 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251322 | 26003H | 3498J | LP1Y-AWNP-112204-02-1 | LP1Y-AWNP-112204-02 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-06 | 2026-04-14 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 48.6223 | 11.23 | sq ft | 11.23 | ft | 2026-01-20 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256313 | 26003H | 3498JA | LP1Y-AWNP-112204-02-2 | LP1Y-AWNP-112204-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P019 |  | 0 | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 14 | 1 | 558.8682 | 37.57 | sq ft | 11.57 | ft | 2026-01-20 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251323 | 26003H | 3499J | LP1Y-AWNP-112204-05-1 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 8 | 1 | 36.6704 | 15.54 | sq ft | 4.04 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251324 | 26003H | 3500J | LP1Y-AWNP-112204-05-2 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 11 | 1 | 283.3022 | 22.72 | sq ft | 2.72 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251325 | 26003H | 3501J | LP1Y-AWNP-112204-05-3 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 12 | 0 | 58.3071 | 13.46 | sq ft | 10.46 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251326 | 26003H | 3502J | LP1Y-AWNP-112204-05-4 | LP1Y-AWNP-112204-05 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 59.2769 | 13.69 | sq ft | 10.69 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251328 | 26003H | 3504J | LP1Y-AWNP-112204-07-2 | LP1Y-AWNP-112204-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 101.5896 | 24.96 | sq ft | 18.96 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251327 | 26003H | 3503J | LP1Y-AWNP-112204-07-1 | LP1Y-AWNP-112204-07 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 29 | 29 | 0 | 327.7308 | 34.33 | sq ft | 7.33 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251329 | 26003H | 3505J | LP1Y-AWNP-112204-08-1 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251333 | 26003H | 3509J | LP1Y-AWNP-112204-08-5 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.5533 | 13.83 | sq ft | 1.33 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251330 | 26003H | 3506J | LP1Y-AWNP-112204-08-2 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 25.9399 | 5.99 | sq ft | 4.49 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251331 | 26003H | 3507J | LP1Y-AWNP-112204-08-3 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 14 | 13 | 1 | 81.6861 | 30.26 | sq ft | 10.26 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251332 | 26003H | 3508J | LP1Y-AWNP-112204-08-4 | LP1Y-AWNP-112204-08 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.5929 | 10.79 | sq ft | 1.29 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251335 | 26003H | 3511J | LP1Y-AWNP-112205-01-2 | LP1Y-AWNP-112205-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 28.8513 | 12.85 | sq ft | 7.35 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251334 | 26003H | 3510J | LP1Y-AWNP-112205-01-1 | LP1Y-AWNP-112205-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 46.25 | 42 | 4.25 | 125.9706 | 55.62 | sq ft | 11.38 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251342 | 26003H | 3518J | LP1Y-AWNP-112207-01-3 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 18 | 0 | 114.6923 | 26.48 | sq ft | 21.98 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251340 | 26003H | 3516J | LP1Y-AWNP-112207-01-1 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 6 | 6 | 0 | 24.3838 | 5.63 | sq ft | 4.13 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251341 | 26003H | 3517J | LP1Y-AWNP-112207-01-2 | LP1Y-AWNP-112207-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 47.5047 | 10.97 | sq ft | 7.97 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251343 | 26003H | 3519J | LP1Y-AWNP-112207-03-1 | LP1Y-AWNP-112207-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112207 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112207 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 18 | 0 | 124.6829 | 28.79 | sq ft | 24.29 | ft | 2026-01-20 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251346 | 26003H | 3522J | LP1Y-AWNP-112217-01-3 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12 | 12 | 0 | 23.9875 | 13.09 | sq ft | 7.09 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251344 | 26003H | 3520J | LP1Y-AWNP-112217-01-1 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12 | 12 | 0 | 64.5638 | 21.05 | sq ft | 4.05 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251345 | 26003H | 3521J | LP1Y-AWNP-112217-01-2 | LP1Y-AWNP-112217-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 31.6313 | 17.6 | sq ft | 6.6 | ft | 2026-01-20 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251347 | 26003H | 3523J | LP1Y-AWNP-112217-03-1 | LP1Y-AWNP-112217-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112217 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112217 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 73.73 | 24.96 | sq ft | 9.46 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251348 | 26003H | 3524J | LP1Y-AWNP-112402-01-1 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251349 | 26003H | 3525J | LP1Y-AWNP-112402-01-2 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 12 | 12 | 0 | 43.3941 | 15.14 | sq ft | 4.82 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251350 | 26003H | 3526J | LP1Y-AWNP-112402-01-3 | LP1Y-AWNP-112402-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 6" SS AWNP (315) (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 481.2425 | 25.1 | sq ft | 10.92 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251351 | 26003H | 3527J | LP1Y-AWNP-112402-02-1 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251352 | 26003H | 3528J | LP1Y-AWNP-112402-02-2 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.6059 | 8.31 | sq ft | 3.09 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251353 | 26003H | 3529J | LP1Y-AWNP-112402-02-3 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 4 | 4 | 0 | 32.8725 | 7.3 | sq ft | 2.25 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251354 | 26003H | 3530J | LP1Y-AWNP-112402-02-4 | LP1Y-AWNP-112402-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) P (108) 112402 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112402 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 22 | 21 | 1 | 317.2707 | 39.7 | sq ft | 5.14 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258539 | 26003H | 3531JA | LP1Y-AWNP-112404-01-2 | LP1Y-AWNP-112404-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 |  |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 12 | 0 | 75.8802 | 19.02 | sq ft | 13.02 | ft | 2026-01-20 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251355 | 26003H | 3531J | LP1Y-AWNP-112404-01-1 | LP1Y-AWNP-112404-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 23 | 23 | 0 | 334.6668 | 35.93 | sq ft | 11.93 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251356 | 26003H | 3532J | LP1Y-AWNP-112404-03-1 | LP1Y-AWNP-112404-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 12 | 11 | 1 | 280.4105 | 22.05 | sq ft | 3.55 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251357 | 26003H | 3533J | LP1Y-AWNP-112404-03-2 | LP1Y-AWNP-112404-03 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 18 | 0 | 72.3251 | 17.76 | sq ft | 9.26 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251358 | 26003H | 3534J | LP1Y-AWNP-112404-04-1 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251362 | 26003H | 3538J | LP1Y-AWNP-112404-04-5 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.5533 | 13.83 | sq ft | 1.33 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251361 | 26003H | 3537J | LP1Y-AWNP-112404-04-4 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.5929 | 10.79 | sq ft | 1.29 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251360 | 26003H | 3536J | LP1Y-AWNP-112404-04-3 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 14 | 13 | 1 | 80.6036 | 30.01 | sq ft | 10.01 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251359 | 26003H | 3535J | LP1Y-AWNP-112404-04-2 | LP1Y-AWNP-112404-04 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112404 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112404 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 25.9399 | 5.99 | sq ft | 4.49 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251364 | 26003H | 3540J | LP1Y-AWNP-112405-01-2 | LP1Y-AWNP-112405-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 28.8513 | 12.85 | sq ft | 7.35 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251363 | 26003H | 3539J | LP1Y-AWNP-112405-01-1 | LP1Y-AWNP-112405-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 4" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 4" | 316 SS | 38.25 | 36 | 2.25 | 119.8106 | 51.95 | sq ft | 10.71 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251369 | 26003H | 3545J | LP1Y-AWNP-112407-01-1 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 6 | 6 | 0 | 24.3613 | 5.63 | sq ft | 4.13 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251371 | 26003H | 3547J | LP1Y-AWNP-112407-01-3 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 12 | 3 | 140.3503 | 34.78 | sq ft | 31.78 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian; ED: 2026-04-28; EL: Jacob Perez | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251370 | 26003H | 3546J | LP1Y-AWNP-112407-01-2 | LP1Y-AWNP-112407-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 3" SS AWNP (315) (108) 112407 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112407 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 130.3209 | 30.09 | sq ft | 25.59 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251372 | 26003H | 3548J | LP1Y-AWNP-112417-01-1 | LP1Y-AWNP-112417-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 16 | 16 | 0 | 70.61 | 23.33 | sq ft | 4.83 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251373 | 26003H | 3549J | LP1Y-AWNP-112417-01-2 | LP1Y-AWNP-112417-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 71.5338 | 32.71 | sq ft | 21.71 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251375 | 26003H | 3551J | LP1Y-AWNP-850001-01-1 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 48.6913 | 22.81 | sq ft | 15.81 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Henrique Barahona | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-21 | 2026-04-17 | 2026-04-21 | 100% | 2026-04-21 | 145134 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S251377 | 26003H | 3553J | LP1Y-AWNP-850001-01-3 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 18.3981 | 13.18 | sq ft | 6.68 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | [6 empty] | 67% |  |  |  | 0%
C34-S251376 | 26003H | 3552J | LP1Y-AWNP-850001-01-2 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 30.4025 | 17.53 | sq ft | 9.03 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | N/A | N/A | Aristeo Banda | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-04-16 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144957 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251378 | 26003H | 3554J | LP1Y-AWNP-850001-01-4 | LP1Y-AWNP-850001-01 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 20.085 | 16.88 | sq ft | 11.38 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 50%
C34-S251381 | 26003H | 3557J | LP1Y-AWNP-850001-02-3 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 49.335 | 20.02 | sq ft | 17.02 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144511 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251382 | 26003H | 3558J | LP1Y-AWNP-850001-02-4 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 28.71 | 11.54 | sq ft | 10.04 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-11 | 144510 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251379 | 26003H | 3555J | LP1Y-AWNP-850001-02-1 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 29.3875 | 12.47 | sq ft | 10.97 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | N/A | N/A | Henrique Barahona | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 2026-04-09 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144668 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251380 | 26003H | 3556J | LP1Y-AWNP-850001-02-2 | LP1Y-AWNP-850001-02 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 102.7025 | 40.24 | sq ft | 38.74 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-03-31 | 2026-04-01 | Passed | No | 2026-04-01 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-14 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 145024 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251386 | 26003H | 3562J | LP1Y-AWNP-850001-10-4 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 26.9363 | 11.54 | sq ft | 8.54 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251384 | 26003H | 3560J | LP1Y-AWNP-850001-10-2 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 12.9975 | 6.84 | sq ft | 1.34 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251385 | 26003H | 3561J | LP1Y-AWNP-850001-10-3 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 16 | 16 | 0 | 133.9838 | 40.01 | sq ft | 13.01 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251383 | 26003H | 3559J | LP1Y-AWNP-850001-10-1 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251387 | 26003H | 3563J | LP1Y-AWNP-850001-10-5 | LP1Y-AWNP-850001-10 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850001 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850001 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 60.1838 | 23.46 | sq ft | 21.96 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251393 | 26003H | 3569J | LP1Y-AWNP-850008-06-1 | LP1Y-AWNP-850008-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E015YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 4.83 | sq ft | 0.83 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251394 | 26003H | 3570J | LP1Y-AWNP-850008-06-2 | LP1Y-AWNP-850008-06 | 0 | N | CWA-E-WEST-TO-EAST | [5 empty] | Released to Production | P025 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E015YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 14 | 14 | 0 | 45.695 | 20.56 | sq ft | 12.06 | ft | 2026-01-20 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245271 | 26003H | 1173J | LP1Y-AWNP-101105-02-1 | LP1Y-AWNP-101105-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 66.6469 | 13.02 | sq ft | 3.51 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144952 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245272 | 26003H | 1174J | LP1Y-AWNP-101105-02-2 | LP1Y-AWNP-101105-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 33 | 32 | 1 | 174.1398 | 40.55 | sq ft | 6.24 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246945 | 26003H | 1173JA | LP1Y-AWNP-101105-02-3 | LP1Y-AWNP-101105-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101105 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101105 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 144870 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245285 | 26003H | 1187J | LP1Y-AWNP-101107-01-2 | LP1Y-AWNP-101107-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 33 | 31 | 2 | 173.3413 | 40.21 | sq ft | 5.4 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245286 | 26003H | 1188J | LP1Y-AWNP-101107-01-3 | LP1Y-AWNP-101107-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 73.4813 | 14.91 | sq ft | 3.06 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-09 | 144071, 144396 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246947 | 26003H | 1186JA | LP1Y-AWNP-101107-01-4 | LP1Y-AWNP-101107-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144655 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245284 | 26003H | 1186J | LP1Y-AWNP-101107-01-1 | LP1Y-AWNP-101107-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101107 | AWNP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101107 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 66.55 | 13 | sq ft | 3.5 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-09 | 144039, 144395 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245291 | 26003H | 1193J | LP1Y-AWNP-101110-01-1 | LP1Y-AWNP-101110-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Visual Inspection | P012 | 2026-05-18 |  | LP1Y 3" SS AWNP (315) (108) 101110 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101110 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 3 | 3 | 0 | 25.7595 | 5.95 | sq ft | 4.45 | ft | 2026-02-13 | CD: 2026-02-25; CL: Jacob Perez; DD: 2026-02-25; DL: George Allahverdian | 2026-04-18 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 145847
C34-S245309 | 26003H | 1211J | LP1Y-AWNP-101305-02-1 | LP1Y-AWNP-101305-02 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 66.55 | 13 | sq ft | 3.5 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-09 | 144072, 144397 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S246953 | 26003H | 1211JA | LP1Y-AWNP-101305-02-3 | LP1Y-AWNP-101305-02 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-09 | 143934, 144398 | [40 empty] | 2026-04-19 | 2026-04-19 |  | 1002-1 | 2026-04-20 | JA Harris Trucking Inc.
C34-S245310 | 26003H | 1212J | LP1Y-AWNP-101305-02-2 | LP1Y-AWNP-101305-02 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101305 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101305 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 33 | 31 | 2 | 174.078 | 40.36 | sq ft | 6.02 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-18 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246972 | 26003H | 1328J-L1 | LP1Y-ENZ-162001-01-1-L1 | LP1Y-ENZ-162001-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-03-12 | 2026-03-12 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-14 | 144662
C34-S245425 | 26003H | 1328J | LP1Y-ENZ-162001-01-1 | LP1Y-ENZ-162001-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1" | 316 SS | 5.75 | 3.75 | 2 | 5.8021 | 7.95 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-04-11 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245426 | 26003H | 1329J | LP1Y-ENZ-162001-01-2 | LP1Y-ENZ-162001-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P016 | 2026-06-08 |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 8.25 | 6 | 2.25 | 19.1306 | 28.27 | sq ft | 3.77 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245427 | 26003H | 1330J | LP1Y-ENZ-162001-01-3 | LP1Y-ENZ-162001-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 1" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 4 | 0 | 4 | 9.672 | 17.73 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-03-03; CL: Jacob Perez; DD: 2026-03-03; DL: George Allahverdian | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Edgar Castaneda | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145808
C34-S246975 | 26003H | 1337JA | LP1Y-ENZ-162305-01-4 | LP1Y-ENZ-162305-01 | 4 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-11 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246974 | 26003H | 1336JA | LP1Y-ENZ-162305-01-3 | LP1Y-ENZ-162305-01 | 4 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 2 | 2 | 0 | 45.26 | 10.5 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245433 | 26003H | 1336J | LP1Y-ENZ-162305-01-1 | LP1Y-ENZ-162305-01 | 4 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 16 | 12 | 4 | 29.5 | 11.67 | sq ft | 6.67 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-29 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-04-29 |  | 88% |  |  |  | 0%
C34-S245434 | 26003H | 1337J | LP1Y-ENZ-162305-01-2 | LP1Y-ENZ-162305-01 | 4 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS ENZ (315) P (108) 162305 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162305 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 2" | 316 SS | 31.5 | 30 | 1.5 | 62.8366 | 38.37 | sq ft | 13.37 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Ramiro Gonzalez | 2026-04-29 | 2026-04-29 | 2026-04-30 | 2026-04-29 |  |  |  |  | 2026-04-30 |  | 82% |  |  |  | 0%
C34-S246198 | 26003H | 1618J | LP1Y-NAOH50-178201-01-2 | LP1Y-NAOH50-178201-01 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-27 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 19 | 17 | 2 | 320.4432 | 41.46 | sq ft | 6.96 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian; ED: 2026-04-28; EL: Jacob Perez | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246197 | 26003H | 1617J | LP1Y-NAOH50-178201-01-1 | LP1Y-NAOH50-178201-01 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Edgar Castaneda | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-04-09 | 143332, 144456
C34-S246199 | 26003H | 1619J | LP1Y-NAOH50-178201-01-3 | LP1Y-NAOH50-178201-01 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 6 | 6 | 0 | 118.6515 | 27.4 | sq ft | 25.9 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian; ED: 2026-03-17; EL: Jacob Perez; FD: 2026-03-17; FL: Jacob Perez | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 | N/A | N/A | Henrique Barahona | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 100% | 2026-03-27 | 2026-03-27 | 2026-03-27 | 100% | 2026-04-09 | 143751, 144391
C34-S246200 | 26003H | 1620J | LP1Y-NAOH50-178201-01-4 | LP1Y-NAOH50-178201-01 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 3 | 3 | 0 | 6.8602 | 2.77 | sq ft | 1.27 | ft | 2026-02-13 | DD: 2026-03-17; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Henrique Barahona | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-04-09 | 143463, 144392
C34-S247008 | 26003H | 1617J-L1 | LP1Y-NAOH50-178201-01-1-L1 | LP1Y-NAOH50-178201-01 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-04-09 | 143586, 144390
C34-S246202 | 26003H | 1622J | LP1Y-NAOH50-178201-02-2 | LP1Y-NAOH50-178201-02 | 3 | R | TR-02 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 28 | 27 | 1 | 308.0905 | 33.55 | sq ft | 5.05 | ft | 2026-02-13 | CD: 2026-03-17; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246201 | 26003H | 1621J | LP1Y-NAOH50-178201-02-1 | LP1Y-NAOH50-178201-02 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS NAOH50 (315) P (108) 178201 | NAOH50 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178201 |  | TFS00D001YSPP |  | 315-NAOH50 | NONE | 3" | 316 SS | 6 | 6 | 0 | 103.068 | 23.8 | sq ft | 22.3 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Edgar Castaneda | 2026-03-20 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-04-09 | 143399, 144393
C34-S246225 | 26003H | 1645J | LP1Y-PV-100307-01-1 | LP1Y-PV-100307-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Passed Visual Inspection | P011 | 2026-05-11 |  | LP1Y 2" SS PV (315) (108) 100307 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100307 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 21.4288 | 13.73 | sq ft | 2.73 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian; ED: 2026-03-25; EL: Jacob Perez; FD: 2026-03-25; FL: Jacob Perez | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Ramiro Gonzalez | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-30 | 145905
C34-S246226 | 26003H | 1646J | LP1Y-PV-100307-01-2 | LP1Y-PV-100307-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-27 | released |  |  | Released to Fabrication | P011 | 2026-05-11 |  | LP1Y 2" SS PV (315) (108) 100307 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100307 |  | TFS00D002YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 23.1825 | 10.11 | sq ft | 7.11 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-04-28 | 2026-04-28 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247356 | 26003H | 1818J | LP1Y-PWP-101705-02-3 | LP1Y-PWP-101705-02 | 2 | R | TR-02 3.26.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247354 | 26003H | 1816J | LP1Y-PWP-101705-02-1 | LP1Y-PWP-101705-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144951 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247355 | 26003H | 1817J | LP1Y-PWP-101705-02-2 | LP1Y-PWP-101705-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101705 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101705 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 6 | 6 | 0 | 64.7094 | 12.64 | sq ft | 3.3 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-09 | 143955, 144394 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247960 | 26003H | 2172J | LP1Y-SRACNP-108104-06-2 | LP1Y-SRACNP-108104-06 | 2 | R | TR-02 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 13 | 12 | 1 | 79.9864 | 28.67 | sq ft | 10.45 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247959 | 26003H | 2171J | LP1Y-SRACNP-108104-06-1 | LP1Y-SRACNP-108104-06 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 2 | 2 | 0 | 10.25 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S247961 | 26003H | 2173J | LP1Y-SRACNP-108104-06-3 | LP1Y-SRACNP-108104-06 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 8 | 8 | 0 | 42.9409 | 10.31 | sq ft | 3.26 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Carlos Montoya | 2026-04-10 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-14 | 144698
C34-S247963 | 26003H | 2175J | LP1Y-SRACNP-108104-06-5 | LP1Y-SRACNP-108104-06 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 11 | 10 | 1 | 51.81 | 15.65 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247962 | 26003H | 2174J | LP1Y-SRACNP-108104-06-4 | LP1Y-SRACNP-108104-06 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 19 | 16 | 3 | 61.2446 | 14.56 | sq ft | 3.13 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 |  | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-30 |  | 2026-04-30 | 2026-05-01 | 2026-04-21 | 2026-05-01 | 100% |  |  |  | 60%
C34-S249515 | 26003H | 2218J | LP1Y-SRACNP-108204-01-1 | LP1Y-SRACNP-108204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 2 | 2 | 0 | 10.25 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-04-21 | Passed | No | 2026-04-21 | 2026-04-22 | 2026-04-22 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249516 | 26003H | 2219J | LP1Y-SRACNP-108204-01-2 | LP1Y-SRACNP-108204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 25 | 24 | 1 | 118.7491 | 38.09 | sq ft | 12.97 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249518 | 26003H | 2221J | LP1Y-SRACNP-108204-01-4 | LP1Y-SRACNP-108204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Production | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 11 | 10 | 1 | 50.4952 | 15.37 | sq ft | 1.43 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249517 | 26003H | 2220J | LP1Y-SRACNP-108204-01-3 | LP1Y-SRACNP-108204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-10 | 2026-04-10 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 16 | 16 | 0 | 56.9966 | 13.59 | sq ft | 2.16 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Guillen | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 75%
C34-S249519 | 26003H | 2222J | LP1Y-SRACNP-108204-01-5 | LP1Y-SRACNP-108204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 4" SS SRACNP (315) P (108) 108204 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108204 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 4" | 316 SS | 38 | 38 | 0 | 135.0427 | 36.62 | sq ft | 15.85 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-14 | 2026-04-14 | 2026-04-16 | 2026-04-20 | N/A | N/A | [5 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23 |  |  |  | 0% |  |  |  | 50%
C34-S249576 | 26003H | 2279J | LP1Y-STORMP-100403-01-4 | LP1Y-STORMP-100403-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 12 | 12 | 0 | 52.8475 | 12.7 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Aristeo Banda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144958 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249577 | 26003H | 2280J | LP1Y-STORMP-100403-01-5 | LP1Y-STORMP-100403-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 19 | 18 | 1 | 56.2688 | 17.49 | sq ft | 1.71 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249575 | 26003H | 2278J | LP1Y-STORMP-100403-01-3 | LP1Y-STORMP-100403-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 11 | 9 | 2 | 38.2633 | 13.56 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249573 | 26003H | 2276J | LP1Y-STORMP-100403-01-1 | LP1Y-STORMP-100403-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 2 | 2 | 0 | 10.25 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S249574 | 26003H | 2277J | LP1Y-STORMP-100403-01-2 | LP1Y-STORMP-100403-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100403 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100403 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 4 | 4 | 0 | 9.9808 | 2.99 | sq ft | 0.99 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Roberto Tobias (WF) | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-14 | 2026-04-14 | 2026-04-14 | 100% | 2026-04-15 | 144773 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S249590 | 26003H | 2293J | LP1Y-STORMP-100406-02-1 | LP1Y-STORMP-100406-02 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100406 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100406 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 28.25 | 24 | 4.25 | 48.4444 | 33.67 | sq ft | 4.2 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249726 | 26003H | 2429D | LP1Y-SWP-101505-02-1 | LP1Y-SWP-101505-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-11 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-20 | 2026-04-20 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249727 | 26003H | 2430D | LP1Y-SWP-101505-02-2 | LP1Y-SWP-101505-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 6 | 6 | 0 | 64.6609 | 12.63 | sq ft | 3.3 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249728 | 26003H | 2431D | LP1Y-SWP-101505-02-3 | LP1Y-SWP-101505-02 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-27 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101505 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101505 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 34 | 33 | 1 | 161.2913 | 37.91 | sq ft | 3.56 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250662 | 26003H | 3097J | LP1Y-ACN-107105-01-6 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 22.1963 | 5.13 | sq ft | 3.63 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250658 | 26003H | 3093J | LP1Y-ACN-107105-01-2 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 16 | 15 | 1 | 56.6441 | 24.3 | sq ft | 2.8 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250660 | 26003H | 3095J | LP1Y-ACN-107105-01-4 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 8 | 1 | 35.7183 | 14.33 | sq ft | 1.83 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250661 | 26003H | 3096J | LP1Y-ACN-107105-01-5 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 11 | 11 | 0 | 72.0552 | 21.52 | sq ft | 10.52 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250657 | 26003H | 3092J | LP1Y-ACN-107105-01-1 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 2 | 2 | 0 | 9.45 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250659 | 26003H | 3094J | LP1Y-ACN-107105-01-3 | LP1Y-ACN-107105-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107105 | ACN |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107105 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 36.6908 | 10.58 | sq ft | 1.08 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-10 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250697 | 26003H | 3132J | LP1Y-ACN-107204-01-2 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250698 | 26003H | 3133J | LP1Y-ACN-107204-01-3 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250699 | 26003H | 3134J | LP1Y-ACN-107204-01-4 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250700 | 26003H | 3135J | LP1Y-ACN-107204-01-5 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250701 | 26003H | 3136J | LP1Y-ACN-107204-01-6 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250696 | 26003H | 3131J | LP1Y-ACN-107204-01-1 | LP1Y-ACN-107204-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107204 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107204 |  | TFS00E005YSPP |  | 315-ACN | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250721 | 26003H | 3156J | LP1Y-ACN-107305-01-2 | LP1Y-ACN-107305-01 | 1 | R | TR-02 3.26.2026 | 2026-04-10 | 2026-04-18 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 16 | 15 | 1 | 56.6441 | 24.3 | sq ft | 2.8 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250720 | 26003H | 3155J | LP1Y-ACN-107305-01-1 | LP1Y-ACN-107305-01 | 1 | R | TR-02 3.26.2026 | 2026-04-10 | 2026-04-18 | released |  |  | Passed Production Test | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 2 | 2 | 0 | 9.45 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-18 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250722 | 26003H | 3157J | LP1Y-ACN-107305-01-3 | LP1Y-ACN-107305-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 9 | 0 | 36.6908 | 10.58 | sq ft | 1.08 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250723 | 26003H | 3158J | LP1Y-ACN-107305-01-4 | LP1Y-ACN-107305-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 9 | 8 | 1 | 35.7634 | 14.34 | sq ft | 1.84 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250724 | 26003H | 3159J | LP1Y-ACN-107305-01-5 | LP1Y-ACN-107305-01 | 1 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 3" SS ACN (315) P (108) 107305 | ACN |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107305 |  | TFS00E005YSPP |  | 315-ACN | NONE | 3" | 316 SS | 3 | 3 | 0 | 27.1833 | 7.33 | sq ft | 3.33 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250827 | 26003H | 3262J | LP1Y-ACN-850013-05-1 | LP1Y-ACN-850013-05 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S250830 | 26003H | 3265J | LP1Y-ACN-850013-05-4 | LP1Y-ACN-850013-05 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 18.5 | 12 | 6.5 | 34.92 | 22.54 | sq ft | 6.04 | ft | 2026-01-20 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-18 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  | 2026-04-24 |  | 92% |  |  |  | 54%
C34-S250829 | 26003H | 3264J | LP1Y-ACN-850013-05-3 | LP1Y-ACN-850013-05 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-27 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 75.8775 | 28.68 | sq ft | 7.68 | ft | 2026-01-20 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250828 | 26003H | 3263J | LP1Y-ACN-850013-05-2 | LP1Y-ACN-850013-05 | 3 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS ACN (315) P (108) 850013 | ACN |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850013 |  | TFS00E003YSPP |  | 315-ACN | NONE | 2" | 316 SS | 2 | 2 | 0 | 10.22 | 5.13 | sq ft | 1.13 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-15 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S251321 | 26003H | 3497J | LP1Y-AWNP-112204-01-3 | LP1Y-AWNP-112204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251319 | 26003H | 3495J | LP1Y-AWNP-112204-01-1 | LP1Y-AWNP-112204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 15 | 15 | 0 | 69.0244 | 15.94 | sq ft | 11.44 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251320 | 26003H | 3496J | LP1Y-AWNP-112204-01-2 | LP1Y-AWNP-112204-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS AWNP (315) (108) 112204 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112204 |  | TFS00E016YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 18 | 18 | 0 | 125.2911 | 30.11 | sq ft | 25.61 | ft | 2026-01-20 | CD: 2026-04-09; CL: Jacob Perez; DD: 2026-04-09; DL: George Allahverdian | 2026-04-09 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251374 | 26003H | 3550J | LP1Y-AWNP-112417-04-1 | LP1Y-AWNP-112417-04 | 1 | R | TR-02 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112417 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112417 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251391 | 26003H | 3567J | LP1Y-AWNP-850008-01-4 | LP1Y-AWNP-850008-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 37.8538 | 15.67 | sq ft | 12.67 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-02 | 2026-04-02 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144980 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S251389 | 26003H | 3565J | LP1Y-AWNP-850008-01-2 | LP1Y-AWNP-850008-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.0575 | 8.55 | sq ft | 5.55 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-02 | 2026-04-02 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145195 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S251390 | 26003H | 3566J | LP1Y-AWNP-850008-01-3 | LP1Y-AWNP-850008-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.8688 | 13.03 | sq ft | 10.03 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-02 | 2026-04-02 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145208 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S251388 | 26003H | 3564J | LP1Y-AWNP-850008-01-1 | LP1Y-AWNP-850008-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 9.875 | 7.44 | sq ft | 1.94 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-15 | 2026-04-16 | 2026-04-15 |  |  |  | 2026-04-15 |  |  | 75% |  |  |  | 0%
C34-S251392 | 26003H | 3568J | LP1Y-AWNP-850008-01-5 | LP1Y-AWNP-850008-01 | 2 | R | TR-02 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS AWNP (315) (108) 850008 | AWNP |  | 108 | 102.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850008 |  | TFS00E003YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 8 | 8 | 0 | 10.56 | 6 | sq ft | 1.5 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-02 | 2026-04-02 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-30 | 145942
C34-S246969 | 26003H | 1322J-L1 | LP1Y-ENZ-108008-02-1-L1 | LP1Y-ENZ-108008-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108008 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108008 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 2 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez | 2026-04-11 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-24 | 2026-04-24 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145574
C34-S245419 | 26003H | 1322J | LP1Y-ENZ-108008-02-1 | LP1Y-ENZ-108008-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 108008 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108008 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0 | 0 | 0 | 1.6296 | 2.43 | sq ft | 2.43 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-04-09 | 2026-04-09 | Passed | No | 2026-04-09 | N/A | N/A | 2026-03-18 | 2026-03-18 | N/A | N/A | NO FITTER | 2026-03-16 | [9 empty] | 100% |  |  |  | 100% | 2026-04-09 | 143268, 144399
C34-S249879 | 26003H | 2511AB | LP1Y-TFA-010025-04-2 | LP1Y-TFA-010025-04 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 6 | 6 | 0 | 13.6713 | 7.1 | sq ft | 1.6 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249881 | 26003H | 2513AB | LP1Y-TFA-010025-04-4 | LP1Y-TFA-010025-04 | 2 | R | TR-03 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 17 | 16.25 | 0.75 | 59.0813 | 34.35 | sq ft | 6.35 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249878 | 26003H | 2510AB | LP1Y-TFA-010025-04-1 | LP1Y-TFA-010025-04 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249882 | 26003H | 2514AB | LP1Y-TFA-010025-04-5 | LP1Y-TFA-010025-04 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 79.0075 | 31.93 | sq ft | 27.43 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249880 | 26003H | 2512AB | LP1Y-TFA-010025-04-3 | LP1Y-TFA-010025-04 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 010025 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010025 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 14.25 | 13.5 | 0.75 | 57.6288 | 30.86 | sq ft | 3.36 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249884 | 26003H | 2516AB | LP1Y-TFA-109203-01-2 | LP1Y-TFA-109203-01 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249883 | 26003H | 2515AB | LP1Y-TFA-109203-01-1 | LP1Y-TFA-109203-01 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249885 | 26003H | 2517AB | LP1Y-TFA-109203-01-3 | LP1Y-TFA-109203-01 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-14 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 27 | 26 | 1 | 160.4557 | 36.72 | sq ft | 5.72 | ft | 2026-02-13 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-14 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249886 | 26003H | 2518AB | LP1Y-TFA-109203-02-1 | LP1Y-TFA-109203-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S249888 | 26003H | 2520AB | LP1Y-TFA-109203-02-3 | LP1Y-TFA-109203-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 16 | 16 | 0 | 59.7302 | 18.77 | sq ft | 6.27 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249887 | 26003H | 2519AB | LP1Y-TFA-109203-02-2 | LP1Y-TFA-109203-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109203 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109203 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 6 | 6 | 0 | 39.3352 | 10.27 | sq ft | 8.77 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249898 | 26003H | 2530AB | LP1Y-TFA-109205-06-2 | LP1Y-TFA-109205-06 | 1 | R | TR-03 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 20 | 19 | 1 | 100.9539 | 35.79 | sq ft | 14.29 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249899 | 26003H | 2531AB | LP1Y-TFA-109205-06-3 | LP1Y-TFA-109205-06 | 1 | R | TR-03 3.26.2026 | 2026-04-18 | 2026-04-27 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 9 | 9 | 0 | 37.6606 | 10.81 | sq ft | 1.31 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-27 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249897 | 26003H | 2529AB | LP1Y-TFA-109205-06-1 | LP1Y-TFA-109205-06 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 3" HAST TFA (332) P (108) 109205 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109205 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 3 | 3 | 0 | 5.36 | 8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249901 | 26003H | 2533AB | LP1Y-TFA-109206-01-2 | LP1Y-TFA-109206-01 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 4.5 | 4.5 | 0 | 8.2579 | 8.43 | sq ft | 2.93 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249903 | 26003H | 2535AB | LP1Y-TFA-109206-01-4 | LP1Y-TFA-109206-01 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 7.5 | 7.5 | 0 | 6.5988 | 7.91 | sq ft | 3.41 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249900 | 26003H | 2532AB | LP1Y-TFA-109206-01-1 | LP1Y-TFA-109206-01 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 2 | 2 | 0 | 9.55 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249902 | 26003H | 2534AB | LP1Y-TFA-109206-01-3 | LP1Y-TFA-109206-01 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) P (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 7.5 | 7.5 | 0 | 27.7315 | 23.4 | sq ft | 16.4 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-18 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249920 | 26003H | 2552AB | LP1Y-TFA-176023-03-2 | LP1Y-TFA-176023-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 21.2138 | 12.55 | sq ft | 1.55 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249921 | 26003H | 2553AB | LP1Y-TFA-176023-03-3 | LP1Y-TFA-176023-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 4 | 4 | 0 | 17.095 | 8.4 | sq ft | 2.9 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249919 | 26003H | 2551AB | LP1Y-TFA-176023-03-1 | LP1Y-TFA-176023-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 6.25 | 5.5 | 0.75 | 24.5888 | 15.78 | sq ft | 2.78 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249922 | 26003H | 2554AB | LP1Y-TFA-176023-03-4 | LP1Y-TFA-176023-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 6 | 6 | 0 | 34.4713 | 14.39 | sq ft | 11.39 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249925 | 26003H | 2557AB | LP1Y-TFA-176023-04-3 | LP1Y-TFA-176023-04 | 1 | R | TR-03 3.26.2026 | 2026-04-02 |  | releasing |  |  | Releasing from Hold | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 16.25 | 15.5 | 0.75 | 55.4575 | 28.39 | sq ft | 2.39 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249923 | 26003H | 2555AB | LP1Y-TFA-176023-04-1 | LP1Y-TFA-176023-04 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-11 | 2026-05-01 | Passed | No | 2026-05-01 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249924 | 26003H | 2556AB | LP1Y-TFA-176023-04-2 | LP1Y-TFA-176023-04 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-09 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 6 | 6 | 0 | 16.4488 | 8.15 | sq ft | 2.65 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-09 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251170 | 26003H | 3346J | LP1Y-AF-162003-02-1 | LP1Y-AF-162003-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 2 | 0.5 | 1.5 | 7.9192 | 11.64 | sq ft | 6.64 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-27 | 2026-04-24 | 2026-04-24 |  | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  | 75% |  |  |  | 50%
C34-S251173 | 26003H | 3349J | LP1Y-AF-162003-02-4 | LP1Y-AF-162003-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-10 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 8.3534 | 13.28 | sq ft | 11.78 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-10 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-01 | 2026-04-01 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | 2026-04-28 | 145685
C34-S251171 | 26003H | 3347J | LP1Y-AF-162003-02-2 | LP1Y-AF-162003-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 5.5 | 0 | 5.5 | 13.2958 | 25.58 | sq ft | 8.08 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-18 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | [6 empty] | 91% |  |  |  | 0%
C34-S251172 | 26003H | 3348J | LP1Y-AF-162003-02-3 | LP1Y-AF-162003-02 | 1 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1/2" | 316 SS | 2 | 0 | 2 | 6.6991 | 12.47 | sq ft | 2.97 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S251174 | 26003H | 3350J | LP1Y-AF-162003-03-1 | LP1Y-AF-162003-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-11 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 3/4" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-11 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251175 | 26003H | 3351J | LP1Y-AF-162003-03-2 | LP1Y-AF-162003-03 | 2 | R | TR-03 3.26.2026 | 2026-04-02 | 2026-04-18 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS AF (315) P (108) 162003 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162003 |  | TFS00E003YSPP |  | 315-AF | NONE | 1" | 316 SS | 12 | 8.25 | 3.75 | 15.7563 | 26.86 | sq ft | 6.36 | ft | 2026-01-20 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-18 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-22 | 2026-04-23 | N/A | N/A | Carlos Montoya | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-04-29 |  | 93% |  |  |  | 0%
C34-S254617 | 26003H | 3603J | LP1Y-STORMP-100412-01-5 | LP1Y-STORMP-100412-01 | 0 | N | PRI-1-2 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100412 | STORMP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100412 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10.25 | 8.75 | 1.5 | 34.065 | 18.52 | sq ft | 7.52 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-11; DL: George Allahverdian | 2026-04-15 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 71%
C34-S254614 | 26003H | 3600J | LP1Y-STORMP-100412-01-2 | LP1Y-STORMP-100412-01 | 0 | N | PRI-1-2 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100412 | STORMP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100412 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10.5 | 7.5 | 3 | 28.9075 | 18.34 | sq ft | 7.34 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-11 | 2026-04-11 | N/A | N/A | Henrique Barahona | 2026-04-15 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-23 | 2026-04-16 | 2026-04-23 | 100% |  |  |  | 44%
C34-S254613 | 26003H | 3599J | LP1Y-STORMP-100412-01-1 | LP1Y-STORMP-100412-01 | 0 | N | PRI-1-2 | 2026-04-14 | 2026-04-15 | released |  |  | Released to Production | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100412 | STORMP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100412 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 4" | 316 SS | 4 | 4 | 0 | 19.5 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-11; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254615 | 26003H | 3601J | LP1Y-STORMP-100412-01-3 | LP1Y-STORMP-100412-01 | 0 | N | PRI-1-2 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100412 | STORMP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100412 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 26.9638 | 10.88 | sq ft | 9.38 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Carlos Montoya | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-14 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 50%
C34-S254616 | 26003H | 3602J | LP1Y-STORMP-100412-01-4 | LP1Y-STORMP-100412-01 | 0 | N | PRI-1-2 | [5 empty] | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 4" SS STORMP (315) (108) 100412 | STORMP |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100412 |  | TFS00D003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 15.345 | 7.15 | sq ft | 4.15 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-09 | 2026-04-10 | Passed | No | 2026-04-10 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | N/A | N/A | Ramiro Gonzalez | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | [6 empty] | 67% |  |  |  | 0%
C34-S254621 | 26003H | 3607J | LP1Y-CIPS-162002-02-4 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 3.5 | 0 | 3.5 | 25.8679 | 11.78 | sq ft | 7.78 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145845
C34-S254618 | 26003H | 3604J | LP1Y-CIPS-162002-02-1 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 21.6975 | 8.89 | sq ft | 7.39 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254619 | 26003H | 3605J | LP1Y-CIPS-162002-02-2 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.7788 | 12.23 | sq ft | 9.23 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-05-02 | 2026-05-02 | 2026-05-02 |  |  |  | 67% |  |  |  | 33%
C34-S254623 | 26003H | 3609J | LP1Y-CIPS-162002-02-6 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 17.37 | 12.5 | sq ft | 0.5 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144983 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254622 | 26003H | 3608J | LP1Y-CIPS-162002-02-5 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 4 | 4 | 0 | 15.435 | 8.35 | sq ft | 0.35 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254620 | 26003H | 3606J | LP1Y-CIPS-162002-02-3 | LP1Y-CIPS-162002-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6 | 6 | 0 | 55.2338 | 22.26 | sq ft | 19.26 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 67% |  |  |  | 0%
C34-S254628 | 26003H | 3614J | LP1Y-CIPS-162002-03-5 | LP1Y-CIPS-162002-03 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 18.38 | 12.5 | sq ft | 0.5 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-22 | 145209 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254624 | 26003H | 3610J | LP1Y-CIPS-162002-03-1 | LP1Y-CIPS-162002-03 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254626 | 26003H | 3612J | LP1Y-CIPS-162002-03-3 | LP1Y-CIPS-162002-03 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.9525 | 6.45 | sq ft | 0.95 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-21 | 145133 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254627 | 26003H | 3613J | LP1Y-CIPS-162002-03-4 | LP1Y-CIPS-162002-03 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9138 | 10.34 | sq ft | 0.84 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 145026 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254625 | 26003H | 3611J | LP1Y-CIPS-162002-03-2 | LP1Y-CIPS-162002-03 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 10 | 10 | 0 | 15.477 | 12.39 | sq ft | 3.89 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254629 | 26003H | 3615J | LP1Y-CIPS-162002-04-1 | LP1Y-CIPS-162002-04 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 58.13 | 30.54 | sq ft | 14.04 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 56% |  |  |  | 33%
C34-S254630 | 26003H | 3616J | LP1Y-CIPS-162002-04-2 | LP1Y-CIPS-162002-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 10 | 8 | 2 | 24.3238 | 11.21 | sq ft | 6.71 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  | 2026-04-21 |  | 80% |  | 2026-04-23 |  | 40%
C34-S254633 | 26003H | 3619J | LP1Y-CIPS-162002-05-3 | LP1Y-CIPS-162002-05 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 109.04 | 45 | sq ft | 39.5 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 145027 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254632 | 26003H | 3618J | LP1Y-CIPS-162002-05-2 | LP1Y-CIPS-162002-05 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-22 | 2026-04-24 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S254631 | 26003H | 3617J | LP1Y-CIPS-162002-05-1 | LP1Y-CIPS-162002-05 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 94.1325 | 35.66 | sq ft | 35.66 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-23 | 2026-04-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254635 | 26003H | 3621J | LP1Y-CIPS-162002-06-2 | LP1Y-CIPS-162002-06 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 10.5 | 4 | 6.5 | 33.4763 | 20.66 | sq ft | 7.16 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  |  |  | 2026-04-23 |  |  | 89% |  |  |  | 0%
C34-S254634 | 26003H | 3620J | LP1Y-CIPS-162002-06-1 | LP1Y-CIPS-162002-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 12.2413 | 5.89 | sq ft | 1.89 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-15 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254636 | 26003H | 3622J | LP1Y-CIPS-162002-06-3 | LP1Y-CIPS-162002-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 12 | 12 | 0 | 92.6888 | 37.78 | sq ft | 31.78 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Edgar Castaneda | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 67% |  |  |  | 67%
C34-S254637 | 26003H | 3623J | LP1Y-CIPS-162002-06-4 | LP1Y-CIPS-162002-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 4 | 4 | 0 | 29.6175 | 11.89 | sq ft | 10.39 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 50% |  |  |  | 0%
C34-S254638 | 26003H | 3624J | LP1Y-CIPS-162002-06-5 | LP1Y-CIPS-162002-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S254639 | 26003H | 3625J | LP1Y-CIPS-162002-07-1 | LP1Y-CIPS-162002-07 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 10 | 10 | 0 | 37.76 | 18.54 | sq ft | 10.04 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | [6 empty] | 80% |  |  |  | 0%
C34-S254640 | 26003H | 3626J | LP1Y-CIPS-162002-07-3 | LP1Y-CIPS-162002-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 14 | 14 | 0 | 32.275 | 15.48 | sq ft | 6.98 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 86% |  |  |  | 0%
C34-S254641 | 26003H | 3627J | LP1Y-CIPS-162002-07-2 | LP1Y-CIPS-162002-07 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162002 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162002 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 48.8738 | 23.46 | sq ft | 13.96 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  |  | 2026-04-22 |  | 83% |  |  |  | 0%
C34-S254644 | 26003H | 3630J | LP1Y-CIPS-162203-01-3 | LP1Y-CIPS-162203-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P 162203 | CIPS |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162203 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 23.4638 | 13.92 | sq ft | 6.92 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-04-29 |  | 71% |  |  |  | 0%
C34-S254645 | 26003H | 3631J | LP1Y-CIPS-162203-01-4 | LP1Y-CIPS-162203-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P 162203 | CIPS |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162203 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.575 | 7.06 | sq ft | 1.56 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145084 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254642 | 26003H | 3628J | LP1Y-CIPS-162203-01-1 | LP1Y-CIPS-162203-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P 162203 | CIPS |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162203 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 0 | 2 | 6.56 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-18 | 144989 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254643 | 26003H | 3629J | LP1Y-CIPS-162203-01-2 | LP1Y-CIPS-162203-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P 162203 | CIPS |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162203 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 14 | 14 | 0 | 17.3975 | 9.93 | sq ft | 3.93 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | [6 empty] | 86% |  |  |  | 0%
C34-S254648 | 26003H | 3634J | LP1Y-CIPS-162204-01-3 | LP1Y-CIPS-162204-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 12.2 | 5.88 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S254647 | 26003H | 3633J | LP1Y-CIPS-162204-01-2 | LP1Y-CIPS-162204-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 12 | 12 | 0 | 22.3175 | 13.64 | sq ft | 2.64 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | [6 empty] | 83% |  |  |  | 0%
C34-S254646 | 26003H | 3632J | LP1Y-CIPS-162204-01-1 | LP1Y-CIPS-162204-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-23 | 145311 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254649 | 26003H | 3635J | LP1Y-CIPS-162204-02-1 | LP1Y-CIPS-162204-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-25 | 145581 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254651 | 26003H | 3637J | LP1Y-CIPS-162204-02-3 | LP1Y-CIPS-162204-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6 | 6 | 0 | 29.2913 | 13.02 | sq ft | 7.52 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | [6 empty] | 67% |  |  |  | 0%
C34-S254652 | 26003H | 3638J | LP1Y-CIPS-162204-02-4 | LP1Y-CIPS-162204-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 2 | 2 | 0 | 17.7513 | 7.39 | sq ft | 5.89 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Guillen | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-29 | 145851
C34-S254650 | 26003H | 3636J | LP1Y-CIPS-162204-02-2 | LP1Y-CIPS-162204-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.1638 | 8.42 | sq ft | 2.92 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S254653 | 26003H | 3639J | LP1Y-CIPS-162204-02-5 | LP1Y-CIPS-162204-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS CIPS (315) P (108) 162204 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162204 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 14.75 | 14 | 0.75 | 62.5763 | 30.37 | sq ft | 17.87 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-24 | 2026-04-23 | 2026-04-24 | 2026-04-23 |  |  |  |  | 2026-04-24 |  | 75% |  |  |  | 0%
C34-S254656 | 26003H | 3642J | LP1Y-CIPS-162205-01-3 | LP1Y-CIPS-162205-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 4" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 3" | 316 SS | 7 | 2 | 5 | 26.0867 | 10.67 | sq ft | 3.67 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-23 | Passed | No | 2026-04-23 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254655 | 26003H | 3641J | LP1Y-CIPS-162205-01-2 | LP1Y-CIPS-162205-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 4" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 3" | 316 SS | 13 | 13 | 0 | 44.2514 | 14.14 | sq ft | 5.64 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  |  |  | 80% |  |  |  | 80%
C34-S254654 | 26003H | 3640J | LP1Y-CIPS-162205-01-1 | LP1Y-CIPS-162205-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 4" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 4" | 316 SS | 4 | 0 | 4 | 22.53 | 7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-24 | 2026-04-27 | Passed | No | 2026-04-27 | 2026-04-28 | 2026-04-28 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254657 | 26003H | 3643J | LP1Y-CIPS-162205-02-1 | LP1Y-CIPS-162205-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 3" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145083 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254658 | 26003H | 3644J | LP1Y-CIPS-162205-02-2 | LP1Y-CIPS-162205-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 3" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 3" | 316 SS | 8 | 8 | 0 | 24.2783 | 9 | sq ft | 3 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-21 | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145728
C34-S254659 | 26003H | 3645J | LP1Y-CIPS-162205-02-3 | LP1Y-CIPS-162205-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 3" SS CIPS (315) P (108) 162205 | CIPS |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162205 |  | TFS00E003YSPP |  | 315-CIPS | NONE | 3" | 316 SS | 15 | 12 | 3 | 52.5579 | 16.29 | sq ft | 3.79 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-23 | 2026-04-29 | 2026-04-23 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-23 | 2026-04-29 | 2026-04-29 | 100% | 2026-04-29 | 2026-04-28 | 2026-04-29 | 100% | 2026-04-29 | 145846
C34-S254660 | 26003H | 3646J | LP1Y-N2(100)-018025-02-1 | LP1Y-N2(100)-018025-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 018025 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018025 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144861 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254662 | 26003H | 3648J | LP1Y-N2(100)-018025-02-3 | LP1Y-N2(100)-018025-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 018025 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018025 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 52.5113 | 20.56 | sq ft | 19.06 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145603 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254661 | 26003H | 3647J | LP1Y-N2(100)-018025-02-2 | LP1Y-N2(100)-018025-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 018025 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018025 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 4 | 2 | 14.3138 | 6.76 | sq ft | 3.76 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-27 | 2026-04-30 | 2026-04-27 | 2026-04-24 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-27 | 2026-04-30 | 2026-04-30 | 100% | 2026-04-30 | 145944
C34-S254667 | 26003H | 3653J | LP1Y-N2(100)-180068-01-1 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 25.4238 | 10.96 | sq ft | 7.96 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Ramiro Gonzalez | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 75%
C34-S254664 | 26003H | 3650J | LP1Y-N2(100)-180068-01-4 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 50.71 | 21.21 | sq ft | 16.71 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 50% |  |  |  | 0%
C34-S254668 | 26003H | 3654J | LP1Y-N2(100)-180068-01-6 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 26.0463 | 11.79 | sq ft | 6.29 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Ramiro Gonzalez | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | [6 empty] | 67% |  |  |  | 0%
C34-S254663 | 26003H | 3649J | LP1Y-N2(100)-180068-01-5 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 17.4475 | 10.26 | sq ft | 4.26 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-05-04 | 2026-05-04 | 2026-05-04 |  |  |  | 80% |  |  |  | 80%
C34-S254666 | 26003H | 3652J | LP1Y-N2(100)-180068-01-2 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 87.175 | 33.69 | sq ft | 32.19 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144979 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254665 | 26003H | 3651J | LP1Y-N2(100)-180068-01-3 | LP1Y-N2(100)-180068-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 82.775 | 32.02 | sq ft | 30.52 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 144953 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254671 | 26003H | 3657J | LP1Y-N2(100)-180068-02-3 | LP1Y-N2(100)-180068-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 7 | 5 | 2 | 15.205 | 11.23 | sq ft | 3.73 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 |  |  |  |  | 2026-04-27 |  | 75% |  |  |  | 0%
C34-S254669 | 26003H | 3655J | LP1Y-N2(100)-180068-02-1 | LP1Y-N2(100)-180068-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 38.5688 | 15.94 | sq ft | 12.94 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145729
C34-S254670 | 26003H | 3656J | LP1Y-N2(100)-180068-02-2 | LP1Y-N2(100)-180068-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180068 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180068 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 18.26 | 8.92 | sq ft | 4.42 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 75% |  |  |  | 0%
C34-S254675 | 26003H | 3661J | LP1Y-N2(100)-180090-01-4 | LP1Y-N2(100)-180090-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180090 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144859 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254672 | 26003H | 3658J | LP1Y-N2(100)-180090-01-1 | LP1Y-N2(100)-180090-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180090 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144860 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254674 | 26003H | 3660J | LP1Y-N2(100)-180090-01-3 | LP1Y-N2(100)-180090-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180090 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 49.6225 | 23.11 | sq ft | 15.61 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 71% |  |  |  | 0%
C34-S254673 | 26003H | 3659J | LP1Y-N2(100)-180090-01-2 | LP1Y-N2(100)-180090-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2(100) (315) E 180090 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180090 |  | TFS00E003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.25 | 8 | 4.25 | 66.1675 | 30.09 | sq ft | 21.59 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 |  | 2026-04-23 |  | 88% |  |  |  | 25%
C34-S254676 | 26003H | 3662J | LP1Y-N2-180078-01-1 | LP1Y-N2-180078-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2 (315) E 180078 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180078 |  | TFS00E003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 10 | 1 | 20.4745 | 20.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254678 | 26003H | 3664J | LP1Y-N2-180078-01-3 | LP1Y-N2-180078-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS N2 (315) E 180078 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180078 |  | TFS00E003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 2 | 4.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Carlos Montoya | 2026-04-17 | 2026-04-16 | 2026-04-17 | 2026-04-16 |  |  |  | 2026-04-16 |  |  | 80% |  |  |  | 0%
C34-S254677 | 26003H | 3663J | LP1Y-N2-180078-01-2 | LP1Y-N2-180078-01 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS N2 (315) E 180078 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180078 |  | TFS00E003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.7525 | 10.66 | sq ft | 1.16 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Edgar Castaneda | 2026-04-16 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% | 2026-04-28 | 2026-04-28 | 2026-04-28 | 100% | 2026-04-28 | 145727
C34-S254681 | 26003H | 3667C | LP1Y-PSC-850002-02-3 | LP1Y-PSC-850002-02 | 0 | N | PRI-1-3 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 3" CS PSC (2) (101) 850002 | PSC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850002 |  | TFS00E003YSPP |  | 2-PSC | P-4 | 3" | CS | 3 | 3 | 0 | 60.5333 | 9.67 | sq ft | 6.67 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254682 | 26003H | 3668C | LP1Y-PSC-850002-02-4 | LP1Y-PSC-850002-02 | 0 | N | PRI-1-3 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 3" CS PSC (2) (101) 850002 | PSC |  | 101 | 212 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-850002 |  | TFS00E003YSPP |  | 2-PSC | P-4 | 3" | CS | 2 | 2 | 0 | 7.8 | 5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-23 | 2026-04-24 | Passed | No | 2026-04-24 |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254680 | 26003H | 3666C | LP1Y-PSC-850002-02-2 | LP1Y-PSC-850002-02 | 0 | N | PRI-1-3 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 3" CS PSC (2) (101) 850002 | PSC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850002 |  | TFS00E003YSPP |  | 2-PSC | P-4 | 3" | CS | 9 | 6 | 3 | 40.6835 | 17.86 | sq ft | 0.86 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254679 | 26003H | 3665C | LP1Y-PSC-850002-02-1 | LP1Y-PSC-850002-02 | 0 | N | PRI-1-3 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 3" CS PSC (2) (101) 850002 | PSC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850002 |  | TFS00E003YSPP |  | 2-PSC | P-4 | 3" | CS | 3 | 3 | 0 | 16.9483 | 3.92 | sq ft | 0.92 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254683 | 26003H | 3669J | LP1Y-PV-850003-02-1 | LP1Y-PV-850003-02 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS PV (315) (108) 850003 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850003 |  | TFS00E003YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144858 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254684 | 26003H | 3670J | LP1Y-PV-850003-02-2 | LP1Y-PV-850003-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PV (315) (108) 850003 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850003 |  | TFS00E003YSPP |  | 315-PV | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 16.4375 | 10.51 | sq ft | 2.51 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-15 | 2026-04-16 | 2026-04-15 |  |  |  | 2026-04-15 |  |  | 75% |  |  |  | 0%
C34-S254685 | 26003H | 3671J | LP1Y-PV-850003-02-3 | LP1Y-PV-850003-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PV (315) (108) 850003 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850003 |  | TFS00E003YSPP |  | 315-PV | NONE | 2" | 316 SS | 2 | 2 | 0 | 23.3238 | 10.09 | sq ft | 6.09 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% |  |  |  | 0%
C34-S254689 | 26003H | 3675J | LP1Y-PVP-162213-01-4 | LP1Y-PVP-162213-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS PVP (315) P (108) 162213 | PVP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162213 |  | TFS00E003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 14.7713 | 8.85 | sq ft | 0.35 | ft | 2026-02-13 |  |  |  |  | 2026-04-10 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145604 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254686 | 26003H | 3672J | LP1Y-PVP-162213-01-1 | LP1Y-PVP-162213-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS PVP (315) P (108) 162213 | PVP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162213 |  | TFS00E003YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144984 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254688 | 26003H | 3674J | LP1Y-PVP-162213-01-3 | LP1Y-PVP-162213-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PVP (315) P (108) 162213 | PVP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162213 |  | TFS00E003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.6888 | 7.48 | sq ft | 1.98 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Carlos Montoya | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 |  |  |  | 2026-04-15 | 2026-04-15 | 2026-04-15 | 100% |  |  |  | 0%
C34-S254687 | 26003H | 3673J | LP1Y-PVP-162213-01-2 | LP1Y-PVP-162213-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PVP (315) P (108) 162213 | PVP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162213 |  | TFS00E003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 23.815 | 9.69 | sq ft | 8.19 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S254692 | 26003H | 3678J | LP1Y-PWP-850051-06-3 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 21.0675 | 12.34 | sq ft | 5.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-10 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 50%
C34-S254696 | 26003H | 3682J | LP1Y-PWP-850051-06-7 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 1 | 1 | 0 | 2.98 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254695 | 26003H | 3681J | LP1Y-PWP-850051-06-6 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 25.2613 | 13.27 | sq ft | 7.77 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Carlos Montoya | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 60% |  |  |  | 0%
C34-S254693 | 26003H | 3679J | LP1Y-PWP-850051-06-4 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 11.5 | 10 | 1.5 | 38.099 | 17.1 | sq ft | 12.6 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-29 | 2026-04-27 | 2026-04-29 | 100% | 2026-04-30 | 2026-04-27 | 2026-04-30 | 100%
C34-S254694 | 26003H | 3680J | LP1Y-PWP-850051-06-5 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 36.5475 | 15.84 | sq ft | 11.34 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Omar Puente | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 |  |  |  | 60% |  |  |  | 40%
C34-S254690 | 26003H | 3676J | LP1Y-PWP-850051-06-1 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 53.4325 | 22.24 | sq ft | 17.74 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-16 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 80% |  |  |  | 60%
C34-S254691 | 26003H | 3677J | LP1Y-PWP-850051-06-2 | LP1Y-PWP-850051-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS PWP (315) (108) 850051 | PWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850051 |  | TFS00E003YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 13.4475 | 6.43 | sq ft | 3.43 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | N/A | N/A | Ramiro Gonzalez | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S254697 | 26003H | 3683J | LP1Y-RV-162110-01-1 | LP1Y-RV-162110-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS RV (315) P (108) 162110 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162110 |  | TFS00E003YSPP |  | 315-RV | NONE | 1" | 316 SS | 2 | 2 | 0 | 10.407 | 8.68 | sq ft | 7.18 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | [6 empty] | 50% |  |  |  | 0%
C34-S254698 | 26003H | 3684J | LP1Y-RV-162110-01-2 | LP1Y-RV-162110-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS RV (315) P (108) 162110 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162110 |  | TFS00E003YSPP |  | 315-RV | NONE | 1" | 316 SS | 4 | 4 | 0 | 4.7686 | 8.3 | sq ft | 1.3 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S254699 | 26003H | 3685C | LP1Y-S(130)-018032-02-1 | LP1Y-S(130)-018032-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 8" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 8" | CS | 20 | 20 | 0 | 181.6574 | 21.88 | sq ft | 5.49 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254703 | 26003H | 3689C | LP1Y-S(130)-018032-02-5 | LP1Y-S(130)-018032-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P013 | 2026-05-25 |  | LP1Y 8" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 8" | CS | 0 | 0 | 0 | 42 | 6.9 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-16 | 2026-04-16 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 0% |  |  |  | 0% | 2026-04-24 | 144903, 145590
C34-S254700 | 26003H | 3686C | LP1Y-S(130)-018032-02-2 | LP1Y-S(130)-018032-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 8" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 6" | CS | 45 | 36 | 9 | 206.2505 | 48.04 | sq ft | 5.8 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254701 | 26003H | 3687C | LP1Y-S(130)-018032-02-3 | LP1Y-S(130)-018032-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 8" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 6" | CS | 29 | 24 | 5 | 167.9417 | 22.2 | sq ft | 5.17 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254702 | 26003H | 3688C | LP1Y-S(130)-018032-02-4 | LP1Y-S(130)-018032-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 8" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 1" | CS | 8.5 | 0 | 8.5 | 34.8276 | 31.01 | sq ft | 4.51 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254707 | 26003H | 3693C | LP1Y-S(130)-018032-03-2 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 27.0391 | 9.53 | sq ft | 6.53 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254704 | 26003H | 3690C | LP1Y-S(130)-018032-03-1 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 25.043 | 8.98 | sq ft | 5.98 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254708 | 26003H | 3694C | LP1Y-S(130)-018032-03-5 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 8 | 2 | 47.8016 | 16.28 | sq ft | 11.78 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254710 | 26003H | 3696C | LP1Y-S(130)-018032-03-7 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 20.4995 | 7.74 | sq ft | 4.74 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254705 | 26003H | 3691C | LP1Y-S(130)-018032-03-3 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 8.75 | 8 | 0.75 | 42.4933 | 24.14 | sq ft | 6.14 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254706 | 26003H | 3692C | LP1Y-S(130)-018032-03-4 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 33.2641 | 11.53 | sq ft | 7.03 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254709 | 26003H | 3695C | LP1Y-S(130)-018032-03-6 | LP1Y-S(130)-018032-03 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 90.3596 | 25.82 | sq ft | 24.32 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254711 | 26003H | 3697C | LP1Y-S(130)-018032-04-1 | LP1Y-S(130)-018032-04 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 74.1818 | 21.39 | sq ft | 19.89 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254712 | 26003H | 3698C | LP1Y-S(130)-018032-04-2 | LP1Y-S(130)-018032-04 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 147.825 | 40.5 | sq ft | 40.5 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254713 | 26003H | 3699C | LP1Y-S(130)-018032-04-3 | LP1Y-S(130)-018032-04 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 113.8375 | 32.25 | sq ft | 30.75 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254714 | 26003H | 3700C | LP1Y-S(130)-018032-05-1 | LP1Y-S(130)-018032-05 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 4.6417 | 2.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254715 | 26003H | 3701C | LP1Y-S(130)-018032-05-2 | LP1Y-S(130)-018032-05 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 76.6721 | 22.07 | sq ft | 20.57 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254718 | 26003H | 3704C | LP1Y-S(130)-018032-05-5 | LP1Y-S(130)-018032-05 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 38.4019 | 25.44 | sq ft | 2.94 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254716 | 26003H | 3702C | LP1Y-S(130)-018032-05-3 | LP1Y-S(130)-018032-05 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 4 | 4 | 0 | 83.3828 | 23.91 | sq ft | 22.41 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254717 | 26003H | 3703C | LP1Y-S(130)-018032-05-4 | LP1Y-S(130)-018032-05 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" CS S(130) (2) (103) 018032 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018032 |  | TFS00E003YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 23.1854 | 7.71 | sq ft | 4.71 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254720 | 26003H | 3706J | LP1Y-S(130)-165625-01-2 | LP1Y-S(130)-165625-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS S(130) (315) (103) 165625 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165625 |  | TFS00E003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 5.9108 | 8.22 | sq ft | 3.72 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | [6 empty] | 80% |  |  |  | 0%
C34-S254721 | 26003H | 3707J | LP1Y-S(130)-165625-01-3 | LP1Y-S(130)-165625-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS S(130) (315) (103) 165625 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165625 |  | TFS00E003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.125 | 2.33 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-21 | 2026-04-21 | N/A | N/A | Carlos Montoya | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S254719 | 26003H | 3705J | LP1Y-S(130)-165625-01-1 | LP1Y-S(130)-165625-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 1" SS S(130) (315) (103) 165625 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165625 |  | TFS00E003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Henrique Barahona | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S254724 | 26003H | 3710J | LP1Y-SRACNP-108104-11-3 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 20.25 | 18 | 2.25 | 80.8263 | 40.87 | sq ft | 23.87 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 |  | 2026-04-24 |  | 2026-04-23 |  | 75% |  |  |  | 42%
C34-S254725 | 26003H | 3711J | LP1Y-SRACNP-108104-11-4 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.5 | 4 | 6.5 | 34.15 | 20.92 | sq ft | 7.42 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-27 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  | 2026-04-30 | 2026-04-30 | 2026-04-24 |  |  | 89% |  |  |  | 11%
C34-S254723 | 26003H | 3709J | LP1Y-SRACNP-108104-11-2 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 26.7025 | 10.11 | sq ft | 10.11 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-14 | 2026-04-14 | N/A | N/A | NO FITTER | 2026-04-20 | [9 empty] | 100% |  |  |  | 100% | 2026-04-20 | 145028, 145049 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254722 | 26003H | 3708J | LP1Y-SRACNP-108104-11-1 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-16 | 144857 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254726 | 26003H | 3712J | LP1Y-SRACNP-108104-11-5 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 39.205 | 20.77 | sq ft | 8.77 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | N/A | N/A | Roberto Tobias (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  |  | 2026-04-17 |  | 80% |  |  |  | 0%
C34-S254727 | 26003H | 3713J | LP1Y-SRACNP-108104-11-6 | LP1Y-SRACNP-108104-11 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E003YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.31 | 6.38 | sq ft | 3.38 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-14 | N/A | N/A | Roberto Tobias (WF) | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% | 2026-04-18 | 144982 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254728 | 26003H | 3714J | LP1Y-STORMP-165624-02-1 | LP1Y-STORMP-165624-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 61.8338 | 24.09 | sq ft | 22.59 | ft | 2026-02-13 |  |  |  |  | 2026-04-10 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254730 | 26003H | 3716J | LP1Y-STORMP-165624-02-3 | LP1Y-STORMP-165624-02 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S254729 | 26003H | 3715J | LP1Y-STORMP-165624-02-2 | LP1Y-STORMP-165624-02 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-22 | 2026-04-22 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254732 | 26003H | 3718J | LP1Y-STORMP-165624-03-2 | LP1Y-STORMP-165624-03 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 40.0875 | 20.14 | sq ft | 10.64 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-29 | 2026-04-29 | 2026-04-29 |  | 2026-04-23 |  | 83% |  | 2026-04-29 |  | 83%
C34-S254733 | 26003H | 3719J | LP1Y-STORMP-165624-03-3 | LP1Y-STORMP-165624-03 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 59.9775 | 24.05 | sq ft | 21.05 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-14 | 2026-04-15 | N/A | N/A | Carlos Montoya | 2026-04-17 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 67% |  |  |  | 0%
C34-S254731 | 26003H | 3717J | LP1Y-STORMP-165624-03-1 | LP1Y-STORMP-165624-03 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS STORMP (315) (108) 165624 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165624 |  | TFS00E003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.0475 | 9.14 | sq ft | 3.64 | ft | 2026-02-13 |  |  |  |  | 2026-04-10 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-16 | N/A | N/A | Ramiro Gonzalez | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 |  |  |  | 2026-04-17 | 2026-04-17 | 2026-04-17 | 100% |  |  |  | 0%
C34-S254735 | 26003H | 3721J | LP1Y-SW-165622-01-2 | LP1Y-SW-165622-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS SW (315) 165622 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165622 |  | TFS00E003YSPP |  | 315-SW | NONE | 2" | 316 SS | 8 | 6 | 2 | 27.3438 | 11.71 | sq ft | 8.21 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-23 | 2026-05-01 | 2026-04-23 | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-04-23 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-04-30 | 2026-05-01 | 100% | 2026-05-02 | 146035
C34-S254734 | 26003H | 3720J | LP1Y-SW-165622-01-1 | LP1Y-SW-165622-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SW (315) 165622 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165622 |  | TFS00E003YSPP |  | 315-SW | NONE | 2" | 316 SS | 6.5 | 6.5 | 0 | 14.3729 | 11.2 | sq ft | 3.7 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | [6 empty] | 75% |  |  |  | 0%
C34-S254741 | 26003H | 3727J | LP1Y-SWP-165623-02-6 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-23 | 2026-04-23 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% |  |  |  | 0%
C34-S254737 | 26003H | 3723J | LP1Y-SWP-165623-02-2 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 25.7188 | 14.69 | sq ft | 5.19 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Omar Puente | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 100% | 2026-04-24 | 2026-04-24 | 2026-04-24 | 100% | 2026-04-27 | 145599 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254740 | 26003H | 3726J | LP1Y-SWP-165623-02-5 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 105.6 | 40 | sq ft | 40 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | N/A | N/A | 2026-04-23 | 2026-04-23 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254739 | 26003H | 3725J | LP1Y-SWP-165623-02-4 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | 2026-04-16 | 2026-04-20 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8 | 8 | 0 | 64.8588 | 25.9 | sq ft | 22.9 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-20 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 75% |  |  |  | 50%
C34-S254736 | 26003H | 3722J | LP1Y-SWP-165623-02-1 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 12.1725 | 5.86 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-15 | 2026-04-15 | N/A | N/A | Carlos Montoya | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 |  |  |  | 2026-04-16 | 2026-04-16 | 2026-04-16 | 100% |  |  |  | 0%
C34-S254738 | 26003H | 3724J | LP1Y-SWP-165623-02-3 | LP1Y-SWP-165623-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 61.7238 | 24.05 | sq ft | 22.55 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 50% |  |  |  | 0%
C34-S254742 | 26003H | 3728J | LP1Y-SWP-165623-03-1 | LP1Y-SWP-165623-03 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 145005 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S254743 | 26003H | 3729J | LP1Y-SWP-165623-03-2 | LP1Y-SWP-165623-03 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S254744 | 26003H | 3730J | LP1Y-SWP-165623-03-3 | LP1Y-SWP-165623-03 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 165623 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-165623 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 18 | 12.5 | 5.5 | 32.6183 | 30.81 | sq ft | 6.81 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 0%
C34-S254750 | 26003H | 3736J | LP1Y-SWP-850004-01-6 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | [5 empty] | Shipped | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 1" | 316 SS | 1 | 1 | 0 | 2.98 | 6 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-14 | Jacob Perez | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | 2026-04-21 | 145082 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S254745 | 26003H | 3731J | LP1Y-SWP-850004-01-1 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 16.25 | 12 | 4.25 | 33.4725 | 20.7 | sq ft | 9.2 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Edgar Castaneda | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-28 | 2026-04-28 | 2026-04-28 |  |  |  | 60% |  |  |  | 60%
C34-S254749 | 26003H | 3735J | LP1Y-SWP-850004-01-5 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 25.2613 | 13.27 | sq ft | 7.77 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  | 60% |  |  |  | 60%
C34-S254748 | 26003H | 3734J | LP1Y-SWP-850004-01-4 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8 | 8 | 0 | 22.715 | 10.6 | sq ft | 6.1 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Carlos Montoya | 2026-04-21 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-05-02 | 2026-05-02 | 2026-05-02 |  |  |  | 75% |  |  |  | 50%
C34-S254747 | 26003H | 3733J | LP1Y-SWP-850004-01-3 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 7.5 | 6 | 1.5 | 26.5631 | 12.31 | sq ft | 9.31 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Omar Puente | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-27 | 2026-04-21 | 2026-04-27 | 100% | 2026-04-27 | 2026-04-24 | 2026-04-27 | 100% | 2026-04-28 | 145679
C34-S254746 | 26003H | 3732J | LP1Y-SWP-850004-01-2 | LP1Y-SWP-850004-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 32.0925 | 12.82 | sq ft | 11.32 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-13 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Roberto Tobias (WF) | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% |  |  |  | 0%
C34-S254751 | 26003H | 3737J | LP1Y-SWP-850004-02-1 | LP1Y-SWP-850004-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.5388 | 13.86 | sq ft | 9.36 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-17 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-17 | 2026-04-17 | 2026-04-17 | 2026-04-17 | [6 empty] | 80% |  |  |  | 0%
C34-S254752 | 26003H | 3738J | LP1Y-SWP-850004-02-2 | LP1Y-SWP-850004-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 30.5563 | 13.58 | sq ft | 10.58 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-14 | 2026-04-15 | N/A | N/A | Ramiro Gonzalez | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | [6 empty] | 67% |  |  |  | 0%
C34-S254753 | 26003H | 3739J | LP1Y-SWP-850004-02-3 | LP1Y-SWP-850004-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850004 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850004 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 38.72 | 15.33 | sq ft | 13.83 | ft | 2026-02-13 | CD: 2026-04-10; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | N/A | N/A | Omar Puente | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% |  |  |  | 50%
C34-S254757 | 26003H | 3743J | LP1Y-SWP-850007-01-4 | LP1Y-SWP-850007-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850007 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850007 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.25 | 10.75 | 3.5 | 42.3175 | 24.64 | sq ft | 10.64 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | N/A | N/A | Roberto Tobias (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  | 2026-04-24 |  | 2026-04-24 |  | 78% |  |  |  | 22%
C34-S256314 | 26003H | 3743JA | LP1Y-SWP-850007-01-5 | LP1Y-SWP-850007-01 | 0 | N | PRI-1-3 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P013 |  | 0 | LP1Y 2" SS SWP (315) (108) 850007 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850007 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254756 | 26003H | 3742J | LP1Y-SWP-850007-01-3 | LP1Y-SWP-850007-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850007 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850007 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.0465 | 10 | 4.0465 | 52.9977 | 22.8 | sq ft | 17.96 | ft | 2026-02-13 |  |  |  |  | 2026-04-13 | Jacob Perez | 2026-04-13 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254755 | 26003H | 3741J | LP1Y-SWP-850007-01-2 | LP1Y-SWP-850007-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850007 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850007 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8 | 6 | 2 | 89.9388 | 34.73 | sq ft | 33.23 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-21 | N/A | N/A | Ramiro Gonzalez | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-24 | 2026-04-29 | 2026-04-24 |  | 2026-04-21 |  | 75% |  | 2026-04-29 |  | 50%
C34-S254754 | 26003H | 3740J | LP1Y-SWP-850007-01-1 | LP1Y-SWP-850007-01 | 0 | N | PRI-1-3 | 2026-04-22 | 2026-04-22 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS SWP (315) (108) 850007 | SWP |  | 108 | 104 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850007 |  | TFS00E003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 72.4213 | 27.43 | sq ft | 27.43 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-22 | 2026-04-22 | Passed | No | 2026-04-22 | N/A | N/A | 2026-04-24 | 2026-04-24 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254760 | 26003H | 3746C | LP1Y-TWRP-850005-02-3 | LP1Y-TWRP-850005-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P013 | 2026-05-25 |  | LP1Y 12" CS TWRP (6) (108) 850005 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-850005 |  | TFS00E003YSPP |  | 6-TWRP | P-4 | 10" | CS | 0 | 0 | 0 | 54 | 8.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-16 | 2026-04-16 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 0% |  |  |  | 0% | 2026-04-24 | 144902, 145591
C34-S254759 | 26003H | 3745C | LP1Y-TWRP-850005-02-2 | LP1Y-TWRP-850005-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 12" CS TWRP (6) (108) 850005 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850005 |  | TFS00E003YSPP |  | 6-TWRP | P-4 | 10" | CS | 10 | 10 | 0 | 141.7067 | 14.98 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254758 | 26003H | 3744C | LP1Y-TWRP-850005-02-1 | LP1Y-TWRP-850005-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 12" CS TWRP (6) (108) 850005 | TWRP |  | 108 | 96.8 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-850005 |  | TFS00E003YSPP |  | 6-TWRP | P-4 | 12" | CS | 47.75 | 44 | 3.75 | 391.3185 | 46.84 | sq ft | 10.8 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254763 | 26003H | 3749C | LP1Y-TWSP-017018-02-3 | LP1Y-TWSP-017018-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Passed Production Test | P013 | 2026-05-25 |  | LP1Y 12" CS TWSP (6) (108) 017018 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Weedy |  |  | LP1Y-017018 |  | TFS00E003YSPP |  | 6-TWSP | P-4 | 10" | CS | 0 | 0 | 0 | 54 | 8.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 | 2026-05-04 | Passed | No |  | 2026-04-16 | 2026-04-16 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 0% |  |  |  | 0% | 2026-04-24 | 144905, 145592
C34-S254762 | 26003H | 3748C | LP1Y-TWSP-017018-02-2 | LP1Y-TWSP-017018-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 12" CS TWSP (6) (108) 017018 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017018 |  | TFS00E003YSPP |  | 6-TWSP | P-4 | 10" | CS | 10 | 10 | 0 | 101.2267 | 12.08 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254761 | 26003H | 3747C | LP1Y-TWSP-017018-02-1 | LP1Y-TWSP-017018-02 | 0 | N | PRI-1-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 12" CS TWSP (6) (108) 017018 | TWSP |  | 108 | 84.92 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017018 |  | TFS00E003YSPP |  | 6-TWSP | P-4 | 12" | CS | 47.75 | 44 | 3.75 | 425.7912 | 48.09 | sq ft | 10.15 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254767 | 26003H | 3753J | LP1Y-WFO-017045-06-4 | LP1Y-WFO-017045-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.9213 | 8.68 | sq ft | 8.68 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254766 | 26003H | 3752J | LP1Y-WFO-017045-06-3 | LP1Y-WFO-017045-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 44.3025 | 16.78 | sq ft | 16.78 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254768 | 26003H | 3754J | LP1Y-WFO-017045-06-5 | LP1Y-WFO-017045-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8975 | 0.72 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254764 | 26003H | 3750J | LP1Y-WFO-017045-06-1 | LP1Y-WFO-017045-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254765 | 26003H | 3751J | LP1Y-WFO-017045-06-2 | LP1Y-WFO-017045-06 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.2488 | 1.61 | sq ft | 1.61 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254772 | 26003H | 3758J | LP1Y-WFO-017045-07-4 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254773 | 26003H | 3759J | LP1Y-WFO-017045-07-5 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 29.9888 | 11.36 | sq ft | 11.36 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254774 | 26003H | 3760J | LP1Y-WFO-017045-07-7 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.9425 | 1.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254775 | 26003H | 3761J | LP1Y-WFO-017045-07-8 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7575 | 1.8 | sq ft | 1.8 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254770 | 26003H | 3756J | LP1Y-WFO-017045-07-2 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254771 | 26003H | 3757J | LP1Y-WFO-017045-07-3 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254777 | 26003H | 3763J | LP1Y-WFO-017045-07-10 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254776 | 26003H | 3762J | LP1Y-WFO-017045-07-9 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.4975 | 3.22 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-05-02 | 2026-05-02 | N/A | N/A | NO FITTER | 2026-04-29 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146034
C34-S254778 | 26003H | 3764J | LP1Y-WFO-017045-07-6 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 47.3413 | 17.93 | sq ft | 17.93 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 0% |  |  |  | 0%
C34-S254769 | 26003H | 3755J | LP1Y-WFO-017045-07-1 | LP1Y-WFO-017045-07 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 38.445 | 14.56 | sq ft | 14.56 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254780 | 26003H | 3766J | LP1Y-WFO-017045-08-2 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.7925 | 2.57 | sq ft | 2.57 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254781 | 26003H | 3767J | LP1Y-WFO-017045-08-3 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.0813 | 6.85 | sq ft | 6.85 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254782 | 26003H | 3768J | LP1Y-WFO-017045-08-4 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254783 | 26003H | 3769J | LP1Y-WFO-017045-08-5 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.18 | 1.58 | sq ft | 1.58 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254779 | 26003H | 3765J | LP1Y-WFO-017045-08-1 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.74 | 1.42 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254784 | 26003H | 3770J | LP1Y-WFO-017045-08-6 | LP1Y-WFO-017045-08 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 017045 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017045 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-01 | 145994
C34-S254787 | 26003H | 3773J | LP1Y-WFO-017068-04-3 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2 | 2 | 0 | 2.06 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254788 | 26003H | 3774J | LP1Y-WFO-017068-04-4 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2 | 2 | 0 | 2.06 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254791 | 26003H | 3777J | LP1Y-WFO-017068-04-7 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.1075 | 1.18 | sq ft | 1.18 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254790 | 26003H | 3776J | LP1Y-WFO-017068-04-6 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 1 1/2" | 316 SS | 2 | 2 | 0 | 5.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-16 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254792 | 26003H | 3778J | LP1Y-WFO-017068-04-8 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.8463 | 1.08 | sq ft | 1.08 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254785 | 26003H | 3771J | LP1Y-WFO-017068-04-1 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 28.4825 | 11.55 | sq ft | 11.55 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-17 | Passed | No | 2026-04-17 | N/A | N/A | 2026-04-24 | 2026-04-24 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 67% |  |  |  | 67%
C34-S254786 | 26003H | 3772J | LP1Y-WFO-017068-04-2 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.09 | 0.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254789 | 26003H | 3775J | LP1Y-WFO-017068-04-5 | LP1Y-WFO-017068-04 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) (108) 017068 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017068 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.335 | 2.02 | sq ft | 2.02 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254793 | 26003H | 3779J | LP1Y-WFO-162210-02-1 | LP1Y-WFO-162210-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 162210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162210 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Roberto Tobias (WF) | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254795 | 26003H | 3781J | LP1Y-WFO-162210-02-3 | LP1Y-WFO-162210-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 162210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162210 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-23 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146015
C34-S254794 | 26003H | 3780J | LP1Y-WFO-162210-02-2 | LP1Y-WFO-162210-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 162210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162210 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-23 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% | 2026-05-02 | 146018
C34-S254797 | 26003H | 3783J | LP1Y-WFO-162210-02-5 | LP1Y-WFO-162210-02 | 0 | N | PRI-1-3 | [5 empty] | Passed Visual Inspection | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 162210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162210 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-29 | [9 empty] | 100% |  |  |  | 100% | 2026-05-01 | 145995
C34-S254796 | 26003H | 3782J | LP1Y-WFO-162210-02-4 | LP1Y-WFO-162210-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WFO (36) 162210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162210 |  | TFS00E003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.1938 | 1.59 | sq ft | 1.59 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254809 | 26003H | 3795J | LP1Y-WPC-017046-02-12 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 3.5575 | 2.14 | sq ft | 1.14 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 50% |  |  |  | 50%
C34-S254807 | 26003H | 3793J | LP1Y-WPC-017046-02-10 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.6788 | 2.15 | sq ft | 2.15 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254808 | 26003H | 3794J | LP1Y-WPC-017046-02-11 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254804 | 26003H | 3790J | LP1Y-WPC-017046-02-7 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.9113 | 0.72 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254803 | 26003H | 3789J | LP1Y-WPC-017046-02-6 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.2513 | 4.64 | sq ft | 4.64 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254802 | 26003H | 3788J | LP1Y-WPC-017046-02-5 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 44.88 | 17 | sq ft | 17 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254801 | 26003H | 3787J | LP1Y-WPC-017046-02-4 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A |  |  | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254798 | 26003H | 3784J | LP1Y-WPC-017046-02-1 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254799 | 26003H | 3785J | LP1Y-WPC-017046-02-2 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254800 | 26003H | 3786J | LP1Y-WPC-017046-02-3 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-05-01 | 2026-05-01 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254806 | 26003H | 3792J | LP1Y-WPC-017046-02-9 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.9813 | 6.43 | sq ft | 6.43 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254805 | 26003H | 3791J | LP1Y-WPC-017046-02-8 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.7863 | 3.33 | sq ft | 3.33 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254810 | 26003H | 3796J | LP1Y-WPC-017046-02-13 | LP1Y-WPC-017046-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 017046 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017046 |  | TFS00E003YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian | 2026-04-14 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254818 | 26003H | 3804J | LP1Y-WPC-194020-01-16 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 21.9304 | 9.27 | sq ft | 9.27 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-17 | Passed | No | 2026-04-17 | N/A | N/A | 2026-04-24 | 2026-04-24 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 67% |  |  |  | 67%
C34-S254823 | 26003H | 3809J | LP1Y-WPC-194020-01-5 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.585 | 0.98 | sq ft | 0.98 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254825 | 26003H | 3811J | LP1Y-WPC-194020-01-7 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.95 | 1.88 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254819 | 26003H | 3805J | LP1Y-WPC-194020-01-17 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.5 | 2 | 4.5 | 8.71 | 7.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254826 | 26003H | 3812J | LP1Y-WPC-194020-01-8 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.9813 | 6.43 | sq ft | 6.43 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254827 | 26003H | 3813J | LP1Y-WPC-194020-01-9 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.6925 | 2.16 | sq ft | 2.16 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254821 | 26003H | 3807J | LP1Y-WPC-194020-01-3 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 3.6813 | 2.18 | sq ft | 1.18 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 50% |  |  |  | 50%
C34-S254817 | 26003H | 3803J | LP1Y-WPC-194020-01-15 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.5713 | 0.97 | sq ft | 0.97 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254820 | 26003H | 3806J | LP1Y-WPC-194020-01-2 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.9463 | 5.66 | sq ft | 5.66 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254824 | 26003H | 3810J | LP1Y-WPC-194020-01-6 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2963 | 0.87 | sq ft | 0.87 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254822 | 26003H | 3808J | LP1Y-WPC-194020-01-4 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.6888 | 1.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254811 | 26003H | 3797J | LP1Y-WPC-194020-01-1 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 45.4713 | 17.22 | sq ft | 17.22 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254812 | 26003H | 3798J | LP1Y-WPC-194020-01-10 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 5.5 | 0 | 5.5 | 3.42 | 2.08 | sq ft | 1.08 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-16 | 2026-04-17 | Passed | No | 2026-04-17 | 2026-04-22 | 2026-04-22 | 2026-04-24 | 2026-04-24 | N/A | N/A |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 50% |  |  |  | 50%
C34-S254814 | 26003H | 3800J | LP1Y-WPC-194020-01-12 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254813 | 26003H | 3799J | LP1Y-WPC-194020-01-11 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | 2026-04-22 |  | active | client | cancelled | On Hold/Cancelled | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254816 | 26003H | 3802J | LP1Y-WPC-194020-01-14 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1725 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254815 | 26003H | 3801J | LP1Y-WPC-194020-01-13 | LP1Y-WPC-194020-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194020 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194020 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; DD: 2026-04-14; DL: George Allahverdian | 2026-04-14 | 2026-04-14 | Passed | No | 2026-04-14 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254831 | 26003H | 3817J | LP1Y-WPC-194025-01-4 | LP1Y-WPC-194025-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.2538 | 11.84 | sq ft | 11.84 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254830 | 26003H | 3816J | LP1Y-WPC-194025-01-3 | LP1Y-WPC-194025-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.1663 | 5.74 | sq ft | 5.74 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254829 | 26003H | 3815J | LP1Y-WPC-194025-01-2 | LP1Y-WPC-194025-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.685 | 1.4 | sq ft | 1.4 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254828 | 26003H | 3814J | LP1Y-WPC-194025-01-1 | LP1Y-WPC-194025-01 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.0925 | 3.82 | sq ft | 3.82 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254834 | 26003H | 3820J | LP1Y-WPC-194025-02-3 | LP1Y-WPC-194025-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-28 | Passed | No | 2026-04-28 | 2026-04-30 | 2026-04-30 | N/A | N/A | N/A | N/A | Omar Puente | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 |  |  |  | 2026-05-01 | 2026-05-01 | 2026-05-01 | 100% |  |  |  | 0%
C34-S254835 | 26003H | 3821J | LP1Y-WPC-194025-02-4 | LP1Y-WPC-194025-02 | 0 | N | PRI-1-3 | 2026-04-14 | 2026-04-16 | released |  |  | Released to Production | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 11.25 | 0 | 11.25 | 21.7375 | 18.21 | sq ft | 7.21 | ft | 2026-02-13 |  |  |  |  | 2026-04-11 | Jacob Perez | 2026-04-12 | George Allahverdian | 2026-04-13 | Jacob Perez | 2026-04-13 | Jacob Perez | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S254832 | 26003H | 3818J | LP1Y-WPC-194025-02-1 | LP1Y-WPC-194025-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.3963 | 1.29 | sq ft | 1.29 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-30 | 2026-04-30 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S254833 | 26003H | 3819J | LP1Y-WPC-194025-02-2 | LP1Y-WPC-194025-02 | 0 | N | PRI-1-3 | [5 empty] | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS WPC (36) (108) 194025 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194025 |  | TFS00E003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.0975 | 1.55 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-04-11; CL: Jacob Perez; DD: 2026-04-12; DL: George Allahverdian | 2026-04-13 | 2026-04-13 | Passed | No | 2026-04-13 | N/A | N/A | 2026-04-29 | 2026-04-29 | N/A | N/A | NO FITTER | 2026-04-23 | [9 empty] | 0% |  |  |  | 0%
C34-S255102 | 26003H | 3823J | LP1Y-DCM-177201-01-2 | LP1Y-DCM-177201-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255103 | 26003H | 3824J | LP1Y-DCM-177201-01-3 | LP1Y-DCM-177201-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 19 | 17 | 2 | 313.1138 | 39.77 | sq ft | 5.27 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255104 | 26003H | 3825J | LP1Y-DCM-177201-01-4 | LP1Y-DCM-177201-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 9 | 9 | 0 | 105.3007 | 24.32 | sq ft | 22.82 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255101 | 26003H | 3822J | LP1Y-DCM-177201-01-1 | LP1Y-DCM-177201-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255106 | 26003H | 3827J | LP1Y-DCM-177201-02-2 | LP1Y-DCM-177201-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 6 | 6 | 0 | 124.7624 | 29.99 | sq ft | 28.49 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255105 | 26003H | 3826J | LP1Y-DCM-177201-02-1 | LP1Y-DCM-177201-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P (108) 177201 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 31 | 30 | 1 | 298.7576 | 33.76 | sq ft | 3.76 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255107 | 26003H | 3828J | LP1Y-DCM-177201-03-1 | LP1Y-DCM-177201-03 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS DCM (315) P 177201 | DCM |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177201 |  | TFS00E016YSPP |  | 315-DCM | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.0773 | 27.05 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255108 | 26003H | 3829J | LP1Y-DCM-177202-04-1 | LP1Y-DCM-177202-04 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 12 | 12 | 0 | 89.1725 | 29.7 | sq ft | 12.7 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; ED: 2026-04-14; EL: Jacob Perez; FD: 2026-04-14; FL: Jacob Perez | 2026-04-14 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255111 | 26003H | 3832J | LP1Y-DCM-177202-04-4 | LP1Y-DCM-177202-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.95 | 11.63 | sq ft | 0.63 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255109 | 26003H | 3830J | LP1Y-DCM-177202-04-2 | LP1Y-DCM-177202-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255110 | 26003H | 3831J | LP1Y-DCM-177202-04-3 | LP1Y-DCM-177202-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 18.82 | 12.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255114 | 26003H | 3835J | LP1Y-DCM-177202-05-3 | LP1Y-DCM-177202-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.46 | 10.17 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255115 | 26003H | 3836J | LP1Y-DCM-177202-05-4 | LP1Y-DCM-177202-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 15.86 | 10.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255113 | 26003H | 3834J | LP1Y-DCM-177202-05-2 | LP1Y-DCM-177202-05 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 13 | 13 | 0 | 39.3795 | 26.62 | sq ft | 2.62 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255112 | 26003H | 3833J | LP1Y-DCM-177202-05-1 | LP1Y-DCM-177202-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E016YSPP |  | 315-DCM | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255119 | 26003H | 3840J | LP1Y-IPA-177101-01-4 | LP1Y-IPA-177101-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 6 | 6 | 0 | 46.7555 | 10.8 | sq ft | 9.3 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255118 | 26003H | 3839J | LP1Y-IPA-177101-01-3 | LP1Y-IPA-177101-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 19 | 17 | 2 | 310.0467 | 39.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255116 | 26003H | 3837J | LP1Y-IPA-177101-01-1 | LP1Y-IPA-177101-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255117 | 26003H | 3838J | LP1Y-IPA-177101-01-2 | LP1Y-IPA-177101-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255121 | 26003H | 3842J | LP1Y-IPA-177101-02-2 | LP1Y-IPA-177101-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 6 | 6 | 0 | 125.0331 | 30.06 | sq ft | 28.56 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255120 | 26003H | 3841J | LP1Y-IPA-177101-02-1 | LP1Y-IPA-177101-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 28 | 27 | 1 | 295.8709 | 33.09 | sq ft | 3.09 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255122 | 26003H | 3843J | LP1Y-IPA-177101-03-1 | LP1Y-IPA-177101-03 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS IPA (315) P 177101 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177101 |  | TFS00E016YSPP |  | 315-IPA | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.4381 | 27.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255125 | 26003H | 3846J | LP1Y-IPA-177102-05-3 | LP1Y-IPA-177102-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255124 | 26003H | 3845J | LP1Y-IPA-177102-05-2 | LP1Y-IPA-177102-05 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 16 | 16 | 0 | 81.6375 | 27.51 | sq ft | 9.01 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255126 | 26003H | 3847J | LP1Y-IPA-177102-05-4 | LP1Y-IPA-177102-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 23.66 | 15.17 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255123 | 26003H | 3844J | LP1Y-IPA-177102-05-1 | LP1Y-IPA-177102-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 29.8925 | 11.99 | sq ft | 10.49 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255127 | 26003H | 3848J | LP1Y-IPA-177102-05-5 | LP1Y-IPA-177102-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.51 | 11.46 | sq ft | 0.46 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255130 | 26003H | 3851J | LP1Y-IPA-177102-06-3 | LP1Y-IPA-177102-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255129 | 26003H | 3850J | LP1Y-IPA-177102-06-2 | LP1Y-IPA-177102-06 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 13 | 13 | 0 | 39.3795 | 26.62 | sq ft | 2.62 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255128 | 26003H | 3849J | LP1Y-IPA-177102-06-1 | LP1Y-IPA-177102-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255131 | 26003H | 3852J | LP1Y-IPA-177102-06-4 | LP1Y-IPA-177102-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E016YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 15.86 | 10.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255132 | 26003H | 3853J | LP1Y-MTBE-063102-07-1 | LP1Y-MTBE-063102-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 063102 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-063102 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 12 | 12 | 0 | 85.4679 | 20.79 | sq ft | 13.79 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255133 | 26003H | 3854J | LP1Y-MTBE-177401-01-1 | LP1Y-MTBE-177401-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255134 | 26003H | 3855J | LP1Y-MTBE-177401-01-2 | LP1Y-MTBE-177401-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255136 | 26003H | 3857J | LP1Y-MTBE-177401-01-4 | LP1Y-MTBE-177401-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 6 | 6 | 0 | 96.3024 | 22.24 | sq ft | 20.74 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255135 | 26003H | 3856J | LP1Y-MTBE-177401-01-3 | LP1Y-MTBE-177401-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 25 | 23 | 2 | 409.8847 | 62.12 | sq ft | 27.62 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255137 | 26003H | 3858J | LP1Y-MTBE-177401-02-1 | LP1Y-MTBE-177401-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 34 | 33 | 1 | 371.1736 | 48.11 | sq ft | 18.11 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255138 | 26003H | 3859J | LP1Y-MTBE-177401-02-2 | LP1Y-MTBE-177401-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 3 | 3 | 0 | 87.2583 | 21.33 | sq ft | 19.83 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255139 | 26003H | 3860J | LP1Y-MTBE-177401-03-1 | LP1Y-MTBE-177401-03 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177401 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177401 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.4381 | 27.13 | sq ft | 1.63 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255141 | 26003H | 3862J | LP1Y-MTBE-177402-06-3 | LP1Y-MTBE-177402-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 24 | 23 | 1 | 63.1435 | 22.1 | sq ft | 11.6 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255142 | 26003H | 3863J | LP1Y-MTBE-177402-06-2 | LP1Y-MTBE-177402-06 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 18 | 15 | 3 | 88.8867 | 25.52 | sq ft | 4.02 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255140 | 26003H | 3861J | LP1Y-MTBE-177402-06-1 | LP1Y-MTBE-177402-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 18 | 17 | 1 | 82.8426 | 27.26 | sq ft | 11.76 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255146 | 26003H | 3867J | LP1Y-MTBE-177402-07-4 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 32.16 | 21.29 | sq ft | 2.29 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255143 | 26003H | 3864J | LP1Y-MTBE-177402-07-1 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255145 | 26003H | 3866J | LP1Y-MTBE-177402-07-3 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9 | 10.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255148 | 26003H | 3869J | LP1Y-MTBE-177402-07-6 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.965 | 9.31 | sq ft | 1.31 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255144 | 26003H | 3865J | LP1Y-MTBE-177402-07-2 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 13 | 13 | 0 | 38.885 | 26.52 | sq ft | 2.02 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; ED: 2026-04-17; EL: Jacob Perez; FD: 2026-04-17; FL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255147 | 26003H | 3868J | LP1Y-MTBE-177402-07-5 | LP1Y-MTBE-177402-07 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E016YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.24 | 13.58 | sq ft | 1.58 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255149 | 26003H | 3870J | LP1Y-N2(100)-018065-02-1 | LP1Y-N2(100)-018065-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 018065 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018065 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255151 | 26003H | 3872J | LP1Y-N2(100)-018065-02-3 | LP1Y-N2(100)-018065-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 018065 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018065 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 57.7775 | 23.89 | sq ft | 19.39 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255150 | 26003H | 3871J | LP1Y-N2(100)-018065-02-2 | LP1Y-N2(100)-018065-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 018065 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018065 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 68.8913 | 22.1 | sq ft | 7.6 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255152 | 26003H | 3873J | LP1Y-N2(100)-181110-01-1 | LP1Y-N2(100)-181110-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 181110 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181110 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255153 | 26003H | 3874J | LP1Y-N2(100)-181110-01-2 | LP1Y-N2(100)-181110-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 181110 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181110 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 18 | 18 | 0 | 84.865 | 28.15 | sq ft | 12.15 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255154 | 26003H | 3875J | LP1Y-N2(100)-181110-02-1 | LP1Y-N2(100)-181110-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2(100) (315) E 181110 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181110 |  | TFS00E016YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 34 | 34 | 0 | 163.7691 | 79.32 | sq ft | 10.32 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255158 | 26003H | 3879J | LP1Y-N2-181036-01-4 | LP1Y-N2-181036-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.8125 | 29.41 | sq ft | 3.41 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255157 | 26003H | 3878J | LP1Y-N2-181036-01-3 | LP1Y-N2-181036-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.59 | 8.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255155 | 26003H | 3876J | LP1Y-N2-181036-01-1 | LP1Y-N2-181036-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6 | 6 | 0 | 52.7175 | 21.3 | sq ft | 18.3 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255156 | 26003H | 3877J | LP1Y-N2-181036-01-2 | LP1Y-N2-181036-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 28.3425 | 13.99 | sq ft | 5.49 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255159 | 26003H | 3880J | LP1Y-N2-181036-02-1 | LP1Y-N2-181036-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 31.75 | 29.5 | 2.25 | 65.677 | 53.42 | sq ft | 4.92 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255160 | 26003H | 3881J | LP1Y-N2-181036-02-2 | LP1Y-N2-181036-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181036 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181036 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 28.975 | 12.9 | sq ft | 7.4 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255161 | 26003H | 3882J | LP1Y-N2-181112-01-1 | LP1Y-N2-181112-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 35.75 | 33.5 | 2.25 | 74.6245 | 56.22 | sq ft | 10.22 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255162 | 26003H | 3883J | LP1Y-N2-181112-02-1 | LP1Y-N2-181112-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6 | 6 | 0 | 26.125 | 11.23 | sq ft | 8.23 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255163 | 26003H | 3884J | LP1Y-N2-181112-02-2 | LP1Y-N2-181112-02 | 0 | N | PRI-1-9 | 2026-04-17 | 2026-04-25 | released |  |  | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 2 | 2 | 0 | 25.1763 | 10.2 | sq ft | 8.7 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255164 | 26003H | 3885J | LP1Y-N2-181112-02-3 | LP1Y-N2-181112-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 15.9638 | 6.71 | sq ft | 5.21 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255165 | 26003H | 3886J | LP1Y-N2-181112-04-1 | LP1Y-N2-181112-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 1" | 316 SS | 1 | 0 | 1 | 2.22 | 1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255166 | 26003H | 3887J | LP1Y-N2-181112-04-2 | LP1Y-N2-181112-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 11 | 11 | 0 | 33.1511 | 16.46 | sq ft | 9.96 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255167 | 26003H | 3888J | LP1Y-N2-181112-04-3 | LP1Y-N2-181112-04 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS N2 (315) E 181112 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181112 |  | TFS00E016YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 49.775 | 21.52 | sq ft | 15.52 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255168 | 26003H | 3889J | LP1Y-PVP-013022-01-1 | LP1Y-PVP-013022-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS PVP (315) P 013022 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-013022 |  | TFS00E016YSPP |  | 315-PVP | NONE | 3" | 316 SS | 11 | 9 | 2 | 34.5771 | 10.45 | sq ft | 6.95 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255176 | 26003H | 3897J | LP1Y-PVP-112109-06-1 | LP1Y-PVP-112109-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 30.43 | 17.54 | sq ft | 9.04 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255180 | 26003H | 3901J | LP1Y-RV-181115-01-1 | LP1Y-RV-181115-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS RV (315) 181115 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181115 |  | TFS00E016YSPP |  | 315-RV | NONE | 3" | 316 SS | 21 | 21 | 0 | 73.6331 | 18.06 | sq ft | 9.56 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255181 | 26003H | 3902J | LP1Y-RV-181116-01-1 | LP1Y-RV-181116-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 3" SS RV (315) 181116 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181116 |  | TFS00E016YSPP |  | 315-RV | NONE | 3" | 316 SS | 21 | 21 | 0 | 60.6205 | 15.05 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255183 | 26003H | 3904C | LP1Y-S(130)-018018-01-2 | LP1Y-S(130)-018018-01 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018018 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018018 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 12 | 0 | 12 | 45.5564 | 56.96 | sq ft | 4.96 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255182 | 26003H | 3903C | LP1Y-S(130)-018018-01-1 | LP1Y-S(130)-018018-01 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018018 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018018 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 12.7269 | 11.73 | sq ft | 7.23 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255185 | 26003H | 3906C | LP1Y-S(130)-018080-02-2 | LP1Y-S(130)-018080-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 10.75 | 10 | 0.75 | 53.0472 | 28.09 | sq ft | 8.59 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255186 | 26003H | 3907C | LP1Y-S(130)-018080-02-3 | LP1Y-S(130)-018080-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 38.9513 | 14.15 | sq ft | 8.15 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255184 | 26003H | 3905C | LP1Y-S(130)-018080-02-1 | LP1Y-S(130)-018080-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 6 | 6 | 0 | 45.7263 | 14.65 | sq ft | 11.65 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255187 | 26003H | 3908C | LP1Y-S(130)-018080-04-1 | LP1Y-S(130)-018080-04 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 8 | 8 | 0 | 78.1422 | 24.59 | sq ft | 20.09 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255189 | 26003H | 3910C | LP1Y-S(130)-018080-04-3 | LP1Y-S(130)-018080-04 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 11.75 | 8 | 3.75 | 36.0942 | 23.63 | sq ft | 4.13 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255188 | 26003H | 3909C | LP1Y-S(130)-018080-04-2 | LP1Y-S(130)-018080-04 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" CS S(130) (2) (103) 018080 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018080 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 2" | CS | 17.75 | 14 | 3.75 | 84.1804 | 37.71 | sq ft | 17.21 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255192 | 26003H | 3913C | LP1Y-S(130)-018123-02-3 | LP1Y-S(130)-018123-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018123 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018123 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255190 | 26003H | 3911C | LP1Y-S(130)-018123-02-1 | LP1Y-S(130)-018123-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018123 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018123 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255191 | 26003H | 3912C | LP1Y-S(130)-018123-02-2 | LP1Y-S(130)-018123-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018123 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018123 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255195 | 26003H | 3916C | LP1Y-S(130)-018125-02-3 | LP1Y-S(130)-018125-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018125 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018125 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.11 | 1 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255194 | 26003H | 3915C | LP1Y-S(130)-018125-02-2 | LP1Y-S(130)-018125-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018125 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018125 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 4 | 0 | 4 | 9.5409 | 4.47 | sq ft | 1.97 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255193 | 26003H | 3914C | LP1Y-S(130)-018125-02-1 | LP1Y-S(130)-018125-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS S(130) (2) (103) 018125 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018125 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255196 | 26003H | 3917C | LP1Y-S(130)-018127-02-1 | LP1Y-S(130)-018127-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018127 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018127 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255197 | 26003H | 3918C | LP1Y-S(130)-018127-02-2 | LP1Y-S(130)-018127-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018127 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018127 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 3 | 0 | 3 | 6.3126 | 4.51 | sq ft | 2.01 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255198 | 26003H | 3919C | LP1Y-S(130)-018127-02-3 | LP1Y-S(130)-018127-02 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018127 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018127 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 2.3167 | 2.33 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255201 | 26003H | 3922C | LP1Y-S(130)-018154-01-3 | LP1Y-S(130)-018154-01 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018154 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018154 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0.75 | 0 | 0.75 | 1.84 | 1 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255199 | 26003H | 3920C | LP1Y-S(130)-018154-01-1 | LP1Y-S(130)-018154-01 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018154 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018154 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 13.8816 | 15.72 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255200 | 26003H | 3921C | LP1Y-S(130)-018154-01-2 | LP1Y-S(130)-018154-01 | 0 | N | PRI-1-9 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS S(130) (2) (103) 018154 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018154 |  | TFS00E016YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 4.5 | 0 | 4.5 | 9.0645 | 7.4 | sq ft | 3.4 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255202 | 26003H | 3923J | LP1Y-S(130)-166801-01-1 | LP1Y-S(130)-166801-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1" SS S(130) (315) (103) 166801 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166801 |  | TFS00E016YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 30.4325 | 23.75 | sq ft | 21.25 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255203 | 26003H | 3924J | LP1Y-S(130)-166801-01-2 | LP1Y-S(130)-166801-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1" SS S(130) (315) (103) 166801 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166801 |  | TFS00E016YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 16.928 | 18.48 | sq ft | 10.98 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255204 | 26003H | 3925J | LP1Y-S(130)-166801-01-4 | LP1Y-S(130)-166801-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1" SS S(130) (315) (103) 166801 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166801 |  | TFS00E016YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 6 | 6 | 0 | 12.165 | 13.83 | sq ft | 7.83 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255205 | 26003H | 3926J | LP1Y-S(130)-166801-01-5 | LP1Y-S(130)-166801-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1" SS S(130) (315) (103) 166801 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166801 |  | TFS00E016YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 2.0969 | 1.6 | sq ft | 1.1 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255206 | 26003H | 3927J | LP1Y-S(130)-166801-01-3 | LP1Y-S(130)-166801-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1" SS S(130) (315) (103) 166801 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166801 |  | TFS00E016YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 30.4325 | 23.75 | sq ft | 21.25 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255207 | 26003H | 3928C | LP1Y-SC-018124-01-1 | LP1Y-SC-018124-01 | 0 | N | PRI-1-9 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS SC (2) (101) 018124 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018124 |  | TFS00E016YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255208 | 26003H | 3929C | LP1Y-SC-018126-01-1 | LP1Y-SC-018126-01 | 0 | N | PRI-1-9 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 1" CS SC (2) (101) 018126 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018126 |  | TFS00E016YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255209 | 26003H | 3930C | LP1Y-SC-018128-01-1 | LP1Y-SC-018128-01 | 0 | N | PRI-1-9 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS SC (2) (101) 018128 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018128 |  | TFS00E016YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 5.133 | 4.52 | sq ft | 3.02 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255210 | 26003H | 3931C | LP1Y-SC-018155-01-1 | LP1Y-SC-018155-01 | 0 | N | PRI-1-9 | 2026-04-21 | 2026-04-23 | released |  |  | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" CS SC (2) (101) 018155 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018155 |  | TFS00E016YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 5.6536 | 4.87 | sq ft | 3.37 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-23 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255212 | 26003H | 3933J | LP1Y-STORMP-166804-02-2 | LP1Y-STORMP-166804-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS STORMP (315) (108) 166804 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166804 |  | TFS00E016YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 18.25 | 16 | 2.25 | 91.2138 | 34.84 | sq ft | 12.34 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255211 | 26003H | 3932J | LP1Y-STORMP-166804-02-1 | LP1Y-STORMP-166804-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS STORMP (315) (108) 166804 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166804 |  | TFS00E016YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.0225 | 7.32 | sq ft | 3.32 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; ED: 2026-04-15; EL: Jacob Perez; FD: 2026-04-15; FL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255215 | 26003H | 3936J | LP1Y-SW-166802-01-3 | LP1Y-SW-166802-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SW (315) 166802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166802 |  | TFS00E016YSPP |  | 315-SW | NONE | 2" | 316 SS | 2 | 2 | 0 | 32.12 | 12.83 | sq ft | 11.33 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255214 | 26003H | 3935J | LP1Y-SW-166802-01-2 | LP1Y-SW-166802-01 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS SW (315) 166802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166802 |  | TFS00E016YSPP |  | 315-SW | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.685 | 16.23 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255213 | 26003H | 3934J | LP1Y-SW-166802-01-1 | LP1Y-SW-166802-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SW (315) 166802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166802 |  | TFS00E016YSPP |  | 315-SW | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 5.85 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255216 | 26003H | 3937J | LP1Y-SW-166802-01-4 | LP1Y-SW-166802-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SW (315) 166802 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166802 |  | TFS00E016YSPP |  | 315-SW | NONE | 2" | 316 SS | 8 | 8 | 0 | 52.905 | 21.4 | sq ft | 17.9 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255217 | 26003H | 3938J | LP1Y-SWP-166803-02-1 | LP1Y-SWP-166803-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 29.7825 | 12.61 | sq ft | 9.61 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255219 | 26003H | 3940J | LP1Y-SWP-166803-02-2 | LP1Y-SWP-166803-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.5638 | 10.09 | sq ft | 4.59 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez; ED: 2026-04-15; EL: Jacob Perez; FD: 2026-04-15; FL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255218 | 26003H | 3939J | LP1Y-SWP-166803-02-3 | LP1Y-SWP-166803-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 62.7375 | 22.72 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255221 | 26003H | 3942J | LP1Y-SWP-166803-03-2 | LP1Y-SWP-166803-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 5.85 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255222 | 26003H | 3943J | LP1Y-SWP-166803-03-3 | LP1Y-SWP-166803-03 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 2" | 316 SS | 17.5 | 13 | 4.5 | 91.6983 | 45.56 | sq ft | 7.56 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255220 | 26003H | 3941J | LP1Y-SWP-166803-03-1 | LP1Y-SWP-166803-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS SWP (315) (108) 166803 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166803 |  | TFS00E016YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 7.71 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255223 | 26003H | 3944J | LP1Y-WFO-017007-69-1 | LP1Y-WFO-017007-69 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.7475 | 2.18 | sq ft | 2.18 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255224 | 26003H | 3945J | LP1Y-WFO-017007-69-2 | LP1Y-WFO-017007-69 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.21 | 4.63 | sq ft | 4.63 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255225 | 26003H | 3946J | LP1Y-WFO-017013-05-1 | LP1Y-WFO-017013-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 34.0038 | 12.88 | sq ft | 12.88 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255227 | 26003H | 3948J | LP1Y-WFO-017013-05-3 | LP1Y-WFO-017013-05 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.07 | 1.54 | sq ft | 1.54 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255226 | 26003H | 3947J | LP1Y-WFO-017013-05-2 | LP1Y-WFO-017013-05 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255228 | 26003H | 3949J | LP1Y-WFO-017013-06-1 | LP1Y-WFO-017013-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.5863 | 9.33 | sq ft | 5.83 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255229 | 26003H | 3950J | LP1Y-WFO-017013-06-2 | LP1Y-WFO-017013-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 42.2538 | 16.01 | sq ft | 16.01 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255230 | 26003H | 3951J | LP1Y-WFO-017013-06-3 | LP1Y-WFO-017013-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4.75 | 0 | 4.75 | 27.3725 | 10.74 | sq ft | 10.24 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255231 | 26003H | 3952J | LP1Y-WFO-017013-06-4 | LP1Y-WFO-017013-06 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.0913 | 2.31 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255232 | 26003H | 3953J | LP1Y-WFO-017013-06-5 | LP1Y-WFO-017013-06 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) 017013 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017013 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 7.75 | 0 | 7.75 | 17.43 | 13.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255240 | 26003H | 3961J | LP1Y-WFO-017082-03-8 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 6 | 0 | 17.59 | 8.58 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255233 | 26003H | 3954J | LP1Y-WFO-017082-03-1 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.235 | 16.1 | sq ft | 14.1 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255234 | 26003H | 3955J | LP1Y-WFO-017082-03-2 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 4 | 0 | 22.745 | 9.48 | sq ft | 7.48 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255236 | 26003H | 3957J | LP1Y-WFO-017082-03-4 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 4 | 0 | 3.8 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255239 | 26003H | 3960J | LP1Y-WFO-017082-03-7 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 4 | 0 | 10.25 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255235 | 26003H | 3956J | LP1Y-WFO-017082-03-3 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255237 | 26003H | 3958J | LP1Y-WFO-017082-03-5 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.28 | 2 | sq ft | 2 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255238 | 26003H | 3959J | LP1Y-WFO-017082-03-6 | LP1Y-WFO-017082-03 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WFO (36) (108) 017082 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017082 |  | TFS00E016YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.72 | 2.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255241 | 26003H | 3962J | LP1Y-WFO-196026-02-1 | LP1Y-WFO-196026-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 0.75" SS WFO (36) 196026 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196026 |  | TFS00E016YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 20.5126 | 19.22 | sq ft | 4.72 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255247 | 26003H | 3968J | LP1Y-WPC-017058-02-6 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255244 | 26003H | 3965J | LP1Y-WPC-017058-02-3 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 2.31 | 0.88 | sq ft | 0.88 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255245 | 26003H | 3966J | LP1Y-WPC-017058-02-4 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 2.31 | 0.88 | sq ft | 0.88 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255246 | 26003H | 3967J | LP1Y-WPC-017058-02-5 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 24.1413 | 14.72 | sq ft | 3.72 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255242 | 26003H | 3963J | LP1Y-WPC-017058-02-1 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/2" | 316 SS | 8.0465 | 0 | 8.0465 | 55.4452 | 22.05 | sq ft | 21.71 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255243 | 26003H | 3964J | LP1Y-WPC-017058-02-2 | LP1Y-WPC-017058-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017058 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017058 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 4.3725 | 1.66 | sq ft | 1.66 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255259 | 26003H | 3980J | LP1Y-WPC-194127-01-12 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255248 | 26003H | 3969J | LP1Y-WPC-194127-01-1 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.64 | 1 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255249 | 26003H | 3970J | LP1Y-WPC-194127-01-2 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255255 | 26003H | 3976J | LP1Y-WPC-194127-01-8 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 46.145 | 17.48 | sq ft | 17.48 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255257 | 26003H | 3978J | LP1Y-WPC-194127-01-10 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.1188 | 2.32 | sq ft | 2.32 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255258 | 26003H | 3979J | LP1Y-WPC-194127-01-11 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 4.8125 | 1.82 | sq ft | 1.82 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255252 | 26003H | 3973J | LP1Y-WPC-194127-01-5 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255250 | 26003H | 3971J | LP1Y-WPC-194127-01-3 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.345 | 1.65 | sq ft | 1.65 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255256 | 26003H | 3977J | LP1Y-WPC-194127-01-9 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8425 | 0.7 | sq ft | 0.7 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255251 | 26003H | 3972J | LP1Y-WPC-194127-01-4 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.58 | 3.25 | sq ft | 3.25 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255253 | 26003H | 3974J | LP1Y-WPC-194127-01-6 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.4425 | 7.36 | sq ft | 7.36 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255254 | 26003H | 3975J | LP1Y-WPC-194127-01-7 | LP1Y-WPC-194127-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194127 | WPC |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.8 | 20 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255261 | 26003H | 3982J | LP1Y-WPC-194127-02-2 | LP1Y-WPC-194127-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194127 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 9.75 | 0 | 9.75 | 18.4938 | 13.22 | sq ft | 6.22 | ft | 2026-02-13 |  |  |  |  | 2026-04-16 | Jacob Perez | 2026-04-16 | George Allahverdian | 2026-04-17 | Jacob Perez | 2026-04-17 | Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255260 | 26003H | 3981J | LP1Y-WPC-194127-02-1 | LP1Y-WPC-194127-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194127 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194127 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 6 | 0 | 6 | 32.2355 | 25.3 | sq ft | 8.3 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez; DD: 2026-04-16; DL: George Allahverdian | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255262 | 26003H | 3983J | LP1Y-WPC-194128-01-1 | LP1Y-WPC-194128-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.2838 | 6.55 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255265 | 26003H | 3986J | LP1Y-WPC-194128-01-4 | LP1Y-WPC-194128-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 6.7661 | 6.38 | sq ft | 3.38 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255263 | 26003H | 3984J | LP1Y-WPC-194128-01-2 | LP1Y-WPC-194128-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1" | 316 SS | 4 | 0 | 4 | 1.9113 | 0.72 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255264 | 26003H | 3985J | LP1Y-WPC-194128-01-3 | LP1Y-WPC-194128-01 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez | 2026-04-15 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255268 | 26003H | 3989J | LP1Y-WPC-194128-02-3 | LP1Y-WPC-194128-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 4.75 | 0 | 4.75 | 11.0481 | 7.1 | sq ft | 4.1 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255269 | 26003H | 3990J | LP1Y-WPC-194128-02-4 | LP1Y-WPC-194128-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 7.5 | 0 | 7.5 | 11.7525 | 8.31 | sq ft | 2.81 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255266 | 26003H | 3987J | LP1Y-WPC-194128-02-1 | LP1Y-WPC-194128-02 | 0 | N | PRI-1-9 | [5 empty] | Released to Production | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 7.75 | 0 | 7.75 | 40.2731 | 28.47 | sq ft | 11.47 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255267 | 26003H | 3988J | LP1Y-WPC-194128-02-2 | LP1Y-WPC-194128-02 | 0 | N | PRI-1-9 | [5 empty] | Passed Production Test | P019 | 2026-06-29 |  | LP1Y 1.25" SS WPC (36) (108) 194128 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194128 |  | TFS00E016YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 2.5 | 0 | 2.5 | 23.7738 | 13.89 | sq ft | 12.39 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian | 2026-04-16 | 2026-05-04 | Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S245313 | 26003H | 1215J | LP1Y-AWNP-101307-01-3 | LP1Y-AWNP-101307-01 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 12 | 12 | 0 | 77.3078 | 15.65 | sq ft | 3.47 | ft | 2026-02-13 |  |  |  |  | 2026-03-27 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Montoya | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-18 | 144074, 144994 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245311 | 26003H | 1213J | LP1Y-AWNP-101307-01-1 | LP1Y-AWNP-101307-01 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 6 | 6 | 0 | 66.9375 | 13.07 | sq ft | 3.54 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-16 | 143931, 144847 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245312 | 26003H | 1214J | LP1Y-AWNP-101307-01-2 | LP1Y-AWNP-101307-01 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-16 | 2026-04-27 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 33 | 32 | 1 | 173.9945 | 40.52 | sq ft | 6.22 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-27 | 2026-04-27 | Passed | No | 2026-04-27 | 2026-04-29 | 2026-04-29 | 2026-04-28 | 2026-04-28 | N/A | N/A | Carlos Montoya | 2026-05-01 | 2026-05-01 |  | 2026-05-01 | 2026-05-01 |  | 2026-05-01 |  |  |  | 63% |  |  |  | 13%
C34-S246954 | 26003H | 1213JA | LP1Y-AWNP-101307-01-4 | LP1Y-AWNP-101307-01 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 6" SS AWNP (315) (108) 101307 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101307 |  | TFS00D003YSPP |  | 315-AWNP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-27; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-30 | 2026-03-30 | N/A | N/A | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 100% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-16 | 143966, 144856 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S245432 | 26003H | 1335J | LP1Y-ENZ-162001-07-2 | LP1Y-ENZ-162001-07 | 0-IR3 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 0.5 | 0 | 0.5 | 10.5519 | 16.56 | sq ft | 15.06 | ft | 2026-02-13 | CD: 2026-03-02; CL: Jacob Perez; DD: 2026-03-02; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | N/A | N/A | Omar Puente | 2026-03-19 | 2026-03-19 | 2026-03-19 | 2026-03-19 |  |  |  | 2026-03-19 | 2026-03-19 | 2026-03-19 | 100% |  |  |  | 0%
C34-S245431 | 26003H | 1334J | LP1Y-ENZ-162001-07-1 | LP1Y-ENZ-162001-07 | 0-IR3 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 0.5" SS ENZ (315) P (108) 162001 | ENZ |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162001 |  | TFS00E006YSPP |  | 315-ENZ | NONE | 1/2" | 316 SS | 3 | 0 | 3 | 19.4255 | 32.02 | sq ft | 24.52 | ft | 2026-02-13 | CD: 2026-03-24; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 | 2026-04-20 | Passed | No | 2026-04-20 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | N/A | N/A | Edgar Castaneda | 2026-04-28 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  |  |  | 83% |  |  |  | 83%
C34-S245493 | 26003H | 1396J | LP1Y-H2SO4-178101-01-1 | LP1Y-H2SO4-178101-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 7 | 7 | 0 | 20.2 | 9.67 | sq ft | 1.67 | ft | 2026-02-13 | DD: 2026-03-19; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 100% | 2026-03-28 | 2026-03-28 | 2026-03-28 | 100% | 2026-04-18 | 143838, 144995
C34-S245496 | 26003H | 1399J | LP1Y-H2SO4-178101-01-4 | LP1Y-H2SO4-178101-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 3 | 3 | 0 | 6.8602 | 2.77 | sq ft | 1.27 | ft | 2026-02-13 | CD: 2026-03-19; CL: Jacob Perez; DD: 2026-03-19; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-20 | 2026-03-20 | 2026-03-21 | 2026-03-21 | N/A | N/A | Carlos Guillen | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-25 | 2026-03-25 | 2026-03-25 | 100% | 2026-04-18 | 143523, 144998
C34-S246984 | 26003H | 1396J-L1 | LP1Y-H2SO4-178101-01-1-L1 | LP1Y-H2SO4-178101-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | [12 empty] | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-21 | 2026-03-21 | N/A | N/A | N/A | N/A | NO FITTER | 2026-04-15 | [9 empty] | 100% |  |  |  | 100% | 2026-04-18 | 143275, 144996
C34-S245495 | 26003H | 1398J | LP1Y-H2SO4-178101-01-3 | LP1Y-H2SO4-178101-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Passed Visual Inspection | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 6 | 6 | 0 | 170.9723 | 39.48 | sq ft | 37.98 | ft | 2026-02-13 | DD: 2026-03-19; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-20 | 2026-03-20 | 2026-03-31 | 2026-03-31 | N/A | N/A | Edgar Castaneda | 2026-03-25 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 100% | 2026-03-26 | 2026-03-26 | 2026-03-26 | 100% | 2026-04-18 | 143906, 144997
C34-S245494 | 26003H | 1397J | LP1Y-H2SO4-178101-01-2 | LP1Y-H2SO4-178101-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Production | P018 | 2026-06-15 |  | LP1Y 3" SS H2SO4 (315) P (108) 178101 | H2SO4 |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-178101 |  | TFS00D001YSPP |  | 315-H2SO4 | NONE | 3" | 316 SS | 19 | 17 | 2 | 327.299 | 43.05 | sq ft | 8.55 | ft | 2026-02-13 |  |  |  |  | 2026-03-30 | Jacob Perez | 2026-04-05 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246041 | 26003H | 1461J | LP1Y-N2(100)-180048-04-1 | LP1Y-N2(100)-180048-04 | 2 | R | TR-04 4.10.2026 | 2026-04-07 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 37.4 | 15.5 | sq ft | 12.5 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Edgar Castaneda | 2026-03-14 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 0% | 2026-03-16 | 2026-03-16 | 2026-03-16 | 0% | 2026-03-16 | 142899
C34-S246043 | 26003H | 1463J | LP1Y-N2(100)-180048-04-3 | LP1Y-N2(100)-180048-04 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.7163 | 21.66 | sq ft | 6.16 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246042 | 26003H | 1462J | LP1Y-N2(100)-180048-04-2 | LP1Y-N2(100)-180048-04 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 2" SS N2(100) (315) 180048 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-180048 |  | TFS00D005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 16.885 | 7.73 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-03-06; CL: Jacob Perez; DD: 2026-03-06; DL: George Allahverdian | 2026-04-29 | 2026-04-29 | Passed | No | 2026-04-29 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-13 | N/A | N/A | Roberto Tobias (WF) | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [6 empty] | 67% |  |  |  | 0%
C34-S246246 | 26003H | 1666J | LP1Y-PV-101612-02-2 | LP1Y-PV-101612-02 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 12 | 11 | 1 | 50.478 | 26.7 | sq ft | 2.2 | ft | 2026-02-13 |  |  |  |  | 2026-03-16 | Jacob Perez | 2026-03-16 | George Allahverdian | 2026-03-17 | Jacob Perez | 2026-03-17 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246245 | 26003H | 1665J | LP1Y-PV-101612-02-1 | LP1Y-PV-101612-02 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Production | P014 | 2026-06-15 |  | LP1Y 3" SS PV (315) (108) 101612 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101612 |  | TFS00D005YSPP |  | 315-PV | NONE | 3" | 316 SS | 6 | 6 | 0 | 272.921 | 16.35 | sq ft | 2.35 | ft | 2026-02-13 | CD: 2026-03-16; CL: Jacob Perez; DD: 2026-03-16; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247322 | 26003H | 1784J | LP1Y-PWP-101604-02-2 | LP1Y-PWP-101604-02 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Shipped | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 6 | 6 | 0 | 64.7094 | 12.64 | sq ft | 3.3 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 100% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 100% | 2026-04-18 | 144038, 144999 | [40 empty] | 2026-04-24 | 2026-04-24 |  | 1003-0 | 2026-04-27 | JA Harris Trucking Inc.
C34-S247321 | 26003H | 1783J | LP1Y-PWP-101604-02-1 | LP1Y-PWP-101604-02 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 4 | 4 | 0 | 25.77 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | Carlos Montoya | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% |  |  |  | 0%
C34-S247323 | 26003H | 1785J | LP1Y-PWP-101604-02-3 | LP1Y-PWP-101604-02 | 1-IR2 | R | TR-04 4.10.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101604 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101604 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247431 | 26003H | 1893J | LP1Y-RV-102015-01-1 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-27 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247432 | 26003H | 1894J | LP1Y-RV-102015-01-2 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 | 2026-04-29 | released |  |  | Released to Production | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 56.1891 | 20.17 | sq ft | 1.37 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-27 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247433 | 26003H | 1895J | LP1Y-RV-102015-01-3 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 | 2026-04-29 | released |  |  | Released to Fabrication | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian | 2026-04-29 | 2026-04-29 | Passed | No | 2026-04-29 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-29 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% |  |  |  | 0%
C34-S247434 | 26003H | 1896J | LP1Y-RV-102015-01-4 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247435 | 26003H | 1897J | LP1Y-RV-102015-01-5 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247436 | 26003H | 1898J | LP1Y-RV-102015-01-6 | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 |  | active | client | notification | On Hold | P015 | 2026-06-01 |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257551 | 26003H | 1896JA | LP1Y-RV-102015-01-4A | LP1Y-RV-102015-01 | 1 | R | TR-04 4.10.2026 | 2026-04-27 |  | active | client | notification | On Hold | P015 |  |  | LP1Y 6" SS RV (315) 102015 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102015 |  | TFS00D006YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-04-10 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247726 | 26003H | 1938J | LP1Y-RV-109207-01-3 | LP1Y-RV-109207-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 |  | active | client | notification | On Hold | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247727 | 26003H | 1939J | LP1Y-RV-109207-01-4 | LP1Y-RV-109207-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 |  | active | client | notification | On Hold | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247724 | 26003H | 1936J | LP1Y-RV-109207-01-1 | LP1Y-RV-109207-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 9.5 | 8 | 1.5 | 58.0436 | 21.93 | sq ft | 1.44 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247725 | 26003H | 1937J | LP1Y-RV-109207-01-2 | LP1Y-RV-109207-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Passed Visual Inspection | P017 | 2026-06-15 |  | LP1Y 4" SS RV (315) (108) 109207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109207 |  | TFS00E007YSPP |  | 315-RV | NONE | 4" | 316 SS | 8 | 8 | 0 | 44.9 | 11 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-29 | 2026-04-29 | Passed | No | 2026-04-29 | 2026-04-01 | 2026-04-01 | N/A | N/A | N/A | N/A | Omar Puente | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-02 | 2026-04-02 | 2026-04-02 | 100% | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-30 | 145914
C34-S247975 | 26003H | 2187J | LP1Y-SRACNP-108106-02-2 | LP1Y-SRACNP-108106-02 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 3" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 7.5 | 7.5 | 0 | 25.8508 | 10.83 | sq ft | 3.33 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247974 | 26003H | 2186J | LP1Y-SRACNP-108106-02-1 | LP1Y-SRACNP-108106-02 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 3" SS SRACNP (315) P (108) 108106 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108106 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 12 | 12 | 0 | 133.6762 | 30.87 | sq ft | 27.87 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249508 | 26003H | 2211J | LP1Y-SRACNP-108135-02-3 | LP1Y-SRACNP-108135-02 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Passed Visual Inspection | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 29.7138 | 13.26 | sq ft | 8.76 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-29 | 2026-04-29 | Passed | No | 2026-04-29 | 2026-04-01 | 2026-04-01 | 2026-04-02 | 2026-04-07 | N/A | N/A | Omar Puente | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 100% | 2026-04-30 | 2026-04-30 | 2026-04-30 | 100% | 2026-05-01 | 145993
C34-S249506 | 26003H | 2209J | LP1Y-SRACNP-108135-02-1 | LP1Y-SRACNP-108135-02 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 6 | 6 | 0 | 93.72 | 36.17 | sq ft | 34.67 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249507 | 26003H | 2210J | LP1Y-SRACNP-108135-02-2 | LP1Y-SRACNP-108135-02 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108135 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108135 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 45.8838 | 19.38 | sq ft | 14.88 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249527 | 26003H | 2230J | LP1Y-SRACNP-108206-01-1 | LP1Y-SRACNP-108206-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 3" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 7.5 | 7.5 | 0 | 25.8508 | 10.83 | sq ft | 3.33 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249528 | 26003H | 2231J | LP1Y-SRACNP-108206-01-2 | LP1Y-SRACNP-108206-01 | 2 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 3" SS SRACNP (315) P (108) 108206 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108206 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 3" | 316 SS | 12 | 12 | 0 | 133.6762 | 30.87 | sq ft | 27.87 | ft | 2026-02-13 | CD: 2026-04-06; CL: Jacob Perez; DD: 2026-04-06; DL: George Allahverdian | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249544 | 26003H | 2247J | LP1Y-SRACNP-108235-01-1 | LP1Y-SRACNP-108235-01 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 16.9963 | 8.79 | sq ft | 3.79 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249545 | 26003H | 2248J | LP1Y-SRACNP-108235-01-2 | LP1Y-SRACNP-108235-01 | 1 | R | TR-04 4.10.2026 | 2026-04-07 | 2026-04-29 | released |  |  | Released to Fabrication | P016 | 2026-06-08 |  | LP1Y 2" SS SRACNP (315) P (108) 108235 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108235 |  | TFS00E006YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10 | 10 | 0 | 101.5575 | 40.47 | sq ft | 35.97 | ft | 2026-02-13 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-29 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249906 | 26003H | 2538AB | LP1Y-TFA-109206-03-3 | LP1Y-TFA-109206-03 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 7.5 | 7.5 | 0 | 12.769 | 12.71 | sq ft | 5.71 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-28 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-31 | Jacob Perez | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249904 | 26003H | 2536AB | LP1Y-TFA-109206-03-1 | LP1Y-TFA-109206-03 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 3" | H C22 | 3 | 3 | 0 | 14.14 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 | 2026-04-15 | Passed | No | 2026-04-15 | 2026-04-06 | 2026-04-06 | N/A | N/A | N/A | N/A | Edgar Castaneda | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 100% |  |  |  | 0%
C34-S249905 | 26003H | 2537AB | LP1Y-TFA-109206-03-2 | LP1Y-TFA-109206-03 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 4.5 | 4.5 | 0 | 6.3694 | 7.08 | sq ft | 1.58 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249907 | 26003H | 2539AB | LP1Y-TFA-109206-03-4 | LP1Y-TFA-109206-03 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 1.5" HAST TFA (332) (108) 109206 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109206 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 7.5 | 7.5 | 0 | 34.4383 | 27.79 | sq ft | 23.29 | ft | 2026-02-13 | CL: Jacob Perez; DD: 2026-04-07; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249908 | 26003H | 2540AB | LP1Y-TFA-109212-01-1 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 2" | H C22 | 2 | 2 | 0 | 8.3 | 5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249910 | 26003H | 2542AB | LP1Y-TFA-109212-01-3 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 4.5 | 4.5 | 0 | 8.0533 | 11.92 | sq ft | 0.42 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249913 | 26003H | 2545AB | LP1Y-TFA-109212-01-6 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 9 | 9 | 0 | 16.0133 | 18.67 | sq ft | 5.67 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-28; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249909 | 26003H | 2541AB | LP1Y-TFA-109212-01-2 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 6 | 6 | 0 | 8.4304 | 9.61 | sq ft | 2.61 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249911 | 26003H | 2543AB | LP1Y-TFA-109212-01-4 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 4.5 | 4.5 | 0 | 10.8027 | 10.24 | sq ft | 4.74 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249912 | 26003H | 2544AB | LP1Y-TFA-109212-01-5 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 9 | 9 | 0 | 18.1108 | 21.23 | sq ft | 6.73 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-15 | 2026-05-01 | Passed | No | 2026-05-01 |  |  |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249914 | 26003H | 2546AB | LP1Y-TFA-109212-01-7 | LP1Y-TFA-109212-01 | 0-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Production | P017 | 2026-06-15 |  | LP1Y 2" HAST TFA (332) (108) 109212 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109212 |  | TFS00E007YSPP |  | 332-TFA | NONE | 1 1/2" | H C22 | 10.5 | 10.5 | 0 | 31.2435 | 26.47 | sq ft | 3.47 | ft | 2026-02-13 | CD: 2026-04-08; CL: Jacob Perez; DD: 2026-04-08; DL: George Allahverdian | 2026-04-15 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256232 | 26003H | 3168J-L1 | LP1Y-ACN-107403-01-1-L1 | LP1Y-ACN-107403-01 | 1 | R | TR-04 4.10.2026 | 2026-04-20 |  | active | client | notification | On Hold | P021 |  |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-04-10 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250733 | 26003H | 3168J | LP1Y-ACN-107403-01-1 | LP1Y-ACN-107403-01 | 1 | R | TR-04 4.10.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-16; CL: Jacob Perez; ED: 2026-04-17; EL: Jacob Perez; FD: 2026-04-17; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256311 | 26003H | 3363JA | LP1Y-AF-162105-01-4 | LP1Y-AF-162105-01 | 2-IR2 | R | TR-04 4.10.2026 | [5 empty] | Released to Fabrication | P013 |  | 0 | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0.75 | 0 | 0.75 | 1.56 | 1 | sq ft | 0 | ft | 2026-04-10 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251185 | 26003H | 3361J | LP1Y-AF-162105-01-1 | LP1Y-AF-162105-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-16 | 2026-04-16 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 0 | 0 | 0 | 1.26 | 0.5 | sq ft | 0 | ft | 2026-01-20 |  |  |  |  | 2026-04-05 | George Allahverdian | 2026-04-05 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-16 | 2026-04-30 | Passed | No | 2026-04-30 | 2026-05-02 | 2026-05-02 | N/A | N/A | N/A | N/A | [11 empty] | 100% |  |  |  | 100%
C34-S251187 | 26003H | 3363J | LP1Y-AF-162105-01-3 | LP1Y-AF-162105-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 29.5 | 28.75 | 0.75 | 50.1595 | 34.84 | sq ft | 9.84 | ft | 2026-01-20 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-15 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Jose G. Rodriguez Gonzales (WF) | 2026-04-24 | 2026-04-24 | 2026-04-24 | 2026-04-24 |  |  |  |  | 2026-04-24 |  | 81% |  |  |  | 0%
C34-S251186 | 26003H | 3362J | LP1Y-AF-162105-01-2 | LP1Y-AF-162105-01 | 2-IR2 | R | TR-04 4.10.2026 | 2026-04-10 | 2026-04-15 | released |  |  | Released to Fabrication | P013 | 2026-05-25 |  | LP1Y 2" SS AF (315) P (108) 162105 | AF |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-162105 |  | TFS00E003YSPP |  | 315-AF | NONE | 2" | 316 SS | 16 | 12 | 4 | 27.3825 | 10.86 | sq ft | 5.86 | ft | 2026-01-20 | CD: 2026-04-05; CL: George Allahverdian; DD: 2026-04-05; DL: George Allahverdian | 2026-04-15 | 2026-04-16 | Passed | No | 2026-04-16 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-20 | N/A | N/A | Ramiro Gonzalez | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 |  | 2026-04-23 |  | 88% |  | 2026-04-23 |  | 75%
C34-S255270 | 26003H | 3991J | LP1Y-N2(100)-018029-02-1 | LP1Y-N2(100)-018029-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 018029 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018029 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 97.9863 | 33.7 | sq ft | 15.2 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258540 | 26003H | 3993JA | LP1Y-N2(100)-181001-02-3 | LP1Y-N2(100)-181001-02 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS N2(100) (315) E 181001 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181001 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255272 | 26003H | 3993J | LP1Y-N2(100)-181001-02-2 | LP1Y-N2(100)-181001-02 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181001 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181001 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 80.9289 | 51.79 | sq ft | 14.29 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255271 | 26003H | 3992J | LP1Y-N2(100)-181001-02-1 | LP1Y-N2(100)-181001-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181001 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181001 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 40.4795 | 31.58 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255274 | 26003H | 3995J | LP1Y-N2(100)-181002-02-2 | LP1Y-N2(100)-181002-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181002 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181002 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 40.4795 | 31.58 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255273 | 26003H | 3994J | LP1Y-N2(100)-181002-02-1 | LP1Y-N2(100)-181002-02 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181002 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181002 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 80.9289 | 51.79 | sq ft | 14.29 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258541 | 26003H | 3994JA | LP1Y-N2(100)-181002-02-3 | LP1Y-N2(100)-181002-02 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS N2(100) (315) E 181002 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181002 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255278 | 26003H | 3999J | LP1Y-N2(100)-181004-02-2 | LP1Y-N2(100)-181004-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E (108) 181004 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181004 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 40.4795 | 31.58 | sq ft | 3.08 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255277 | 26003H | 3998J | LP1Y-N2(100)-181004-02-1 | LP1Y-N2(100)-181004-02 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E (108) 181004 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181004 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 16 | 16 | 0 | 80.9289 | 51.79 | sq ft | 14.29 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258542 | 26003H | 3998JA | LP1Y-N2(100)-181004-02-3 | LP1Y-N2(100)-181004-02 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS N2(100) (315) E (108) 181004 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181004 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255279 | 26003H | 4000J | LP1Y-N2(100)-181075-02-1 | LP1Y-N2(100)-181075-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181075 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181075 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 25 | 25 | 0 | 103.6888 | 43.65 | sq ft | 14.65 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255280 | 26003H | 4001J | LP1Y-N2(100)-181103-01-1 | LP1Y-N2(100)-181103-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181103 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181103 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 18.25 | 16 | 2.25 | 103.7225 | 38.91 | sq ft | 16.41 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255281 | 26003H | 4002J | LP1Y-N2-181083-01-1 | LP1Y-N2-181083-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2 (315) E 181083 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181083 |  | TFS00E005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255282 | 26003H | 4003J | LP1Y-N2-181083-01-2 | LP1Y-N2-181083-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2 (315) E 181083 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181083 |  | TFS00E005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255283 | 26003H | 4004J | LP1Y-N2-181083-01-3 | LP1Y-N2-181083-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS N2 (315) E 181083 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181083 |  | TFS00E005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 2 | 4.25 | 12.39 | 9 | sq ft | 0.5 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255285 | 26003H | 4006J | LP1Y-PV-107061-01-2 | LP1Y-PV-107061-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107061 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 24.9838 | 16.34 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255284 | 26003H | 4005J | LP1Y-PV-107061-01-1 | LP1Y-PV-107061-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107061 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 28 | 28 | 0 | 151.5363 | 57.33 | sq ft | 34.33 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255287 | 26003H | 4008J | LP1Y-PV-107062-01-2 | LP1Y-PV-107062-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107062 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 22 | 22 | 0 | 120.66 | 42.96 | sq ft | 22.96 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255286 | 26003H | 4007J | LP1Y-PV-107062-01-1 | LP1Y-PV-107062-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107062 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107062 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 24.3513 | 16.1 | sq ft | 2.6 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255289 | 26003H | 4010J | LP1Y-PV-107063-01-2 | LP1Y-PV-107063-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107063 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 24.9838 | 16.34 | sq ft | 2.84 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255288 | 26003H | 4009J | LP1Y-PV-107063-01-1 | LP1Y-PV-107063-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) (108) 107063 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107063 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 28 | 28 | 0 | 151.5363 | 57.33 | sq ft | 34.33 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255290 | 26003H | 4011J | LP1Y-PV-107064-01-1 | LP1Y-PV-107064-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) 107064 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107064 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 25.805 | 15.31 | sq ft | 3.31 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258543 | 26003H | 4013JA | LP1Y-PV-107064-01-4 | LP1Y-PV-107064-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS PV (315) 107064 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107064 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255292 | 26003H | 4013J | LP1Y-PV-107064-01-3 | LP1Y-PV-107064-01 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) 107064 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107064 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 35.1588 | 14.65 | sq ft | 11.65 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255291 | 26003H | 4012J | LP1Y-PV-107064-01-2 | LP1Y-PV-107064-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PV (315) 107064 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107064 |  | TFS00E005YSPP |  | 315-PV | NONE | 2" | 316 SS | 14 | 14 | 0 | 81.2113 | 26.68 | sq ft | 9.68 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255293 | 26003H | 4014J | LP1Y-PVP-107112-01-1 | LP1Y-PVP-107112-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107112 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107112 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 75.9925 | 28.2 | sq ft | 3.2 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255294 | 26003H | 4015J | LP1Y-PVP-107114-01-1 | LP1Y-PVP-107114-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107114 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107114 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 77.5975 | 28.34 | sq ft | 7.34 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255295 | 26003H | 4016J | LP1Y-PVP-107115-01-1 | LP1Y-PVP-107115-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107115 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107115 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 77.5975 | 28.34 | sq ft | 7.34 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255296 | 26003H | 4017J | LP1Y-PVP-107209-01-1 | LP1Y-PVP-107209-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107209 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107209 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 77.3775 | 28.26 | sq ft | 7.26 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255297 | 26003H | 4018J | LP1Y-PVP-107212-01-1 | LP1Y-PVP-107212-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107212 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107212 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 75.9925 | 28.2 | sq ft | 3.2 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255298 | 26003H | 4019J | LP1Y-PVP-107309-01-1 | LP1Y-PVP-107309-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P 107309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107309 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 14 | 14 | 0 | 32.5225 | 15.66 | sq ft | 9.66 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255299 | 26003H | 4020J | LP1Y-PVP-107309-02-1 | LP1Y-PVP-107309-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P 107309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107309 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 31.0613 | 13.77 | sq ft | 9.27 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255300 | 26003H | 4021J | LP1Y-PVP-107309-03-1 | LP1Y-PVP-107309-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P 107309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107309 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 16 | 16 | 0 | 34.5813 | 15.77 | sq ft | 9.77 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258544 | 26003H | 4022JA | LP1Y-PVP-107309-04-2 | LP1Y-PVP-107309-04 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS PVP (315) P 107309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107309 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-30 | Jacob Perez | 2026-05-01 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255301 | 26003H | 4022J | LP1Y-PVP-107309-04-1 | LP1Y-PVP-107309-04 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P 107309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107309 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 28.25 | 26 | 2.25 | 111.4775 | 43.18 | sq ft | 17.68 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255302 | 26003H | 4023J | LP1Y-PVP-107312-01-1 | LP1Y-PVP-107312-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P (108) 107312 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107312 |  | TFS00E005YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 75.9925 | 28.2 | sq ft | 3.2 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-18 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255303 | 26003H | 4024J | LP1Y-PVP-107413-01-1 | LP1Y-PVP-107413-01 | 0 | N | PRI-2-1 | 2026-04-14 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS PVP (315) P 107413 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107413 |  | TFS00E005YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255304 | 26003H | 4025J | LP1Y-PWP-107073-03-1 | LP1Y-PWP-107073-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PWP (315) (108) 107073 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107073 |  | TFS00E005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 32 | 32 | 0 | 225.9338 | 69.63 | sq ft | 8.63 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255305 | 26003H | 4026J | LP1Y-PWP-107073-04-1 | LP1Y-PWP-107073-04 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS PWP (315) (108) 107073 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107073 |  | TFS00E005YSPP |  | 315-PWP | NONE | 2" | 316 SS | 23 | 20 | 3 | 120.295 | 49.85 | sq ft | 20.85 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258545 | 26003H | 4029JA | LP1Y-RV-107107-01-4 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258555 | 26003H | 4029JB | LP1Y-RV-107107-01-5 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258556 | 26003H | 4029JC | LP1Y-RV-107107-01-6 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255308 | 26003H | 4029J | LP1Y-RV-107107-01-3 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 167.3625 | 34.22 | sq ft | 10.79 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255306 | 26003H | 4027J | LP1Y-RV-107107-01-1 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 13.5 | 12 | 1.5 | 84.5219 | 25.77 | sq ft | 0.76 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255307 | 26003H | 4028J | LP1Y-RV-107107-01-2 | LP1Y-RV-107107-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107107 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107107 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258546 | 26003H | 4032JA | LP1Y-RV-107207-01-4 | LP1Y-RV-107207-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107207 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258557 | 26003H | 4032JB | LP1Y-RV-107207-01-5 | LP1Y-RV-107207-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107207 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255311 | 26003H | 4032J | LP1Y-RV-107207-01-3 | LP1Y-RV-107207-01 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107207 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 42 | 42 | 0 | 185.8172 | 40.5 | sq ft | 12.78 | ft | 2026-02-13 |  |  |  |  | 2026-04-24 | Jacob Perez | 2026-04-25 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255310 | 26003H | 4031J | LP1Y-RV-107207-01-2 | LP1Y-RV-107207-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107207 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255309 | 26003H | 4030J | LP1Y-RV-107207-01-1 | LP1Y-RV-107207-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107207 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107207 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 13.5 | 12 | 1.5 | 84.5219 | 25.77 | sq ft | 0.76 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258558 | 26003H | 4035JB | LP1Y-RV-107307-01-5 | LP1Y-RV-107307-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107307 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107307 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258547 | 26003H | 4035JA | LP1Y-RV-107307-01-4 | LP1Y-RV-107307-01 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 6" SS RV (315) (108) 107307 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107307 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-30 | Jacob Perez | 2026-05-01 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255314 | 26003H | 4035J | LP1Y-RV-107307-01-3 | LP1Y-RV-107307-01 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107307 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107307 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 215.5578 | 43.55 | sq ft | 15.97 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255313 | 26003H | 4034J | LP1Y-RV-107307-01-2 | LP1Y-RV-107307-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107307 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107307 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255312 | 26003H | 4033J | LP1Y-RV-107307-01-1 | LP1Y-RV-107307-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) (108) 107307 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107307 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 13.5 | 12 | 1.5 | 84.5219 | 25.77 | sq ft | 0.76 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255317 | 26003H | 4038J | LP1Y-RV-107408-01-3 | LP1Y-RV-107408-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) 107408 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107408 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255316 | 26003H | 4037J | LP1Y-RV-107408-01-2 | LP1Y-RV-107408-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) 107408 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107408 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 84 | 84 | 0 | 295.8375 | 61.37 | sq ft | 19.88 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255315 | 26003H | 4036J | LP1Y-RV-107408-01-1 | LP1Y-RV-107408-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 6" SS RV (315) 107408 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107408 |  | TFS00E005YSPP |  | 315-RV | NONE | 6" | 316 SS | 13.5 | 12 | 1.5 | 82.7781 | 25.43 | sq ft | 0.57 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255318 | 26003H | 4039J | LP1Y-RV-107423-01-1 | LP1Y-RV-107423-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS RV (315) P 107423 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107423 |  | TFS00E005YSPP |  | 315-RV | NONE | 2" | 316 SS | 13 | 13 | 0 | 64.42 | 24.46 | sq ft | 2.96 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255319 | 26003H | 4040C | LP1Y-S(130)-018072-02-1 | LP1Y-S(130)-018072-02 | 0 | N | PRI-2-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" CS S(130) (2) (103) 018072 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018072 |  | TFS00E005YSPP |  | 2-S(130) | P-5 | 2" | CS | 16.75 | 14 | 2.75 | 55.9193 | 30.16 | sq ft | 9.16 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255320 | 26003H | 4041C | LP1Y-S(130)-018072-02-2 | LP1Y-S(130)-018072-02 | 0 | N | PRI-2-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" CS S(130) (2) (103) 018072 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018072 |  | TFS00E005YSPP |  | 2-S(130) | P-5 | 2" | CS | 16 | 16 | 0 | 87.282 | 29.52 | sq ft | 20.52 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255321 | 26003H | 4042C | LP1Y-S(130)-018072-05-1 | LP1Y-S(130)-018072-05 | 0 | N | PRI-2-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" CS S(130) (2) (103) 018072 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018072 |  | TFS00E005YSPP |  | 2-S(130) | P-5 | 2" | CS | 13 | 10 | 3 | 63.289 | 20.53 | sq ft | 16.03 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258548 | 26003H | 4042CA | LP1Y-S(130)-018072-05-3 | LP1Y-S(130)-018072-05 | 0 | N | PRI-2-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P021 |  |  | LP1Y 2" CS S(130) (2) (103) 018072 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018072 |  | TFS00E005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255322 | 26003H | 4043C | LP1Y-S(130)-018072-05-2 | LP1Y-S(130)-018072-05 | 0 | N | PRI-2-1 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" CS S(130) (2) (103) 018072 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018072 |  | TFS00E005YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.5238 | 24.37 | sq ft | 1.88 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255323 | 26003H | 4044J | LP1Y-S(130)-166105-01-1 | LP1Y-S(130)-166105-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 1" SS S(130) (315) (103) 166105 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166105 |  | TFS00E005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 10 | 10 | 0 | 14.322 | 17.18 | sq ft | 8.68 | ft | 2026-02-13 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258549 | 26003H | 4045JA | LP1Y-STORMP-166104-04-3 | LP1Y-STORMP-166104-04 | 0 | N | PRI-2-1 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS STORMP (315) (108) 166104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166104 |  | TFS00E005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255325 | 26003H | 4046J | LP1Y-STORMP-166104-04-2 | LP1Y-STORMP-166104-04 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS STORMP (315) (108) 166104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166104 |  | TFS00E005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.45 | 9.67 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255324 | 26003H | 4045J | LP1Y-STORMP-166104-04-1 | LP1Y-STORMP-166104-04 | 0 | N | PRI-2-1 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS STORMP (315) (108) 166104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166104 |  | TFS00E005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 84.775 | 30.4 | sq ft | 10.9 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255326 | 26003H | 4047J | LP1Y-SW-166102-01-1 | LP1Y-SW-166102-01 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SW (315) 166102 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166102 |  | TFS00E005YSPP |  | 315-SW | NONE | 2" | 316 SS | 11 | 11 | 0 | 67.9183 | 24.86 | sq ft | 6.86 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255328 | 26003H | 4049J | LP1Y-SWP-107083-02-2 | LP1Y-SWP-107083-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 107083 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107083 |  | TFS00E005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.5463 | 4.87 | sq ft | 0.87 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255327 | 26003H | 4048J | LP1Y-SWP-107083-02-1 | LP1Y-SWP-107083-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 107083 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107083 |  | TFS00E005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 23 | 20 | 3 | 117.215 | 48.69 | sq ft | 19.69 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255330 | 26003H | 4051J | LP1Y-SWP-166103-04-2 | LP1Y-SWP-166103-04 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 166103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166103 |  | TFS00E005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.41 | 10.17 | sq ft | 3.17 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255329 | 26003H | 4050J | LP1Y-SWP-166103-04-1 | LP1Y-SWP-166103-04 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 166103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166103 |  | TFS00E005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 26.25 | 22 | 4.25 | 150.17 | 57.17 | sq ft | 33.17 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255331 | 26003H | 4052J | LP1Y-SWP-166103-05-1 | LP1Y-SWP-166103-05 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 166103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166103 |  | TFS00E005YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 7.71 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255332 | 26003H | 4053J | LP1Y-SWP-166103-05-2 | LP1Y-SWP-166103-05 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS SWP (315) (108) 166103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166103 |  | TFS00E005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 22.5 | 18 | 4.5 | 101.4366 | 51.52 | sq ft | 9.02 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255335 | 26003H | 4056J | LP1Y-WFO-017047-06-3 | LP1Y-WFO-017047-06 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 017047 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017047 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.7825 | 7.11 | sq ft | 7.11 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255333 | 26003H | 4054J | LP1Y-WFO-017047-06-1 | LP1Y-WFO-017047-06 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 017047 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017047 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 24.365 | 9.23 | sq ft | 9.23 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255334 | 26003H | 4055J | LP1Y-WFO-017047-06-2 | LP1Y-WFO-017047-06 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 017047 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017047 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.42 | 0.92 | sq ft | 0.92 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255336 | 26003H | 4057J | LP1Y-WFO-017047-07-1 | LP1Y-WFO-017047-07 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 017047 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017047 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.1238 | 4.21 | sq ft | 4.21 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255337 | 26003H | 4058J | LP1Y-WFO-017047-07-2 | LP1Y-WFO-017047-07 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 017047 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017047 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255340 | 26003H | 4061J | LP1Y-WFO-107110-02-3 | LP1Y-WFO-107110-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107110 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255338 | 26003H | 4059J | LP1Y-WFO-107110-02-1 | LP1Y-WFO-107110-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107110 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255339 | 26003H | 4060J | LP1Y-WFO-107110-02-2 | LP1Y-WFO-107110-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107110 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.94 | 2.25 | sq ft | 2.25 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255343 | 26003H | 4064J | LP1Y-WFO-107210-02-3 | LP1Y-WFO-107210-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107210 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255341 | 26003H | 4062J | LP1Y-WFO-107210-02-1 | LP1Y-WFO-107210-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107210 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255342 | 26003H | 4063J | LP1Y-WFO-107210-02-2 | LP1Y-WFO-107210-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107210 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.9125 | 2.24 | sq ft | 2.24 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255346 | 26003H | 4067J | LP1Y-WFO-107310-02-3 | LP1Y-WFO-107310-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107310 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107310 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255344 | 26003H | 4065J | LP1Y-WFO-107310-02-1 | LP1Y-WFO-107310-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107310 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107310 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255345 | 26003H | 4066J | LP1Y-WFO-107310-02-2 | LP1Y-WFO-107310-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107310 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107310 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.7612 | 2.18 | sq ft | 2.18 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255348 | 26003H | 4069J | LP1Y-WFO-107410-02-2 | LP1Y-WFO-107410-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107410 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.4375 | 1.3 | sq ft | 1.3 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255349 | 26003H | 4070J | LP1Y-WFO-107410-02-3 | LP1Y-WFO-107410-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107410 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255347 | 26003H | 4068J | LP1Y-WFO-107410-02-1 | LP1Y-WFO-107410-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 107410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107410 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255355 | 26003H | 4076J | LP1Y-WFO-196001-03-6 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255350 | 26003H | 4071J | LP1Y-WFO-196001-03-1 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.3913 | 11.89 | sq ft | 11.89 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255354 | 26003H | 4075J | LP1Y-WFO-196001-03-5 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9188 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255351 | 26003H | 4072J | LP1Y-WFO-196001-03-2 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.7113 | 4.06 | sq ft | 4.06 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255352 | 26003H | 4073J | LP1Y-WFO-196001-03-3 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255353 | 26003H | 4074J | LP1Y-WFO-196001-03-4 | LP1Y-WFO-196001-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196001 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196001 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-16; CL: Jacob Perez | 2026-04-17 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255361 | 26003H | 4082J | LP1Y-WFO-196002-03-6 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255356 | 26003H | 4077J | LP1Y-WFO-196002-03-1 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.3913 | 11.89 | sq ft | 11.89 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255359 | 26003H | 4080J | LP1Y-WFO-196002-03-4 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255360 | 26003H | 4081J | LP1Y-WFO-196002-03-5 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9188 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255358 | 26003H | 4079J | LP1Y-WFO-196002-03-3 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255357 | 26003H | 4078J | LP1Y-WFO-196002-03-2 | LP1Y-WFO-196002-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196002 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196002 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.67 | 4.04 | sq ft | 4.04 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255363 | 26003H | 4084J | LP1Y-WFO-196003-03-2 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.1238 | 8.38 | sq ft | 8.38 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255362 | 26003H | 4083J | LP1Y-WFO-196003-03-1 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 42.24 | 16 | sq ft | 16 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255364 | 26003H | 4085J | LP1Y-WFO-196003-03-3 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.72 | 2.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255365 | 26003H | 4086J | LP1Y-WFO-196003-03-4 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255366 | 26003H | 4087J | LP1Y-WFO-196003-03-5 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9875 | 1.51 | sq ft | 1.51 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255367 | 26003H | 4088J | LP1Y-WFO-196003-03-6 | LP1Y-WFO-196003-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196003 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196003 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255368 | 26003H | 4089J | LP1Y-WFO-196004-03-1 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 31.3913 | 11.89 | sq ft | 11.89 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255369 | 26003H | 4090J | LP1Y-WFO-196004-03-2 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 10.78 | 4.08 | sq ft | 4.08 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255370 | 26003H | 4091J | LP1Y-WFO-196004-03-3 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.3188 | 3.15 | sq ft | 3.15 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255371 | 26003H | 4092J | LP1Y-WFO-196004-03-4 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.7738 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255372 | 26003H | 4093J | LP1Y-WFO-196004-03-5 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.905 | 1.48 | sq ft | 1.48 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255373 | 26003H | 4094J | LP1Y-WFO-196004-03-6 | LP1Y-WFO-196004-03 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 2" SS WFO (36) 196004 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196004 |  | TFS00E005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255376 | 26003H | 4097J | LP1Y-WPC-017048-03-3 | LP1Y-WPC-017048-03 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 017048 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017048 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255377 | 26003H | 4098J | LP1Y-WPC-017048-03-4 | LP1Y-WPC-017048-03 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 017048 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017048 |  | TFS00E005YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255378 | 26003H | 4099J | LP1Y-WPC-017048-03-5 | LP1Y-WPC-017048-03 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 017048 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017048 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255374 | 26003H | 4095J | LP1Y-WPC-017048-03-1 | LP1Y-WPC-017048-03 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 017048 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017048 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255375 | 26003H | 4096J | LP1Y-WPC-017048-03-2 | LP1Y-WPC-017048-03 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 017048 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017048 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255384 | 26003H | 4105J | LP1Y-WPC-194102-01-6 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255383 | 26003H | 4104J | LP1Y-WPC-194102-01-5 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255382 | 26003H | 4103J | LP1Y-WPC-194102-01-4 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255379 | 26003H | 4100J | LP1Y-WPC-194102-01-1 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255380 | 26003H | 4101J | LP1Y-WPC-194102-01-2 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255381 | 26003H | 4102J | LP1Y-WPC-194102-01-3 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255390 | 26003H | 4111J | LP1Y-WPC-194102-01-9 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255391 | 26003H | 4112J | LP1Y-WPC-194102-01-10 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255389 | 26003H | 4110J | LP1Y-WPC-194102-01-8 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255388 | 26003H | 4109J | LP1Y-WPC-194102-01-13 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255387 | 26003H | 4108J | LP1Y-WPC-194102-01-12 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255386 | 26003H | 4107J | LP1Y-WPC-194102-01-11 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255385 | 26003H | 4106J | LP1Y-WPC-194102-01-7 | LP1Y-WPC-194102-01 | 0 | N | PRI-2-1 | 2026-04-16 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-17; CL: Jacob Perez; DD: 2026-04-17; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255392 | 26003H | 4113J | LP1Y-WPC-194102-02-1 | LP1Y-WPC-194102-02 | 0 | N | PRI-2-1 | [5 empty] | Released to Production | P021 | 2026-07-20 |  | LP1Y 1.25" SS WPC (36) (108) 194102 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194102 |  | TFS00E005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 35.29 | 27.48 | sq ft | 7.48 | ft | 2026-02-13 |  |  |  |  | 2026-04-17 | Jacob Perez | 2026-04-17 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255419 | 26003H | 4114J | LP1Y-DMSO-010029-04-1 | LP1Y-DMSO-010029-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 010029 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010029 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 26.75 | 26 | 0.75 | 300.9382 | 29.01 | sq ft | 2.51 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255420 | 26003H | 4115J | LP1Y-DMSO-010029-04-2 | LP1Y-DMSO-010029-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 010029 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010029 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 28.4206 | 6.56 | sq ft | 5.06 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255421 | 26003H | 4116J | LP1Y-DMSO-110002-01-1 | LP1Y-DMSO-110002-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.2975 | 7.22 | sq ft | 5.72 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255422 | 26003H | 4117J | LP1Y-DMSO-110002-01-2 | LP1Y-DMSO-110002-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.9338 | 8.51 | sq ft | 5.51 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255423 | 26003H | 4118J | LP1Y-DMSO-110002-04-1 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255424 | 26003H | 4119J | LP1Y-DMSO-110002-04-2 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.1625 | 6.91 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255425 | 26003H | 4120J | LP1Y-DMSO-110002-04-3 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 20.25 | 18 | 2.25 | 125.0238 | 42.55 | sq ft | 6.05 | ft | 2026-02-13 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255426 | 26003H | 4121J | LP1Y-DMSO-110002-04-4 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 8 | 8 | 0 | 65.8 | 23.08 | sq ft | 2.08 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255427 | 26003H | 4122J | LP1Y-DMSO-110002-04-5 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 68.5913 | 23.6 | sq ft | 5.6 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255428 | 26003H | 4123J | LP1Y-DMSO-110002-04-6 | LP1Y-DMSO-110002-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110002 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110002 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 12 | 12 | 0 | 73.7413 | 30.6 | sq ft | 24.6 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255429 | 26003H | 4124J | LP1Y-DMSO-110201-01-1 | LP1Y-DMSO-110201-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110201 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110201 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255431 | 26003H | 4126J | LP1Y-DMSO-110201-01-3 | LP1Y-DMSO-110201-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110201 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110201 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 21 | 20 | 1 | 298.553 | 27.55 | sq ft | 3.05 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255430 | 26003H | 4125J | LP1Y-DMSO-110201-01-2 | LP1Y-DMSO-110201-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110201 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110201 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 29.5112 | 7.87 | sq ft | 2.37 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255433 | 26003H | 4128J | LP1Y-DMSO-110203-01-2 | LP1Y-DMSO-110203-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 31.0638 | 12.5 | sq ft | 2.63 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255432 | 26003H | 4127J | LP1Y-DMSO-110203-01-1 | LP1Y-DMSO-110203-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 6" | 316 SS | 6 | 6 | 0 | 39.52 | 10.3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255434 | 26003H | 4129J | LP1Y-DMSO-110203-01-3 | LP1Y-DMSO-110203-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 12 | 11 | 1 | 490.0914 | 37.52 | sq ft | 9.29 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255435 | 26003H | 4130J | LP1Y-DMSO-110203-02-1 | LP1Y-DMSO-110203-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255436 | 26003H | 4131J | LP1Y-DMSO-110203-02-2 | LP1Y-DMSO-110203-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 4 | 4 | 0 | 34.275 | 7.6 | sq ft | 2.5 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255437 | 26003H | 4132J | LP1Y-DMSO-110203-02-3 | LP1Y-DMSO-110203-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 4 | 4 | 0 | 49.3519 | 10.83 | sq ft | 5.19 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255438 | 26003H | 4133J | LP1Y-DMSO-110203-02-4 | LP1Y-DMSO-110203-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110203 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110203 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 24 | 24 | 0 | 480.9144 | 28.12 | sq ft | 5.1 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255441 | 26003H | 4136J | LP1Y-DMSO-110204-01-3 | LP1Y-DMSO-110204-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110204 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110204 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 16.3525 | 8.11 | sq ft | 2.61 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255439 | 26003H | 4134J | LP1Y-DMSO-110204-01-1 | LP1Y-DMSO-110204-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110204 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110204 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 2 | 2 | 0 | 22.77 | 9.29 | sq ft | 7.79 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255440 | 26003H | 4135J | LP1Y-DMSO-110204-01-2 | LP1Y-DMSO-110204-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110204 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110204 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 23.2413 | 14.72 | sq ft | 2.72 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255442 | 26003H | 4137J | LP1Y-DMSO-110204-04-1 | LP1Y-DMSO-110204-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110204 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110204 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 9.75 | 6 | 3.75 | 65.3863 | 23.37 | sq ft | 5.87 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255443 | 26003H | 4138J | LP1Y-DMSO-110205-01-1 | LP1Y-DMSO-110205-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 1.5 | 1.5 | 0 | 5.61 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255444 | 26003H | 4139J | LP1Y-DMSO-110205-01-2 | LP1Y-DMSO-110205-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 12 | 11 | 1 | 47.4933 | 21.55 | sq ft | 4.47 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255445 | 26003H | 4140J | LP1Y-DMSO-110205-01-3 | LP1Y-DMSO-110205-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 8 | 8 | 0 | 26.9291 | 6.89 | sq ft | 0.41 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255446 | 26003H | 4141J | LP1Y-DMSO-110205-01-4 | LP1Y-DMSO-110205-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 54.25 | 13 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255447 | 26003H | 4142J | LP1Y-DMSO-110205-02-1 | LP1Y-DMSO-110205-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 11 | 10 | 1 | 55.4916 | 16.44 | sq ft | 2.32 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255448 | 26003H | 4143J | LP1Y-DMSO-110205-02-2 | LP1Y-DMSO-110205-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 8 | 8 | 0 | 38.3244 | 9.33 | sq ft | 2.44 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255449 | 26003H | 4144J | LP1Y-DMSO-110205-03-1 | LP1Y-DMSO-110205-03 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 26 | 26 | 0 | 491.1347 | 32.96 | sq ft | 9.64 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255450 | 26003H | 4145J | LP1Y-DMSO-110205-03-2 | LP1Y-DMSO-110205-03 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 4" | 316 SS | 12 | 12 | 0 | 57.8425 | 18.99 | sq ft | 1.49 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255451 | 26003H | 4146J | LP1Y-DMSO-110205-04-1 | LP1Y-DMSO-110205-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 10 | 10 | 0 | 77.4994 | 20.68 | sq ft | 3.68 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255452 | 26003H | 4147J | LP1Y-DMSO-110205-05-1 | LP1Y-DMSO-110205-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 15 | 14 | 1 | 61.7905 | 19.3 | sq ft | 7.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255453 | 26003H | 4148J | LP1Y-DMSO-110205-07-1 | LP1Y-DMSO-110205-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 9 | 9 | 0 | 59.7505 | 13.8 | sq ft | 10.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255454 | 26003H | 4149J | LP1Y-DMSO-110205-08-1 | LP1Y-DMSO-110205-08 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 33 | 32 | 1 | 558.5334 | 40.59 | sq ft | 6.09 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255455 | 26003H | 4150J | LP1Y-DMSO-110205-09-1 | LP1Y-DMSO-110205-09 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 30 | 29 | 1 | 553.3865 | 39.4 | sq ft | 6.4 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255456 | 26003H | 4151J | LP1Y-DMSO-110205-10-1 | LP1Y-DMSO-110205-10 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 10 | 10 | 0 | 75.8215 | 20.64 | sq ft | 4.64 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255457 | 26003H | 4152J | LP1Y-DMSO-110205-10-2 | LP1Y-DMSO-110205-10 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 18.75 | 18 | 0.75 | 118.3775 | 38.09 | sq ft | 4.59 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255459 | 26003H | 4154J | LP1Y-DMSO-110205-11-2 | LP1Y-DMSO-110205-11 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 12 | 12 | 0 | 71.9561 | 16.61 | sq ft | 12.11 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255458 | 26003H | 4153J | LP1Y-DMSO-110205-11-1 | LP1Y-DMSO-110205-11 | 0 | N | PRI-2-2 | 2026-04-17 | 2026-04-25 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 282.9035 | 17.6 | sq ft | 7.6 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258550 | 26003H | 4153JA | LP1Y-DMSO-110205-11-3 | LP1Y-DMSO-110205-11 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 |  |  | LP1Y 3" SS DMSO (315) P (108) 110205 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110205 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 9 | 9 | 0 | 60.6526 | 14.01 | sq ft | 11.01 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255461 | 26003H | 4156J | LP1Y-DMSO-110207-02-2 | LP1Y-DMSO-110207-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110207 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110207 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 10 | 10 | 0 | 47.3275 | 20.59 | sq ft | 14.59 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255462 | 26003H | 4157J | LP1Y-DMSO-110207-02-3 | LP1Y-DMSO-110207-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110207 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110207 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 12 | 12 | 0 | 69.8913 | 28.47 | sq ft | 23.97 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255460 | 26003H | 4155J | LP1Y-DMSO-110207-02-1 | LP1Y-DMSO-110207-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110207 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110207 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 15.5113 | 8.22 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255464 | 26003H | 4159J | LP1Y-DMSO-110208-01-2 | LP1Y-DMSO-110208-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110208 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110208 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 12 | 12 | 0 | 41.9175 | 19.72 | sq ft | 8.72 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255463 | 26003H | 4158J | LP1Y-DMSO-110208-01-1 | LP1Y-DMSO-110208-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS DMSO (315) P (108) 110208 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110208 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 24.5588 | 14.67 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255466 | 26003H | 4161J | LP1Y-DMSO-110208-02-2 | LP1Y-DMSO-110208-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110208 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110208 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 63.4625 | 22.32 | sq ft | 2.82 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255465 | 26003H | 4160J | LP1Y-DMSO-110208-02-1 | LP1Y-DMSO-110208-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110208 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110208 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255467 | 26003H | 4162J | LP1Y-DMSO-110212-01-1 | LP1Y-DMSO-110212-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110212 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110212 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255468 | 26003H | 4163J | LP1Y-DMSO-110212-01-2 | LP1Y-DMSO-110212-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110212 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110212 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 24.7527 | 6.77 | sq ft | 1.27 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255469 | 26003H | 4164J | LP1Y-DMSO-110212-01-3 | LP1Y-DMSO-110212-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 110212 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110212 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 18 | 17 | 1 | 298.9614 | 28.89 | sq ft | 3.39 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255471 | 26003H | 4166J | LP1Y-DMSO-176202-05-2 | LP1Y-DMSO-176202-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 59.4748 | 13.73 | sq ft | 12.23 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255472 | 26003H | 4167J | LP1Y-DMSO-176202-05-3 | LP1Y-DMSO-176202-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 18 | 18 | 0 | 79.0199 | 18.24 | sq ft | 12.24 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255470 | 26003H | 4165J | LP1Y-DMSO-176202-05-1 | LP1Y-DMSO-176202-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 21 | 21 | 0 | 312.8482 | 25.57 | sq ft | 8.57 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255473 | 26003H | 4168J | LP1Y-DMSO-176202-06-1 | LP1Y-DMSO-176202-06 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 12 | 12 | 0 | 38.7059 | 13.09 | sq ft | 2.09 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255474 | 26003H | 4169J | LP1Y-DMSO-176202-07-1 | LP1Y-DMSO-176202-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E009YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 27 | 25 | 2 | 552.158 | 41.05 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255475 | 26003H | 4170J | LP1Y-N2(100)-018038-02-1 | LP1Y-N2(100)-018038-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 018038 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018038 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255476 | 26003H | 4171J | LP1Y-N2(100)-018038-02-2 | LP1Y-N2(100)-018038-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 018038 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018038 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 88.8938 | 29.01 | sq ft | 14.51 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255478 | 26003H | 4173J | LP1Y-N2(100)-181012-02-2 | LP1Y-N2(100)-181012-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181012 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181012 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 45.805 | 20.02 | sq ft | 15.52 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255477 | 26003H | 4172J | LP1Y-N2(100)-181012-02-1 | LP1Y-N2(100)-181012-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181012 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181012 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 46.9838 | 18.46 | sq ft | 16.96 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255479 | 26003H | 4174J | LP1Y-N2(100)-181012-03-1 | LP1Y-N2(100)-181012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181012 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181012 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 32.8361 | 28.38 | sq ft | 1.38 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255480 | 26003H | 4175J | LP1Y-N2(100)-181012-03-2 | LP1Y-N2(100)-181012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181012 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181012 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 45.4233 | 38.64 | sq ft | 2.64 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255481 | 26003H | 4176J | LP1Y-N2(100)-181012-03-3 | LP1Y-N2(100)-181012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181012 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181012 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.19 | 6.04 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255483 | 26003H | 4178J | LP1Y-N2(100)-181016-02-2 | LP1Y-N2(100)-181016-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181016 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181016 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 51.7688 | 20.94 | sq ft | 17.94 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255482 | 26003H | 4177J | LP1Y-N2(100)-181016-02-1 | LP1Y-N2(100)-181016-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181016 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181016 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 52.1675 | 21.76 | sq ft | 17.26 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255484 | 26003H | 4179J | LP1Y-N2(100)-181016-03-1 | LP1Y-N2(100)-181016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181016 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181016 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 32.9536 | 28.46 | sq ft | 1.46 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255485 | 26003H | 4180J | LP1Y-N2(100)-181016-03-2 | LP1Y-N2(100)-181016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181016 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181016 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 45.438 | 38.65 | sq ft | 2.65 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255486 | 26003H | 4181J | LP1Y-N2(100)-181016-03-3 | LP1Y-N2(100)-181016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181016 | N2(100) |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181016 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.19 | 6.04 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255487 | 26003H | 4182J | LP1Y-N2(100)-181079-02-1 | LP1Y-N2(100)-181079-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181079 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181079 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 25.2063 | 13.12 | sq ft | 6.12 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255488 | 26003H | 4183J | LP1Y-N2(100)-181079-02-2 | LP1Y-N2(100)-181079-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181079 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181079 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 13 | 13 | 0 | 72.3775 | 26.89 | sq ft | 7.89 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255489 | 26003H | 4184J | LP1Y-N2(100)-181091-01-1 | LP1Y-N2(100)-181091-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 0.5" SS N2(100) (315) E 181091 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181091 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 1/2" | 316 SS | 1 | 0 | 1 | 2.1398 | 4.1 | sq ft | 2.1 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255490 | 26003H | 4185J | LP1Y-N2(100)-181106-01-1 | LP1Y-N2(100)-181106-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255492 | 26003H | 4187J | LP1Y-N2(100)-181106-01-3 | LP1Y-N2(100)-181106-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 40.04 | 16.5 | sq ft | 13.5 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255491 | 26003H | 4186J | LP1Y-N2(100)-181106-01-2 | LP1Y-N2(100)-181106-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8.25 | 6 | 2.25 | 59.32 | 19.5 | sq ft | 4 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255493 | 26003H | 4188J | LP1Y-N2(100)-181106-04-1 | LP1Y-N2(100)-181106-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 46.31 | 18.21 | sq ft | 16.71 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255494 | 26003H | 4189J | LP1Y-N2(100)-181106-04-2 | LP1Y-N2(100)-181106-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 45.2925 | 17.82 | sq ft | 16.32 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255495 | 26003H | 4190J | LP1Y-N2(100)-181106-05-1 | LP1Y-N2(100)-181106-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 6.7788 | 3.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255496 | 26003H | 4191J | LP1Y-N2(100)-181106-05-2 | LP1Y-N2(100)-181106-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E 181106 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.5 | 10 | 2.5 | 63.2371 | 50.91 | sq ft | 5.91 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255497 | 26003H | 4192J | LP1Y-N2(100)-181106-06-1 | LP1Y-N2(100)-181106-06 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2(100) (315) E (108) 181106 | N2(100) |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181106 |  | TFS00E009YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 35.5795 | 29.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255498 | 26003H | 4193J | LP1Y-N2-181087-01-1 | LP1Y-N2-181087-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2 (315) E 181087 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181087 |  | TFS00E009YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255499 | 26003H | 4194J | LP1Y-N2-181087-01-2 | LP1Y-N2-181087-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2 (315) E 181087 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181087 |  | TFS00E009YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255500 | 26003H | 4195J | LP1Y-N2-181087-01-3 | LP1Y-N2-181087-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS N2 (315) E 181087 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181087 |  | TFS00E009YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 2 | 4.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-04-18 | Jacob Perez | 2026-04-18 | George Allahverdian | 2026-04-20 | Jacob Perez | 2026-04-20 | Jacob Perez | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255501 | 26003H | 4196J | LP1Y-PV-110061-01-1 | LP1Y-PV-110061-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110061 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 59.0388 | 29.23 | sq ft | 14.23 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255502 | 26003H | 4197J | LP1Y-PV-110061-02-1 | LP1Y-PV-110061-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110061 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 12 | 12 | 0 | 86.4225 | 28.66 | sq ft | 11.66 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255503 | 26003H | 4198J | LP1Y-PV-110061-02-2 | LP1Y-PV-110061-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110061 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 8 | 8 | 0 | 24.2138 | 10.51 | sq ft | 7.51 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255504 | 26003H | 4199J | LP1Y-PV-110066-01-1 | LP1Y-PV-110066-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110066 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110066 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 59.0388 | 29.23 | sq ft | 14.23 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255505 | 26003H | 4200J | LP1Y-PV-110066-02-1 | LP1Y-PV-110066-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110066 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110066 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 10 | 10 | 0 | 84.9925 | 27.45 | sq ft | 11.95 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255506 | 26003H | 4201J | LP1Y-PV-110066-02-2 | LP1Y-PV-110066-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110066 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110066 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 10 | 10 | 0 | 25.19 | 11.54 | sq ft | 7.04 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255507 | 26003H | 4202J | LP1Y-PV-110067-02-1 | LP1Y-PV-110067-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 36.5 | 32 | 4.5 | 296.7763 | 99.62 | sq ft | 36.12 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255508 | 26003H | 4203J | LP1Y-PV-110067-02-2 | LP1Y-PV-110067-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 86.1425 | 34.95 | sq ft | 31.95 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255509 | 26003H | 4204J | LP1Y-PV-110067-03-1 | LP1Y-PV-110067-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 22.25 | 20 | 2.25 | 186.565 | 64.6 | sq ft | 32.1 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255510 | 26003H | 4205J | LP1Y-PV-110067-03-2 | LP1Y-PV-110067-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 22.25 | 20 | 2.25 | 147.5138 | 52.13 | sq ft | 16.63 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255511 | 26003H | 4206J | LP1Y-PV-110067-04-1 | LP1Y-PV-110067-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 16 | 16 | 0 | 78.6813 | 26.39 | sq ft | 7.89 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255512 | 26003H | 4207J | LP1Y-PV-110067-04-2 | LP1Y-PV-110067-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 25.2313 | 10.89 | sq ft | 7.89 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255513 | 26003H | 4208J | LP1Y-PV-110067-05-1 | LP1Y-PV-110067-05 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PV (315) (108) 110067 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110067 |  | TFS00E009YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 44.9038 | 23.21 | sq ft | 9.71 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255515 | 26003H | 4210J | LP1Y-PVP-110215-01-2 | LP1Y-PVP-110215-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS PVP (315) P (108) 110215 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110215 |  | TFS00E009YSPP |  | 315-PVP | NONE | 3" | 316 SS | 10 | 10 | 0 | 19.8238 | 10.31 | sq ft | 1.31 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255516 | 26003H | 4211J | LP1Y-PVP-110215-01-3 | LP1Y-PVP-110215-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS PVP (315) P (108) 110215 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110215 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 16 | 16 | 0 | 66.9113 | 21.93 | sq ft | 3.43 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255514 | 26003H | 4209J | LP1Y-PVP-110215-01-1 | LP1Y-PVP-110215-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 3" SS PVP (315) P (108) 110215 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110215 |  | TFS00E009YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 12.75 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255517 | 26003H | 4212J | LP1Y-PVP-110218-06-1 | LP1Y-PVP-110218-06 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 158.8725 | 53.45 | sq ft | 22.45 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255518 | 26003H | 4213J | LP1Y-PVP-110218-07-1 | LP1Y-PVP-110218-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255519 | 26003H | 4214J | LP1Y-PVP-110218-07-2 | LP1Y-PVP-110218-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 22.8525 | 13.32 | sq ft | 5.32 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255520 | 26003H | 4215J | LP1Y-PVP-110218-07-3 | LP1Y-PVP-110218-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 2 | 2 | 0 | 12.925 | 5.56 | sq ft | 4.06 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255521 | 26003H | 4216J | LP1Y-PVP-110218-07-4 | LP1Y-PVP-110218-07 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 16 | 16 | 0 | 48.455 | 21.69 | sq ft | 14.19 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255522 | 26003H | 4217J | LP1Y-PVP-110606-01-1 | LP1Y-PVP-110606-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110606 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110606 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255523 | 26003H | 4218J | LP1Y-PVP-110606-01-2 | LP1Y-PVP-110606-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110606 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110606 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 13.7938 | 8.8 | sq ft | 1.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255524 | 26003H | 4219J | LP1Y-PVP-110606-01-3 | LP1Y-PVP-110606-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110606 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110606 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 16 | 16 | 0 | 66.9525 | 21.95 | sq ft | 3.45 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255525 | 26003H | 4220J | LP1Y-PVP-110806-01-1 | LP1Y-PVP-110806-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110806 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110806 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255526 | 26003H | 4221J | LP1Y-PVP-110806-01-2 | LP1Y-PVP-110806-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110806 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110806 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 13.6013 | 8.72 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255527 | 26003H | 4222J | LP1Y-PVP-110806-01-3 | LP1Y-PVP-110806-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PVP (315) P (108) 110806 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110806 |  | TFS00E009YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 64.505 | 20.35 | sq ft | 3.35 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255529 | 26003H | 4224J | LP1Y-PWP-110074-04-2 | LP1Y-PWP-110074-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PWP (315) (108) 110074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110074 |  | TFS00E009YSPP |  | 315-PWP | NONE | 2" | 316 SS | 15 | 12 | 3 | 93.0525 | 37.53 | sq ft | 11.53 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255528 | 26003H | 4223J | LP1Y-PWP-110074-04-1 | LP1Y-PWP-110074-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PWP (315) (108) 110074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110074 |  | TFS00E009YSPP |  | 315-PWP | NONE | 2" | 316 SS | 12 | 12 | 0 | 22.8013 | 11.97 | sq ft | 5.97 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255530 | 26003H | 4225J | LP1Y-PWP-110074-05-1 | LP1Y-PWP-110074-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PWP (315) (108) 110074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110074 |  | TFS00E009YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.6525 | 13.74 | sq ft | 1.74 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255532 | 26003H | 4227J | LP1Y-PWP-110074-05-3 | LP1Y-PWP-110074-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PWP (315) (108) 110074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110074 |  | TFS00E009YSPP |  | 315-PWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 103.1825 | 29.32 | sq ft | 2.32 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255531 | 26003H | 4226J | LP1Y-PWP-110074-05-2 | LP1Y-PWP-110074-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS PWP (315) (108) 110074 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110074 |  | TFS00E009YSPP |  | 315-PWP | NONE | 2" | 316 SS | 20 | 20 | 0 | 122.325 | 40.15 | sq ft | 6.15 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255533 | 26003H | 4228J | LP1Y-RV-110206-01-1 | LP1Y-RV-110206-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110206 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110206 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255534 | 26003H | 4229J | LP1Y-RV-110206-01-2 | LP1Y-RV-110206-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110206 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110206 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 4 | 4 | 0 | 7.6625 | 4.91 | sq ft | 1.91 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255535 | 26003H | 4230J | LP1Y-RV-110206-01-3 | LP1Y-RV-110206-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110206 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110206 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 5 | 5 | 0 | 55.6025 | 19.2 | sq ft | 3.2 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255536 | 26003H | 4231J | LP1Y-RV-110214-01-1 | LP1Y-RV-110214-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110214 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110214 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 15 | 15 | 0 | 63.5088 | 23.53 | sq ft | 4.53 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255538 | 26003H | 4233J | LP1Y-RV-110223-01-2 | LP1Y-RV-110223-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110223 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110223 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 54.3 | 19.8 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255537 | 26003H | 4232J | LP1Y-RV-110223-01-1 | LP1Y-RV-110223-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110223 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110223 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255539 | 26003H | 4234J | LP1Y-RV-110223-01-3 | LP1Y-RV-110223-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110223 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110223 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255541 | 26003H | 4236J | LP1Y-RV-110223-01-5 | LP1Y-RV-110223-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110223 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110223 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 24 | 24 | 0 | 152.4422 | 30.65 | sq ft | 14.03 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255540 | 26003H | 4235J | LP1Y-RV-110223-01-4 | LP1Y-RV-110223-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110223 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110223 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 141.1094 | 29.14 | sq ft | 7.97 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255543 | 26003H | 4238J | LP1Y-RV-110602-01-2 | LP1Y-RV-110602-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110602 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110602 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 9 | 9 | 0 | 61.8725 | 22.24 | sq ft | 4.74 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255542 | 26003H | 4237J | LP1Y-RV-110602-01-1 | LP1Y-RV-110602-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110602 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110602 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255548 | 26003H | 4243J | LP1Y-RV-110609-01-5 | LP1Y-RV-110609-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110609 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110609 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 140.9672 | 29 | sq ft | 11.61 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255544 | 26003H | 4239J | LP1Y-RV-110609-01-1 | LP1Y-RV-110609-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110609 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110609 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255546 | 26003H | 4241J | LP1Y-RV-110609-01-3 | LP1Y-RV-110609-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110609 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110609 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255547 | 26003H | 4242J | LP1Y-RV-110609-01-4 | LP1Y-RV-110609-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110609 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110609 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 30 | 30 | 0 | 139.4625 | 28.82 | sq ft | 7.79 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255545 | 26003H | 4240J | LP1Y-RV-110609-01-2 | LP1Y-RV-110609-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 6" SS RV (315) (108) 110609 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110609 |  | TFS00E009YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 54.3 | 19.8 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255549 | 26003H | 4244J | LP1Y-RV-110611-01-1 | LP1Y-RV-110611-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110611 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110611 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.44 | 5 | sq ft | 3.5 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255550 | 26003H | 4245J | LP1Y-RV-110611-01-2 | LP1Y-RV-110611-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110611 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110611 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 13.25 | 11 | 2.25 | 64.9275 | 27.09 | sq ft | 4.09 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255551 | 26003H | 4246J | LP1Y-RV-110809-01-1 | LP1Y-RV-110809-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS RV (315) (108) 110809 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110809 |  | TFS00E009YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255552 | 26003H | 4247J | LP1Y-RV-110809-01-2 | LP1Y-RV-110809-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS RV (315) (108) 110809 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110809 |  | TFS00E009YSPP |  | 315-RV | NONE | 4" | 316 SS | 5.5 | 4 | 1.5 | 36.245 | 17 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255555 | 26003H | 4250J | LP1Y-RV-110809-01-5 | LP1Y-RV-110809-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS RV (315) (108) 110809 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110809 |  | TFS00E009YSPP |  | 315-RV | NONE | 4" | 316 SS | 20 | 20 | 0 | 82.7406 | 20.27 | sq ft | 12.4 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255553 | 26003H | 4248J | LP1Y-RV-110809-01-3 | LP1Y-RV-110809-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS RV (315) (108) 110809 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110809 |  | TFS00E009YSPP |  | 315-RV | NONE | 4" | 316 SS | 8 | 8 | 0 | 44.9 | 11 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255554 | 26003H | 4249J | LP1Y-RV-110809-01-4 | LP1Y-RV-110809-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 4" SS RV (315) (108) 110809 | RV |  | 108,NI | 84.2 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110809 |  | TFS00E009YSPP |  | 315-RV | NONE | 4" | 316 SS | 16 | 16 | 0 | 66.2163 | 16.15 | sq ft | 6.63 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255556 | 26003H | 4251J | LP1Y-RV-110811-01-1 | LP1Y-RV-110811-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110811 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110811 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255557 | 26003H | 4252J | LP1Y-RV-110811-01-2 | LP1Y-RV-110811-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS RV (315) P (108) 110811 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110811 |  | TFS00E009YSPP |  | 315-RV | NONE | 2" | 316 SS | 11 | 11 | 0 | 62.9313 | 22.64 | sq ft | 5.14 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255558 | 26003H | 4253C | LP1Y-S(130)-018069-02-1 | LP1Y-S(130)-018069-02 | 1 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 16.75 | 16 | 0.75 | 51.7941 | 29.03 | sq ft | 8.03 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255559 | 26003H | 4254C | LP1Y-S(130)-018069-02-2 | LP1Y-S(130)-018069-02 | 1 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 48.0984 | 17.72 | sq ft | 10.22 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255560 | 26003H | 4255C | LP1Y-S(130)-018069-02-3 | LP1Y-S(130)-018069-02 | 1 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 10 | 10 | 0 | 43.4672 | 15.09 | sq ft | 10.59 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255561 | 26003H | 4256C | LP1Y-S(130)-018069-05-1 | LP1Y-S(130)-018069-05 | 0 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 12 | 12 | 0 | 53.926 | 19.02 | sq ft | 13.02 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255562 | 26003H | 4257C | LP1Y-S(130)-018069-05-2 | LP1Y-S(130)-018069-05 | 0 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 16 | 16 | 0 | 139.5195 | 42.77 | sq ft | 35.27 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255563 | 26003H | 4258C | LP1Y-S(130)-018069-06-1 | LP1Y-S(130)-018069-06 | 0 | N | PRI-2-2 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" CS S(130) (2) (103) 018069 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018069 |  | TFS00E009YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 34.4857 | 24.36 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255564 | 26003H | 4259J | LP1Y-S(130)-166405-01-1 | LP1Y-S(130)-166405-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 1" SS S(130) (315) (103) 166405 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166405 |  | TFS00E009YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 10 | 10 | 0 | 11.9323 | 16.67 | sq ft | 7.17 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255565 | 26003H | 4260J | LP1Y-S(130)-166405-01-2 | LP1Y-S(130)-166405-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 1" SS S(130) (315) (103) 166405 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166405 |  | TFS00E009YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 3.9255 | 2.9 | sq ft | 2.4 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255566 | 26003H | 4261J | LP1Y-STORMP-166404-04-1 | LP1Y-STORMP-166404-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS STORMP (315) (108) 166404 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166404 |  | TFS00E009YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 31.0613 | 13.77 | sq ft | 9.27 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255567 | 26003H | 4262J | LP1Y-STORMP-166404-04-2 | LP1Y-STORMP-166404-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS STORMP (315) (108) 166404 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166404 |  | TFS00E009YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.75 | 12 | 0.75 | 88.1963 | 33.33 | sq ft | 9.83 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255568 | 26003H | 4263J | LP1Y-STORMP-166404-04-3 | LP1Y-STORMP-166404-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS STORMP (315) (108) 166404 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166404 |  | TFS00E009YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.6425 | 9.74 | sq ft | 4.24 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255569 | 26003H | 4264J | LP1Y-SW-166402-01-1 | LP1Y-SW-166402-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SW (315) 166402 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166402 |  | TFS00E009YSPP |  | 315-SW | NONE | 2" | 316 SS | 7 | 7 | 0 | 53.5094 | 19.58 | sq ft | 2.08 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255570 | 26003H | 4265J | LP1Y-SW-166402-01-2 | LP1Y-SW-166402-01 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SW (315) 166402 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166402 |  | TFS00E009YSPP |  | 315-SW | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.2913 | 5.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255572 | 26003H | 4267J | LP1Y-SWP-110084-04-2 | LP1Y-SWP-110084-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 110084 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110084 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 17 | 14 | 3 | 99.295 | 40.56 | sq ft | 13.06 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255571 | 26003H | 4266J | LP1Y-SWP-110084-04-1 | LP1Y-SWP-110084-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 110084 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110084 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 23.925 | 11.73 | sq ft | 5.73 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255573 | 26003H | 4268J | LP1Y-SWP-110084-04-3 | LP1Y-SWP-110084-04 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 110084 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110084 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.57 | 4.5 | sq ft | 0.5 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255575 | 26003H | 4270J | LP1Y-SWP-166403-04-2 | LP1Y-SWP-166403-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 166403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166403 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 12.75 | 12 | 0.75 | 88.1963 | 33.33 | sq ft | 9.83 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255574 | 26003H | 4269J | LP1Y-SWP-166403-04-1 | LP1Y-SWP-166403-04 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 166403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166403 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 37.7438 | 16.3 | sq ft | 11.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255576 | 26003H | 4271J | LP1Y-SWP-166403-05-1 | LP1Y-SWP-166403-05 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 166403 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166403 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 13.25 | 11 | 2.25 | 42.337 | 31.76 | sq ft | 3.76 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255577 | 26003H | 4272J | LP1Y-SWP-166403-06-1 | LP1Y-SWP-166403-06 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 166403 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166403 |  | TFS00E009YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 7.71 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255578 | 26003H | 4273J | LP1Y-SWP-166403-06-2 | LP1Y-SWP-166403-06 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS SWP (315) (108) 166403 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166403 |  | TFS00E009YSPP |  | 315-SWP | NONE | 2" | 316 SS | 9.75 | 7.5 | 2.25 | 64.38 | 25.08 | sq ft | 5.08 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255579 | 26003H | 4274J | LP1Y-WFO-017011-08-1 | LP1Y-WFO-017011-08 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 24.365 | 9.23 | sq ft | 9.23 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255580 | 26003H | 4275J | LP1Y-WFO-017011-08-2 | LP1Y-WFO-017011-08 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.0875 | 1.93 | sq ft | 1.93 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255581 | 26003H | 4276J | LP1Y-WFO-017011-08-3 | LP1Y-WFO-017011-08 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.2313 | 5.39 | sq ft | 5.39 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255584 | 26003H | 4279J | LP1Y-WFO-017011-09-3 | LP1Y-WFO-017011-09 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.96 | 1.5 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255585 | 26003H | 4280J | LP1Y-WFO-017011-09-4 | LP1Y-WFO-017011-09 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255582 | 26003H | 4277J | LP1Y-WFO-017011-09-1 | LP1Y-WFO-017011-09 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 49.17 | 18.63 | sq ft | 18.63 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255583 | 26003H | 4278J | LP1Y-WFO-017011-09-2 | LP1Y-WFO-017011-09 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9325 | 1.49 | sq ft | 1.49 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255587 | 26003H | 4282J | LP1Y-WFO-017011-10-2 | LP1Y-WFO-017011-10 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-21; CL: Jacob Perez; DD: 2026-04-21; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255586 | 26003H | 4281J | LP1Y-WFO-017011-10-1 | LP1Y-WFO-017011-10 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 017011 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017011 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.19 | 5.38 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255589 | 26003H | 4284J | LP1Y-WFO-110221-02-2 | LP1Y-WFO-110221-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110221 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110221 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1038 | 0.8 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255590 | 26003H | 4285J | LP1Y-WFO-110221-02-3 | LP1Y-WFO-110221-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110221 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110221 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255592 | 26003H | 4287J | LP1Y-WFO-110221-02-5 | LP1Y-WFO-110221-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110221 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110221 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255588 | 26003H | 4283J | LP1Y-WFO-110221-02-1 | LP1Y-WFO-110221-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110221 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110221 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255591 | 26003H | 4286J | LP1Y-WFO-110221-02-4 | LP1Y-WFO-110221-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110221 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110221 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2588 | 1.23 | sq ft | 1.23 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255594 | 26003H | 4289J | LP1Y-WFO-110607-02-2 | LP1Y-WFO-110607-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110607 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110607 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1038 | 0.8 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255595 | 26003H | 4290J | LP1Y-WFO-110607-02-3 | LP1Y-WFO-110607-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110607 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110607 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255596 | 26003H | 4291J | LP1Y-WFO-110607-02-4 | LP1Y-WFO-110607-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110607 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110607 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2588 | 1.23 | sq ft | 1.23 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255597 | 26003H | 4292J | LP1Y-WFO-110607-02-5 | LP1Y-WFO-110607-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110607 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110607 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255593 | 26003H | 4288J | LP1Y-WFO-110607-02-1 | LP1Y-WFO-110607-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110607 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110607 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255598 | 26003H | 4293J | LP1Y-WFO-110807-02-1 | LP1Y-WFO-110807-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110807 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110807 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255599 | 26003H | 4294J | LP1Y-WFO-110807-02-2 | LP1Y-WFO-110807-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110807 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110807 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1038 | 0.8 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255600 | 26003H | 4295J | LP1Y-WFO-110807-02-3 | LP1Y-WFO-110807-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110807 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110807 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.9663 | 0.74 | sq ft | 0.74 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255601 | 26003H | 4296J | LP1Y-WFO-110807-02-4 | LP1Y-WFO-110807-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110807 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110807 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6713 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255602 | 26003H | 4297J | LP1Y-WFO-110807-02-5 | LP1Y-WFO-110807-02 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 110807 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110807 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255604 | 26003H | 4299J | LP1Y-WFO-196012-03-2 | LP1Y-WFO-196012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196012 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9325 | 1.49 | sq ft | 1.49 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255603 | 26003H | 4298J | LP1Y-WFO-196012-03-1 | LP1Y-WFO-196012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196012 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 43.89 | 16.63 | sq ft | 16.63 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255605 | 26003H | 4300J | LP1Y-WFO-196012-03-3 | LP1Y-WFO-196012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196012 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.96 | 1.5 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255606 | 26003H | 4301J | LP1Y-WFO-196012-03-4 | LP1Y-WFO-196012-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196012 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255609 | 26003H | 4304J | LP1Y-WFO-196016-03-3 | LP1Y-WFO-196016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196016 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196016 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.96 | 1.5 | sq ft | 1.5 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255610 | 26003H | 4305J | LP1Y-WFO-196016-03-4 | LP1Y-WFO-196016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196016 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196016 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255608 | 26003H | 4303J | LP1Y-WFO-196016-03-2 | LP1Y-WFO-196016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196016 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196016 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9325 | 1.49 | sq ft | 1.49 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255607 | 26003H | 4302J | LP1Y-WFO-196016-03-1 | LP1Y-WFO-196016-03 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WFO (36) 196016 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196016 |  | TFS00E009YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 43.89 | 16.63 | sq ft | 16.63 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255616 | 26003H | 4311J | LP1Y-WPC-017053-04-6 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255613 | 26003H | 4308J | LP1Y-WPC-017053-04-3 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255612 | 26003H | 4307J | LP1Y-WPC-017053-04-2 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255611 | 26003H | 4306J | LP1Y-WPC-017053-04-1 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255614 | 26003H | 4309J | LP1Y-WPC-017053-04-4 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255615 | 26003H | 4310J | LP1Y-WPC-017053-04-5 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255617 | 26003H | 4312J | LP1Y-WPC-017053-04-7 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255618 | 26003H | 4313J | LP1Y-WPC-017053-04-8 | LP1Y-WPC-017053-04 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 017053 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017053 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255625 | 26003H | 4320J | LP1Y-WPC-017074-01-7 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.1713 | 3.47 | sq ft | 3.47 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255626 | 26003H | 4321J | LP1Y-WPC-017074-01-8 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.935 | 4.52 | sq ft | 4.52 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255621 | 26003H | 4316J | LP1Y-WPC-017074-01-3 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 33.5363 | 12.7 | sq ft | 12.7 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255622 | 26003H | 4317J | LP1Y-WPC-017074-01-4 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 23.8563 | 9.04 | sq ft | 9.04 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255623 | 26003H | 4318J | LP1Y-WPC-017074-01-5 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.105 | 2.31 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255624 | 26003H | 4319J | LP1Y-WPC-017074-01-6 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 37.2313 | 19.68 | sq ft | 8.68 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255619 | 26003H | 4314J | LP1Y-WPC-017074-01-1 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255620 | 26003H | 4315J | LP1Y-WPC-017074-01-2 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.3275 | 5.43 | sq ft | 5.43 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255627 | 26003H | 4322J | LP1Y-WPC-017074-01-9 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 32.6563 | 12.37 | sq ft | 12.37 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255628 | 26003H | 4323J | LP1Y-WPC-017074-01-10 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255629 | 26003H | 4324J | LP1Y-WPC-017074-01-11 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.7125 | 5.57 | sq ft | 5.57 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255630 | 26003H | 4325J | LP1Y-WPC-017074-01-12 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255631 | 26003H | 4326J | LP1Y-WPC-017074-01-13 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.3163 | 4.29 | sq ft | 4.29 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255632 | 26003H | 4327J | LP1Y-WPC-017074-01-14 | LP1Y-WPC-017074-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-06-29 |  | LP1Y 2" SS WPC (36) (108) 017074 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017074 |  | TFS00E008YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7988 | 1.82 | sq ft | 1.82 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255633 | 26003H | 4328J | LP1Y-WPC-194113-01-1 | LP1Y-WPC-194113-01 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255634 | 26003H | 4329J | LP1Y-WPC-194113-01-2 | LP1Y-WPC-194113-01 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255635 | 26003H | 4330J | LP1Y-WPC-194113-01-3 | LP1Y-WPC-194113-01 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255636 | 26003H | 4331J | LP1Y-WPC-194113-01-4 | LP1Y-WPC-194113-01 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255637 | 26003H | 4332J | LP1Y-WPC-194113-01-5 | LP1Y-WPC-194113-01 | 0 | N | PRI-2-2 | 2026-04-16 |  | active | client | notification | On Hold | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255638 | 26003H | 4333J | LP1Y-WPC-194113-02-1 | LP1Y-WPC-194113-02 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 1.25" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 36.278 | 28.73 | sq ft | 7.73 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255640 | 26003H | 4335J | LP1Y-WPC-194113-05-2 | LP1Y-WPC-194113-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.2963 | 0.87 | sq ft | 0.87 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255641 | 26003H | 4336J | LP1Y-WPC-194113-05-3 | LP1Y-WPC-194113-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 21.065 | 7.98 | sq ft | 7.98 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255639 | 26003H | 4334J | LP1Y-WPC-194113-05-1 | LP1Y-WPC-194113-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255642 | 26003H | 4337J | LP1Y-WPC-194113-05-4 | LP1Y-WPC-194113-05 | 0 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194113 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194113 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.9563 | 5.29 | sq ft | 5.29 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez; DD: 2026-04-18; DL: George Allahverdian | 2026-04-20 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255646 | 26003H | 4341J | LP1Y-WPC-194115-01-4 | LP1Y-WPC-194115-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194115 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194115 |  | TFS00E009YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 34.7586 | 27.28 | sq ft | 7.28 | ft | 2026-02-13 |  |  |  |  | 2026-04-20 | Jacob Perez | 2026-04-20 | George Allahverdian | 2026-04-21 | Jacob Perez | 2026-04-21 | Jacob Perez | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255643 | 26003H | 4338J | LP1Y-WPC-194115-01-1 | LP1Y-WPC-194115-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194115 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194115 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.7913 | 1.06 | sq ft | 1.06 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255644 | 26003H | 4339J | LP1Y-WPC-194115-01-2 | LP1Y-WPC-194115-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194115 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194115 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.7713 | 1.81 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255645 | 26003H | 4340J | LP1Y-WPC-194115-01-3 | LP1Y-WPC-194115-01 | 1 | N | PRI-2-2 | [5 empty] | Released to Production | P022 | 2026-07-13 |  | LP1Y 2" SS WPC (36) (108) 194115 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194115 |  | TFS00E009YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-20; CL: Jacob Perez; DD: 2026-04-20; DL: George Allahverdian | 2026-04-21 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249711 | 26003H | 2414J | LP1Y-SWP-100404-01-2 | LP1Y-SWP-100404-01 | 4 | R | TR-05 04.14.2026 | 2026-04-15 | 2026-04-24 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 21 | 18 | 3 | 72.6488 | 19.87 | sq ft | 9.88 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-04-06 | Jacob Perez | 2026-04-06 | Jacob Perez | 2026-04-24 | 2026-04-25 | Passed | No | 2026-04-25 | 2026-04-29 | 2026-04-29 | 2026-04-27 | 2026-04-27 | N/A | N/A | Omar Puente | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-04-30 | 2026-05-01 |  | 2026-05-01 |  | 2026-05-01 |  | 86% |  |  |  | 71%
C34-S249712 | 26003H | 2415J | LP1Y-SWP-100404-01-4 | LP1Y-SWP-100404-01 | 4 | R | TR-05 04.14.2026 | 2026-04-15 | 2026-04-24 | released |  |  | Shipped | P012 | 2026-05-18 |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 12 | 12 | 0 | 52.2632 | 12.07 | sq ft | 9.07 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-24 | 2026-04-24 | Passed | No | 2026-04-24 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | N/A | N/A | Carlos Guillen | 2026-04-07 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 100% | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | 2026-04-25 | 144667, 145560 | [40 empty] | 2026-05-01 | 2026-05-01 |  | 1004-0 | 2026-05-04 | JA Harris Trucking Inc.
C34-S249710 | 26003H | 2413J | LP1Y-SWP-100404-01-1 | LP1Y-SWP-100404-01 | 4 | R | TR-05 04.14.2026 | 2026-04-15 | 2026-04-24 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 4" | 316 SS | 26.5 | 26.5 | 0 | 61.7299 | 26.39 | sq ft | 8.49 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-24 | 2026-04-25 | Passed | No | 2026-04-25 | 2026-04-01 |  | 2026-04-01 | 2026-04-27 | N/A | N/A | Carlos Guillen | 2026-04-08 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 70% |  |  |  | 70%
C34-S249713 | 26003H | 2416J | LP1Y-SWP-100404-01-3 | LP1Y-SWP-100404-01 | 4 | R | TR-05 04.14.2026 | 2026-04-15 | 2026-04-24 | released |  |  | Released to Fabrication | P012 | 2026-05-18 |  | LP1Y 3" SS SWP (315) (108) 100404 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-100404 |  | TFS00D003YSPP |  | 315-SWP | NONE | 3" | 316 SS | 9 | 8 | 1 | 42.7771 | 15.96 | sq ft | 3.46 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-30; DL: George Allahverdian | 2026-04-24 | 2026-04-27 | Passed | No | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255921 | 26003H | 4344C | LP1Y-CHWR-111405-05-3 | LP1Y-CHWR-111405-05 | 0 | N | PRI-2-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWR (6) (108) 111405 | CHWR |  | 108 | 57.02 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111405 |  | TFS00E010YSPP |  | 6-CHWR | P-4 | 2" | CS | 5.75 | 4 | 1.75 | 18.4809 | 8.47 | sq ft | 1.47 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255920 | 26003H | 4343C | LP1Y-CHWR-111405-05-2 | LP1Y-CHWR-111405-05 | 0 | N | PRI-2-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWR (6) (108) 111405 | CHWR |  | 108 | 57.02 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111405 |  | TFS00E010YSPP |  | 6-CHWR | P-4 | 2" | CS | 14.75 | 14 | 0.75 | 36.4075 | 17.25 | sq ft | 5.75 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255923 | 26003H | 4346C | LP1Y-CHWR-111405-05-5 | LP1Y-CHWR-111405-05 | 0 | N | PRI-2-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWR (6) (108) 111405 | CHWR |  | 108 | 57.02 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111405 |  | TFS00E010YSPP |  | 6-CHWR | P-4 | 2" | CS | 6 | 6 | 0 | 83.3099 | 24.95 | sq ft | 21.95 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255922 | 26003H | 4345C | LP1Y-CHWR-111405-05-4 | LP1Y-CHWR-111405-05 | 0 | N | PRI-2-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWR (6) (108) 111405 | CHWR |  | 108 | 57.02 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111405 |  | TFS00E010YSPP |  | 6-CHWR | P-4 | 2" | CS | 16.75 | 16 | 0.75 | 29.5869 | 16.44 | sq ft | 2.44 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255919 | 26003H | 4342C | LP1Y-CHWR-111405-05-1 | LP1Y-CHWR-111405-05 | 0 | N | PRI-2-3 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWR (6) (108) 111405 | CHWR |  | 108 | 57.02 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111405 |  | TFS00E010YSPP |  | 6-CHWR | P-4 | 2" | CS | 2 | 2 | 0 | 7.6 | 4.5 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-22; EL: Jacob Perez; FD: 2026-04-22; FL: Jacob Perez | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255924 | 26003H | 4347C | LP1Y-CHWS-017040-06-1 | LP1Y-CHWS-017040-06 | 0 | N | PRI-2-3 | 2026-04-21 | 2026-04-25 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWS (6) (108) 017040 | CHWS |  | 108 | 42.08 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017040 |  | TFS00E010YSPP |  | 6-CHWS | P-3 | 2" | CS | 2 | 2 | 0 | 7.6 | 4.5 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255925 | 26003H | 4348C | LP1Y-CHWS-017040-06-2 | LP1Y-CHWS-017040-06 | 0 | N | PRI-2-3 | 2026-04-21 | 2026-04-25 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWS (6) (108) 017040 | CHWS |  | 108 | 42.08 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017040 |  | TFS00E010YSPP |  | 6-CHWS | P-3 | 2" | CS | 6.75 | 6 | 0.75 | 49.3947 | 16.34 | sq ft | 11.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255927 | 26003H | 4350C | LP1Y-CHWS-017040-06-4 | LP1Y-CHWS-017040-06 | 0 | N | PRI-2-3 | 2026-04-21 | 2026-04-25 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWS (6) (108) 017040 | CHWS |  | 108 | 42.08 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017040 |  | TFS00E010YSPP |  | 6-CHWS | P-3 | 2" | CS | 8 | 8 | 0 | 71.8862 | 23.1 | sq ft | 18.6 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255926 | 26003H | 4349C | LP1Y-CHWS-017040-06-3 | LP1Y-CHWS-017040-06 | 0 | N | PRI-2-3 | 2026-04-21 | 2026-04-25 | released |  |  | Released to Production | P023 |  |  | LP1Y 2" CS CHWS (6) (108) 017040 | CHWS |  | 108 | 42.08 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017040 |  | TFS00E010YSPP |  | 6-CHWS | P-3 | 2" | CS | 6 | 6 | 0 | 23.5414 | 11.2 | sq ft | 2.2 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-04-25 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255930 | 26003H | 4353J | LP1Y-DCM-111403-01-3 | LP1Y-DCM-111403-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 16 | 16 | 0 | 55.4873 | 16.73 | sq ft | 6.73 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255928 | 26003H | 4351J | LP1Y-DCM-111403-01-1 | LP1Y-DCM-111403-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 4" | 316 SS | 4 | 4 | 0 | 22.53 | 7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255929 | 26003H | 4352J | LP1Y-DCM-111403-01-2 | LP1Y-DCM-111403-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 6 | 6 | 0 | 65.1129 | 15.04 | sq ft | 13.54 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255931 | 26003H | 4354J | LP1Y-DCM-111403-02-1 | LP1Y-DCM-111403-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 2 | 2 | 0 | 9.45 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255933 | 26003H | 4356J | LP1Y-DCM-111403-02-3 | LP1Y-DCM-111403-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 22 | 21 | 1 | 324.8321 | 41.6 | sq ft | 6.1 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255932 | 26003H | 4355J | LP1Y-DCM-111403-02-2 | LP1Y-DCM-111403-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111403 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111403 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 3 | 3 | 0 | 23.4848 | 6.48 | sq ft | 2.48 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255935 | 26003H | 4358J | LP1Y-DCM-111404-03-2 | LP1Y-DCM-111404-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111404 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 20.25 | 18 | 2.25 | 104.9038 | 41.67 | sq ft | 16.17 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255934 | 26003H | 4357J | LP1Y-DCM-111404-03-1 | LP1Y-DCM-111404-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111404 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 63.3213 | 20.89 | sq ft | 3.89 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255936 | 26003H | 4359J | LP1Y-DCM-111404-04-1 | LP1Y-DCM-111404-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111404 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 25 | 25 | 0 | 355.6987 | 42.12 | sq ft | 6.12 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255940 | 26003H | 4363J | LP1Y-DCM-111404-05-4 | LP1Y-DCM-111404-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111404 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 9 | 8 | 1 | 35.7835 | 14.6 | sq ft | 1.6 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-23; EL: Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255938 | 26003H | 4361J | LP1Y-DCM-111404-05-2 | LP1Y-DCM-111404-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111404 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 20 | 19 | 1 | 60.2206 | 25.56 | sq ft | 3.06 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255939 | 26003H | 4362J | LP1Y-DCM-111404-05-3 | LP1Y-DCM-111404-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111404 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 9 | 9 | 0 | 38.1342 | 10.92 | sq ft | 1.42 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255937 | 26003H | 4360J | LP1Y-DCM-111404-05-1 | LP1Y-DCM-111404-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111404 | DCM |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111404 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 3 | 3 | 0 | 5.36 | 8 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255943 | 26003H | 4366J | LP1Y-DCM-111406-01-3 | LP1Y-DCM-111406-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 18.75 | 18 | 0.75 | 35.565 | 18.02 | sq ft | 6.52 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255941 | 26003H | 4364J | LP1Y-DCM-111406-01-1 | LP1Y-DCM-111406-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255942 | 26003H | 4365J | LP1Y-DCM-111406-01-2 | LP1Y-DCM-111406-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 8 | 8 | 0 | 17.8963 | 10.04 | sq ft | 3.04 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255944 | 26003H | 4367J | LP1Y-DCM-111406-01-4 | LP1Y-DCM-111406-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 39.05 | 16.13 | sq ft | 13.13 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255948 | 26003H | 4371J | LP1Y-DCM-111406-03-4 | LP1Y-DCM-111406-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 11 | 11 | 0 | 69.4425 | 33.07 | sq ft | 22.57 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-23; EL: Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255947 | 26003H | 4370J | LP1Y-DCM-111406-03-3 | LP1Y-DCM-111406-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 12 | 12 | 0 | 66.4338 | 21.76 | sq ft | 4.76 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255945 | 26003H | 4368J | LP1Y-DCM-111406-03-1 | LP1Y-DCM-111406-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255946 | 26003H | 4369J | LP1Y-DCM-111406-03-2 | LP1Y-DCM-111406-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111406 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111406 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255950 | 26003H | 4373J | LP1Y-DCM-111416-01-2 | LP1Y-DCM-111416-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111416 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111416 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 8 | 8 | 0 | 30.625 | 14.19 | sq ft | 7.19 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255949 | 26003H | 4372J | LP1Y-DCM-111416-01-1 | LP1Y-DCM-111416-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111416 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111416 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.0338 | 9.13 | sq ft | 3.63 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255951 | 26003H | 4374J | LP1Y-DCM-111416-01-3 | LP1Y-DCM-111416-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111416 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111416 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 25.5475 | 11.01 | sq ft | 8.01 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255952 | 26003H | 4375J | LP1Y-DCM-111416-03-1 | LP1Y-DCM-111416-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111416 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111416 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 19 | 16 | 3 | 83.2938 | 35.26 | sq ft | 10.26 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255953 | 26003H | 4376J | LP1Y-DCM-111417-01-1 | LP1Y-DCM-111417-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111417 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111417 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 10 | 10 | 0 | 46.1038 | 19.46 | sq ft | 14.96 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255956 | 26003H | 4379J | LP1Y-DCM-111417-03-3 | LP1Y-DCM-111417-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111417 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111417 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 4 | 4 | 0 | 36.9775 | 16.01 | sq ft | 13.01 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255954 | 26003H | 4377J | LP1Y-DCM-111417-03-1 | LP1Y-DCM-111417-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111417 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111417 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 18.3988 | 9.32 | sq ft | 4.32 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255955 | 26003H | 4378J | LP1Y-DCM-111417-03-2 | LP1Y-DCM-111417-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 111417 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111417 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 36.4825 | 15.82 | sq ft | 12.82 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255961 | 26003H | 4384J | LP1Y-DCM-111419-01-5 | LP1Y-DCM-111419-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111419 | DCM |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111419 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 51.9538 | 25.96 | sq ft | 13.46 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255959 | 26003H | 4382J | LP1Y-DCM-111419-01-3 | LP1Y-DCM-111419-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111419 | DCM |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111419 |  | TFS00E010YSPP |  | 315-DCM | NONE | 3" | 316 SS | 17 | 12 | 5 | 37.5788 | 21.73 | sq ft | 5.23 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255960 | 26003H | 4383J | LP1Y-DCM-111419-01-4 | LP1Y-DCM-111419-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111419 | DCM |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111419 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.35 | 10.13 | sq ft | 0.63 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255957 | 26003H | 4380J | LP1Y-DCM-111419-01-1 | LP1Y-DCM-111419-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111419 | DCM |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111419 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255958 | 26003H | 4381J | LP1Y-DCM-111419-01-2 | LP1Y-DCM-111419-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS DCM (315) P (108) 111419 | DCM |  | 108 | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111419 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 15.17 | 8.33 | sq ft | 1.33 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255962 | 26003H | 4385J | LP1Y-DCM-177202-02-1 | LP1Y-DCM-177202-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 6 | 6 | 0 | 106.755 | 34.44 | sq ft | 22.94 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255965 | 26003H | 4388J | LP1Y-DCM-177202-03-3 | LP1Y-DCM-177202-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 14.25 | 10 | 4.25 | 74.15 | 27.62 | sq ft | 4.13 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255963 | 26003H | 4386J | LP1Y-DCM-177202-03-1 | LP1Y-DCM-177202-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255966 | 26003H | 4389J | LP1Y-DCM-177202-03-4 | LP1Y-DCM-177202-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.7338 | 7.21 | sq ft | 3.21 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255964 | 26003H | 4387J | LP1Y-DCM-177202-03-2 | LP1Y-DCM-177202-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS DCM (315) P (108) 177202 | DCM |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177202 |  | TFS00E010YSPP |  | 315-DCM | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255968 | 26003H | 4391J | LP1Y-IPA-111603-01-2 | LP1Y-IPA-111603-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS IPA (315) P 111603 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111603 |  | TFS00E010YSPP |  | 315-IPA | NONE | 4" | 316 SS | 16 | 16 | 0 | 82.4303 | 23.49 | sq ft | 11.78 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255967 | 26003H | 4390J | LP1Y-IPA-111603-01-1 | LP1Y-IPA-111603-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS IPA (315) P 111603 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111603 |  | TFS00E010YSPP |  | 315-IPA | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255969 | 26003H | 4392J | LP1Y-IPA-111603-02-1 | LP1Y-IPA-111603-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS IPA (315) P 111603 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111603 |  | TFS00E010YSPP |  | 315-IPA | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255970 | 26003H | 4393J | LP1Y-IPA-111603-02-2 | LP1Y-IPA-111603-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS IPA (315) P 111603 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111603 |  | TFS00E010YSPP |  | 315-IPA | NONE | 4" | 316 SS | 4 | 4 | 0 | 39.213 | 8.66 | sq ft | 3.38 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255971 | 26003H | 4394J | LP1Y-IPA-111603-02-3 | LP1Y-IPA-111603-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 4" SS IPA (315) P 111603 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111603 |  | TFS00E010YSPP |  | 315-IPA | NONE | 4" | 316 SS | 38 | 34 | 4 | 515.8492 | 40.19 | sq ft | 7.25 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-23; EL: Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255976 | 26003H | 4399J | LP1Y-IPA-111604-02-5 | LP1Y-IPA-111604-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 9 | 8 | 1 | 33.9142 | 13.92 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255975 | 26003H | 4398J | LP1Y-IPA-111604-02-4 | LP1Y-IPA-111604-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 9 | 9 | 0 | 37.638 | 10.8 | sq ft | 1.3 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255973 | 26003H | 4396J | LP1Y-IPA-111604-02-2 | LP1Y-IPA-111604-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 3 | 3 | 0 | 26.2556 | 6.06 | sq ft | 4.56 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255972 | 26003H | 4395J | LP1Y-IPA-111604-02-1 | LP1Y-IPA-111604-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 1.5 | 1.5 | 0 | 4.94 | 6 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255974 | 26003H | 4397J | LP1Y-IPA-111604-02-3 | LP1Y-IPA-111604-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 14 | 13 | 1 | 80.1968 | 30.18 | sq ft | 9.18 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian; ED: 2026-04-23; EL: Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255977 | 26003H | 4400J | LP1Y-IPA-111604-03-1 | LP1Y-IPA-111604-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 26 | 26 | 0 | 322.6967 | 34.67 | sq ft | 7.67 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255979 | 26003H | 4402J | LP1Y-IPA-111604-04-2 | LP1Y-IPA-111604-04 | 2 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 15 | 14 | 1 | 35.6952 | 15.02 | sq ft | 1.52 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255980 | 26003H | 4403J | LP1Y-IPA-111604-04-3 | LP1Y-IPA-111604-04 | 2 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 31 | 30 | 1 | 566.1072 | 38.72 | sq ft | 8.22 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255981 | 26003H | 4404J | LP1Y-IPA-111604-04-4 | LP1Y-IPA-111604-04 | 2 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 12 | 12 | 0 | 332.1898 | 28.98 | sq ft | 15.98 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255978 | 26003H | 4401J | LP1Y-IPA-111604-04-1 | LP1Y-IPA-111604-04 | 2 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS IPA (315) P 111604 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111604 |  | TFS00E010YSPP |  | 315-IPA | NONE | 3" | 316 SS | 3 | 3 | 0 | 23.372 | 6.45 | sq ft | 2.45 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255982 | 26003H | 4405J | LP1Y-IPA-111605-01-1 | LP1Y-IPA-111605-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111605 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111605 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 8 | 8 | 0 | 63.0063 | 19.12 | sq ft | 3.62 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255983 | 26003H | 4406J | LP1Y-IPA-111605-01-2 | LP1Y-IPA-111605-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111605 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111605 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 51.28 | 25.04 | sq ft | 14.04 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255984 | 26003H | 4407J | LP1Y-IPA-111605-03-1 | LP1Y-IPA-111605-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111605 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111605 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 74.095 | 27.77 | sq ft | 9.27 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255986 | 26003H | 4409J | LP1Y-IPA-111606-01-2 | LP1Y-IPA-111606-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.7213 | 12.68 | sq ft | 11.18 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255985 | 26003H | 4408J | LP1Y-IPA-111606-01-1 | LP1Y-IPA-111606-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 80.4675 | 28.18 | sq ft | 11.18 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255989 | 26003H | 4412J | LP1Y-IPA-111606-04-3 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 76.9138 | 29.34 | sq ft | 4.34 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255988 | 26003H | 4411J | LP1Y-IPA-111606-04-2 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255990 | 26003H | 4413J | LP1Y-IPA-111606-04-4 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.6775 | 11.39 | sq ft | 1.89 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255991 | 26003H | 4414J | LP1Y-IPA-111606-04-5 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.3663 | 7.45 | sq ft | 3.45 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255987 | 26003H | 4410J | LP1Y-IPA-111606-04-1 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255992 | 26003H | 4415J | LP1Y-IPA-111606-04-6 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 39.3388 | 15.57 | sq ft | 14.07 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255993 | 26003H | 4416J | LP1Y-IPA-111606-04-7 | LP1Y-IPA-111606-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111606 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111606 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.96 | 19.5 | sq ft | 16.5 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255994 | 26003H | 4417J | LP1Y-IPA-111608-01-1 | LP1Y-IPA-111608-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111608 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111608 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 31.7213 | 12.68 | sq ft | 11.18 | ft | 2026-02-13 | DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255995 | 26003H | 4418J | LP1Y-IPA-111608-04-1 | LP1Y-IPA-111608-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111608 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111608 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 15.2363 | 8.12 | sq ft | 3.12 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255997 | 26003H | 4420J | LP1Y-IPA-111608-04-3 | LP1Y-IPA-111608-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111608 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111608 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 44.6775 | 18.93 | sq ft | 15.93 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255996 | 26003H | 4419J | LP1Y-IPA-111608-04-2 | LP1Y-IPA-111608-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 111608 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111608 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 10 | 10 | 0 | 47.8363 | 20.12 | sq ft | 15.62 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255999 | 26003H | 4422J | LP1Y-IPA-177102-03-2 | LP1Y-IPA-177102-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 8 | 8 | 0 | 69.345 | 21.52 | sq ft | 6.02 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256001 | 26003H | 4424J | LP1Y-IPA-177102-03-4 | LP1Y-IPA-177102-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 57.64 | 22.5 | sq ft | 21 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256000 | 26003H | 4423J | LP1Y-IPA-177102-03-3 | LP1Y-IPA-177102-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 23.4988 | 10.23 | sq ft | 7.23 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255998 | 26003H | 4421J | LP1Y-IPA-177102-03-1 | LP1Y-IPA-177102-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-22 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256005 | 26003H | 4428J | LP1Y-IPA-177102-04-4 | LP1Y-IPA-177102-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4.25 | 2 | 2.25 | 20.71 | 11.54 | sq ft | 6.04 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256004 | 26003H | 4427J | LP1Y-IPA-177102-04-3 | LP1Y-IPA-177102-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 72.235 | 25.65 | sq ft | 6.15 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256002 | 26003H | 4425J | LP1Y-IPA-177102-04-1 | LP1Y-IPA-177102-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256003 | 26003H | 4426J | LP1Y-IPA-177102-04-2 | LP1Y-IPA-177102-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS IPA (315) P 177102 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177102 |  | TFS00E010YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258551 | 26003H | 4429J-L1 | LP1Y-N2(100)-018041-02-1-L1 | LP1Y-N2(100)-018041-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 018041 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018041 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256007 | 26003H | 4430J | LP1Y-N2(100)-018041-02-2 | LP1Y-N2(100)-018041-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 018041 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018041 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 31.295 | 12.52 | sq ft | 11.02 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256006 | 26003H | 4429J | LP1Y-N2(100)-018041-02-1 | LP1Y-N2(100)-018041-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 018041 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018041 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 58.2038 | 16.71 | sq ft | 3.71 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256010 | 26003H | 4433J | LP1Y-N2(100)-181020-02-3 | LP1Y-N2(100)-181020-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181020 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181020 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 14 | 14 | 0 | 88.602 | 39.04 | sq ft | 6.04 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256008 | 26003H | 4431J | LP1Y-N2(100)-181020-02-1 | LP1Y-N2(100)-181020-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181020 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181020 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 78.76 | 30.5 | sq ft | 29 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256009 | 26003H | 4432J | LP1Y-N2(100)-181020-02-2 | LP1Y-N2(100)-181020-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181020 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181020 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.355 | 19.27 | sq ft | 16.27 | ft | 2026-02-13 |  |  |  |  | 2026-04-22 | Jacob Perez | 2026-04-22 | George Allahverdian | 2026-04-23 | Jacob Perez | 2026-04-23 | Jacob Perez | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256012 | 26003H | 4435J | LP1Y-N2(100)-181020-03-2 | LP1Y-N2(100)-181020-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181020 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181020 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 40.9595 | 27.26 | sq ft | 2.26 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256011 | 26003H | 4434J | LP1Y-N2(100)-181020-03-1 | LP1Y-N2(100)-181020-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181020 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181020 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 57.96 | 17.21 | sq ft | 1.71 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256014 | 26003H | 4437J | LP1Y-N2(100)-181022-02-2 | LP1Y-N2(100)-181022-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181022 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181022 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 25.2588 | 10.23 | sq ft | 8.73 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256013 | 26003H | 4436J | LP1Y-N2(100)-181022-02-1 | LP1Y-N2(100)-181022-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181022 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181022 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.08 | 19.17 | sq ft | 16.17 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256015 | 26003H | 4438J | LP1Y-N2(100)-181022-02-3 | LP1Y-N2(100)-181022-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181022 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181022 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 51.0358 | 39.2 | sq ft | 4.7 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256017 | 26003H | 4440J | LP1Y-N2(100)-181022-03-2 | LP1Y-N2(100)-181022-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181022 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181022 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 38.3758 | 31.62 | sq ft | 3.13 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256016 | 26003H | 4439J | LP1Y-N2(100)-181022-03-1 | LP1Y-N2(100)-181022-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181022 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181022 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 58.5513 | 17.43 | sq ft | 1.93 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256020 | 26003H | 4443J | LP1Y-N2(100)-181024-02-3 | LP1Y-N2(100)-181024-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181024 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181024 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 51.4033 | 38.23 | sq ft | 5.23 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256018 | 26003H | 4441J | LP1Y-N2(100)-181024-02-1 | LP1Y-N2(100)-181024-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181024 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181024 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 53.2538 | 22.17 | sq ft | 17.67 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256019 | 26003H | 4442J | LP1Y-N2(100)-181024-02-2 | LP1Y-N2(100)-181024-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181024 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181024 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 47.5613 | 18.68 | sq ft | 17.18 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256021 | 26003H | 4444J | LP1Y-N2(100)-181024-03-1 | LP1Y-N2(100)-181024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181024 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181024 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12 | 12 | 0 | 61.81 | 19.33 | sq ft | 2.33 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256022 | 26003H | 4445J | LP1Y-N2(100)-181024-03-2 | LP1Y-N2(100)-181024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181024 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181024 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 35.9723 | 29.43 | sq ft | 2.43 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256023 | 26003H | 4446J | LP1Y-N2(100)-181080-02-1 | LP1Y-N2(100)-181080-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181080 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181080 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 30.7388 | 14.98 | sq ft | 10.48 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256024 | 26003H | 4447J | LP1Y-N2(100)-181080-02-2 | LP1Y-N2(100)-181080-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181080 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181080 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 19 | 19 | 0 | 80.3413 | 33.47 | sq ft | 7.47 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256025 | 26003H | 4448J | LP1Y-N2(100)-181107-01-1 | LP1Y-N2(100)-181107-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181107 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181107 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256027 | 26003H | 4450J | LP1Y-N2(100)-181107-01-3 | LP1Y-N2(100)-181107-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181107 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181107 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 28.82 | 12.25 | sq ft | 9.25 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256026 | 26003H | 4449J | LP1Y-N2(100)-181107-01-2 | LP1Y-N2(100)-181107-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2(100) (315) E 181107 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181107 |  | TFS00E010YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 77.0025 | 26.86 | sq ft | 9.86 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256030 | 26003H | 4453J | LP1Y-N2-111213-01-3 | LP1Y-N2-111213-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 1" SS N2 (315) 111213 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111213 |  | TFS00E010YSPP |  | 315-N2 | NONE | 1" | 316 SS | 4 | 2.5 | 1.5 | 6.9465 | 9.52 | sq ft | 3.52 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256028 | 26003H | 4451J | LP1Y-N2-111213-01-1 | LP1Y-N2-111213-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 1" SS N2 (315) 111213 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111213 |  | TFS00E010YSPP |  | 315-N2 | NONE | 1" | 316 SS | 2 | 2 | 0 | 20.16 | 15.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256029 | 26003H | 4452J | LP1Y-N2-111213-01-2 | LP1Y-N2-111213-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 1" SS N2 (315) 111213 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111213 |  | TFS00E010YSPP |  | 315-N2 | NONE | 1" | 316 SS | 4 | 4 | 0 | 5.517 | 6.52 | sq ft | 3.52 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256032 | 26003H | 4455J | LP1Y-N2-181088-01-2 | LP1Y-N2-181088-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2 (315) E 181088 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181088 |  | TFS00E010YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256031 | 26003H | 4454J | LP1Y-N2-181088-01-1 | LP1Y-N2-181088-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2 (315) E 181088 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181088 |  | TFS00E010YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256033 | 26003H | 4456J | LP1Y-N2-181088-01-3 | LP1Y-N2-181088-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS N2 (315) E 181088 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181088 |  | TFS00E010YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256034 | 26003H | 4457J | LP1Y-PV-111061-01-1 | LP1Y-PV-111061-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111061 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 20.5113 | 13.31 | sq ft | 1.31 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256035 | 26003H | 4458J | LP1Y-PV-111061-01-2 | LP1Y-PV-111061-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111061 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 12 | 12 | 0 | 69.7338 | 23.01 | sq ft | 6.01 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256037 | 26003H | 4460J | LP1Y-PV-111061-02-2 | LP1Y-PV-111061-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111061 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 42.3225 | 16.7 | sq ft | 15.2 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256036 | 26003H | 4459J | LP1Y-PV-111061-02-1 | LP1Y-PV-111061-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111061 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 49.5138 | 20.09 | sq ft | 17.09 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256038 | 26003H | 4461J | LP1Y-PV-111063-01-1 | LP1Y-PV-111063-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111063 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111063 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.9138 | 13.84 | sq ft | 1.84 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256039 | 26003H | 4462J | LP1Y-PV-111063-01-2 | LP1Y-PV-111063-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111063 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111063 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 23.145 | 10.69 | sq ft | 5.19 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256041 | 26003H | 4464J | LP1Y-PV-111063-02-2 | LP1Y-PV-111063-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111063 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111063 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 57.365 | 15.73 | sq ft | 4.23 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256040 | 26003H | 4463J | LP1Y-PV-111063-02-1 | LP1Y-PV-111063-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111063 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111063 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 27.9675 | 11.93 | sq ft | 8.93 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256042 | 26003H | 4465J | LP1Y-PV-111066-01-1 | LP1Y-PV-111066-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111066 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111066 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 34.4813 | 19.27 | sq ft | 5.77 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256043 | 26003H | 4466J | LP1Y-PV-111066-01-2 | LP1Y-PV-111066-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111066 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111066 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.0775 | 8.01 | sq ft | 2.51 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256044 | 26003H | 4467J | LP1Y-PV-111066-02-1 | LP1Y-PV-111066-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111066 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111066 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 44.2475 | 18.09 | sq ft | 15.09 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256045 | 26003H | 4468J | LP1Y-PV-111066-02-2 | LP1Y-PV-111066-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PV (315) 111066 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111066 |  | TFS00E010YSPP |  | 315-PV | NONE | 2" | 316 SS | 6 | 6 | 0 | 61.2975 | 17.22 | sq ft | 5.72 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256046 | 26003H | 4469J | LP1Y-PV-121008-02-1 | LP1Y-PV-121008-02 | 0 | N | PRI-2-3 | [5 empty] | In Engineering | P023 |  |  | LP1Y 3" SS PV (315) (108) 121008 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121008 |  | TFS00E010YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256047 | 26003H | 4470J | LP1Y-PV-121008-03-1 | LP1Y-PV-121008-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS PV (315) (108) 121008 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-121008 |  | TFS00E010YSPP |  | 315-PV | NONE | 3" | 316 SS | 46.25 | 43 | 3.25 | 758.3222 | 96.01 | sq ft | 32.01 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256052 | 26003H | 4475J | LP1Y-PVP-111209-05-5 | LP1Y-PVP-111209-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 23.7188 | 10.98 | sq ft | 6.48 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256049 | 26003H | 4472J | LP1Y-PVP-111209-05-2 | LP1Y-PVP-111209-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 22.25 | 20 | 2.25 | 86.3388 | 31.73 | sq ft | 11.73 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256051 | 26003H | 4474J | LP1Y-PVP-111209-05-4 | LP1Y-PVP-111209-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 69.52 | 27 | sq ft | 25.5 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256048 | 26003H | 4471J | LP1Y-PVP-111209-05-1 | LP1Y-PVP-111209-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256050 | 26003H | 4473J | LP1Y-PVP-111209-05-3 | LP1Y-PVP-111209-05 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 30.1263 | 12.74 | sq ft | 9.74 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256054 | 26003H | 4477J | LP1Y-PVP-111214-01-2 | LP1Y-PVP-111214-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS PVP (315) P 111214 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111214 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 14.5638 | 9.09 | sq ft | 2.09 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256053 | 26003H | 4476J | LP1Y-PVP-111214-01-1 | LP1Y-PVP-111214-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 3" SS PVP (315) P 111214 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111214 |  | TFS00E010YSPP |  | 315-PVP | NONE | 3" | 316 SS | 3 | 3 | 0 | 14.95 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256055 | 26003H | 4478J | LP1Y-PVP-111409-02-1 | LP1Y-PVP-111409-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256057 | 26003H | 4480J | LP1Y-PVP-111409-02-3 | LP1Y-PVP-111409-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 64.4188 | 19.07 | sq ft | 6.07 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256056 | 26003H | 4479J | LP1Y-PVP-111409-02-2 | LP1Y-PVP-111409-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 12.7738 | 5.51 | sq ft | 4.01 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256058 | 26003H | 4481J | LP1Y-PVP-111409-02-4 | LP1Y-PVP-111409-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 35.86 | 15.58 | sq ft | 11.08 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256059 | 26003H | 4482J | LP1Y-PVP-111411-01-1 | LP1Y-PVP-111411-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111411 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111411 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256060 | 26003H | 4483J | LP1Y-PVP-111411-01-2 | LP1Y-PVP-111411-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111411 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111411 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.5663 | 7.95 | sq ft | 0.95 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256061 | 26003H | 4484J | LP1Y-PVP-111609-02-1 | LP1Y-PVP-111609-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256062 | 26003H | 4485J | LP1Y-PVP-111609-02-2 | LP1Y-PVP-111609-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12.25 | 8 | 4.25 | 73.7988 | 25.65 | sq ft | 8.65 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256063 | 26003H | 4486J | LP1Y-PVP-111609-02-3 | LP1Y-PVP-111609-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 6 | 6 | 0 | 39.8888 | 16.44 | sq ft | 13.44 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256064 | 26003H | 4487J | LP1Y-PVP-111609-02-4 | LP1Y-PVP-111609-02 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 27.8063 | 13.2 | sq ft | 8.7 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256065 | 26003H | 4488J | LP1Y-PVP-111611-01-1 | LP1Y-PVP-111611-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111611 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111611 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256066 | 26003H | 4489J | LP1Y-PVP-111611-01-2 | LP1Y-PVP-111611-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PVP (315) P 111611 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111611 |  | TFS00E010YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 11.5663 | 7.95 | sq ft | 0.95 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256068 | 26003H | 4491J | LP1Y-PWP-111072-03-2 | LP1Y-PWP-111072-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PWP (315) (108) 111072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111072 |  | TFS00E010YSPP |  | 315-PWP | NONE | 2" | 316 SS | 21 | 18 | 3 | 86.7213 | 37.81 | sq ft | 8.81 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256067 | 26003H | 4490J | LP1Y-PWP-111072-03-1 | LP1Y-PWP-111072-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PWP (315) (108) 111072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111072 |  | TFS00E010YSPP |  | 315-PWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 25.7263 | 11.74 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256069 | 26003H | 4492J | LP1Y-PWP-111072-04-1 | LP1Y-PWP-111072-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PWP (315) (108) 111072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111072 |  | TFS00E010YSPP |  | 315-PWP | NONE | 2" | 316 SS | 18 | 18 | 0 | 118.4475 | 38.68 | sq ft | 4.68 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256070 | 26003H | 4493J | LP1Y-PWP-111072-04-2 | LP1Y-PWP-111072-04 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS PWP (315) (108) 111072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111072 |  | TFS00E010YSPP |  | 315-PWP | NONE | 2" | 316 SS | 22 | 22 | 0 | 125.53 | 39.71 | sq ft | 7.21 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256073 | 26003H | 4496J | LP1Y-RV-111208-01-3 | LP1Y-RV-111208-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 6" SS RV (315) 111208 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111208 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 12 | 12 | 0 | 79 | 16.1 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256074 | 26003H | 4497J | LP1Y-RV-111208-01-4 | LP1Y-RV-111208-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 6" SS RV (315) 111208 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111208 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 46 | 42 | 4 | 223.8467 | 45.51 | sq ft | 18.1 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256072 | 26003H | 4495J | LP1Y-RV-111208-01-2 | LP1Y-RV-111208-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 6" SS RV (315) 111208 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111208 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 7.5 | 6 | 1.5 | 55.3656 | 20.01 | sq ft | 1.28 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256071 | 26003H | 4494J | LP1Y-RV-111208-01-1 | LP1Y-RV-111208-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 6" SS RV (315) 111208 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111208 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256076 | 26003H | 4499J | LP1Y-RV-111215-01-2 | LP1Y-RV-111215-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P 111215 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111215 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 9 | 9 | 0 | 61.075 | 21.94 | sq ft | 4.44 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256075 | 26003H | 4498J | LP1Y-RV-111215-01-1 | LP1Y-RV-111215-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P 111215 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111215 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256081 | 26003H | 4504J | LP1Y-RV-111407-01-5 | LP1Y-RV-111407-01 | 3 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111407 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111407 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256077 | 26003H | 4500J | LP1Y-RV-111407-01-1 | LP1Y-RV-111407-01 | 3 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111407 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111407 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256078 | 26003H | 4501J | LP1Y-RV-111407-01-2 | LP1Y-RV-111407-01 | 3 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111407 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111407 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256079 | 26003H | 4502J | LP1Y-RV-111407-01-3 | LP1Y-RV-111407-01 | 3 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111407 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111407 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256080 | 26003H | 4503J | LP1Y-RV-111407-01-4 | LP1Y-RV-111407-01 | 3 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111407 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111407 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256082 | 26003H | 4505J | LP1Y-RV-111408-01-1 | LP1Y-RV-111408-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P (108) 111408 | RV |  | 108 | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111408 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 20.25 | 18 | 2.25 | 102.045 | 38.27 | sq ft | 15.77 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256083 | 26003H | 4506C | LP1Y-RV-111413-01-1 | LP1Y-RV-111413-01 | 0 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS RV (6) (108) 111413 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111413 |  | TFS00E010YSPP |  | 6-RV | P-4 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256084 | 26003H | 4507C | LP1Y-RV-111413-01-2 | LP1Y-RV-111413-01 | 0 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS RV (6) (108) 111413 | RV |  | 108,NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111413 |  | TFS00E010YSPP |  | 6-RV | P-4 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256085 | 26003H | 4508J | LP1Y-RV-111418-01-1 | LP1Y-RV-111418-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P (108) 111418 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111418 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256086 | 26003H | 4509J | LP1Y-RV-111418-01-2 | LP1Y-RV-111418-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P (108) 111418 | RV |  | 108 | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111418 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 13 | 13 | 0 | 68.2788 | 26.98 | sq ft | 6.48 | ft | 2026-02-13 | DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256088 | 26003H | 4511J | LP1Y-RV-111607-01-2 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256087 | 26003H | 4510J | LP1Y-RV-111607-01-1 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256089 | 26003H | 4512J | LP1Y-RV-111607-01-3 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256092 | 26003H | 4515J | LP1Y-RV-111607-01-6 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256090 | 26003H | 4513J | LP1Y-RV-111607-01-4 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256091 | 26003H | 4514J | LP1Y-RV-111607-01-5 | LP1Y-RV-111607-01 | 1 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 6" SS RV (315) 111607 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111607 |  | TFS00E010YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256094 | 26003H | 4517J | LP1Y-RV-111612-01-2 | LP1Y-RV-111612-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P 111612 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111612 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 9 | 9 | 0 | 60.14 | 21.58 | sq ft | 4.08 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256093 | 26003H | 4516J | LP1Y-RV-111612-01-1 | LP1Y-RV-111612-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS RV (315) P 111612 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111612 |  | TFS00E010YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256097 | 26003H | 4520C | LP1Y-S(130)-018068-02-3 | LP1Y-S(130)-018068-02 | 1 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256095 | 26003H | 4518C | LP1Y-S(130)-018068-02-1 | LP1Y-S(130)-018068-02 | 1 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256096 | 26003H | 4519C | LP1Y-S(130)-018068-02-2 | LP1Y-S(130)-018068-02 | 1 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256098 | 26003H | 4521C | LP1Y-S(130)-018068-02-4 | LP1Y-S(130)-018068-02 | 1 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256099 | 26003H | 4522C | LP1Y-S(130)-018068-05-1 | LP1Y-S(130)-018068-05 | 0 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256100 | 26003H | 4523C | LP1Y-S(130)-018068-05-2 | LP1Y-S(130)-018068-05 | 0 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256101 | 26003H | 4524C | LP1Y-S(130)-018068-05-3 | LP1Y-S(130)-018068-05 | 0 | N | PRI-2-3 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P023 |  |  | LP1Y 2" CS S(130) (2) (103) 018068 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018068 |  | TFS00E010YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256102 | 26003H | 4525J | LP1Y-S(130)-166501-01-1 | LP1Y-S(130)-166501-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 1" SS S(130) (315) (103) 166501 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166501 |  | TFS00E010YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 10 | 10 | 0 | 12.0866 | 16.78 | sq ft | 7.28 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256103 | 26003H | 4526J | LP1Y-S(130)-166501-01-2 | LP1Y-S(130)-166501-01 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 1" SS S(130) (315) (103) 166501 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166501 |  | TFS00E010YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 0 | 1 | 3.0883 | 2.31 | sq ft | 1.81 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256106 | 26003H | 4529J | LP1Y-STORMP-166504-04-3 | LP1Y-STORMP-166504-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS STORMP (315) (108) 166504 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166504 |  | TFS00E010YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.2025 | 9.57 | sq ft | 4.07 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256104 | 26003H | 4527J | LP1Y-STORMP-166504-04-1 | LP1Y-STORMP-166504-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS STORMP (315) (108) 166504 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166504 |  | TFS00E010YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 35.2 | 14.67 | sq ft | 11.67 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256105 | 26003H | 4528J | LP1Y-STORMP-166504-04-2 | LP1Y-STORMP-166504-04 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS STORMP (315) (108) 166504 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166504 |  | TFS00E010YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.75 | 12 | 0.75 | 88.155 | 33.31 | sq ft | 9.81 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256107 | 26003H | 4530J | LP1Y-SW-166502-01-1 | LP1Y-SW-166502-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SW (315) 166502 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166502 |  | TFS00E010YSPP |  | 315-SW | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256108 | 26003H | 4531J | LP1Y-SW-166502-01-2 | LP1Y-SW-166502-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SW (315) 166502 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166502 |  | TFS00E010YSPP |  | 315-SW | NONE | 2" | 316 SS | 5.5 | 5.5 | 0 | 50.499 | 15.96 | sq ft | 2.46 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256109 | 26003H | 4532J | LP1Y-SW-166502-01-3 | LP1Y-SW-166502-01 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SW (315) 166502 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166502 |  | TFS00E010YSPP |  | 315-SW | NONE | 2" | 316 SS | 2 | 2 | 0 | 13.2913 | 5.06 | sq ft | 4.56 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256110 | 26003H | 4533J | LP1Y-SWP-111082-03-1 | LP1Y-SWP-111082-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 111082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111082 |  | TFS00E010YSPP |  | 315-SWP | NONE | 2" | 316 SS | 8 | 8 | 0 | 27.9263 | 11.91 | sq ft | 8.91 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256111 | 26003H | 4534J | LP1Y-SWP-111082-03-2 | LP1Y-SWP-111082-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 111082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111082 |  | TFS00E010YSPP |  | 315-SWP | NONE | 2" | 316 SS | 23 | 20 | 3 | 87.6425 | 38.82 | sq ft | 8.32 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256113 | 26003H | 4536J | LP1Y-SWP-166503-05-2 | LP1Y-SWP-166503-05 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 166503 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166503 |  | TFS00E010YSPP |  | 315-SWP | NONE | 2" | 316 SS | 12.75 | 12 | 0.75 | 88.155 | 33.31 | sq ft | 9.81 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256112 | 26003H | 4535J | LP1Y-SWP-166503-05-1 | LP1Y-SWP-166503-05 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 166503 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166503 |  | TFS00E010YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 35.2 | 14.67 | sq ft | 11.67 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256114 | 26003H | 4537J | LP1Y-SWP-166503-06-1 | LP1Y-SWP-166503-06 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 166503 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166503 |  | TFS00E010YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256115 | 26003H | 4538J | LP1Y-SWP-166503-06-2 | LP1Y-SWP-166503-06 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 166503 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166503 |  | TFS00E010YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256116 | 26003H | 4539J | LP1Y-SWP-166503-06-3 | LP1Y-SWP-166503-06 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS SWP (315) (108) 166503 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166503 |  | TFS00E010YSPP |  | 315-SWP | NONE | 2" | 316 SS | 25 | 20.5 | 4.5 | 106.847 | 56.34 | sq ft | 8.34 | ft | 2026-02-13 |  |  |  |  | 2026-04-23 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256121 | 26003H | 4544J | LP1Y-WFO-017012-07-5 | LP1Y-WFO-017012-07 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.9125 | 6.41 | sq ft | 6.41 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256117 | 26003H | 4540J | LP1Y-WFO-017012-07-1 | LP1Y-WFO-017012-07 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.2088 | 7.28 | sq ft | 7.28 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256118 | 26003H | 4541J | LP1Y-WFO-017012-07-2 | LP1Y-WFO-017012-07 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.2325 | 2.74 | sq ft | 2.74 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256120 | 26003H | 4543J | LP1Y-WFO-017012-07-4 | LP1Y-WFO-017012-07 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 4 | 2 | 10.345 | 4.98 | sq ft | 2.48 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256119 | 26003H | 4542J | LP1Y-WFO-017012-07-3 | LP1Y-WFO-017012-07 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.7125 | 1.41 | sq ft | 1.41 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256123 | 26003H | 4546J | LP1Y-WFO-017012-08-2 | LP1Y-WFO-017012-08 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 5.75 | 2.75 | 3 | 24.966 | 20.24 | sq ft | 4.74 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256122 | 26003H | 4545J | LP1Y-WFO-017012-08-1 | LP1Y-WFO-017012-08 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 017012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017012 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.2875 | 6.93 | sq ft | 6.93 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256127 | 26003H | 4550J | LP1Y-WFO-111210-02-4 | LP1Y-WFO-111210-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111210 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256125 | 26003H | 4548J | LP1Y-WFO-111210-02-2 | LP1Y-WFO-111210-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111210 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.8188 | 1.07 | sq ft | 1.07 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256126 | 26003H | 4549J | LP1Y-WFO-111210-02-3 | LP1Y-WFO-111210-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111210 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.8063 | 2.58 | sq ft | 2.58 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256124 | 26003H | 4547J | LP1Y-WFO-111210-02-1 | LP1Y-WFO-111210-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111210 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111210 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256129 | 26003H | 4552J | LP1Y-WFO-111410-02-2 | LP1Y-WFO-111410-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111410 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256132 | 26003H | 4555J | LP1Y-WFO-111410-02-5 | LP1Y-WFO-111410-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111410 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256128 | 26003H | 4551J | LP1Y-WFO-111410-02-1 | LP1Y-WFO-111410-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111410 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256131 | 26003H | 4554J | LP1Y-WFO-111410-02-4 | LP1Y-WFO-111410-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111410 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.7225 | 1.03 | sq ft | 1.03 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256130 | 26003H | 4553J | LP1Y-WFO-111410-02-3 | LP1Y-WFO-111410-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111410 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111410 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256134 | 26003H | 4557J | LP1Y-WFO-111610-02-2 | LP1Y-WFO-111610-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111610 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3788 | 0.9 | sq ft | 0.9 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256133 | 26003H | 4556J | LP1Y-WFO-111610-02-1 | LP1Y-WFO-111610-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111610 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 0 | 3.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256137 | 26003H | 4560J | LP1Y-WFO-111610-02-5 | LP1Y-WFO-111610-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111610 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256136 | 26003H | 4559J | LP1Y-WFO-111610-02-4 | LP1Y-WFO-111610-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111610 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.2213 | 1.6 | sq ft | 1.6 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256135 | 26003H | 4558J | LP1Y-WFO-111610-02-3 | LP1Y-WFO-111610-02 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 111610 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111610 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256143 | 26003H | 4566J | LP1Y-WFO-196020-03-6 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.18 | 1.58 | sq ft | 1.58 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256138 | 26003H | 4561J | LP1Y-WFO-196020-03-1 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.5913 | 4.39 | sq ft | 4.39 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256139 | 26003H | 4562J | LP1Y-WFO-196020-03-2 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.4988 | 4.73 | sq ft | 4.73 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256140 | 26003H | 4563J | LP1Y-WFO-196020-03-3 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 52.7863 | 19.99 | sq ft | 19.99 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256141 | 26003H | 4564J | LP1Y-WFO-196020-03-4 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8288 | 0.69 | sq ft | 0.69 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256142 | 26003H | 4565J | LP1Y-WFO-196020-03-5 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.6938 | 3.67 | sq ft | 3.67 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256144 | 26003H | 4567J | LP1Y-WFO-196020-03-7 | LP1Y-WFO-196020-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196020 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196020 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256147 | 26003H | 4570J | LP1Y-WFO-196022-03-3 | LP1Y-WFO-196022-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196022 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196022 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256146 | 26003H | 4569J | LP1Y-WFO-196022-03-2 | LP1Y-WFO-196022-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196022 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196022 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 42.8313 | 16.22 | sq ft | 16.22 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256145 | 26003H | 4568J | LP1Y-WFO-196022-03-1 | LP1Y-WFO-196022-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196022 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196022 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.0888 | 3.44 | sq ft | 3.44 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian | 2026-04-24 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256153 | 26003H | 4576J | LP1Y-WFO-196024-03-6 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256148 | 26003H | 4571J | LP1Y-WFO-196024-03-1 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6713 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256149 | 26003H | 4572J | LP1Y-WFO-196024-03-2 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256150 | 26003H | 4573J | LP1Y-WFO-196024-03-3 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 7.59 | 2.88 | sq ft | 2.88 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256151 | 26003H | 4574J | LP1Y-WFO-196024-03-4 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256152 | 26003H | 4575J | LP1Y-WFO-196024-03-5 | LP1Y-WFO-196024-03 | 0 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WFO (36) 196024 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196024 |  | TFS00E010YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 45.9113 | 17.39 | sq ft | 17.39 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256157 | 26003H | 4580J | LP1Y-WPC-017054-03-4 | LP1Y-WPC-017054-03 | 2 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 017054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017054 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256154 | 26003H | 4577J | LP1Y-WPC-017054-03-1 | LP1Y-WPC-017054-03 | 2 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 017054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017054 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256155 | 26003H | 4578J | LP1Y-WPC-017054-03-2 | LP1Y-WPC-017054-03 | 2 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 017054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017054 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256156 | 26003H | 4579J | LP1Y-WPC-017054-03-3 | LP1Y-WPC-017054-03 | 2 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 017054 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017054 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256164 | 26003H | 4587J | LP1Y-WPC-194117-01-7 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256158 | 26003H | 4581J | LP1Y-WPC-194117-01-1 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256159 | 26003H | 4582J | LP1Y-WPC-194117-01-2 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256160 | 26003H | 4583J | LP1Y-WPC-194117-01-3 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256161 | 26003H | 4584J | LP1Y-WPC-194117-01-4 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256162 | 26003H | 4585J | LP1Y-WPC-194117-01-5 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256163 | 26003H | 4586J | LP1Y-WPC-194117-01-6 | LP1Y-WPC-194117-01 | 0 | N | PRI-2-3 | 2026-04-20 |  | active | client | notification | On Hold | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256165 | 26003H | 4588J | LP1Y-WPC-194117-03-1 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.2313 | 1.22 | sq ft | 1.22 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256166 | 26003H | 4589J | LP1Y-WPC-194117-03-2 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.3113 | 2.39 | sq ft | 2.39 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256167 | 26003H | 4590J | LP1Y-WPC-194117-03-3 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.5138 | 6.26 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256168 | 26003H | 4591J | LP1Y-WPC-194117-03-4 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.0963 | 4.2 | sq ft | 4.2 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256169 | 26003H | 4592J | LP1Y-WPC-194117-03-5 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256170 | 26003H | 4593J | LP1Y-WPC-194117-03-6 | LP1Y-WPC-194117-03 | 1 | N | PRI-2-3 | [5 empty] | Released to Production | P023 |  |  | LP1Y 2" SS WPC (36) (108) 194117 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194117 |  | TFS00E010YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 34.6011 | 27.16 | sq ft | 7.16 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256315 | 26003H | 4594J | LP1Y-H2SO4-016019-06-1 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256318 | 26003H | 4597J | LP1Y-H2SO4-016019-06-4 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 7 | 4 | 3 | 56.585 | 20.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256316 | 26003H | 4595J | LP1Y-H2SO4-016019-06-2 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 14.6063 | 7.45 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256319 | 26003H | 4598J | LP1Y-H2SO4-016019-06-5 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 45.6913 | 17.31 | sq ft | 17.31 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256317 | 26003H | 4596J | LP1Y-H2SO4-016019-06-3 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.75 | 10 | 2.75 | 71.4088 | 25.32 | sq ft | 3.32 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256320 | 26003H | 4599J | LP1Y-H2SO4-016019-06-6 | LP1Y-H2SO4-016019-06 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016019 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016019 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 8 | 8 | 0 | 39.7238 | 16.38 | sq ft | 13.38 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256321 | 26003H | 4600J | LP1Y-H2SO4-016021-03-1 | LP1Y-H2SO4-016021-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016021 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016021 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256323 | 26003H | 4602J | LP1Y-H2SO4-016021-03-3 | LP1Y-H2SO4-016021-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016021 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016021 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12.75 | 10 | 2.75 | 71.4088 | 25.32 | sq ft | 3.32 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256324 | 26003H | 4603J | LP1Y-H2SO4-016021-03-4 | LP1Y-H2SO4-016021-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016021 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016021 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 9 | 6 | 3 | 71.5588 | 25.82 | sq ft | 6.82 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256322 | 26003H | 4601J | LP1Y-H2SO4-016021-03-2 | LP1Y-H2SO4-016021-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016021 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016021 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 6 | 6 | 0 | 14.6063 | 7.45 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256325 | 26003H | 4604J | LP1Y-H2SO4-016021-03-5 | LP1Y-H2SO4-016021-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS H2SO4 (315) P (108) 016021 | H2SO4 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016021 |  | TFS00E011YSPP |  | 315-H2SO4 | NONE | 2" | 316 SS | 12 | 12 | 0 | 66.8938 | 27.34 | sq ft | 22.84 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256328 | 26003H | 4607J | LP1Y-IPA-010020-05-3 | LP1Y-IPA-010020-05 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS IPA (315) P 010020 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010020 |  | TFS00E011YSPP |  | 315-IPA | NONE | 2" | 316 SS | 12 | 12 | 0 | 82.93 | 27.33 | sq ft | 10.33 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256329 | 26003H | 4608J | LP1Y-IPA-010020-05-4 | LP1Y-IPA-010020-05 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS IPA (315) P 010020 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010020 |  | TFS00E011YSPP |  | 315-IPA | NONE | 2" | 316 SS | 8 | 8 | 0 | 18.5663 | 9.7 | sq ft | 5.2 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256330 | 26003H | 4609J | LP1Y-IPA-010020-05-5 | LP1Y-IPA-010020-05 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS IPA (315) P 010020 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010020 |  | TFS00E011YSPP |  | 315-IPA | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.005 | 10.9 | sq ft | 9.4 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256326 | 26003H | 4605J | LP1Y-IPA-010020-05-1 | LP1Y-IPA-010020-05 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS IPA (315) P 010020 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010020 |  | TFS00E011YSPP |  | 315-IPA | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 5.85 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256327 | 26003H | 4606J | LP1Y-IPA-010020-05-2 | LP1Y-IPA-010020-05 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS IPA (315) P 010020 | IPA |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-010020 |  | TFS00E011YSPP |  | 315-IPA | NONE | 2" | 316 SS | 4 | 4 | 0 | 14.8125 | 7.53 | sq ft | 2.03 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256333 | 26003H | 4612J | LP1Y-MTBE-112001-01-3 | LP1Y-MTBE-112001-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112001 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112001 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.9138 | 9.26 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256331 | 26003H | 4610J | LP1Y-MTBE-112001-01-1 | LP1Y-MTBE-112001-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112001 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112001 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 4 | 4 | 0 | 54.385 | 15.19 | sq ft | 1.19 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256332 | 26003H | 4611J | LP1Y-MTBE-112001-01-2 | LP1Y-MTBE-112001-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112001 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112001 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 33.79 | 18.42 | sq ft | 7.42 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256334 | 26003H | 4613J | LP1Y-MTBE-112001-03-1 | LP1Y-MTBE-112001-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112001 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112001 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 65.4663 | 21.16 | sq ft | 7.16 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256335 | 26003H | 4614J | LP1Y-MTBE-112103-01-1 | LP1Y-MTBE-112103-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 0 | 0 | 0 | 20.25 | 4.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256337 | 26003H | 4616J | LP1Y-MTBE-112103-01-3 | LP1Y-MTBE-112103-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 12 | 12 | 0 | 458.9572 | 21.66 | sq ft | 6.55 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256336 | 26003H | 4615J | LP1Y-MTBE-112103-01-2 | LP1Y-MTBE-112103-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 16 | 16 | 0 | 51.4292 | 16.86 | sq ft | 6.26 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian; ED: 2026-04-28; EL: Jacob Perez | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256338 | 26003H | 4617J | LP1Y-MTBE-112103-02-1 | LP1Y-MTBE-112103-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 3 | 3 | 0 | 15.03 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256339 | 26003H | 4618J | LP1Y-MTBE-112103-02-2 | LP1Y-MTBE-112103-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 4 | 4 | 0 | 37.6644 | 8.32 | sq ft | 3.1 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256340 | 26003H | 4619J | LP1Y-MTBE-112103-02-3 | LP1Y-MTBE-112103-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112103 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112103 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 32 | 31 | 1 | 516.792 | 46.6 | sq ft | 4.68 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256341 | 26003H | 4620J | LP1Y-MTBE-112105-02-1 | LP1Y-MTBE-112105-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 1.5 | 1.5 | 0 | 5.61 | 6.4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256343 | 26003H | 4622J | LP1Y-MTBE-112105-02-3 | LP1Y-MTBE-112105-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 16 | 16 | 0 | 62.7527 | 14.82 | sq ft | 3.18 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256344 | 26003H | 4623J | LP1Y-MTBE-112105-02-4 | LP1Y-MTBE-112105-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 11 | 10 | 1 | 47.9239 | 14.82 | sq ft | 0.97 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256342 | 26003H | 4621J | LP1Y-MTBE-112105-02-2 | LP1Y-MTBE-112105-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 24 | 23 | 1 | 112.1752 | 36.52 | sq ft | 11.1 | ft | 2026-02-13 |  |  |  |  | 2026-04-25 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256345 | 26003H | 4624J | LP1Y-MTBE-112105-03-1 | LP1Y-MTBE-112105-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 40 | 40 | 0 | 550.2073 | 50.96 | sq ft | 13.48 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256346 | 26003H | 4625J | LP1Y-MTBE-112105-04-1 | LP1Y-MTBE-112105-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 3" SS MTBE (315) P 112105 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112105 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 42 | 40 | 2 | 630.2593 | 63.68 | sq ft | 19.18 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256347 | 26003H | 4626J | LP1Y-MTBE-112107-01-1 | LP1Y-MTBE-112107-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 4" | 316 SS | 14.25 | 12 | 2.25 | 78.4625 | 28.68 | sq ft | 9.28 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256348 | 26003H | 4627J | LP1Y-MTBE-112107-01-2 | LP1Y-MTBE-112107-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 10 | 10 | 0 | 31.9138 | 14.09 | sq ft | 9.59 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256349 | 26003H | 4628J | LP1Y-MTBE-112107-03-1 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256350 | 26003H | 4629J | LP1Y-MTBE-112107-03-2 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 4 | 4 | 0 | 13.7675 | 7.14 | sq ft | 1.64 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256351 | 26003H | 4630J | LP1Y-MTBE-112107-03-3 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 70.5425 | 26.01 | sq ft | 3.01 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256352 | 26003H | 4631J | LP1Y-MTBE-112107-03-4 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 8 | 8 | 0 | 22.3925 | 11.66 | sq ft | 2.16 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256353 | 26003H | 4632J | LP1Y-MTBE-112107-03-5 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.235 | 6.65 | sq ft | 2.65 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256354 | 26003H | 4633J | LP1Y-MTBE-112107-03-6 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 2 | 2 | 0 | 24.3788 | 9.9 | sq ft | 8.4 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256355 | 26003H | 4634J | LP1Y-MTBE-112107-03-7 | LP1Y-MTBE-112107-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112107 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112107 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.685 | 19.4 | sq ft | 16.4 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256356 | 26003H | 4635J | LP1Y-MTBE-112113-01-1 | LP1Y-MTBE-112113-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 4 | 4 | 0 | 31.6663 | 12.66 | sq ft | 11.16 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256357 | 26003H | 4636J | LP1Y-MTBE-112113-01-2 | LP1Y-MTBE-112113-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 8 | 8 | 0 | 29.4113 | 13.14 | sq ft | 8.64 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-27; DL: George Allahverdian | 2026-04-28 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256358 | 26003H | 4637J | LP1Y-MTBE-112113-03-1 | LP1Y-MTBE-112113-03 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256359 | 26003H | 4638J | LP1Y-MTBE-112113-03-2 | LP1Y-MTBE-112113-03 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256360 | 26003H | 4639J | LP1Y-MTBE-112113-03-3 | LP1Y-MTBE-112113-03 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256361 | 26003H | 4640J | LP1Y-MTBE-112113-03-4 | LP1Y-MTBE-112113-03 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS MTBE (315) P 112113 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112113 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256362 | 26003H | 4641J | LP1Y-MTBE-177402-03-1 | LP1Y-MTBE-177402-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 15 | 14 | 1 | 55.8117 | 18.17 | sq ft | 6.17 | ft | 2026-02-13 |  |  |  |  | 2026-04-25 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256363 | 26003H | 4642J | LP1Y-MTBE-177402-03-2 | LP1Y-MTBE-177402-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 15 | 15 | 0 | 75.8802 | 17.52 | sq ft | 13.02 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256364 | 26003H | 4643J | LP1Y-MTBE-177402-05-1 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256365 | 26003H | 4644J | LP1Y-MTBE-177402-05-2 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256366 | 26003H | 4645J | LP1Y-MTBE-177402-05-3 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256367 | 26003H | 4646J | LP1Y-MTBE-177402-05-4 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256368 | 26003H | 4647J | LP1Y-MTBE-177402-05-5 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256369 | 26003H | 4648J | LP1Y-MTBE-177402-05-6 | LP1Y-MTBE-177402-05 | 1 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256370 | 26003H | 4649J | LP1Y-MTBE-177402-09-1 | LP1Y-MTBE-177402-09 | 0 | N | PRI-2-4 | [5 empty] | In Engineering | P024 |  |  | LP1Y 3" SS MTBE (315) P 177402 | MTBE |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-177402 |  | TFS00E011YSPP |  | 315-MTBE | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256371 | 26003H | 4650J | LP1Y-N2(100)-018044-02-1 | LP1Y-N2(100)-018044-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 018044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018044 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256373 | 26003H | 4652J | LP1Y-N2(100)-018044-02-3 | LP1Y-N2(100)-018044-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 018044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018044 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 28.545 | 11.48 | sq ft | 9.98 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256372 | 26003H | 4651J | LP1Y-N2(100)-018044-02-2 | LP1Y-N2(100)-018044-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 018044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018044 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 82.1425 | 25.78 | sq ft | 12.78 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256376 | 26003H | 4655J | LP1Y-N2(100)-181027-02-3 | LP1Y-N2(100)-181027-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181027 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 48.6511 | 36.66 | sq ft | 3.16 | ft | 2026-02-13 |  |  |  |  | 2026-04-27 | Jacob Perez | 2026-04-28 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256374 | 26003H | 4653J | LP1Y-N2(100)-181027-02-1 | LP1Y-N2(100)-181027-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181027 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.685 | 19.4 | sq ft | 16.4 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256375 | 26003H | 4654J | LP1Y-N2(100)-181027-02-2 | LP1Y-N2(100)-181027-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181027 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 10 | 10 | 0 | 43.21 | 19.71 | sq ft | 15.21 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256377 | 26003H | 4656J | LP1Y-N2(100)-181027-02-4 | LP1Y-N2(100)-181027-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181027 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181027 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 33.357 | 28.21 | sq ft | 1.21 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256378 | 26003H | 4657J | LP1Y-N2(100)-181031-02-1 | LP1Y-N2(100)-181031-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181031 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181031 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 9 | 9 | 0 | 68.9263 | 24.91 | sq ft | 7.41 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256379 | 26003H | 4658J | LP1Y-N2(100)-181031-02-2 | LP1Y-N2(100)-181031-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181031 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181031 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 4 | 4 | 0 | 24.2137 | 10.51 | sq ft | 7.51 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256380 | 26003H | 4659J | LP1Y-N2(100)-181081-02-1 | LP1Y-N2(100)-181081-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181081 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181081 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.2563 | 11.58 | sq ft | 7.58 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256382 | 26003H | 4661J | LP1Y-N2(100)-181108-01-2 | LP1Y-N2(100)-181108-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181108 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181108 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 78.0475 | 27.93 | sq ft | 9.43 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256383 | 26003H | 4662J | LP1Y-N2(100)-181108-01-3 | LP1Y-N2(100)-181108-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181108 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181108 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 18.535 | 8.35 | sq ft | 5.35 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256384 | 26003H | 4663J | LP1Y-N2(100)-181108-01-4 | LP1Y-N2(100)-181108-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181108 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181108 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 44.4125 | 18.16 | sq ft | 15.16 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256381 | 26003H | 4660J | LP1Y-N2(100)-181108-01-1 | LP1Y-N2(100)-181108-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181108 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181108 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256385 | 26003H | 4664J | LP1Y-N2(100)-181127-02-1 | LP1Y-N2(100)-181127-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181127 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181127 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 11 | 11 | 0 | 69.38 | 25.75 | sq ft | 6.75 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256386 | 26003H | 4665J | LP1Y-N2(100)-181129-02-1 | LP1Y-N2(100)-181129-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2(100) (315) E 181129 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181129 |  | TFS00E011YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 2 | 2 | 0 | 27.3113 | 11.6 | sq ft | 7.6 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256387 | 26003H | 4666J | LP1Y-N2-181089-01-1 | LP1Y-N2-181089-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181089 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181089 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256388 | 26003H | 4667J | LP1Y-N2-181089-01-2 | LP1Y-N2-181089-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181089 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181089 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 17.4425 | 9.11 | sq ft | 1.11 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256389 | 26003H | 4668J | LP1Y-N2-181089-01-3 | LP1Y-N2-181089-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181089 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181089 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 2 | 4.25 | 12.4038 | 9.01 | sq ft | 0.51 | ft | 2026-02-13 |  |  |  |  | 2026-04-25 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256392 | 26003H | 4671J | LP1Y-N2-181128-01-3 | LP1Y-N2-181128-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181128 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181128 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 14.4525 | 9.78 | sq ft | 1.28 | ft | 2026-02-13 |  |  |  |  | 2026-04-25 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256390 | 26003H | 4669J | LP1Y-N2-181128-01-1 | LP1Y-N2-181128-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181128 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181128 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 37.9745 | 30.22 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256391 | 26003H | 4670J | LP1Y-N2-181128-01-2 | LP1Y-N2-181128-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS N2 (315) E 181128 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181128 |  | TFS00E011YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 15.38 | 8.33 | sq ft | 0.33 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256393 | 26003H | 4672J | LP1Y-NAOH50-016020-05-1 | LP1Y-NAOH50-016020-05 | 0 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016020 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016020 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256394 | 26003H | 4673J | LP1Y-NAOH50-016020-05-2 | LP1Y-NAOH50-016020-05 | 0 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016020 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016020 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256395 | 26003H | 4674J | LP1Y-NAOH50-016020-05-3 | LP1Y-NAOH50-016020-05 | 0 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016020 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016020 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256396 | 26003H | 4675J | LP1Y-NAOH50-016020-05-4 | LP1Y-NAOH50-016020-05 | 0 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016020 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016020 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256397 | 26003H | 4676J | LP1Y-NAOH50-016020-05-5 | LP1Y-NAOH50-016020-05 | 0 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016020 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016020 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256398 | 26003H | 4677J | LP1Y-NAOH50-016022-03-1 | LP1Y-NAOH50-016022-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016022 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016022 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256400 | 26003H | 4679J | LP1Y-NAOH50-016022-03-2 | LP1Y-NAOH50-016022-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016022 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016022 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 6 | 6 | 0 | 14.8263 | 7.54 | sq ft | 2.04 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256401 | 26003H | 4680J | LP1Y-NAOH50-016022-03-3 | LP1Y-NAOH50-016022-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016022 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016022 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 10.75 | 8 | 2.75 | 68.9613 | 23.72 | sq ft | 3.22 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256402 | 26003H | 4681J | LP1Y-NAOH50-016022-03-5 | LP1Y-NAOH50-016022-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016022 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016022 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 8 | 8 | 0 | 67.3613 | 26.85 | sq ft | 23.85 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256399 | 26003H | 4678J | LP1Y-NAOH50-016022-03-4 | LP1Y-NAOH50-016022-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS NAOH50 (315) P (108) 016022 | NAOH50 |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-016022 |  | TFS00E011YSPP |  | 315-NAOH50 | NONE | 2" | 316 SS | 9 | 6 | 3 | 75.2025 | 27.2 | sq ft | 8.2 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256403 | 26003H | 4682J | LP1Y-PV-112061-02-1 | LP1Y-PV-112061-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PV (315) 112061 | PV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112061 |  | TFS00E011YSPP |  | 315-PV | NONE | 2" | 316 SS | 16 | 16 | 0 | 39.5113 | 19.64 | sq ft | 12.14 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256404 | 26003H | 4683J | LP1Y-PV-112061-02-2 | LP1Y-PV-112061-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PV (315) 112061 | PV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112061 |  | TFS00E011YSPP |  | 315-PV | NONE | 2" | 316 SS | 14 | 14 | 0 | 81.72 | 26.87 | sq ft | 9.88 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256405 | 26003H | 4684J | LP1Y-PV-112061-02-3 | LP1Y-PV-112061-02 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PV (315) 112061 | PV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112061 |  | TFS00E011YSPP |  | 315-PV | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.212 | 13.33 | sq ft | 1.83 | ft | 2026-02-13 | DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256406 | 26003H | 4685J | LP1Y-PVP-112109-04-1 | LP1Y-PVP-112109-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256409 | 26003H | 4688J | LP1Y-PVP-112109-04-4 | LP1Y-PVP-112109-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 4 | 4 | 0 | 47.685 | 19.4 | sq ft | 16.4 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256407 | 26003H | 4686J | LP1Y-PVP-112109-04-2 | LP1Y-PVP-112109-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 18.75 | 18 | 0.75 | 86.0613 | 31.93 | sq ft | 10.93 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256408 | 26003H | 4687J | LP1Y-PVP-112109-04-3 | LP1Y-PVP-112109-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 2 | 2 | 0 | 12.4988 | 5.4 | sq ft | 3.9 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256410 | 26003H | 4689J | LP1Y-PVP-112112-01-1 | LP1Y-PVP-112112-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112112 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112112 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256411 | 26003H | 4690J | LP1Y-PVP-112112-01-2 | LP1Y-PVP-112112-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PVP (315) P 112112 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112112 |  | TFS00E011YSPP |  | 315-PVP | NONE | 2" | 316 SS | 12 | 12 | 0 | 68.5225 | 24.78 | sq ft | 2.28 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256416 | 26003H | 4695J | LP1Y-PWP-112072-03-5 | LP1Y-PWP-112072-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PWP (315) (108) 112072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112072 |  | TFS00E011YSPP |  | 315-PWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 67.6538 | 20.88 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256412 | 26003H | 4691J | LP1Y-PWP-112072-03-1 | LP1Y-PWP-112072-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PWP (315) (108) 112072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112072 |  | TFS00E011YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.4213 | 20.43 | sq ft | 17.43 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256415 | 26003H | 4694J | LP1Y-PWP-112072-03-4 | LP1Y-PWP-112072-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PWP (315) (108) 112072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112072 |  | TFS00E011YSPP |  | 315-PWP | NONE | 2" | 316 SS | 18 | 18 | 0 | 120.7438 | 39.55 | sq ft | 5.55 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256413 | 26003H | 4692J | LP1Y-PWP-112072-03-2 | LP1Y-PWP-112072-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PWP (315) (108) 112072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112072 |  | TFS00E011YSPP |  | 315-PWP | NONE | 2" | 316 SS | 17 | 14 | 3 | 85.7925 | 35.45 | sq ft | 7.95 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256414 | 26003H | 4693J | LP1Y-PWP-112072-03-3 | LP1Y-PWP-112072-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS PWP (315) (108) 112072 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112072 |  | TFS00E011YSPP |  | 315-PWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 60.4338 | 19.8 | sq ft | 2.8 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256417 | 26003H | 4696J | LP1Y-RV-112108-01-1 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256418 | 26003H | 4697J | LP1Y-RV-112108-01-2 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256419 | 26003H | 4698J | LP1Y-RV-112108-01-3 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256420 | 26003H | 4699J | LP1Y-RV-112108-01-4 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256421 | 26003H | 4700J | LP1Y-RV-112108-01-5 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256422 | 26003H | 4701J | LP1Y-RV-112108-01-6 | LP1Y-RV-112108-01 | 2 | N | PRI-2-4 | 2026-04-23 |  | active | client | notification | On Hold | P024 |  |  | LP1Y 6" SS RV (315) 112108 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112108 |  | TFS00E011YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256423 | 26003H | 4702J | LP1Y-RV-112114-01-1 | LP1Y-RV-112114-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS RV (315) P 112114 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112114 |  | TFS00E011YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256424 | 26003H | 4703J | LP1Y-RV-112114-01-2 | LP1Y-RV-112114-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS RV (315) P 112114 | RV |  | NI | 149 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112114 |  | TFS00E011YSPP |  | 315-RV | NONE | 2" | 316 SS | 9 | 9 | 0 | 59.4388 | 21.32 | sq ft | 3.82 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256425 | 26003H | 4704C | LP1Y-S(130)-018067-02-1 | LP1Y-S(130)-018067-02 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256426 | 26003H | 4705C | LP1Y-S(130)-018067-02-2 | LP1Y-S(130)-018067-02 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256428 | 26003H | 4707C | LP1Y-S(130)-018067-03-3 | LP1Y-S(130)-018067-03 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256429 | 26003H | 4708C | LP1Y-S(130)-018067-03-2 | LP1Y-S(130)-018067-03 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256427 | 26003H | 4706C | LP1Y-S(130)-018067-03-1 | LP1Y-S(130)-018067-03 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256430 | 26003H | 4709C | LP1Y-S(130)-018067-05-1 | LP1Y-S(130)-018067-05 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256431 | 26003H | 4710C | LP1Y-S(130)-018067-05-2 | LP1Y-S(130)-018067-05 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256432 | 26003H | 4711C | LP1Y-S(130)-018067-05-3 | LP1Y-S(130)-018067-05 | 1 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018067 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018067 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256433 | 26003H | 4712C | LP1Y-S(130)-018092-02-1 | LP1Y-S(130)-018092-02 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256434 | 26003H | 4713C | LP1Y-S(130)-018092-02-2 | LP1Y-S(130)-018092-02 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256435 | 26003H | 4714C | LP1Y-S(130)-018092-02-3 | LP1Y-S(130)-018092-02 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256436 | 26003H | 4715C | LP1Y-S(130)-018092-03-1 | LP1Y-S(130)-018092-03 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256437 | 26003H | 4716C | LP1Y-S(130)-018092-03-2 | LP1Y-S(130)-018092-03 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256438 | 26003H | 4717C | LP1Y-S(130)-018092-03-3 | LP1Y-S(130)-018092-03 | 0 | N | PRI-2-4 | 2026-04-21 |  | releasing |  |  | Releasing from Hold | P024 |  |  | LP1Y 2" CS S(130) (2) (103) 018092 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018092 |  | TFS00E011YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256439 | 26003H | 4718J | LP1Y-S(130)-166601-01-1 | LP1Y-S(130)-166601-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 1" SS S(130) (315) (103) 166601 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166601 |  | TFS00E011YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256440 | 26003H | 4719J | LP1Y-S(130)-166601-01-2 | LP1Y-S(130)-166601-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 1" SS S(130) (315) (103) 166601 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166601 |  | TFS00E011YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 8.1803 | 9.82 | sq ft | 4.82 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256441 | 26003H | 4720J | LP1Y-S(130)-166608-01-1 | LP1Y-S(130)-166608-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 1" SS S(130) (315) (103) 166608 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166608 |  | TFS00E011YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 7 | 7 | 0 | 7.9453 | 9.66 | sq ft | 4.66 | ft | 2026-02-13 |  |  |  |  | 2026-04-27 | Jacob Perez | 2026-04-28 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256442 | 26003H | 4721J | LP1Y-S(130)-166608-01-2 | LP1Y-S(130)-166608-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 1" SS S(130) (315) (103) 166608 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166608 |  | TFS00E011YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 4 | 4 | 0 | 6.855 | 9.17 | sq ft | 4.17 | ft | 2026-02-13 |  |  |  |  | 2026-04-27 | Jacob Perez | 2026-04-28 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258552 | 26003H | 4724JA | LP1Y-STORMP-166604-04-3A | LP1Y-STORMP-166604-04 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166604 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.4363 | 4.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256443 | 26003H | 4722J | LP1Y-STORMP-166604-04-1 | LP1Y-STORMP-166604-04 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166604 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.6563 | 9.74 | sq ft | 4.24 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256445 | 26003H | 4724J | LP1Y-STORMP-166604-04-3 | LP1Y-STORMP-166604-04 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166604 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 8.75 | 8 | 0.75 | 41.4288 | 21.03 | sq ft | 11.53 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256444 | 26003H | 4723J | LP1Y-STORMP-166604-04-2 | LP1Y-STORMP-166604-04 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166604 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 77.1988 | 28.19 | sq ft | 7.19 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256449 | 26003H | 4728J | LP1Y-STORMP-166607-03-4 | LP1Y-STORMP-166607-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166607 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166607 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 56.98 | 22.92 | sq ft | 19.92 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256448 | 26003H | 4727J | LP1Y-STORMP-166607-03-3 | LP1Y-STORMP-166607-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166607 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166607 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 10 | 10 | 0 | 17.0363 | 8.45 | sq ft | 3.95 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256446 | 26003H | 4725J | LP1Y-STORMP-166607-03-1 | LP1Y-STORMP-166607-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166607 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166607 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 6 | 6 | 0 | 20.6563 | 9.74 | sq ft | 4.24 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256447 | 26003H | 4726J | LP1Y-STORMP-166607-03-2 | LP1Y-STORMP-166607-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS STORMP (315) (108) 166607 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166607 |  | TFS00E011YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 18.25 | 16 | 2.25 | 98.2088 | 36.82 | sq ft | 14.32 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256450 | 26003H | 4729J | LP1Y-SW-166602-01-1 | LP1Y-SW-166602-01 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SW (315) 166602 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166602 |  | TFS00E011YSPP |  | 315-SW | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256451 | 26003H | 4730J | LP1Y-SW-166602-01-2 | LP1Y-SW-166602-01 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SW (315) 166602 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166602 |  | TFS00E011YSPP |  | 315-SW | NONE | 2" | 316 SS | 9.5 | 9.5 | 0 | 63.9673 | 20.57 | sq ft | 6.57 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256452 | 26003H | 4731J | LP1Y-SW-166609-01-1 | LP1Y-SW-166609-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SW (315) 166609 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166609 |  | TFS00E011YSPP |  | 315-SW | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 3.55 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256453 | 26003H | 4732J | LP1Y-SW-166609-01-2 | LP1Y-SW-166609-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SW (315) 166609 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166609 |  | TFS00E011YSPP |  | 315-SW | NONE | 2" | 316 SS | 9.5 | 9.5 | 0 | 64.5506 | 20.99 | sq ft | 6.99 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256454 | 26003H | 4733J | LP1Y-SWP-112082-03-1 | LP1Y-SWP-112082-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 112082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112082 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 50.4075 | 20.43 | sq ft | 17.43 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256455 | 26003H | 4734J | LP1Y-SWP-112082-03-2 | LP1Y-SWP-112082-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 112082 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112082 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 17 | 14 | 3 | 82.9275 | 34.11 | sq ft | 7.11 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256458 | 26003H | 4737J | LP1Y-SWP-166603-03-3 | LP1Y-SWP-166603-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6.75 | 6 | 0.75 | 34.87 | 18.54 | sq ft | 9.04 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256456 | 26003H | 4735J | LP1Y-SWP-166603-03-1 | LP1Y-SWP-166603-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 15.6238 | 7.17 | sq ft | 3.17 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256457 | 26003H | 4736J | LP1Y-SWP-166603-03-2 | LP1Y-SWP-166603-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 84.0301 | 30.6 | sq ft | 10.1 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258553 | 26003H | 4737JA | LP1Y-SWP-166603-03-3A | LP1Y-SWP-166603-03 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 9.45 | 4.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256459 | 26003H | 4738J | LP1Y-SWP-166603-04-1 | LP1Y-SWP-166603-04 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 7.71 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256460 | 26003H | 4739J | LP1Y-SWP-166603-04-2 | LP1Y-SWP-166603-04 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.16 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256461 | 26003H | 4740J | LP1Y-SWP-166603-04-3 | LP1Y-SWP-166603-04 | 1 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166603 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 25.5 | 21 | 4.5 | 96.2534 | 52.05 | sq ft | 9.05 | ft | 2026-02-13 |  |  |  |  | 2026-04-28 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256464 | 26003H | 4743J | LP1Y-SWP-166606-03-3 | LP1Y-SWP-166606-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 10 | 10 | 0 | 39.3388 | 16.9 | sq ft | 12.4 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256462 | 26003H | 4741J | LP1Y-SWP-166606-03-1 | LP1Y-SWP-166606-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 2 | 2 | 0 | 14.3038 | 6.67 | sq ft | 2.67 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256463 | 26003H | 4742J | LP1Y-SWP-166606-03-2 | LP1Y-SWP-166606-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 14.25 | 12 | 2.25 | 77.2651 | 28.04 | sq ft | 7.54 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256465 | 26003H | 4744J | LP1Y-SWP-166606-03-4 | LP1Y-SWP-166606-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.96 | 23.67 | sq ft | 20.67 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256466 | 26003H | 4745J | LP1Y-SWP-166606-04-1 | LP1Y-SWP-166606-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 3 | 3 | 0 | 7.71 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256467 | 26003H | 4746J | LP1Y-SWP-166606-04-2 | LP1Y-SWP-166606-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 5.85 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256468 | 26003H | 4747J | LP1Y-SWP-166606-04-3 | LP1Y-SWP-166606-04 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS SWP (315) (108) 166606 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166606 |  | TFS00E011YSPP |  | 315-SWP | NONE | 2" | 316 SS | 17.5 | 13 | 4.5 | 90.1159 | 44.73 | sq ft | 6.73 | ft | 2026-02-13 |  |  |  |  | 2026-04-28 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256469 | 26003H | 4748J | LP1Y-WFO-017014-08-1 | LP1Y-WFO-017014-08 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 017014 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017014 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 13.7913 | 5.22 | sq ft | 5.22 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256470 | 26003H | 4749J | LP1Y-WFO-017014-08-2 | LP1Y-WFO-017014-08 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 017014 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017014 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.0075 | 0.76 | sq ft | 0.76 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256471 | 26003H | 4750J | LP1Y-WFO-017014-08-3 | LP1Y-WFO-017014-08 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 017014 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017014 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 29.4938 | 11.17 | sq ft | 11.17 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256472 | 26003H | 4751J | LP1Y-WFO-017014-09-1 | LP1Y-WFO-017014-09 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 017014 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017014 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 15.5513 | 5.89 | sq ft | 5.89 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256473 | 26003H | 4752J | LP1Y-WFO-017014-09-2 | LP1Y-WFO-017014-09 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 017014 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017014 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256475 | 26003H | 4754J | LP1Y-WFO-112110-02-2 | LP1Y-WFO-112110-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112110 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.3925 | 0.91 | sq ft | 0.91 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256476 | 26003H | 4755J | LP1Y-WFO-112110-02-3 | LP1Y-WFO-112110-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112110 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8563 | 0.7 | sq ft | 0.7 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256478 | 26003H | 4757J | LP1Y-WFO-112110-02-5 | LP1Y-WFO-112110-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112110 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256474 | 26003H | 4753J | LP1Y-WFO-112110-02-1 | LP1Y-WFO-112110-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112110 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256477 | 26003H | 4756J | LP1Y-WFO-112110-02-4 | LP1Y-WFO-112110-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112110 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112110 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.8775 | 1.47 | sq ft | 1.47 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256479 | 26003H | 4758J | LP1Y-WFO-112208-02-1 | LP1Y-WFO-112208-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112208 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112208 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256480 | 26003H | 4759J | LP1Y-WFO-112208-02-2 | LP1Y-WFO-112208-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112208 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112208 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.74 | 1.42 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256481 | 26003H | 4760J | LP1Y-WFO-112208-02-3 | LP1Y-WFO-112208-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112208 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112208 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256483 | 26003H | 4762J | LP1Y-WFO-112408-02-2 | LP1Y-WFO-112408-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112408 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112408 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.74 | 1.42 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256484 | 26003H | 4763J | LP1Y-WFO-112408-02-3 | LP1Y-WFO-112408-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112408 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112408 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256482 | 26003H | 4761J | LP1Y-WFO-112408-02-1 | LP1Y-WFO-112408-02 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 112408 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112408 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 3.5 | 2 | 1.5 | 6.1 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256487 | 26003H | 4766J | LP1Y-WFO-196027-03-3 | LP1Y-WFO-196027-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196027 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256485 | 26003H | 4764J | LP1Y-WFO-196027-03-1 | LP1Y-WFO-196027-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196027 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 14.9875 | 5.68 | sq ft | 5.68 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256486 | 26003H | 4765J | LP1Y-WFO-196027-03-2 | LP1Y-WFO-196027-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196027 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196027 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.4263 | 4.33 | sq ft | 4.33 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256491 | 26003H | 4770J | LP1Y-WFO-196035-03-4 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 27.9125 | 10.57 | sq ft | 10.57 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256490 | 26003H | 4769J | LP1Y-WFO-196035-03-3 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 36.9463 | 13.99 | sq ft | 13.99 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256493 | 26003H | 4772J | LP1Y-WFO-196035-03-6 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256489 | 26003H | 4768J | LP1Y-WFO-196035-03-2 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256492 | 26003H | 4771J | LP1Y-WFO-196035-03-5 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.1425 | 1.95 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256488 | 26003H | 4767J | LP1Y-WFO-196035-03-1 | LP1Y-WFO-196035-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196035 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196035 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8563 | 0.7 | sq ft | 0.7 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256496 | 26003H | 4775J | LP1Y-WFO-196036-03-3 | LP1Y-WFO-196036-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196036 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196036 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 27.9125 | 10.57 | sq ft | 10.57 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256495 | 26003H | 4774J | LP1Y-WFO-196036-03-2 | LP1Y-WFO-196036-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196036 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196036 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 36.5063 | 13.83 | sq ft | 13.83 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256494 | 26003H | 4773J | LP1Y-WFO-196036-03-1 | LP1Y-WFO-196036-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196036 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196036 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8563 | 0.7 | sq ft | 0.7 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256497 | 26003H | 4776J | LP1Y-WFO-196036-03-4 | LP1Y-WFO-196036-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196036 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196036 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.1425 | 1.95 | sq ft | 1.95 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256498 | 26003H | 4777J | LP1Y-WFO-196036-03-5 | LP1Y-WFO-196036-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WFO (36) 196036 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196036 |  | TFS00E011YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0.8 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256500 | 26003H | 4779J | LP1Y-WPC-017055-03-2 | LP1Y-WPC-017055-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017055 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017055 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.5375 | 1.72 | sq ft | 1.72 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256501 | 26003H | 4780J | LP1Y-WPC-017055-03-3 | LP1Y-WPC-017055-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017055 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017055 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 20.3875 | 13.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256502 | 26003H | 4781J | LP1Y-WPC-017055-03-4 | LP1Y-WPC-017055-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017055 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017055 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.8975 | 0.72 | sq ft | 0.72 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256503 | 26003H | 4782J | LP1Y-WPC-017055-03-5 | LP1Y-WPC-017055-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017055 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017055 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256499 | 26003H | 4778J | LP1Y-WPC-017055-03-1 | LP1Y-WPC-017055-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017055 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017055 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 22.1788 | 8.4 | sq ft | 8.4 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256511 | 26003H | 4790J | LP1Y-WPC-017075-01-8 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.935 | 4.52 | sq ft | 4.52 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256512 | 26003H | 4791J | LP1Y-WPC-017075-01-9 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 30.0163 | 11.37 | sq ft | 11.37 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256515 | 26003H | 4794J | LP1Y-WPC-017075-01-12 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256517 | 26003H | 4796J | LP1Y-WPC-017075-01-14 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.1588 | 0.82 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256516 | 26003H | 4795J | LP1Y-WPC-017075-01-13 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 11.9763 | 4.54 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256509 | 26003H | 4788J | LP1Y-WPC-017075-01-6 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 16.3075 | 6.18 | sq ft | 6.18 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256505 | 26003H | 4784J | LP1Y-WPC-017075-01-2 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.13 | 3.46 | sq ft | 3.46 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256506 | 26003H | 4785J | LP1Y-WPC-017075-01-3 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 28.5863 | 10.83 | sq ft | 10.83 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256507 | 26003H | 4786J | LP1Y-WPC-017075-01-4 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 42.03 | 21.5 | sq ft | 10.5 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256508 | 26003H | 4787J | LP1Y-WPC-017075-01-5 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.8263 | 1.83 | sq ft | 1.83 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256504 | 26003H | 4783J | LP1Y-WPC-017075-01-1 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 8.05 | 4.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256510 | 26003H | 4789J | LP1Y-WPC-017075-01-7 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.1713 | 3.47 | sq ft | 3.47 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256513 | 26003H | 4792J | LP1Y-WPC-017075-01-10 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256514 | 26003H | 4793J | LP1Y-WPC-017075-01-11 | LP1Y-WPC-017075-01 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 017075 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017075 |  | TFS00E012YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 9.515 | 3.6 | sq ft | 3.6 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256518 | 26003H | 4797J | LP1Y-WPC-194120-01-1 | LP1Y-WPC-194120-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.315 | 6.94 | sq ft | 6.94 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256519 | 26003H | 4798J | LP1Y-WPC-194120-01-2 | LP1Y-WPC-194120-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 20.3875 | 13.3 | sq ft | 2.3 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256520 | 26003H | 4799J | LP1Y-WPC-194120-01-3 | LP1Y-WPC-194120-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-23; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256522 | 26003H | 4801J | LP1Y-WPC-194120-03-2 | LP1Y-WPC-194120-03 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6575 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256523 | 26003H | 4802J | LP1Y-WPC-194120-03-3 | LP1Y-WPC-194120-03 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.6338 | 1.76 | sq ft | 1.76 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256524 | 26003H | 4803J | LP1Y-WPC-194120-03-4 | LP1Y-WPC-194120-03 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256521 | 26003H | 4800J | LP1Y-WPC-194120-03-1 | LP1Y-WPC-194120-03 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 18.7275 | 7.09 | sq ft | 7.09 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256525 | 26003H | 4804J | LP1Y-WPC-194120-03-5 | LP1Y-WPC-194120-03 | 2 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194120 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194120 |  | TFS00E011YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 34.873 | 27.24 | sq ft | 7.24 | ft | 2026-02-13 |  |  |  |  | 2026-04-27 | Jacob Perez | 2026-04-28 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256526 | 26003H | 4805J | LP1Y-WPC-194129-03-1 | LP1Y-WPC-194129-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194129 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194129 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.7925 | 6.74 | sq ft | 6.74 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256527 | 26003H | 4806J | LP1Y-WPC-194129-03-2 | LP1Y-WPC-194129-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194129 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194129 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.6575 | 1.39 | sq ft | 1.39 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256528 | 26003H | 4807J | LP1Y-WPC-194129-03-3 | LP1Y-WPC-194129-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194129 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194129 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.6338 | 1.76 | sq ft | 1.76 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256529 | 26003H | 4808J | LP1Y-WPC-194129-03-4 | LP1Y-WPC-194129-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194129 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194129 |  | TFS00E011YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-25; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256530 | 26003H | 4809J | LP1Y-WPC-194129-03-5 | LP1Y-WPC-194129-03 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 2" SS WPC (36) (108) 194129 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194129 |  | TFS00E011YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12 | 0 | 12 | 34.873 | 27.24 | sq ft | 7.24 | ft | 2026-02-13 |  |  |  |  | 2026-04-25 | Jacob Perez | 2026-04-26 | George Allahverdian | 2026-04-27 | Jacob Perez | 2026-04-27 | Jacob Perez | 2026-04-27 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256531 | 26003H | 4810J | LP1Y-WV-112206-01-1 | LP1Y-WV-112206-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112206 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112206 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 4 | 4 | 0 | 25.85 | 8.2 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-27 | Jacob Perez | 2026-04-28 | George Allahverdian | 2026-04-29 | Jacob Perez | 2026-04-29 | Jacob Perez | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256532 | 26003H | 4811J | LP1Y-WV-112206-01-2 | LP1Y-WV-112206-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112206 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112206 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 4 | 4 | 0 | 41.8584 | 9.81 | sq ft | 6.68 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256533 | 26003H | 4812J | LP1Y-WV-112206-01-3 | LP1Y-WV-112206-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112206 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112206 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 16 | 16 | 0 | 34.2788 | 9.05 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256535 | 26003H | 4814J | LP1Y-WV-112406-01-2 | LP1Y-WV-112406-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112406 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112406 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 4 | 4 | 0 | 41.8584 | 9.81 | sq ft | 6.68 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256534 | 26003H | 4813J | LP1Y-WV-112406-01-1 | LP1Y-WV-112406-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112406 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112406 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 4 | 4 | 0 | 25.85 | 8.2 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256536 | 26003H | 4815J | LP1Y-WV-112406-01-3 | LP1Y-WV-112406-01 | 0 | N | PRI-2-4 | [5 empty] | Released to Production | P024 |  |  | LP1Y 4" SS WV (315) (108) 112406 | WV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112406 |  | TFS00E011YSPP |  | 315-WV | NONE | 4" | 316 SS | 16 | 16 | 0 | 34.2788 | 9.05 | sq ft | 4.54 | ft | 2026-02-13 | CD: 2026-04-27; CL: Jacob Perez; DD: 2026-04-28; DL: George Allahverdian | 2026-04-29 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256624 | 26003H | 4816J | LP1Y-DMSO-176201-01-1 | LP1Y-DMSO-176201-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176201 | DMSO |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 4.4 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256625 | 26003H | 4817J | LP1Y-DMSO-176201-01-2 | LP1Y-DMSO-176201-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176201 | DMSO |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 5 | 5 | 0 | 20.67 | 8.17 | sq ft | 2.17 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256626 | 26003H | 4818J | LP1Y-DMSO-176201-01-3 | LP1Y-DMSO-176201-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176201 | DMSO |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 31 | 29 | 2 | 420.7598 | 64.63 | sq ft | 28.63 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256628 | 26003H | 4820J | LP1Y-DMSO-176201-02-2 | LP1Y-DMSO-176201-02 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176201 | DMSO |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-29 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256627 | 26003H | 4819J | LP1Y-DMSO-176201-02-1 | LP1Y-DMSO-176201-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176201 | DMSO |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 3 | 3 | 0 | 87.98 | 21.5 | sq ft | 20 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256630 | 26003H | 4822J | LP1Y-DMSO-176201-03-2 | LP1Y-DMSO-176201-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P 176201 | DMSO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 0 | 0 | 0 | 0.37 | 0.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256629 | 26003H | 4821J | LP1Y-DMSO-176201-03-1 | LP1Y-DMSO-176201-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P 176201 | DMSO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176201 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 9 | 0 | 9 | 32.0773 | 27.05 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256635 | 26003H | 4827J | LP1Y-DMSO-176202-08-5 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 6.25 | 4 | 2.25 | 21.46 | 13.67 | sq ft | 1.67 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256632 | 26003H | 4824J | LP1Y-DMSO-176202-08-2 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-29 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256631 | 26003H | 4823J | LP1Y-DMSO-176202-08-1 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 1 | 1 | 0 | 3.16 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256633 | 26003H | 4825J | LP1Y-DMSO-176202-08-3 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 6 | 6 | 0 | 19.78 | 10.67 | sq ft | 1.17 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256634 | 26003H | 4826J | LP1Y-DMSO-176202-08-4 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 31.28 | 20.96 | sq ft | 1.96 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256636 | 26003H | 4828J | LP1Y-DMSO-176202-08-6 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 2" | 316 SS | 4 | 4 | 0 | 18.02 | 9.33 | sq ft | 1.33 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256637 | 26003H | 4829J | LP1Y-DMSO-176202-08-7 | LP1Y-DMSO-176202-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 6 | 6 | 0 | 55.4025 | 16.74 | sq ft | 0.74 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256638 | 26003H | 4830J | LP1Y-DMSO-176202-09-1 | LP1Y-DMSO-176202-09 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS DMSO (315) P (108) 176202 | DMSO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176202 |  | TFS00E015YSPP |  | 315-DMSO | NONE | 3" | 316 SS | 15 | 15 | 0 | 87.4043 | 20.18 | sq ft | 15.68 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256639 | 26003H | 4831J | LP1Y-N2(100)-018063-02-1 | LP1Y-N2(100)-018063-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 018063 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018063 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256640 | 26003H | 4832J | LP1Y-N2(100)-018063-02-2 | LP1Y-N2(100)-018063-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 018063 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018063 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 8 | 8 | 0 | 72.49 | 22.13 | sq ft | 9.13 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256641 | 26003H | 4833J | LP1Y-N2(100)-018063-02-3 | LP1Y-N2(100)-018063-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 018063 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018063 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.8625 | 9.61 | sq ft | 6.61 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256643 | 26003H | 4835J | LP1Y-N2(100)-181109-01-2 | LP1Y-N2(100)-181109-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 181109 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181109 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 6 | 6 | 0 | 64.2675 | 18.34 | sq ft | 6.84 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256642 | 26003H | 4834J | LP1Y-N2(100)-181109-01-1 | LP1Y-N2(100)-181109-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 181109 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181109 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256644 | 26003H | 4836J | LP1Y-N2(100)-181109-02-1 | LP1Y-N2(100)-181109-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 181109 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181109 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 36 | 36 | 0 | 163.5716 | 81.33 | sq ft | 9.33 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256645 | 26003H | 4837J | LP1Y-N2(100)-181109-03-1 | LP1Y-N2(100)-181109-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2(100) (315) E 181109 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181109 |  | TFS00E015YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 20.5 | 20 | 0.5 | 109.6145 | 50.88 | sq ft | 15.38 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256646 | 26003H | 4838AB | LP1Y-N2-176304-01-1 | LP1Y-N2-176304-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" HAST N2 (332) P 176304 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176304 |  | TFS00E015YSPP |  | 332-N2 | NONE | 1" | H C22 | 3 | 3 | 0 | 6.43 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256647 | 26003H | 4839AB | LP1Y-N2-176311-01-1 | LP1Y-N2-176311-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST N2 (332) P 176311 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176311 |  | TFS00E015YSPP |  | 332-N2 | NONE | 2" | H C22 | 16 | 16 | 0 | 32.7638 | 18.26 | sq ft | 4.26 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256648 | 26003H | 4840AB | LP1Y-N2-176311-01-2 | LP1Y-N2-176311-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST N2 (332) P 176311 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176311 |  | TFS00E015YSPP |  | 332-N2 | NONE | 2" | H C22 | 4 | 4 | 0 | 17.4838 | 9.13 | sq ft | 1.13 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256650 | 26003H | 4842AB | LP1Y-N2-176311-01-4 | LP1Y-N2-176311-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST N2 (332) P 176311 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176311 |  | TFS00E015YSPP |  | 332-N2 | NONE | 2" | H C22 | 13 | 13 | 0 | 31.4238 | 31.54 | sq ft | 1.54 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256649 | 26003H | 4841AB | LP1Y-N2-176311-01-3 | LP1Y-N2-176311-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST N2 (332) P 176311 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176311 |  | TFS00E015YSPP |  | 332-N2 | NONE | 2" | H C22 | 6 | 6 | 0 | 20.55 | 10.96 | sq ft | 1.46 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256651 | 26003H | 4843J | LP1Y-N2-181032-01-1 | LP1Y-N2-181032-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 24.1863 | 10.49 | sq ft | 7.49 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256652 | 26003H | 4844J | LP1Y-N2-181032-01-2 | LP1Y-N2-181032-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 14 | 14 | 0 | 63.02 | 27.12 | sq ft | 18.63 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256653 | 26003H | 4845J | LP1Y-N2-181032-01-3 | LP1Y-N2-181032-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 16.59 | 8.79 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256654 | 26003H | 4846J | LP1Y-N2-181032-01-4 | LP1Y-N2-181032-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16.5 | 12 | 4.5 | 71.3436 | 29.12 | sq ft | 3.12 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256656 | 26003H | 4848J | LP1Y-N2-181032-02-2 | LP1Y-N2-181032-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 34.5163 | 14.99 | sq ft | 9.49 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256655 | 26003H | 4847J | LP1Y-N2-181032-02-1 | LP1Y-N2-181032-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181032 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181032 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 31.75 | 29.5 | 2.25 | 65.6765 | 53.18 | sq ft | 5.18 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256657 | 26003H | 4849J | LP1Y-N2-181033-01-1 | LP1Y-N2-181033-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181033 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181033 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 12 | 12 | 0 | 44.7225 | 20.86 | sq ft | 12.36 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256658 | 26003H | 4850J | LP1Y-N2-181033-01-2 | LP1Y-N2-181033-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181033 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181033 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6 | 6 | 0 | 51.3012 | 20.77 | sq ft | 17.77 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256659 | 26003H | 4851J | LP1Y-N2-181033-01-3 | LP1Y-N2-181033-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181033 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181033 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 28.5 | 28 | 0.5 | 111.8983 | 59.42 | sq ft | 13.42 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256660 | 26003H | 4852J | LP1Y-N2-181111-01-1 | LP1Y-N2-181111-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 7 | 5 | 2 | 10.9373 | 6.87 | sq ft | 2.37 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256661 | 26003H | 4853J | LP1Y-N2-181111-01-2 | LP1Y-N2-181111-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 4 | 4 | 0 | 26.2488 | 11.28 | sq ft | 8.28 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256662 | 26003H | 4854J | LP1Y-N2-181111-01-3 | LP1Y-N2-181111-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 16 | 16 | 0 | 60.665 | 26.31 | sq ft | 18.81 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256663 | 26003H | 4855J | LP1Y-N2-181111-01-4 | LP1Y-N2-181111-01 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256664 | 26003H | 4856J | LP1Y-N2-181111-01-5 | LP1Y-N2-181111-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 6 | 6 | 0 | 29.5213 | 12.52 | sq ft | 9.52 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256665 | 26003H | 4857J | LP1Y-N2-181111-02-1 | LP1Y-N2-181111-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS N2 (315) E 181111 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181111 |  | TFS00E015YSPP |  | 315-N2 | NONE | 2" | 316 SS | 33.75 | 31.5 | 2.25 | 79.8445 | 57.29 | sq ft | 13.29 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256669 | 26003H | 4861J | LP1Y-PVP-110218-05-1 | LP1Y-PVP-110218-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 25.3138 | 11.59 | sq ft | 7.09 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256674 | 26003H | 4866J | LP1Y-RV-176107-01-1 | LP1Y-RV-176107-01 | 0 | N | PRI-2-5 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS RV (315) (108) 176107 | RV |  | 108,NI | 32 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176107 |  | TFS00E015YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256675 | 26003H | 4867J | LP1Y-RV-181034-01-1 | LP1Y-RV-181034-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS RV (315) 181034 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181034 |  | TFS00E015YSPP |  | 315-RV | NONE | 2" | 316 SS | 6 | 6 | 0 | 22.2925 | 10.36 | sq ft | 4.86 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256676 | 26003H | 4868J | LP1Y-RV-181113-01-1 | LP1Y-RV-181113-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS RV (315) 181113 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181113 |  | TFS00E015YSPP |  | 315-RV | NONE | 3" | 316 SS | 21 | 21 | 0 | 88.7655 | 21.55 | sq ft | 13.05 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256677 | 26003H | 4869J | LP1Y-RV-181114-01-1 | LP1Y-RV-181114-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 3" SS RV (315) 181114 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181114 |  | TFS00E015YSPP |  | 315-RV | NONE | 3" | 316 SS | 21 | 21 | 0 | 75.55 | 18.5 | sq ft | 10 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256678 | 26003H | 4870C | LP1Y-S(130)-018017-01-1 | LP1Y-S(130)-018017-01 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018017 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018017 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256679 | 26003H | 4871C | LP1Y-S(130)-018017-01-2 | LP1Y-S(130)-018017-01 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018017 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018017 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256680 | 26003H | 4872C | LP1Y-S(130)-018017-01-3 | LP1Y-S(130)-018017-01 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 0.75" CS S(130) (2) (103) 018017 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018017 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256683 | 26003H | 4875C | LP1Y-S(130)-018081-02-3 | LP1Y-S(130)-018081-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256681 | 26003H | 4873C | LP1Y-S(130)-018081-02-1 | LP1Y-S(130)-018081-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256682 | 26003H | 4874C | LP1Y-S(130)-018081-02-2 | LP1Y-S(130)-018081-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256684 | 26003H | 4876C | LP1Y-S(130)-018081-04-1 | LP1Y-S(130)-018081-04 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 12.75 | 12 | 0.75 | 71.8872 | 25.62 | sq ft | 16.12 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256685 | 26003H | 4877C | LP1Y-S(130)-018081-04-2 | LP1Y-S(130)-018081-04 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 64.5625 | 18.75 | sq ft | 17.25 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256686 | 26003H | 4878C | LP1Y-S(130)-018081-04-3 | LP1Y-S(130)-018081-04 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 2 | 2 | 0 | 29.5833 | 9.17 | sq ft | 7.67 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256687 | 26003H | 4879C | LP1Y-S(130)-018081-04-4 | LP1Y-S(130)-018081-04 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018081 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018081 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 2" | CS | 11.75 | 8 | 3.75 | 36.0942 | 23.63 | sq ft | 4.13 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256688 | 26003H | 4880C | LP1Y-S(130)-018088-02-1 | LP1Y-S(130)-018088-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018088 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018088 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256689 | 26003H | 4881C | LP1Y-S(130)-018088-02-2 | LP1Y-S(130)-018088-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018088 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018088 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256690 | 26003H | 4882C | LP1Y-S(130)-018088-02-3 | LP1Y-S(130)-018088-02 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018088 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018088 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256692 | 26003H | 4884C | LP1Y-S(130)-018119-02-2 | LP1Y-S(130)-018119-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018119 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256693 | 26003H | 4885C | LP1Y-S(130)-018119-02-3 | LP1Y-S(130)-018119-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018119 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256691 | 26003H | 4883C | LP1Y-S(130)-018119-02-1 | LP1Y-S(130)-018119-02 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018119 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 1 | 0 | 1 | 3.2166 | 2.28 | sq ft | 0.78 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256694 | 26003H | 4886C | LP1Y-S(130)-018121-02-1 | LP1Y-S(130)-018121-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018121 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018121 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256695 | 26003H | 4887C | LP1Y-S(130)-018121-02-2 | LP1Y-S(130)-018121-02 | 0 | N | PRI-2-5 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018121 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018121 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256696 | 26003H | 4888C | LP1Y-S(130)-018121-02-3 | LP1Y-S(130)-018121-02 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS S(130) (2) (103) 018121 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018121 |  | TFS00E015YSPP |  | 2-S(130) | P-5 | 1" | CS | 3 | 0 | 3 | 4.2282 | 3.95 | sq ft | 0.95 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256698 | 26003H | 4890C | LP1Y-S(130)-018156-01-2 | LP1Y-S(130)-018156-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018156 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018156 |  | TFS00E015YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 1.8491 | 0.95 | sq ft | 0.95 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256697 | 26003H | 4889C | LP1Y-S(130)-018156-01-1 | LP1Y-S(130)-018156-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018156 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018156 |  | TFS00E015YSPP |  | 2-S(130) | NONE | 2" | CS | 9.5 | 2 | 7.5 | 27.1723 | 28.61 | sq ft | 3.11 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256699 | 26003H | 4891C | LP1Y-S(130)-018156-01-3 | LP1Y-S(130)-018156-01 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018156 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018156 |  | TFS00E015YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-29 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256700 | 26003H | 4892C | LP1Y-S(130)-018156-01-4 | LP1Y-S(130)-018156-01 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" CS S(130) (2) (103) 018156 | S(130) |  | 103,NI | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018156 |  | TFS00E015YSPP |  | 2-S(130) | NONE | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-29 | Jacob Perez | 2026-04-29 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256704 | 26003H | 4896J | LP1Y-S(130)-166701-01-4 | LP1Y-S(130)-166701-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" SS S(130) (315) (103) 166701 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166701 |  | TFS00E015YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 5 | 5 | 0 | 10.945 | 11.67 | sq ft | 7.17 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256705 | 26003H | 4897J | LP1Y-S(130)-166701-01-5 | LP1Y-S(130)-166701-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" SS S(130) (315) (103) 166701 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166701 |  | TFS00E015YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 1 | 1 | 0 | 2.0969 | 1.6 | sq ft | 1.1 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256701 | 26003H | 4893J | LP1Y-S(130)-166701-01-1 | LP1Y-S(130)-166701-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" SS S(130) (315) (103) 166701 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166701 |  | TFS00E015YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 30.4325 | 23.75 | sq ft | 21.25 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256702 | 26003H | 4894J | LP1Y-S(130)-166701-01-2 | LP1Y-S(130)-166701-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" SS S(130) (315) (103) 166701 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166701 |  | TFS00E015YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 8 | 8 | 0 | 16.503 | 19.48 | sq ft | 10.48 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256703 | 26003H | 4895J | LP1Y-S(130)-166701-01-3 | LP1Y-S(130)-166701-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1" SS S(130) (315) (103) 166701 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166701 |  | TFS00E015YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 3 | 3 | 0 | 30.4325 | 23.75 | sq ft | 21.25 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256706 | 26003H | 4898C | LP1Y-SC-018061-01-1 | LP1Y-SC-018061-01 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS SC (2) (101) 018061 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018061 |  | TFS00E015YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256707 | 26003H | 4899C | LP1Y-SC-018120-01-1 | LP1Y-SC-018120-01 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS SC (2) (101) 018120 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018120 |  | TFS00E015YSPP |  | 2-SC | P-4 | 1" | CS | 2 | 0 | 2 | 9.5909 | 5.46 | sq ft | 3.96 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256708 | 26003H | 4900C | LP1Y-SC-018122-01-1 | LP1Y-SC-018122-01 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 1" CS SC (2) (101) 018122 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018122 |  | TFS00E015YSPP |  | 2-SC | P-4 | 1" | CS | 4 | 0 | 4 | 14.7627 | 8.89 | sq ft | 5.89 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256709 | 26003H | 4901C | LP1Y-SC-018157-01-1 | LP1Y-SC-018157-01 | 0 | N | PRI-2-5 | 2026-04-30 | 2026-05-01 | released |  |  | Released to Production | P025 |  |  | LP1Y 0.75" CS SC (2) (101) 018157 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018157 |  | TFS00E015YSPP |  | 2-SC | P-4 | 3/4" | CS | 1.5 | 0 | 1.5 | 6.3886 | 5.37 | sq ft | 3.87 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-05-01 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256710 | 26003H | 4902J | LP1Y-SRACNP-108104-01-1 | LP1Y-SRACNP-108104-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SRACNP (315) P (108) 108104 | SRACNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-108104 |  | TFS00E015YSPP |  | 315-SRACNP | NONE | 2" | 316 SS | 10.25 | 8 | 2.25 | 57.1738 | 27.67 | sq ft | 19.17 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256712 | 26003H | 4904J | LP1Y-STORMP-166704-02-2 | LP1Y-STORMP-166704-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS STORMP (315) (108) 166704 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166704 |  | TFS00E015YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 62.765 | 22.73 | sq ft | 3.23 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256713 | 26003H | 4905J | LP1Y-STORMP-166704-02-3 | LP1Y-STORMP-166704-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS STORMP (315) (108) 166704 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166704 |  | TFS00E015YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 4 | 4 | 0 | 29.7688 | 12.61 | sq ft | 9.61 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256711 | 26003H | 4903J | LP1Y-STORMP-166704-02-1 | LP1Y-STORMP-166704-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS STORMP (315) (108) 166704 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166704 |  | TFS00E015YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 2 | 2 | 0 | 16.0225 | 7.32 | sq ft | 3.32 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256716 | 26003H | 4908J | LP1Y-SW-166702-01-3 | LP1Y-SW-166702-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SW (315) 166702 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166702 |  | TFS00E015YSPP |  | 315-SW | NONE | 2" | 316 SS | 8 | 8 | 0 | 53.0975 | 21.47 | sq ft | 17.97 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256714 | 26003H | 4906J | LP1Y-SW-166702-01-1 | LP1Y-SW-166702-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SW (315) 166702 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166702 |  | TFS00E015YSPP |  | 315-SW | NONE | 2" | 316 SS | 1.5 | 1.5 | 0 | 5.85 | 6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256715 | 26003H | 4907J | LP1Y-SW-166702-01-2 | LP1Y-SW-166702-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SW (315) 166702 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166702 |  | TFS00E015YSPP |  | 315-SW | NONE | 2" | 316 SS | 6 | 6 | 0 | 58.355 | 16.1 | sq ft | 4.6 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256718 | 26003H | 4910J | LP1Y-SWP-166703-02-2 | LP1Y-SWP-166703-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SWP (315) (108) 166703 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166703 |  | TFS00E015YSPP |  | 315-SWP | NONE | 2" | 316 SS | 6 | 6 | 0 | 21.5775 | 10.09 | sq ft | 4.59 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256717 | 26003H | 4909J | LP1Y-SWP-166703-02-1 | LP1Y-SWP-166703-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SWP (315) (108) 166703 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166703 |  | TFS00E015YSPP |  | 315-SWP | NONE | 2" | 316 SS | 18.25 | 16 | 2.25 | 91.1863 | 34.83 | sq ft | 12.33 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256719 | 26003H | 4911J | LP1Y-SWP-166703-03-1 | LP1Y-SWP-166703-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS SWP (315) (108) 166703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166703 |  | TFS00E015YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 2 | 2 | 0 | 5.04 | 9.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256720 | 26003H | 4912J | LP1Y-SWP-166703-03-2 | LP1Y-SWP-166703-03 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS SWP (315) (108) 166703 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-166703 |  | TFS00E015YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256721 | 26003H | 4913AB | LP1Y-TFA-176023-05-1 | LP1Y-TFA-176023-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256722 | 26003H | 4914AB | LP1Y-TFA-176023-05-2 | LP1Y-TFA-176023-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 11 | 11 | 0 | 33.7116 | 25.48 | sq ft | 2.98 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256723 | 26003H | 4915AB | LP1Y-TFA-176023-05-3 | LP1Y-TFA-176023-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176023 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176023 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 4 | 4 | 0 | 33.0725 | 14.45 | sq ft | 8.95 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256724 | 26003H | 4916AB | LP1Y-TFA-176101-02-1 | LP1Y-TFA-176101-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 19.25 | 18.5 | 0.75 | 75.3739 | 50.49 | sq ft | 1.99 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256727 | 26003H | 4919AB | LP1Y-TFA-176101-03-3 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 2.3 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256729 | 26003H | 4921AB | LP1Y-TFA-176101-03-5 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 17.9575 | 8.14 | sq ft | 5.14 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256730 | 26003H | 4922AB | LP1Y-TFA-176101-03-6 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256725 | 26003H | 4917AB | LP1Y-TFA-176101-03-1 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 12 | 12 | 0 | 61.015 | 28.6 | sq ft | 16.1 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256726 | 26003H | 4918AB | LP1Y-TFA-176101-03-2 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 14 | 12.5 | 1.5 | 63.6864 | 42.62 | sq ft | 6.12 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256728 | 26003H | 4920AB | LP1Y-TFA-176101-03-4 | LP1Y-TFA-176101-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176101 | TFA |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176101 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 8 | 8 | 0 | 33.7738 | 15.38 | sq ft | 8.38 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256734 | 26003H | 4926AB | LP1Y-TFA-176108-01-1 | LP1Y-TFA-176108-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 0.5" HAST TFA (332) 176108 | TFA |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176108 |  | TFS00E015YSPP |  | 332-TFA | NONE | 1/2" | H C22 | 0 | 0 | 0 | 1 | 3 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256735 | 26003H | 4927AB | LP1Y-TFA-176108-01-2 | LP1Y-TFA-176108-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 0.5" HAST TFA (332) 176108 | TFA |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176108 |  | TFS00E015YSPP |  | 332-TFA | NONE | 1/2" | H C22 | 0 | 0 | 0 | 1.3 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256736 | 26003H | 4928AB | LP1Y-TFA-176305-01-1 | LP1Y-TFA-176305-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" HAST TFA (332) P (108) 176305 | TFA |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176305 |  | TFS00E015YSPP |  | 332-TFA | NONE | 2" | H C22 | 10.75 | 10 | 0.75 | 36.6047 | 28.21 | sq ft | 3.71 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256737 | 26003H | 4929J | LP1Y-WFO-017007-68-1 | LP1Y-WFO-017007-68 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.345 | 1.65 | sq ft | 1.65 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256738 | 26003H | 4930J | LP1Y-WFO-017007-68-2 | LP1Y-WFO-017007-68 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) (108) 017007 | WFO |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017007 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 12.21 | 4.63 | sq ft | 4.63 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256740 | 26003H | 4932J | LP1Y-WFO-017010-05-2 | LP1Y-WFO-017010-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 47.0113 | 17.81 | sq ft | 17.81 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256743 | 26003H | 4935J | LP1Y-WFO-017010-05-5 | LP1Y-WFO-017010-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 7.75 | 0 | 7.75 | 17.43 | 13.83 | sq ft | 0.83 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256739 | 26003H | 4931J | LP1Y-WFO-017010-05-1 | LP1Y-WFO-017010-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.0575 | 7.22 | sq ft | 7.22 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256742 | 26003H | 4934J | LP1Y-WFO-017010-05-4 | LP1Y-WFO-017010-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 6.0913 | 2.31 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256741 | 26003H | 4933J | LP1Y-WFO-017010-05-3 | LP1Y-WFO-017010-05 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4.75 | 0 | 4.75 | 29.5863 | 11.58 | sq ft | 11.08 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256744 | 26003H | 4936J | LP1Y-WFO-017010-06-1 | LP1Y-WFO-017010-06 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 6 | 0 | 6 | 34.2238 | 12.96 | sq ft | 12.96 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256745 | 26003H | 4937J | LP1Y-WFO-017010-06-2 | LP1Y-WFO-017010-06 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 2.75 | 2 | 0.75 | 19.55 | 12.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256746 | 26003H | 4938J | LP1Y-WFO-017010-06-3 | LP1Y-WFO-017010-06 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WFO (36) 017010 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017010 |  | TFS00E015YSPP |  | 36-WFO | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.0325 | 1.91 | sq ft | 1.91 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256747 | 26003H | 4939J | LP1Y-WFO-196025-02-1 | LP1Y-WFO-196025-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 0.75" SS WFO (36) 196025 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-196025 |  | TFS00E015YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 3.75 | 0 | 3.75 | 20.0602 | 18.7 | sq ft | 4.2 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256748 | 26003H | 4940J | LP1Y-WPC-017057-02-1 | LP1Y-WPC-017057-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 017057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017057 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 24.9013 | 9.43 | sq ft | 9.43 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256749 | 26003H | 4941J | LP1Y-WPC-017057-02-2 | LP1Y-WPC-017057-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 017057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017057 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.9363 | 1.87 | sq ft | 1.87 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256750 | 26003H | 4942J | LP1Y-WPC-017057-02-3 | LP1Y-WPC-017057-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 017057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-017057 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 16.25 | 14 | 2.25 | 32.3313 | 21.1 | sq ft | 3.1 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256754 | 26003H | 4946J | LP1Y-WPC-194123-01-4 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 8.8275 | 3.34 | sq ft | 3.34 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256755 | 26003H | 4947J | LP1Y-WPC-194123-01-5 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256759 | 26003H | 4951J | LP1Y-WPC-194123-01-9 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 6.25 | 0 | 6.25 | 16.895 | 11.98 | sq ft | 0.98 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256757 | 26003H | 4949J | LP1Y-WPC-194123-01-7 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 40.8513 | 15.47 | sq ft | 15.47 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256758 | 26003H | 4950J | LP1Y-WPC-194123-01-8 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256760 | 26003H | 4952J | LP1Y-WPC-194123-01-10 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256761 | 26003H | 4953J | LP1Y-WPC-194123-01-11 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 5.885 | 2.23 | sq ft | 2.23 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256752 | 26003H | 4944J | LP1Y-WPC-194123-01-2 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 2 | 2 | 0 | 3.24 | 2.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256751 | 26003H | 4943J | LP1Y-WPC-194123-01-1 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 2.9975 | 1.14 | sq ft | 1.14 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256753 | 26003H | 4945J | LP1Y-WPC-194123-01-3 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.025 | 1.15 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256756 | 26003H | 4948J | LP1Y-WPC-194123-01-6 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 19.1263 | 7.24 | sq ft | 7.24 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256762 | 26003H | 4954J | LP1Y-WPC-194123-01-12 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 1.76 | 0.67 | sq ft | 0.67 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256763 | 26003H | 4955J | LP1Y-WPC-194123-01-13 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.2763 | 1.62 | sq ft | 1.62 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256764 | 26003H | 4956J | LP1Y-WPC-194123-01-14 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 4.6888 | 1.78 | sq ft | 1.78 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256765 | 26003H | 4957J | LP1Y-WPC-194123-01-15 | LP1Y-WPC-194123-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256767 | 26003H | 4959J | LP1Y-WPC-194123-02-2 | LP1Y-WPC-194123-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 12.5 | 1.25 | 11.25 | 37.9256 | 27.04 | sq ft | 8.54 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256766 | 26003H | 4958J | LP1Y-WPC-194123-02-1 | LP1Y-WPC-194123-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194123 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194123 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 7.405 | 6.83 | sq ft | 3.83 | ft | 2026-02-13 | CD: 2026-04-29; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256768 | 26003H | 4960J | LP1Y-WPC-194124-01-1 | LP1Y-WPC-194124-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 17.16 | 6.5 | sq ft | 6.5 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256769 | 26003H | 4961J | LP1Y-WPC-194124-01-2 | LP1Y-WPC-194124-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 2" | 316 SS | 4 | 0 | 4 | 3.9325 | 1.49 | sq ft | 1.49 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256770 | 26003H | 4962J | LP1Y-WPC-194124-01-3 | LP1Y-WPC-194124-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1" | 316 SS | 3 | 2 | 1 | 5.13 | 5.5 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256771 | 26003H | 4963J | LP1Y-WPC-194124-01-4 | LP1Y-WPC-194124-01 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1" | 316 SS | 1 | 0 | 1 | 5.2606 | 5.31 | sq ft | 2.31 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256772 | 26003H | 4964J | LP1Y-WPC-194124-02-1 | LP1Y-WPC-194124-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 6.5 | 0 | 6.5 | 39.8712 | 27.57 | sq ft | 12.07 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256774 | 26003H | 4966J | LP1Y-WPC-194124-02-3 | LP1Y-WPC-194124-02 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256775 | 26003H | 4967J | LP1Y-WPC-194124-02-4 | LP1Y-WPC-194124-02 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256773 | 26003H | 4965J | LP1Y-WPC-194124-02-2 | LP1Y-WPC-194124-02 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 1.25" SS WPC (36) (108) 194124 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-194124 |  | TFS00E015YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 3.75 | 0 | 3.75 | 24.8038 | 15.14 | sq ft | 12.14 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256778 | 26003H | 4970J | LP1Y-WTFAP-109105-03-3 | LP1Y-WTFAP-109105-03 | 0 | N | PRI-2-5 | [5 empty] | In Engineering | P025 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E015YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256776 | 26003H | 4968J | LP1Y-WTFAP-109105-03-1 | LP1Y-WTFAP-109105-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E015YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 0 | 0 | 0 | 7.25 | 4 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256777 | 26003H | 4969J | LP1Y-WTFAP-109105-03-2 | LP1Y-WTFAP-109105-03 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E015YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 6 | 6 | 0 | 33.7425 | 14.11 | sq ft | 11.11 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez | 2026-05-02 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256780 | 26003H | 4972J | LP1Y-WTFAP-109105-08-2 | LP1Y-WTFAP-109105-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E015YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 6 | 6 | 0 | 39.9575 | 16.47 | sq ft | 13.47 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256779 | 26003H | 4971J | LP1Y-WTFAP-109105-08-1 | LP1Y-WTFAP-109105-08 | 0 | N | PRI-2-5 | [5 empty] | Released to Production | P025 |  |  | LP1Y 2" SS WTFAP (315) (108) 109105 | WTFAP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-109105 |  | TFS00E015YSPP |  | 315-WTFAP | NONE | 2" | 316 SS | 12.25 | 10 | 2.25 | 83.3825 | 29.28 | sq ft | 12.28 | ft | 2026-02-13 | CD: 2026-04-28; CL: Jacob Perez; DD: 2026-04-29; DL: George Allahverdian | 2026-04-30 |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257689 | 26003H | 4973J | LP1Y-AI(100)-034066-02-1 | LP1Y-AI(100)-034066-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS AI(100) (315) 034066 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034066 |  | TFS00I003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257690 | 26003H | 4974J | LP1Y-AI(100)-034066-02-2 | LP1Y-AI(100)-034066-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS AI(100) (315) 034066 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034066 |  | TFS00I003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257691 | 26003H | 4975J | LP1Y-AI(100)-034066-02-3 | LP1Y-AI(100)-034066-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS AI(100) (315) 034066 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034066 |  | TFS00I003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257692 | 26003H | 4976J | LP1Y-AI(100)-034066-02-4 | LP1Y-AI(100)-034066-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS AI(100) (315) 034066 | AI(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034066 |  | TFS00I003YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257693 | 26003H | 4977J | LP1Y-APL(100)-034074-02-1 | LP1Y-APL(100)-034074-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS APL(100) (315) 034074 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034074 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257694 | 26003H | 4978J | LP1Y-APL(100)-034074-02-2 | LP1Y-APL(100)-034074-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS APL(100) (315) 034074 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034074 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257695 | 26003H | 4979J | LP1Y-APL(100)-034074-02-3 | LP1Y-APL(100)-034074-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS APL(100) (315) 034074 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034074 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257696 | 26003H | 4980J | LP1Y-APL(100)-034161-02-1 | LP1Y-APL(100)-034161-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257697 | 26003H | 4981J | LP1Y-APL(100)-034161-02-2 | LP1Y-APL(100)-034161-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257698 | 26003H | 4982J | LP1Y-APL(100)-034161-03-1 | LP1Y-APL(100)-034161-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257701 | 26003H | 4985J | LP1Y-APL(100)-034161-04-3 | LP1Y-APL(100)-034161-04 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257699 | 26003H | 4983J | LP1Y-APL(100)-034161-04-1 | LP1Y-APL(100)-034161-04 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257700 | 26003H | 4984J | LP1Y-APL(100)-034161-04-2 | LP1Y-APL(100)-034161-04 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" SS APL(100) (315) 034161 | APL(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034161 |  | TFS00I003YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257702 | 26003H | 4986J | LP1Y-N2(100)-034050-03-1 | LP1Y-N2(100)-034050-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2(100) (315) E 034050 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034050 |  | TFS00I003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257703 | 26003H | 4987J | LP1Y-N2(100)-034050-03-2 | LP1Y-N2(100)-034050-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2(100) (315) E 034050 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034050 |  | TFS00I003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257705 | 26003H | 4989J | LP1Y-N2(100)-350044-01-2 | LP1Y-N2(100)-350044-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2(100) (315) E 350044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350044 |  | TFS00I003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257706 | 26003H | 4990J | LP1Y-N2(100)-350044-01-3 | LP1Y-N2(100)-350044-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2(100) (315) E 350044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350044 |  | TFS00I003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257704 | 26003H | 4988J | LP1Y-N2(100)-350044-01-1 | LP1Y-N2(100)-350044-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2(100) (315) E 350044 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350044 |  | TFS00I003YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257707 | 26003H | 4991J | LP1Y-N2-350015-01-1 | LP1Y-N2-350015-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257709 | 26003H | 4993J | LP1Y-N2-350015-02-2 | LP1Y-N2-350015-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257710 | 26003H | 4994J | LP1Y-N2-350015-02-3 | LP1Y-N2-350015-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257711 | 26003H | 4995J | LP1Y-N2-350015-02-4 | LP1Y-N2-350015-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257712 | 26003H | 4996J | LP1Y-N2-350015-02-5 | LP1Y-N2-350015-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257708 | 26003H | 4992J | LP1Y-N2-350015-02-1 | LP1Y-N2-350015-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257713 | 26003H | 4997J | LP1Y-N2-350015-03-1 | LP1Y-N2-350015-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257714 | 26003H | 4998J | LP1Y-N2-350015-03-2 | LP1Y-N2-350015-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257715 | 26003H | 4999J | LP1Y-N2-350015-03-3 | LP1Y-N2-350015-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257716 | 26003H | 5000J | LP1Y-N2-350015-03-4 | LP1Y-N2-350015-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350015 | N2 |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350015 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257717 | 26003H | 5001J | LP1Y-N2-350046-01-1 | LP1Y-N2-350046-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257718 | 26003H | 5002J | LP1Y-N2-350046-03-1 | LP1Y-N2-350046-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257719 | 26003H | 5003J | LP1Y-N2-350046-03-2 | LP1Y-N2-350046-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257720 | 26003H | 5004J | LP1Y-N2-350046-03-3 | LP1Y-N2-350046-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257721 | 26003H | 5005J | LP1Y-N2-350046-03-4 | LP1Y-N2-350046-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257722 | 26003H | 5006J | LP1Y-N2-350046-03-5 | LP1Y-N2-350046-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS N2 (315) E 350046 | N2 |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350046 |  | TFS00I003YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257735 | 26003H | 5019J | LP1Y-RV-350049-01-1 | LP1Y-RV-350049-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS RV (315) 350049 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350049 |  | TFS00I003YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257736 | 26003H | 5020J | LP1Y-RV-350049-01-2 | LP1Y-RV-350049-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS RV (315) 350049 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350049 |  | TFS00I003YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257737 | 26003H | 5021J | LP1Y-RV-350049-01-3 | LP1Y-RV-350049-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS RV (315) 350049 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350049 |  | TFS00I003YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257738 | 26003H | 5022J | LP1Y-RV-350050-01-1 | LP1Y-RV-350050-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS RV (315) 350050 | RV |  | NI | 77 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350050 |  | TFS00I003YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257739 | 26003H | 5023C | LP1Y-S(130)-034047-01-1 | LP1Y-S(130)-034047-01 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034047 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034047 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257740 | 26003H | 5024C | LP1Y-S(130)-034047-01-2 | LP1Y-S(130)-034047-01 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034047 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034047 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257741 | 26003H | 5025C | LP1Y-S(130)-034047-01-3 | LP1Y-S(130)-034047-01 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034047 | S(130) |  | 103 | 356 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034047 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257742 | 26003H | 5026C | LP1Y-S(130)-034077-02-1 | LP1Y-S(130)-034077-02 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 2" CS S(130) (2) (103) 034077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034077 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257743 | 26003H | 5027C | LP1Y-S(130)-034077-02-2 | LP1Y-S(130)-034077-02 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 2" CS S(130) (2) (103) 034077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034077 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257744 | 26003H | 5028C | LP1Y-S(130)-034077-02-3 | LP1Y-S(130)-034077-02 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 2" CS S(130) (2) (103) 034077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034077 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257745 | 26003H | 5029C | LP1Y-S(130)-034077-02-4 | LP1Y-S(130)-034077-02 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 2" CS S(130) (2) (103) 034077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034077 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257746 | 26003H | 5030C | LP1Y-S(130)-034077-02-5 | LP1Y-S(130)-034077-02 | 0 | N | PRI-2-6 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P026 |  |  | LP1Y 2" CS S(130) (2) (103) 034077 | S(130) |  | 103 | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034077 |  | TFS00I003YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257747 | 26003H | 5031C | LP1Y-S(130)-034117-02-1 | LP1Y-S(130)-034117-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034117 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034117 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257748 | 26003H | 5032C | LP1Y-S(130)-034117-02-2 | LP1Y-S(130)-034117-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034117 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034117 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257749 | 26003H | 5033C | LP1Y-S(130)-034117-02-3 | LP1Y-S(130)-034117-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034117 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034117 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257750 | 26003H | 5034C | LP1Y-S(130)-034119-02-1 | LP1Y-S(130)-034119-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034119 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257751 | 26003H | 5035C | LP1Y-S(130)-034119-02-2 | LP1Y-S(130)-034119-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034119 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257752 | 26003H | 5036C | LP1Y-S(130)-034119-02-3 | LP1Y-S(130)-034119-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS S(130) (2) (103) 034119 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034119 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257754 | 26003H | 5038C | LP1Y-S(130)-034182-01-2 | LP1Y-S(130)-034182-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034182 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034182 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257755 | 26003H | 5039C | LP1Y-S(130)-034182-01-3 | LP1Y-S(130)-034182-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034182 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034182 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257753 | 26003H | 5037C | LP1Y-S(130)-034182-01-1 | LP1Y-S(130)-034182-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" CS S(130) (2) (103) 034182 | S(130) |  | 103,NI | 365 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034182 |  | TFS00I003YSPP |  | 2-S(130) | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257758 | 26003H | 5042J | LP1Y-S(130)-365605-01-3 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257759 | 26003H | 5043J | LP1Y-S(130)-365605-01-4 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257760 | 26003H | 5044J | LP1Y-S(130)-365605-01-5 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257761 | 26003H | 5045J | LP1Y-S(130)-365605-01-6 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257756 | 26003H | 5040J | LP1Y-S(130)-365605-01-1 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257757 | 26003H | 5041J | LP1Y-S(130)-365605-01-2 | LP1Y-S(130)-365605-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" SS S(130) (315) (103) 365605 | S(130) |  | 103,NI | 59 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365605 |  | TFS00I003YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257762 | 26003H | 5046C | LP1Y-SC-034118-01-1 | LP1Y-SC-034118-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS SC (2) (101) 034118 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034118 |  | TFS00I003YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257763 | 26003H | 5047C | LP1Y-SC-034120-01-1 | LP1Y-SC-034120-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1" CS SC (2) (101) 034120 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034120 |  | TFS00I003YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257764 | 26003H | 5048C | LP1Y-SC-034183-01-1 | LP1Y-SC-034183-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" CS SC (2) (101) 034183 | SC |  | 101 | 212 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034183 |  | TFS00I003YSPP |  | 2-SC | P-4 | 3/4" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-30 | Jacob Perez | 2026-05-01 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257767 | 26003H | 5051J | LP1Y-SOLV-320101-01-3 | LP1Y-SOLV-320101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257765 | 26003H | 5049J | LP1Y-SOLV-320101-01-1 | LP1Y-SOLV-320101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257766 | 26003H | 5050J | LP1Y-SOLV-320101-01-2 | LP1Y-SOLV-320101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257768 | 26003H | 5052J | LP1Y-SOLV-320101-02-1 | LP1Y-SOLV-320101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257769 | 26003H | 5053J | LP1Y-SOLV-320101-02-2 | LP1Y-SOLV-320101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257770 | 26003H | 5054J | LP1Y-SOLV-320101-02-3 | LP1Y-SOLV-320101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257771 | 26003H | 5055J | LP1Y-SOLV-320101-02-4 | LP1Y-SOLV-320101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 320101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257772 | 26003H | 5056J | LP1Y-SOLV-320101-03-1 | LP1Y-SOLV-320101-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320101 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257773 | 26003H | 5057J | LP1Y-SOLV-320102-01-1 | LP1Y-SOLV-320102-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257774 | 26003H | 5058J | LP1Y-SOLV-320102-01-2 | LP1Y-SOLV-320102-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257775 | 26003H | 5059J | LP1Y-SOLV-320102-01-3 | LP1Y-SOLV-320102-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257776 | 26003H | 5060J | LP1Y-SOLV-320102-01-4 | LP1Y-SOLV-320102-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257778 | 26003H | 5062J | LP1Y-SOLV-320102-05-2 | LP1Y-SOLV-320102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257779 | 26003H | 5063J | LP1Y-SOLV-320102-05-3 | LP1Y-SOLV-320102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257777 | 26003H | 5061J | LP1Y-SOLV-320102-05-1 | LP1Y-SOLV-320102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257780 | 26003H | 5064J | LP1Y-SOLV-320102-06-1 | LP1Y-SOLV-320102-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257781 | 26003H | 5065J | LP1Y-SOLV-320102-06-2 | LP1Y-SOLV-320102-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257782 | 26003H | 5066J | LP1Y-SOLV-320102-06-3 | LP1Y-SOLV-320102-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257783 | 26003H | 5067J | LP1Y-SOLV-320102-06-4 | LP1Y-SOLV-320102-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257784 | 26003H | 5068J | LP1Y-SOLV-320201-01-1 | LP1Y-SOLV-320201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257785 | 26003H | 5069J | LP1Y-SOLV-320201-01-2 | LP1Y-SOLV-320201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257786 | 26003H | 5070J | LP1Y-SOLV-320201-01-3 | LP1Y-SOLV-320201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257787 | 26003H | 5071J | LP1Y-SOLV-320201-02-1 | LP1Y-SOLV-320201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257788 | 26003H | 5072J | LP1Y-SOLV-320201-02-2 | LP1Y-SOLV-320201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257789 | 26003H | 5073J | LP1Y-SOLV-320201-02-3 | LP1Y-SOLV-320201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257790 | 26003H | 5074J | LP1Y-SOLV-320201-02-4 | LP1Y-SOLV-320201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257791 | 26003H | 5075J | LP1Y-SOLV-320201-03-1 | LP1Y-SOLV-320201-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257792 | 26003H | 5076J | LP1Y-SOLV-320202-03-1 | LP1Y-SOLV-320202-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257793 | 26003H | 5077J | LP1Y-SOLV-320202-03-2 | LP1Y-SOLV-320202-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257794 | 26003H | 5078J | LP1Y-SOLV-320202-03-3 | LP1Y-SOLV-320202-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257795 | 26003H | 5079J | LP1Y-SOLV-320202-03-4 | LP1Y-SOLV-320202-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257796 | 26003H | 5080J | LP1Y-SOLV-320202-05-1 | LP1Y-SOLV-320202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257797 | 26003H | 5081J | LP1Y-SOLV-320202-05-2 | LP1Y-SOLV-320202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257798 | 26003H | 5082J | LP1Y-SOLV-320202-05-3 | LP1Y-SOLV-320202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257800 | 26003H | 5084J | LP1Y-SOLV-320202-06-2 | LP1Y-SOLV-320202-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257801 | 26003H | 5085J | LP1Y-SOLV-320202-06-3 | LP1Y-SOLV-320202-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257802 | 26003H | 5086J | LP1Y-SOLV-320202-06-4 | LP1Y-SOLV-320202-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257799 | 26003H | 5083J | LP1Y-SOLV-320202-06-1 | LP1Y-SOLV-320202-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257803 | 26003H | 5087J | LP1Y-SOLV-320301-01-1 | LP1Y-SOLV-320301-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257804 | 26003H | 5088J | LP1Y-SOLV-320301-01-2 | LP1Y-SOLV-320301-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257805 | 26003H | 5089J | LP1Y-SOLV-320301-01-3 | LP1Y-SOLV-320301-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257807 | 26003H | 5091J | LP1Y-SOLV-320301-02-2 | LP1Y-SOLV-320301-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257808 | 26003H | 5092J | LP1Y-SOLV-320301-02-3 | LP1Y-SOLV-320301-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257806 | 26003H | 5090J | LP1Y-SOLV-320301-02-1 | LP1Y-SOLV-320301-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257809 | 26003H | 5093J | LP1Y-SOLV-320301-03-1 | LP1Y-SOLV-320301-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320301 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320301 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257810 | 26003H | 5094J | LP1Y-SOLV-320302-03-1 | LP1Y-SOLV-320302-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257812 | 26003H | 5096J | LP1Y-SOLV-320302-03-3 | LP1Y-SOLV-320302-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257813 | 26003H | 5097J | LP1Y-SOLV-320302-03-4 | LP1Y-SOLV-320302-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257811 | 26003H | 5095J | LP1Y-SOLV-320302-03-2 | LP1Y-SOLV-320302-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257814 | 26003H | 5098J | LP1Y-SOLV-320302-05-1 | LP1Y-SOLV-320302-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257815 | 26003H | 5099J | LP1Y-SOLV-320302-05-2 | LP1Y-SOLV-320302-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257816 | 26003H | 5100J | LP1Y-SOLV-320302-05-3 | LP1Y-SOLV-320302-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257817 | 26003H | 5101J | LP1Y-SOLV-320302-06-1 | LP1Y-SOLV-320302-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257819 | 26003H | 5103J | LP1Y-SOLV-320302-06-3 | LP1Y-SOLV-320302-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257818 | 26003H | 5102J | LP1Y-SOLV-320302-06-2 | LP1Y-SOLV-320302-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257820 | 26003H | 5104J | LP1Y-SOLV-320302-06-4 | LP1Y-SOLV-320302-06 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257822 | 26003H | 5106J | LP1Y-SOLV-320401-01-2 | LP1Y-SOLV-320401-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257823 | 26003H | 5107J | LP1Y-SOLV-320401-01-3 | LP1Y-SOLV-320401-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257821 | 26003H | 5105J | LP1Y-SOLV-320401-01-1 | LP1Y-SOLV-320401-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257824 | 26003H | 5108J | LP1Y-SOLV-320401-02-1 | LP1Y-SOLV-320401-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257825 | 26003H | 5109J | LP1Y-SOLV-320401-03-1 | LP1Y-SOLV-320401-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257826 | 26003H | 5110J | LP1Y-SOLV-320401-03-2 | LP1Y-SOLV-320401-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257827 | 26003H | 5111J | LP1Y-SOLV-320401-03-3 | LP1Y-SOLV-320401-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 320401 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320401 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257828 | 26003H | 5112J | LP1Y-SOLV-320402-03-1 | LP1Y-SOLV-320402-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257829 | 26003H | 5113J | LP1Y-SOLV-320402-03-2 | LP1Y-SOLV-320402-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257830 | 26003H | 5114J | LP1Y-SOLV-320402-03-3 | LP1Y-SOLV-320402-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257831 | 26003H | 5115J | LP1Y-SOLV-320402-03-4 | LP1Y-SOLV-320402-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257832 | 26003H | 5116J | LP1Y-SOLV-320402-04-1 | LP1Y-SOLV-320402-04 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257833 | 26003H | 5117J | LP1Y-SOLV-320402-04-2 | LP1Y-SOLV-320402-04 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257834 | 26003H | 5118J | LP1Y-SOLV-320402-05-1 | LP1Y-SOLV-320402-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257835 | 26003H | 5119J | LP1Y-SOLV-320402-05-2 | LP1Y-SOLV-320402-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257836 | 26003H | 5120J | LP1Y-SOLV-320402-05-3 | LP1Y-SOLV-320402-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257837 | 26003H | 5121J | LP1Y-SOLV-320402-05-4 | LP1Y-SOLV-320402-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257838 | 26003H | 5122J | LP1Y-SOLV-322101-01-1 | LP1Y-SOLV-322101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257839 | 26003H | 5123J | LP1Y-SOLV-322101-01-2 | LP1Y-SOLV-322101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257840 | 26003H | 5124J | LP1Y-SOLV-322101-01-3 | LP1Y-SOLV-322101-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257841 | 26003H | 5125J | LP1Y-SOLV-322101-02-1 | LP1Y-SOLV-322101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257842 | 26003H | 5126J | LP1Y-SOLV-322101-02-2 | LP1Y-SOLV-322101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257843 | 26003H | 5127J | LP1Y-SOLV-322101-02-3 | LP1Y-SOLV-322101-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322101 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257844 | 26003H | 5128J | LP1Y-SOLV-322101-03-1 | LP1Y-SOLV-322101-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 322101 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322101 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257845 | 26003H | 5129J | LP1Y-SOLV-322102-05-1 | LP1Y-SOLV-322102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257846 | 26003H | 5130J | LP1Y-SOLV-322102-05-2 | LP1Y-SOLV-322102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257847 | 26003H | 5131J | LP1Y-SOLV-322102-05-3 | LP1Y-SOLV-322102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257848 | 26003H | 5132J | LP1Y-SOLV-322102-05-4 | LP1Y-SOLV-322102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257849 | 26003H | 5133J | LP1Y-SOLV-322102-05-5 | LP1Y-SOLV-322102-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257850 | 26003H | 5134J | LP1Y-SOLV-322102-07-1 | LP1Y-SOLV-322102-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257851 | 26003H | 5135J | LP1Y-SOLV-322102-07-2 | LP1Y-SOLV-322102-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian; ED: 2026-05-02; EL: Jacob Perez; FD: 2026-05-02; FL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257852 | 26003H | 5136J | LP1Y-SOLV-322102-07-3 | LP1Y-SOLV-322102-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257853 | 26003H | 5137J | LP1Y-SOLV-322102-07-4 | LP1Y-SOLV-322102-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322102 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322102 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257854 | 26003H | 5138J | LP1Y-SOLV-322201-01-1 | LP1Y-SOLV-322201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257855 | 26003H | 5139J | LP1Y-SOLV-322201-01-2 | LP1Y-SOLV-322201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257856 | 26003H | 5140J | LP1Y-SOLV-322201-01-3 | LP1Y-SOLV-322201-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257857 | 26003H | 5141J | LP1Y-SOLV-322201-02-1 | LP1Y-SOLV-322201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257858 | 26003H | 5142J | LP1Y-SOLV-322201-02-2 | LP1Y-SOLV-322201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257859 | 26003H | 5143J | LP1Y-SOLV-322201-02-3 | LP1Y-SOLV-322201-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P (108) 322201 | SOLV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257860 | 26003H | 5144J | LP1Y-SOLV-322201-03-1 | LP1Y-SOLV-322201-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 3" SS SOLV (315) P 322201 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322201 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257864 | 26003H | 5148J | LP1Y-SOLV-322202-05-4 | LP1Y-SOLV-322202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257861 | 26003H | 5145J | LP1Y-SOLV-322202-05-1 | LP1Y-SOLV-322202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257862 | 26003H | 5146J | LP1Y-SOLV-322202-05-2 | LP1Y-SOLV-322202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257863 | 26003H | 5147J | LP1Y-SOLV-322202-05-3 | LP1Y-SOLV-322202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257865 | 26003H | 5149J | LP1Y-SOLV-322202-05-5 | LP1Y-SOLV-322202-05 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257866 | 26003H | 5150J | LP1Y-SOLV-322202-07-1 | LP1Y-SOLV-322202-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257867 | 26003H | 5151J | LP1Y-SOLV-322202-07-2 | LP1Y-SOLV-322202-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-05-01 | Jacob Perez | 2026-05-01 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257868 | 26003H | 5152J | LP1Y-SOLV-322202-07-3 | LP1Y-SOLV-322202-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257869 | 26003H | 5153J | LP1Y-SOLV-322202-07-4 | LP1Y-SOLV-322202-07 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SOLV (315) P (108) 322202 | SOLV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-322202 |  | TFS00I003YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257870 | 26003H | 5154J | LP1Y-STORMP-365604-02-1 | LP1Y-STORMP-365604-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS STORMP (315) (108) 365604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365604 |  | TFS00I003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257871 | 26003H | 5155J | LP1Y-STORMP-365604-02-2 | LP1Y-STORMP-365604-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS STORMP (315) (108) 365604 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365604 |  | TFS00I003YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257873 | 26003H | 5157J | LP1Y-SW-365602-01-2 | LP1Y-SW-365602-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SW (315) 365602 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365602 |  | TFS00I003YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257874 | 26003H | 5158J | LP1Y-SW-365602-01-3 | LP1Y-SW-365602-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SW (315) 365602 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365602 |  | TFS00I003YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257872 | 26003H | 5156J | LP1Y-SW-365602-01-1 | LP1Y-SW-365602-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SW (315) 365602 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365602 |  | TFS00I003YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257876 | 26003H | 5160J | LP1Y-SWP-365603-02-2 | LP1Y-SWP-365603-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SWP (315) (108) 365603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365603 |  | TFS00I003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257875 | 26003H | 5159J | LP1Y-SWP-365603-02-1 | LP1Y-SWP-365603-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SWP (315) (108) 365603 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365603 |  | TFS00I003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257877 | 26003H | 5161J | LP1Y-SWP-365603-03-1 | LP1Y-SWP-365603-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SWP (315) (108) 365603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365603 |  | TFS00I003YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257878 | 26003H | 5162J | LP1Y-SWP-365603-03-2 | LP1Y-SWP-365603-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SWP (315) (108) 365603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365603 |  | TFS00I003YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257879 | 26003H | 5163J | LP1Y-SWP-365603-03-3 | LP1Y-SWP-365603-03 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS SWP (315) (108) 365603 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365603 |  | TFS00I003YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257880 | 26003H | 5164J | LP1Y-WFO-033056-08-1 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257881 | 26003H | 5165J | LP1Y-WFO-033056-08-2 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257882 | 26003H | 5166J | LP1Y-WFO-033056-08-3 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257883 | 26003H | 5167J | LP1Y-WFO-033056-08-4 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257884 | 26003H | 5168J | LP1Y-WFO-033056-08-5 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257885 | 26003H | 5169J | LP1Y-WFO-033056-08-6 | LP1Y-WFO-033056-08 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WFO (36) 033056 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033056 |  | TFS00I003YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257886 | 26003H | 5170J | LP1Y-WFO-370012-02-1 | LP1Y-WFO-370012-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 0.75" SS WFO (36) 370012 | WFO |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370012 |  | TFS00I003YSPP |  | 36-WFO | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257887 | 26003H | 5171J | LP1Y-WPC-033057-02-1 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257888 | 26003H | 5172J | LP1Y-WPC-033057-02-2 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257889 | 26003H | 5173J | LP1Y-WPC-033057-02-3 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257890 | 26003H | 5174J | LP1Y-WPC-033057-02-4 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257891 | 26003H | 5175J | LP1Y-WPC-033057-02-5 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257892 | 26003H | 5176J | LP1Y-WPC-033057-02-6 | LP1Y-WPC-033057-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 033057 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033057 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257897 | 26003H | 5181J | LP1Y-WPC-375012-01-5 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257898 | 26003H | 5182J | LP1Y-WPC-375012-01-6 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257893 | 26003H | 5177J | LP1Y-WPC-375012-01-1 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257894 | 26003H | 5178J | LP1Y-WPC-375012-01-2 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257895 | 26003H | 5179J | LP1Y-WPC-375012-01-3 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257896 | 26003H | 5180J | LP1Y-WPC-375012-01-4 | LP1Y-WPC-375012-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-30; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257899 | 26003H | 5183J | LP1Y-WPC-375012-02-1 | LP1Y-WPC-375012-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257900 | 26003H | 5184J | LP1Y-WPC-375012-02-2 | LP1Y-WPC-375012-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257901 | 26003H | 5185J | LP1Y-WPC-375012-02-3 | LP1Y-WPC-375012-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257902 | 26003H | 5186J | LP1Y-WPC-375012-02-4 | LP1Y-WPC-375012-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375012 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375012 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257903 | 26003H | 5187J | LP1Y-WPC-375013-01-1 | LP1Y-WPC-375013-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257904 | 26003H | 5188J | LP1Y-WPC-375013-01-2 | LP1Y-WPC-375013-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257905 | 26003H | 5189J | LP1Y-WPC-375013-01-3 | LP1Y-WPC-375013-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257906 | 26003H | 5190J | LP1Y-WPC-375013-01-4 | LP1Y-WPC-375013-01 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 2" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-01; CL: Jacob Perez; DD: 2026-05-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257909 | 26003H | 5193J | LP1Y-WPC-375013-02-3 | LP1Y-WPC-375013-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1.25" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257907 | 26003H | 5191J | LP1Y-WPC-375013-02-1 | LP1Y-WPC-375013-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1.25" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257908 | 26003H | 5192J | LP1Y-WPC-375013-02-2 | LP1Y-WPC-375013-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1.25" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257910 | 26003H | 5194J | LP1Y-WPC-375013-02-4 | LP1Y-WPC-375013-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1.25" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257911 | 26003H | 5195J | LP1Y-WPC-375013-02-5 | LP1Y-WPC-375013-02 | 0 | N | PRI-2-6 | [5 empty] | In Engineering | P026 |  |  | LP1Y 1.25" SS WPC (36) (108) 375013 | WPC |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375013 |  | TFS00I003YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-05-02; CL: Jacob Perez; DD: 2026-05-03; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258116 | 26003H | 5196J | LP1Y-N2(100)-018004-02-1 | LP1Y-N2(100)-018004-02 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258117 | 26003H | 5197J | LP1Y-N2(100)-018004-02-2 | LP1Y-N2(100)-018004-02 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258118 | 26003H | 5198J | LP1Y-N2(100)-018004-03-1 | LP1Y-N2(100)-018004-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258119 | 26003H | 5199J | LP1Y-N2(100)-018004-04-1 | LP1Y-N2(100)-018004-04 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258120 | 26003H | 5200J | LP1Y-N2(100)-018004-04-2 | LP1Y-N2(100)-018004-04 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258121 | 26003H | 5201J | LP1Y-N2(100)-018004-04-3 | LP1Y-N2(100)-018004-04 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258122 | 26003H | 5202J | LP1Y-N2(100)-018004-04-4 | LP1Y-N2(100)-018004-04 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 018004 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018004 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258123 | 26003H | 5203J | LP1Y-N2(100)-199003-02-1 | LP1Y-N2(100)-199003-02 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258124 | 26003H | 5204J | LP1Y-N2(100)-199003-03-1 | LP1Y-N2(100)-199003-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258125 | 26003H | 5205J | LP1Y-N2(100)-199003-03-2 | LP1Y-N2(100)-199003-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258126 | 26003H | 5206J | LP1Y-N2(100)-199003-03-3 | LP1Y-N2(100)-199003-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258127 | 26003H | 5207J | LP1Y-N2(100)-199003-03-4 | LP1Y-N2(100)-199003-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258128 | 26003H | 5208J | LP1Y-N2(100)-199003-03-5 | LP1Y-N2(100)-199003-03 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS N2(100) (315) E 199003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199003 |  | TFS00E014YSPP |  | 315-N2(100) | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258129 | 26003H | 5209J | LP1Y-RV-199015-01-1 | LP1Y-RV-199015-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS RV (315) 199015 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199015 |  | TFS00E014YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258130 | 26003H | 5210J | LP1Y-RV-199015-01-2 | LP1Y-RV-199015-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 3" SS RV (315) 199015 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199015 |  | TFS00E014YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258131 | 26003H | 5211J | LP1Y-RV-199016-01-1 | LP1Y-RV-199016-01 | 1 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 4" SS RV (315) 199016 | RV |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-199016 |  | TFS00E014YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258132 | 26003H | 5212C | LP1Y-S(130)-018111-02-1 | LP1Y-S(130)-018111-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018111 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018111 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258133 | 26003H | 5213C | LP1Y-S(130)-018111-02-2 | LP1Y-S(130)-018111-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018111 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018111 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258134 | 26003H | 5214C | LP1Y-S(130)-018111-02-3 | LP1Y-S(130)-018111-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018111 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018111 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258136 | 26003H | 5216C | LP1Y-S(130)-018113-02-2 | LP1Y-S(130)-018113-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018113 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018113 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258137 | 26003H | 5217C | LP1Y-S(130)-018113-02-3 | LP1Y-S(130)-018113-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018113 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018113 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258135 | 26003H | 5215C | LP1Y-S(130)-018113-02-1 | LP1Y-S(130)-018113-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018113 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018113 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258139 | 26003H | 5219C | LP1Y-S(130)-018115-02-2 | LP1Y-S(130)-018115-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018115 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018115 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258140 | 26003H | 5220C | LP1Y-S(130)-018115-02-3 | LP1Y-S(130)-018115-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018115 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018115 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258138 | 26003H | 5218C | LP1Y-S(130)-018115-02-1 | LP1Y-S(130)-018115-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018115 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018115 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258142 | 26003H | 5222C | LP1Y-S(130)-018117-02-2 | LP1Y-S(130)-018117-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018117 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018117 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258141 | 26003H | 5221C | LP1Y-S(130)-018117-02-1 | LP1Y-S(130)-018117-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018117 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018117 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258143 | 26003H | 5223C | LP1Y-S(130)-018117-02-3 | LP1Y-S(130)-018117-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018117 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018117 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258144 | 26003H | 5224C | LP1Y-S(130)-018141-02-1 | LP1Y-S(130)-018141-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018141 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018141 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258145 | 26003H | 5225C | LP1Y-S(130)-018141-02-2 | LP1Y-S(130)-018141-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018141 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018141 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258146 | 26003H | 5226C | LP1Y-S(130)-018141-02-3 | LP1Y-S(130)-018141-02 | 1 | N | PRI-2-7 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P027 |  |  | LP1Y 1" CS S(130) (2) (103) 018141 | S(130) |  | 103,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018141 |  | TFS00E014YSPP |  | 2-S(130) | P-5 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258147 | 26003H | 5227C | LP1Y-SC-018112-01-1 | LP1Y-SC-018112-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 1" CS SC (2) (101) 018112 | SC |  | 101 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018112 |  | TFS00E014YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258148 | 26003H | 5228C | LP1Y-SC-018114-01-1 | LP1Y-SC-018114-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 1" CS SC (2) (101) 018114 | SC |  | 101 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018114 |  | TFS00E014YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258149 | 26003H | 5229C | LP1Y-SC-018116-01-1 | LP1Y-SC-018116-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 1" CS SC (2) (101) 018116 | SC |  | 101 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018116 |  | TFS00E014YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258150 | 26003H | 5230C | LP1Y-SC-018118-01-1 | LP1Y-SC-018118-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 1" CS SC (2) (101) 018118 | SC |  | 101 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018118 |  | TFS00E014YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258151 | 26003H | 5231C | LP1Y-SC-018142-01-1 | LP1Y-SC-018142-01 | 0 | N | PRI-2-7 | [5 empty] | In Engineering | P027 |  |  | LP1Y 1" CS SC (2) (101) 018142 | SC |  | 101 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-018142 |  | TFS00E014YSPP |  | 2-SC | P-4 | 1" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246239 | 26003H | 1659D | LP1Y-PV-101510-02-2 | LP1Y-PV-101510-02 | 3 | R | TR-06 04.28.2026 | 2026-04-07 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 12 | 11 | 1 | 47.4733 | 27.06 | sq ft | 2.56 | ft | 2026-02-13 | CD: 2026-03-18; CL: Jacob Perez; DD: 2026-03-18; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246238 | 26003H | 1658D | LP1Y-PV-101510-02-1 | LP1Y-PV-101510-02 | 3 | R | TR-06 04.28.2026 | 2026-04-07 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP PV (344) (108) 101510 | PV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101510 |  | TFS00D005YSPP |  | 344-PV | NONE | 3" | 2205 | 6 | 6 | 0 | 28.319 | 8.65 | sq ft | 0.65 | ft | 2026-02-13 | CD: 2026-03-13; CL: Shannon Carpenter; DD: 2026-03-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246240 | 26003H | 1660J | LP1Y-PV-101518-01-1 | LP1Y-PV-101518-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 35 | 34 | 1 | 262.457 | 58.18 | sq ft | 22.19 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246241 | 26003H | 1661J | LP1Y-PV-101518-01-2 | LP1Y-PV-101518-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101518 | PV |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101518 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 30 | 24 | 6 | 177.6172 | 36.14 | sq ft | 15.44 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246248 | 26003H | 1668J | LP1Y-PV-101617-01-2 | LP1Y-PV-101617-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 36 | 30 | 6 | 212.0078 | 42.79 | sq ft | 19.14 | ft | 2026-02-13 | CD: 2026-03-26; CL: Jacob Perez; DD: 2026-03-27; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S246247 | 26003H | 1667J | LP1Y-PV-101617-01-1 | LP1Y-PV-101617-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101617 | PV |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101617 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 29 | 28 | 1 | 226.6028 | 51.09 | sq ft | 18.16 | ft | 2026-02-13 | DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-28 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247216 | 26003H | 1678J | LP1Y-PV-101717-01-3 | LP1Y-PV-101717-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 3 | 3 | 0 | 5.8038 | 10.04 | sq ft | 0.54 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 | 2026-04-07 | 2026-04-07 | N/A | N/A | Aristeo Banda | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-08 |  |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | 0% |  |  |  | 0%
C34-S247215 | 26003H | 1677J | LP1Y-PV-101717-01-2 | LP1Y-PV-101717-01 | 2 | R | TR-06 04.28.2026 | 2026-04-28 |  | releasing |  |  | Releasing from Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PV (315) (108) 101717 | PV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101717 |  | TFS00D005YSPP |  | 315-PV | NONE | 6" | 316 SS | 23 | 22 | 1 | 214.8528 | 48.28 | sq ft | 18.12 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247255 | 26003H | 1717J | LP1Y-PVP-102109-04-1 | LP1Y-PVP-102109-04 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 3" SS PVP (315) P 102109 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D007YSPP |  | 315-PVP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247256 | 26003H | 1718J | LP1Y-PVP-102109-04-2 | LP1Y-PVP-102109-04 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 3" SS PVP (315) P 102109 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-102109 |  | TFS00D007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 8 | 8 | 0 | 25.7025 | 12.32 | sq ft | 5.32 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247287 | 26003H | 1749J | LP1Y-PWP-014002-09-3 | LP1Y-PWP-014002-09 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256296 | 26003H | 1750JA | LP1Y-PWP-014002-09-5 | LP1Y-PWP-014002-09 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 |  | 0 | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-18; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247286 | 26003H | 1748J | LP1Y-PWP-014002-09-2 | LP1Y-PWP-014002-09 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 23 | 22 | 1 | 78.6825 | 22.85 | sq ft | 2.58 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247285 | 26003H | 1747J | LP1Y-PWP-014002-09-1 | LP1Y-PWP-014002-09 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247288 | 26003H | 1750J | LP1Y-PWP-014002-09-4 | LP1Y-PWP-014002-09 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247295 | 26003H | 1757J | LP1Y-PWP-014002-12-5 | LP1Y-PWP-014002-12 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 76.525 | 15.05 | sq ft | 0.92 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Edgar Castaneda | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 0% | 2026-04-01 | 144040
C34-S247292 | 26003H | 1754J | LP1Y-PWP-014002-12-2 | LP1Y-PWP-014002-12 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 52.3625 | 10.82 | sq ft | 0.79 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Omar Puente | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0% | 2026-04-01 | 144000
C34-S247293 | 26003H | 1755J | LP1Y-PWP-014002-12-3 | LP1Y-PWP-014002-12 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 42 | 42 | 0 | 156.4875 | 33.87 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247291 | 26003H | 1753J | LP1Y-PWP-014002-12-1 | LP1Y-PWP-014002-12 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247294 | 26003H | 1756J | LP1Y-PWP-014002-12-4 | LP1Y-PWP-014002-12 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 014002 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014002 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 97.6438 | 19.14 | sq ft | 3.19 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247304 | 26003H | 1766D | LP1Y-PWP-014007-18-2 | LP1Y-PWP-014007-18 | 5 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 110 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247305 | 26003H | 1767D | LP1Y-PWP-014007-18-3 | LP1Y-PWP-014007-18 | 5 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 111 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 6 | 6 | 0 | 72.9438 | 14.24 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247303 | 26003H | 1765D | LP1Y-PWP-014007-18-1 | LP1Y-PWP-014007-18 | 5 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 014007 | PWP |  | 109 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014007 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 15 | 14 | 1 | 88.1194 | 21.64 | sq ft | 1.8 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247361 | 26003H | 1823D | LP1Y-PWP-101706-07-1 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247363 | 26003H | 1825D | LP1Y-PWP-101706-07-3 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247364 | 26003H | 1826D | LP1Y-PWP-101706-07-4 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247366 | 26003H | 1828D | LP1Y-PWP-101706-07-6 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 6 | 6 | 0 | 72.9438 | 14.24 | sq ft | 4.19 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247365 | 26003H | 1827D | LP1Y-PWP-101706-07-5 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 9 | 8 | 1 | 64.2938 | 16.66 | sq ft | 3.15 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-29 | George Allahverdian | 2026-03-30 | Jacob Perez | 2026-03-30 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247362 | 26003H | 1824D | LP1Y-PWP-101706-07-2 | LP1Y-PWP-101706-07 | 4 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D007YSPP |  | 344-PWP | NONE | 6" | 2205 | 15 | 14 | 1 | 80.66 | 20.2 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247371 | 26003H | 1833D | LP1Y-PWP-101706-10-1 | LP1Y-PWP-101706-10 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 12 | 12 | 0 | 86.9391 | 17.07 | sq ft | 2.04 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247373 | 26003H | 1835D | LP1Y-PWP-101706-10-3 | LP1Y-PWP-101706-10 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 15 | 14 | 1 | 64.46 | 18.9 | sq ft | 1 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247372 | 26003H | 1834D | LP1Y-PWP-101706-10-2 | LP1Y-PWP-101706-10 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 35 | 34 | 1 | 124.8575 | 34.5 | sq ft | 4.5 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247374 | 26003H | 1836D | LP1Y-PWP-101706-10-4 | LP1Y-PWP-101706-10 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP PWP (344) (108) 101706 | PWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101706 |  | TFS00D005YSPP |  | 344-PWP | NONE | 6" | 2205 | 12 | 12 | 0 | 87.4234 | 17.16 | sq ft | 2.09 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-26 | Jacob Perez | 2026-03-26 | Jacob Perez |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249671 | 26003H | 2374D | LP1Y-SWP-014001-01-5 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 92.4609 | 18.13 | sq ft | 2.63 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249672 | 26003H | 2375D | LP1Y-SWP-014001-01-6 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 79.9641 | 15.72 | sq ft | 1.29 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249667 | 26003H | 2370D | LP1Y-SWP-014001-01-1 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-03-31 | Jacob Perez | 2026-03-31 | George Allahverdian | 2026-04-02 | Jacob Perez | 2026-04-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249668 | 26003H | 2371D | LP1Y-SWP-014001-01-2 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 52.4109 | 10.83 | sq ft | 0.8 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249669 | 26003H | 2372D | LP1Y-SWP-014001-01-3 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 79.4391 | 16.07 | sq ft | 3.7 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249670 | 26003H | 2373D | LP1Y-SWP-014001-01-4 | LP1Y-SWP-014001-01 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 24 | 24 | 0 | 86.2031 | 19.58 | sq ft | 2.66 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249681 | 26003H | 2384D | LP1Y-SWP-014001-09-2 | LP1Y-SWP-014001-09 | 3 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249679 | 26003H | 2382D | LP1Y-SWP-014001-09-1 | LP1Y-SWP-014001-09 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 105.2375 | 22.57 | sq ft | 9.54 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249680 | 26003H | 2383D | LP1Y-SWP-014001-09-3 | LP1Y-SWP-014001-09 | 3 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 102.6375 | 20.67 | sq ft | 2.54 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249684 | 26003H | 2387D | LP1Y-SWP-014001-12-1 | LP1Y-SWP-014001-12 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 91.25 | 17.9 | sq ft | 2.5 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249685 | 26003H | 2388D | LP1Y-SWP-014001-12-2 | LP1Y-SWP-014001-12 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 26.25 | 24.75 | 1.5 | 95.6163 | 23.76 | sq ft | 1.48 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249689 | 26003H | 2392D | LP1Y-SWP-014001-14-2 | LP1Y-SWP-014001-14 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 21 | 21 | 0 | 60.2666 | 23.69 | sq ft | 0.82 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249690 | 26003H | 2393D | LP1Y-SWP-014001-14-3 | LP1Y-SWP-014001-14 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 12 | 12 | 0 | 53.6072 | 12.86 | sq ft | 1.55 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249688 | 26003H | 2391D | LP1Y-SWP-014001-14-1 | LP1Y-SWP-014001-14 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 4" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 4" | 2205 | 16 | 16 | 0 | 33.2781 | 9.57 | sq ft | 1.15 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249701 | 26003H | 2404D | LP1Y-SWP-014001-20-1 | LP1Y-SWP-014001-20 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 9 | 9 | 0 | 31.7263 | 8.38 | sq ft | 1.38 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249703 | 26003H | 2406D | LP1Y-SWP-014001-20-3 | LP1Y-SWP-014001-20 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 9 | 9 | 0 | 40.0511 | 11.36 | sq ft | 1.86 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249702 | 26003H | 2405D | LP1Y-SWP-014001-20-2 | LP1Y-SWP-014001-20 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 014001 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-014001 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 15 | 14 | 1 | 41.4942 | 15.92 | sq ft | 1.42 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249730 | 26003H | 2433D | LP1Y-SWP-101506-01-2 | LP1Y-SWP-101506-01 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 6 | 6 | 0 | 44.2281 | 9.13 | sq ft | 3.57 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249729 | 26003H | 2432D | LP1Y-SWP-101506-01-1 | LP1Y-SWP-101506-01 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 3 | 3 | 0 | 17.79 | 7.6 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  |  |  | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249732 | 26003H | 2435D | LP1Y-SWP-101506-01-4 | LP1Y-SWP-101506-01 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 18 | 18 | 0 | 99.4891 | 20.07 | sq ft | 2.2 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-14 | 2026-04-14 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249731 | 26003H | 2434D | LP1Y-SWP-101506-01-3 | LP1Y-SWP-101506-01 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 22 | 21 | 1 | 124.0866 | 36.54 | sq ft | 6.74 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249733 | 26003H | 2436D | LP1Y-SWP-101506-01-5 | LP1Y-SWP-101506-01 | 2 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108,NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 15 | 14 | 1 | 89.96 | 22 | sq ft | 2 | ft | 2026-02-13 |  |  |  |  | 2026-03-25 | Jacob Perez | 2026-03-25 | George Allahverdian | 2026-03-27 | Jacob Perez | 2026-03-27 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249735 | 26003H | 2438D | LP1Y-SWP-101506-02-2 | LP1Y-SWP-101506-02 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 24 | 24 | 0 | 107.5969 | 23.02 | sq ft | 2.34 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249736 | 26003H | 2439D | LP1Y-SWP-101506-02-3 | LP1Y-SWP-101506-02 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 12 | 12 | 0 | 85.825 | 16.85 | sq ft | 1.92 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249734 | 26003H | 2437D | LP1Y-SWP-101506-02-1 | LP1Y-SWP-101506-02 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 16 | 14 | 2 | 151.6497 | 32.42 | sq ft | 8.07 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249737 | 26003H | 2440D | LP1Y-SWP-101506-02-4 | LP1Y-SWP-101506-02 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 27 | 26 | 1 | 120.0444 | 28.39 | sq ft | 4.05 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249738 | 26003H | 2441D | LP1Y-SWP-101506-02-5 | LP1Y-SWP-101506-02 | 3 | R | TR-06 04.28.2026 | 2026-04-16 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" DUP SWP (344) (108) 101506 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101506 |  | TFS00D005YSPP |  | 344-SWP | NONE | 6" | 2205 | 36 | 36 | 0 | 192.2594 | 39.04 | sq ft | 13.47 | ft | 2026-02-13 | CD: 2026-04-01; CL: Jacob Perez; DD: 2026-04-01; DL: George Allahverdian |  |  | Not Passed | No | [5 empty] | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249743 | 26003H | 2446D | LP1Y-SWP-101509-04-1 | LP1Y-SWP-101509-04 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian; ED: 2026-04-17; EL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249744 | 26003H | 2447D | LP1Y-SWP-101509-04-2 | LP1Y-SWP-101509-04 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249746 | 26003H | 2449D | LP1Y-SWP-101509-04-4 | LP1Y-SWP-101509-04 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249745 | 26003H | 2448D | LP1Y-SWP-101509-04-3 | LP1Y-SWP-101509-04 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 12 | 11 | 1 | 40.547 | 15.7 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S249747 | 26003H | 2450D | LP1Y-SWP-101509-04-5 | LP1Y-SWP-101509-04 | 2 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 3" DUP SWP (344) (108) 101509 | SWP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101509 |  | TFS00D005YSPP |  | 344-SWP | NONE | 3" | 2205 | 9 | 8 | 1 | 33.4832 | 14.07 | sq ft | 1.07 | ft | 2026-02-13 | CD: 2026-03-30; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250436 | 26003H | 3066D | LP1Y-WV-175013-04-2 | LP1Y-WV-175013-04 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250435 | 26003H | 3065D | LP1Y-WV-175013-04-1 | LP1Y-WV-175013-04 | 1 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P036 | 2026-08-24 |  | LP1Y 3" DUP WV (344) (108) 175013 | WV |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-175013 |  | TFS00D007YSPP |  | 344-WV | NONE | 3" | 2205 | 9 | 9 | 0 | 40.3588 | 10.37 | sq ft | 4.88 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-29; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250734 | 26003H | 3169J | LP1Y-ACN-107403-02-1 | LP1Y-ACN-107403-02 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250736 | 26003H | 3171J | LP1Y-ACN-107403-02-3 | LP1Y-ACN-107403-02 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250735 | 26003H | 3170J | LP1Y-ACN-107403-02-2 | LP1Y-ACN-107403-02 | 3 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 6" SS ACN (315) P 107403 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107403 |  | TFS00E005YSPP |  | 315-ACN | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250737 | 26003H | 3172J | LP1Y-ACN-107405-02-1 | LP1Y-ACN-107405-02 | 2 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250739 | 26003H | 3174J | LP1Y-ACN-107405-02-3 | LP1Y-ACN-107405-02 | 2 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250738 | 26003H | 3173J | LP1Y-ACN-107405-02-2 | LP1Y-ACN-107405-02 | 2 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S250740 | 26003H | 3175J | LP1Y-ACN-107405-02-4 | LP1Y-ACN-107405-02 | 2 | R | TR-06 04.28.2026 | 2026-04-02 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 4" SS ACN (315) P 107405 | ACN |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-107405 |  | TFS00E005YSPP |  | 315-ACN | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-13; CL: Jacob Perez; DD: 2026-04-13; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251336 | 26003H | 3512J | LP1Y-AWNP-112205-02-1 | LP1Y-AWNP-112205-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251337 | 26003H | 3513J | LP1Y-AWNP-112205-02-2 | LP1Y-AWNP-112205-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251338 | 26003H | 3514J | LP1Y-AWNP-112205-02-3 | LP1Y-AWNP-112205-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251339 | 26003H | 3515J | LP1Y-AWNP-112205-02-4 | LP1Y-AWNP-112205-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112205 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112205 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251367 | 26003H | 3543J | LP1Y-AWNP-112405-02-3 | LP1Y-AWNP-112405-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251368 | 26003H | 3544J | LP1Y-AWNP-112405-02-4 | LP1Y-AWNP-112405-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251365 | 26003H | 3541J | LP1Y-AWNP-112405-02-1 | LP1Y-AWNP-112405-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-26; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S251366 | 26003H | 3542J | LP1Y-AWNP-112405-02-2 | LP1Y-AWNP-112405-02 | 1 | R | TR-06 04.28.2026 | 2026-04-20 |  | active | client | notification | On Hold | P024 | 2026-07-27 |  | LP1Y 2" SS AWNP (315) (108) 112405 | AWNP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112405 |  | TFS00E011YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-01-20 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255169 | 26003H | 3890J | LP1Y-PVP-111209-06-1 | LP1Y-PVP-111209-06 | 2 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255170 | 26003H | 3891J | LP1Y-PVP-111209-06-2 | LP1Y-PVP-111209-06 | 2 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 |  |  |  |  | 2026-04-15 | Jacob Perez | 2026-04-15 | George Allahverdian | 2026-04-16 | Jacob Perez | 2026-04-16 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255171 | 26003H | 3892J | LP1Y-PVP-111209-06-3 | LP1Y-PVP-111209-06 | 2 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111209 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111209 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-15; CL: Jacob Perez; DD: 2026-04-15; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255173 | 26003H | 3894J | LP1Y-PVP-111409-04-2 | LP1Y-PVP-111409-04 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255172 | 26003H | 3893J | LP1Y-PVP-111409-04-1 | LP1Y-PVP-111409-04 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111409 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111409 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255174 | 26003H | 3895J | LP1Y-PVP-111609-05-1 | LP1Y-PVP-111609-05 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255175 | 26003H | 3896J | LP1Y-PVP-111609-05-2 | LP1Y-PVP-111609-05 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 111609 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-111609 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255177 | 26003H | 3898J | LP1Y-PVP-112109-07-1 | LP1Y-PVP-112109-07 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255178 | 26003H | 3899J | LP1Y-PVP-112109-07-2 | LP1Y-PVP-112109-07 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255179 | 26003H | 3900J | LP1Y-PVP-112109-07-3 | LP1Y-PVP-112109-07 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P019 | 2026-06-29 |  | LP1Y 2" SS PVP (315) P 112109 | PVP |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-112109 |  | TFS00E016YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-14; CL: Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258554 | 26003H | 3997JA | LP1Y-N2(100)-181003-02-3 | LP1Y-N2(100)-181003-02 | 1 | R | TR-06 04.28.2026 | [5 empty] | In Engineering | P021 |  |  | LP1Y 2" SS N2(100) (315) E 181003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181003 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-04-28 |  |  |  |  | 2026-04-30 | Jacob Perez | 2026-05-01 | George Allahverdian | 2026-05-02 | Jacob Perez | 2026-05-02 | Jacob Perez |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255275 | 26003H | 3996J | LP1Y-N2(100)-181003-02-1 | LP1Y-N2(100)-181003-02 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181003 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-22; CL: Jacob Perez; DD: 2026-04-22; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S255276 | 26003H | 3997J | LP1Y-N2(100)-181003-02-2 | LP1Y-N2(100)-181003-02 | 1 | R | TR-06 04.28.2026 | 2026-04-14 |  | active | client | notification | On Hold | P021 | 2026-07-20 |  | LP1Y 2" SS N2(100) (315) E 181003 | N2(100) |  | NI | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-181003 |  | TFS00E005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-04-24; CL: Jacob Perez; DD: 2026-04-25; DL: George Allahverdian |  |  | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256666 | 26003H | 4858J | LP1Y-PVP-110218-03-1 | LP1Y-PVP-110218-03 | 3 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256667 | 26003H | 4859J | LP1Y-PVP-110218-03-2 | LP1Y-PVP-110218-03 | 3 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256668 | 26003H | 4860J | LP1Y-PVP-110218-03-3 | LP1Y-PVP-110218-03 | 3 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) P (108) 110218 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-110218 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256671 | 26003H | 4863J | LP1Y-PVP-176001-01-2 | LP1Y-PVP-176001-01 | 2 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256672 | 26003H | 4864J | LP1Y-PVP-176001-01-3 | LP1Y-PVP-176001-01 | 2 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256673 | 26003H | 4865J | LP1Y-PVP-176001-01-4 | LP1Y-PVP-176001-01 | 2 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256670 | 26003H | 4862J | LP1Y-PVP-176001-01-1 | LP1Y-PVP-176001-01 | 2 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 2" SS PVP (315) (108) 176001 | PVP |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176001 |  | TFS00E015YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256732 | 26003H | 4924AB | LP1Y-TFA-176106-01-2 | LP1Y-TFA-176106-01 | 1 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 1" HAST TFA (332) P (108) 176106 | TFA |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176106 |  | TFS00E015YSPP |  | 332-TFA | NONE | 1" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256731 | 26003H | 4923AB | LP1Y-TFA-176106-01-1 | LP1Y-TFA-176106-01 | 1 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 1" HAST TFA (332) P (108) 176106 | TFA |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176106 |  | TFS00E015YSPP |  | 332-TFA | NONE | 1" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S256733 | 26003H | 4925AB | LP1Y-TFA-176106-01-3 | LP1Y-TFA-176106-01 | 1 | R | TR-06 04.28.2026 | 2026-04-23 |  | active | client | notification | On Hold | P025 |  |  | LP1Y 1" HAST TFA (332) P (108) 176106 | TFA |  | 108 | 95 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-176106 |  | TFS00E015YSPP |  | 332-TFA | NONE | 1" | H C22 | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257723 | 26003H | 5007J | LP1Y-PVP-300308-05-1 | LP1Y-PVP-300308-05 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 300308 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-300308 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257724 | 26003H | 5008J | LP1Y-PVP-300308-05-2 | LP1Y-PVP-300308-05 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 300308 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-300308 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257725 | 26003H | 5009J | LP1Y-PVP-300408-05-1 | LP1Y-PVP-300408-05 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 300408 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-300408 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257726 | 26003H | 5010J | LP1Y-PVP-300408-05-2 | LP1Y-PVP-300408-05 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 300408 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-300408 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257727 | 26003H | 5011J | LP1Y-PVP-301109-03-1 | LP1Y-PVP-301109-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257728 | 26003H | 5012J | LP1Y-PVP-301109-03-2 | LP1Y-PVP-301109-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257730 | 26003H | 5014J | LP1Y-PVP-301209-03-2 | LP1Y-PVP-301209-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257729 | 26003H | 5013J | LP1Y-PVP-301209-03-1 | LP1Y-PVP-301209-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257731 | 26003H | 5015J | LP1Y-PVP-301309-03-1 | LP1Y-PVP-301309-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257732 | 26003H | 5016J | LP1Y-PVP-301309-03-2 | LP1Y-PVP-301309-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257734 | 26003H | 5018J | LP1Y-PVP-301409-03-2 | LP1Y-PVP-301409-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S257733 | 26003H | 5017J | LP1Y-PVP-301409-03-1 | LP1Y-PVP-301409-03 | 1 | R | TR-06 04.28.2026 | 2026-04-28 |  | active | client | notification | On Hold | P026 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I003YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258185 | 26003H | 5232J | LP1Y-APL(100)-034002-02-1 | LP1Y-APL(100)-034002-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258186 | 26003H | 5233J | LP1Y-APL(100)-034002-02-2 | LP1Y-APL(100)-034002-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258187 | 26003H | 5234J | LP1Y-APL(100)-034002-02-3 | LP1Y-APL(100)-034002-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258188 | 26003H | 5235J | LP1Y-APL(100)-034002-02-4 | LP1Y-APL(100)-034002-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258189 | 26003H | 5236J | LP1Y-APL(100)-034002-04-1 | LP1Y-APL(100)-034002-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 0.75" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258190 | 26003H | 5237J | LP1Y-APL(100)-034002-04-2 | LP1Y-APL(100)-034002-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 0.75" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258191 | 26003H | 5238J | LP1Y-APL(100)-034002-04-3 | LP1Y-APL(100)-034002-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 0.75" SS APL(100) (315) 034002 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034002 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258192 | 26003H | 5239J | LP1Y-APL(100)-357004-02-1 | LP1Y-APL(100)-357004-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS APL(100) (315) 357004 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-357004 |  | TFS00I004YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258193 | 26003H | 5240J | LP1Y-AWNP-303091-02-1 | LP1Y-AWNP-303091-02 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258194 | 26003H | 5241J | LP1Y-AWNP-303091-02-2 | LP1Y-AWNP-303091-02 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258195 | 26003H | 5242J | LP1Y-AWNP-303091-02-3 | LP1Y-AWNP-303091-02 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258196 | 26003H | 5243J | LP1Y-AWNP-303091-05-1 | LP1Y-AWNP-303091-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258197 | 26003H | 5244J | LP1Y-AWNP-303091-05-2 | LP1Y-AWNP-303091-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258198 | 26003H | 5245J | LP1Y-AWNP-303091-05-3 | LP1Y-AWNP-303091-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS AWNP (315) (108) 303091 | AWNP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303091 |  | TFS00I004YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258199 | 26003H | 5246J | LP1Y-N2(100)-034042-02-1 | LP1Y-N2(100)-034042-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 034042 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034042 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258200 | 26003H | 5247J | LP1Y-N2(100)-034042-02-2 | LP1Y-N2(100)-034042-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 034042 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034042 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258201 | 26003H | 5248J | LP1Y-N2(100)-350001-01-1 | LP1Y-N2(100)-350001-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350001 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350001 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258202 | 26003H | 5249J | LP1Y-N2(100)-350001-01-2 | LP1Y-N2(100)-350001-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350001 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350001 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258203 | 26003H | 5250J | LP1Y-N2(100)-350001-01-3 | LP1Y-N2(100)-350001-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350001 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350001 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258204 | 26003H | 5251J | LP1Y-N2(100)-350001-01-4 | LP1Y-N2(100)-350001-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350001 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350001 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258205 | 26003H | 5252J | LP1Y-N2(100)-350011-01-1 | LP1Y-N2(100)-350011-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350011 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350011 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258206 | 26003H | 5253J | LP1Y-N2(100)-350011-01-2 | LP1Y-N2(100)-350011-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350011 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350011 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258207 | 26003H | 5254J | LP1Y-N2(100)-350039-01-1 | LP1Y-N2(100)-350039-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350039 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350039 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258208 | 26003H | 5255J | LP1Y-N2(100)-350039-01-2 | LP1Y-N2(100)-350039-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350039 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350039 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258209 | 26003H | 5256J | LP1Y-N2(100)-350039-01-3 | LP1Y-N2(100)-350039-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350039 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350039 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258210 | 26003H | 5257J | LP1Y-N2(100)-350039-01-4 | LP1Y-N2(100)-350039-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350039 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350039 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258211 | 26003H | 5258J | LP1Y-N2(100)-350039-01-5 | LP1Y-N2(100)-350039-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2(100) (315) E 350039 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350039 |  | TFS00I004YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258214 | 26003H | 5261J | LP1Y-N2-350013-01-3 | LP1Y-N2-350013-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2 (315) E 350013 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350013 |  | TFS00I004YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258212 | 26003H | 5259J | LP1Y-N2-350013-01-1 | LP1Y-N2-350013-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2 (315) E 350013 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350013 |  | TFS00I004YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258213 | 26003H | 5260J | LP1Y-N2-350013-01-2 | LP1Y-N2-350013-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS N2 (315) E 350013 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350013 |  | TFS00I004YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258215 | 26003H | 5262J | LP1Y-PV-303061-01-1 | LP1Y-PV-303061-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PV (315) 303061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303061 |  | TFS00I004YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258216 | 26003H | 5263J | LP1Y-PV-303061-01-2 | LP1Y-PV-303061-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PV (315) 303061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303061 |  | TFS00I004YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258217 | 26003H | 5264J | LP1Y-PV-303061-02-1 | LP1Y-PV-303061-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PV (315) 303061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303061 |  | TFS00I004YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258218 | 26003H | 5265J | LP1Y-PV-303061-02-2 | LP1Y-PV-303061-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PV (315) 303061 | PV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303061 |  | TFS00I004YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258219 | 26003H | 5266J | LP1Y-PV-311001-01-1 | LP1Y-PV-311001-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PV (315) (108) 311001 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-311001 |  | TFS00I004YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258220 | 26003H | 5267J | LP1Y-PVP-303109-03-1 | LP1Y-PVP-303109-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303109 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258221 | 26003H | 5268J | LP1Y-PVP-303109-03-2 | LP1Y-PVP-303109-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303109 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258222 | 26003H | 5269J | LP1Y-PVP-303109-03-3 | LP1Y-PVP-303109-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303109 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258223 | 26003H | 5270J | LP1Y-PVP-303109-03-4 | LP1Y-PVP-303109-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303109 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303109 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258224 | 26003H | 5271J | LP1Y-PVP-303111-01-1 | LP1Y-PVP-303111-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303111 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303111 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258225 | 26003H | 5272J | LP1Y-PVP-303111-01-2 | LP1Y-PVP-303111-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PVP (315) P 303111 | PVP |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303111 |  | TFS00I004YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258226 | 26003H | 5273J | LP1Y-PWP-303071-02-1 | LP1Y-PWP-303071-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258227 | 26003H | 5274J | LP1Y-PWP-303071-02-2 | LP1Y-PWP-303071-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258228 | 26003H | 5275J | LP1Y-PWP-303071-02-3 | LP1Y-PWP-303071-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258229 | 26003H | 5276J | LP1Y-PWP-303071-02-4 | LP1Y-PWP-303071-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258230 | 26003H | 5277J | LP1Y-PWP-303071-04-1 | LP1Y-PWP-303071-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258231 | 26003H | 5278J | LP1Y-PWP-303071-04-2 | LP1Y-PWP-303071-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258232 | 26003H | 5279J | LP1Y-PWP-303071-04-3 | LP1Y-PWP-303071-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS PWP (315) (108) 303071 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303071 |  | TFS00I004YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258234 | 26003H | 5281J | LP1Y-RV-303107-01-2 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258235 | 26003H | 5282J | LP1Y-RV-303107-01-3 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258236 | 26003H | 5283J | LP1Y-RV-303107-01-4 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258237 | 26003H | 5284J | LP1Y-RV-303107-01-5 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258238 | 26003H | 5285J | LP1Y-RV-303107-01-6 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258233 | 26003H | 5280J | LP1Y-RV-303107-01-1 | LP1Y-RV-303107-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 6" SS RV (315) 303107 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303107 |  | TFS00I004YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258239 | 26003H | 5286J | LP1Y-RV-303117-01-1 | LP1Y-RV-303117-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS RV (315) P 303117 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303117 |  | TFS00I004YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258240 | 26003H | 5287J | LP1Y-RV-303117-01-2 | LP1Y-RV-303117-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS RV (315) P 303117 | RV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303117 |  | TFS00I004YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258241 | 26003H | 5288C | LP1Y-S(130)-034052-01-1 | LP1Y-S(130)-034052-01 | 0 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258242 | 26003H | 5289C | LP1Y-S(130)-034052-01-2 | LP1Y-S(130)-034052-01 | 0 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258243 | 26003H | 5290C | LP1Y-S(130)-034052-01-3 | LP1Y-S(130)-034052-01 | 0 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258244 | 26003H | 5291C | LP1Y-S(130)-034052-02-1 | LP1Y-S(130)-034052-02 | 1 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258246 | 26003H | 5293C | LP1Y-S(130)-034052-04-2 | LP1Y-S(130)-034052-04 | 0 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258245 | 26003H | 5292C | LP1Y-S(130)-034052-04-1 | LP1Y-S(130)-034052-04 | 0 | N | PRI-3-1 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P031 |  |  | LP1Y 2" CS S(130) (2) (103) 034052 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034052 |  | TFS00I004YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258249 | 26003H | 5296J | LP1Y-S(130)-365105-01-3 | LP1Y-S(130)-365105-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 1" SS S(130) (315) (103) 365105 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365105 |  | TFS00I004YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258247 | 26003H | 5294J | LP1Y-S(130)-365105-01-1 | LP1Y-S(130)-365105-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 1" SS S(130) (315) (103) 365105 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365105 |  | TFS00I004YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258248 | 26003H | 5295J | LP1Y-S(130)-365105-01-2 | LP1Y-S(130)-365105-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 1" SS S(130) (315) (103) 365105 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365105 |  | TFS00I004YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258250 | 26003H | 5297J | LP1Y-SOLV-303103-01-1 | LP1Y-SOLV-303103-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303103 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303103 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258251 | 26003H | 5298J | LP1Y-SOLV-303103-01-2 | LP1Y-SOLV-303103-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303103 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303103 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258252 | 26003H | 5299J | LP1Y-SOLV-303103-02-1 | LP1Y-SOLV-303103-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303103 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303103 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258253 | 26003H | 5300J | LP1Y-SOLV-303103-02-2 | LP1Y-SOLV-303103-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303103 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303103 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258254 | 26003H | 5301J | LP1Y-SOLV-303103-02-3 | LP1Y-SOLV-303103-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303103 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303103 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258255 | 26003H | 5302J | LP1Y-SOLV-303104-04-1 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258256 | 26003H | 5303J | LP1Y-SOLV-303104-04-2 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258257 | 26003H | 5304J | LP1Y-SOLV-303104-04-3 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258258 | 26003H | 5305J | LP1Y-SOLV-303104-04-4 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258259 | 26003H | 5306J | LP1Y-SOLV-303104-04-5 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258260 | 26003H | 5307J | LP1Y-SOLV-303104-04-6 | LP1Y-SOLV-303104-04 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258262 | 26003H | 5309J | LP1Y-SOLV-303104-05-2 | LP1Y-SOLV-303104-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258263 | 26003H | 5310J | LP1Y-SOLV-303104-05-3 | LP1Y-SOLV-303104-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258261 | 26003H | 5308J | LP1Y-SOLV-303104-05-1 | LP1Y-SOLV-303104-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 4" SS SOLV (315) P 303104 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303104 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258264 | 26003H | 5311J | LP1Y-SOLV-303106-01-1 | LP1Y-SOLV-303106-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258265 | 26003H | 5312J | LP1Y-SOLV-303106-01-2 | LP1Y-SOLV-303106-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258266 | 26003H | 5313J | LP1Y-SOLV-303106-02-1 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258267 | 26003H | 5314J | LP1Y-SOLV-303106-02-2 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258268 | 26003H | 5315J | LP1Y-SOLV-303106-02-3 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258269 | 26003H | 5316J | LP1Y-SOLV-303106-02-4 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258270 | 26003H | 5317J | LP1Y-SOLV-303106-02-5 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258271 | 26003H | 5318J | LP1Y-SOLV-303106-02-6 | LP1Y-SOLV-303106-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303106 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303106 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258272 | 26003H | 5319J | LP1Y-SOLV-303115-01-1 | LP1Y-SOLV-303115-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303115 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303115 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258273 | 26003H | 5320J | LP1Y-SOLV-303115-01-2 | LP1Y-SOLV-303115-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303115 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303115 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258274 | 26003H | 5321J | LP1Y-SOLV-303115-01-3 | LP1Y-SOLV-303115-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303115 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303115 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258275 | 26003H | 5322J | LP1Y-SOLV-303115-02-1 | LP1Y-SOLV-303115-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303115 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303115 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258276 | 26003H | 5323J | LP1Y-SOLV-303116-01-1 | LP1Y-SOLV-303116-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303116 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303116 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258277 | 26003H | 5324J | LP1Y-SOLV-303116-01-2 | LP1Y-SOLV-303116-01 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303116 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303116 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258278 | 26003H | 5325J | LP1Y-SOLV-303116-03-1 | LP1Y-SOLV-303116-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 303116 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303116 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258281 | 26003H | 5328J | LP1Y-SOLV-321102-03-3 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258282 | 26003H | 5329J | LP1Y-SOLV-321102-03-4 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258279 | 26003H | 5326J | LP1Y-SOLV-321102-03-1 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258280 | 26003H | 5327J | LP1Y-SOLV-321102-03-2 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258283 | 26003H | 5330J | LP1Y-SOLV-321102-03-5 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258284 | 26003H | 5331J | LP1Y-SOLV-321102-03-6 | LP1Y-SOLV-321102-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SOLV (315) P 321102 | SOLV |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321102 |  | TFS00I004YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258285 | 26003H | 5332J | LP1Y-STORMP-365104-03-1 | LP1Y-STORMP-365104-03 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258286 | 26003H | 5333J | LP1Y-STORMP-365104-03-2 | LP1Y-STORMP-365104-03 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258287 | 26003H | 5334J | LP1Y-STORMP-365104-03-3 | LP1Y-STORMP-365104-03 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258288 | 26003H | 5335J | LP1Y-STORMP-365104-03-4 | LP1Y-STORMP-365104-03 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258289 | 26003H | 5336J | LP1Y-STORMP-365104-04-1 | LP1Y-STORMP-365104-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258290 | 26003H | 5337J | LP1Y-STORMP-365104-04-2 | LP1Y-STORMP-365104-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258291 | 26003H | 5338J | LP1Y-STORMP-365104-04-3 | LP1Y-STORMP-365104-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS STORMP (315) (108) 365104 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365104 |  | TFS00I004YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258292 | 26003H | 5339J | LP1Y-SW-365102-01-1 | LP1Y-SW-365102-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SW (315) 365102 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365102 |  | TFS00I004YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258293 | 26003H | 5340J | LP1Y-SW-365102-01-2 | LP1Y-SW-365102-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SW (315) 365102 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365102 |  | TFS00I004YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258294 | 26003H | 5341J | LP1Y-SWP-303081-02-1 | LP1Y-SWP-303081-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 303081 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303081 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258295 | 26003H | 5342J | LP1Y-SWP-303081-02-2 | LP1Y-SWP-303081-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 303081 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303081 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258296 | 26003H | 5343J | LP1Y-SWP-303081-04-1 | LP1Y-SWP-303081-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 303081 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303081 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258297 | 26003H | 5344J | LP1Y-SWP-303081-04-2 | LP1Y-SWP-303081-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 303081 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303081 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258298 | 26003H | 5345J | LP1Y-SWP-303081-04-3 | LP1Y-SWP-303081-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 303081 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303081 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258299 | 26003H | 5346J | LP1Y-SWP-365103-03-1 | LP1Y-SWP-365103-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258300 | 26003H | 5347J | LP1Y-SWP-365103-03-2 | LP1Y-SWP-365103-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258301 | 26003H | 5348J | LP1Y-SWP-365103-03-3 | LP1Y-SWP-365103-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258302 | 26003H | 5349J | LP1Y-SWP-365103-03-4 | LP1Y-SWP-365103-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258303 | 26003H | 5350J | LP1Y-SWP-365103-04-1 | LP1Y-SWP-365103-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258304 | 26003H | 5351J | LP1Y-SWP-365103-04-2 | LP1Y-SWP-365103-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258305 | 26003H | 5352J | LP1Y-SWP-365103-04-3 | LP1Y-SWP-365103-04 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258306 | 26003H | 5353J | LP1Y-SWP-365103-05-1 | LP1Y-SWP-365103-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258307 | 26003H | 5354J | LP1Y-SWP-365103-05-2 | LP1Y-SWP-365103-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258308 | 26003H | 5355J | LP1Y-SWP-365103-05-3 | LP1Y-SWP-365103-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS SWP (315) (108) 365103 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365103 |  | TFS00I004YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258309 | 26003H | 5356J | LP1Y-WFO-033008-05-1 | LP1Y-WFO-033008-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 033008 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033008 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258310 | 26003H | 5357J | LP1Y-WFO-033008-05-2 | LP1Y-WFO-033008-05 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 033008 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033008 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258311 | 26003H | 5358J | LP1Y-WFO-033008-06-1 | LP1Y-WFO-033008-06 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 033008 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033008 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258312 | 26003H | 5359J | LP1Y-WFO-033008-06-2 | LP1Y-WFO-033008-06 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 033008 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033008 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258313 | 26003H | 5360J | LP1Y-WFO-033033-03-1 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258314 | 26003H | 5361J | LP1Y-WFO-033033-03-2 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258315 | 26003H | 5362J | LP1Y-WFO-033033-03-3 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258316 | 26003H | 5363J | LP1Y-WFO-033033-03-4 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258317 | 26003H | 5364J | LP1Y-WFO-033033-03-5 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258318 | 26003H | 5365J | LP1Y-WFO-033033-03-6 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258319 | 26003H | 5366J | LP1Y-WFO-033033-03-7 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258320 | 26003H | 5367J | LP1Y-WFO-033033-03-8 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258321 | 26003H | 5368J | LP1Y-WFO-033033-03-9 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258322 | 26003H | 5369J | LP1Y-WFO-033033-03-10 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258323 | 26003H | 5370J | LP1Y-WFO-033033-03-11 | LP1Y-WFO-033033-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) (108) 033033 | WFO |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033033 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258324 | 26003H | 5371J | LP1Y-WFO-303110-02-1 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258325 | 26003H | 5372J | LP1Y-WFO-303110-02-2 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258326 | 26003H | 5373J | LP1Y-WFO-303110-02-3 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258327 | 26003H | 5374J | LP1Y-WFO-303110-02-4 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258328 | 26003H | 5375J | LP1Y-WFO-303110-02-5 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258329 | 26003H | 5376J | LP1Y-WFO-303110-02-6 | LP1Y-WFO-303110-02 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 303110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-303110 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258333 | 26003H | 5380J | LP1Y-WFO-370001-03-4 | LP1Y-WFO-370001-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 370001 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370001 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258334 | 26003H | 5381J | LP1Y-WFO-370001-03-5 | LP1Y-WFO-370001-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 370001 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370001 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258330 | 26003H | 5377J | LP1Y-WFO-370001-03-1 | LP1Y-WFO-370001-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 370001 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370001 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258331 | 26003H | 5378J | LP1Y-WFO-370001-03-2 | LP1Y-WFO-370001-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 370001 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370001 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258332 | 26003H | 5379J | LP1Y-WFO-370001-03-3 | LP1Y-WFO-370001-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WFO (36) 370001 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370001 |  | TFS00I004YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258335 | 26003H | 5382J | LP1Y-WPC-033009-03-1 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258336 | 26003H | 5383J | LP1Y-WPC-033009-03-2 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258337 | 26003H | 5384J | LP1Y-WPC-033009-03-3 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258338 | 26003H | 5385J | LP1Y-WPC-033009-03-4 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258339 | 26003H | 5386J | LP1Y-WPC-033009-03-5 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258340 | 26003H | 5387J | LP1Y-WPC-033009-03-6 | LP1Y-WPC-033009-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033009 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033009 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258341 | 26003H | 5388J | LP1Y-WPC-033065-03-1 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258342 | 26003H | 5389J | LP1Y-WPC-033065-03-2 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258343 | 26003H | 5390J | LP1Y-WPC-033065-03-3 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258344 | 26003H | 5391J | LP1Y-WPC-033065-03-4 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258345 | 26003H | 5392J | LP1Y-WPC-033065-03-5 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258346 | 26003H | 5393J | LP1Y-WPC-033065-03-6 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258347 | 26003H | 5394J | LP1Y-WPC-033065-03-7 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258348 | 26003H | 5395J | LP1Y-WPC-033065-03-8 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258349 | 26003H | 5396J | LP1Y-WPC-033065-03-9 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258350 | 26003H | 5397J | LP1Y-WPC-033065-03-10 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258351 | 26003H | 5398J | LP1Y-WPC-033065-03-11 | LP1Y-WPC-033065-03 | 0 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 033065 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033065 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258357 | 26003H | 5404J | LP1Y-WPC-375002-01-6 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258358 | 26003H | 5405J | LP1Y-WPC-375002-01-7 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258352 | 26003H | 5399J | LP1Y-WPC-375002-01-1 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258353 | 26003H | 5400J | LP1Y-WPC-375002-01-2 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258354 | 26003H | 5401J | LP1Y-WPC-375002-01-3 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258355 | 26003H | 5402J | LP1Y-WPC-375002-01-4 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258356 | 26003H | 5403J | LP1Y-WPC-375002-01-5 | LP1Y-WPC-375002-01 | 1 | N | PRI-3-1 | [5 empty] | In Engineering | P031 |  |  | LP1Y 2" SS WPC (36) (108) 375002 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375002 |  | TFS00I004YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247346 | 26003H | 1808J | LP1Y-PWP-101702-04-1 | LP1Y-PWP-101702-04 | 2 | R | TR-07 04.29.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 0 | 0 | 0 | 34 | 6.7 | sq ft | 0 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247348 | 26003H | 1810J | LP1Y-PWP-101702-04-3 | LP1Y-PWP-101702-04 | 2 | R | TR-07 04.29.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 42 | 42 | 0 | 156.4875 | 33.87 | sq ft | 5.38 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 | 2026-04-02 |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247349 | 26003H | 1811J | LP1Y-PWP-101702-04-4 | LP1Y-PWP-101702-04 | 2 | R | TR-07 04.29.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 93.8172 | 18.4 | sq ft | 2.78 | ft | 2026-02-13 | CD: 2026-03-31; CL: Jacob Perez; DD: 2026-03-31; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-04-02 | 2026-04-02 |  |  | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S247347 | 26003H | 1809J | LP1Y-PWP-101702-04-2 | LP1Y-PWP-101702-04 | 2 | R | TR-07 04.29.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 52.5563 | 10.86 | sq ft | 0.81 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A | Carlos Guillen | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 0% | 2026-04-01 | 2026-04-01 | 2026-04-01 | 0% | 2026-04-02 | 144075
C34-S247350 | 26003H | 1812J | LP1Y-PWP-101702-04-5 | LP1Y-PWP-101702-04 | 2 | R | TR-07 04.29.2026 | 2026-04-02 |  | active | client | notification | On Hold | P014 | 2026-06-15 |  | LP1Y 6" SS PWP (315) (108) 101702 | PWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-101702 |  | TFS00D005YSPP |  | 315-PWP | NONE | 6" | 316 SS | 12 | 12 | 0 | 79.1891 | 15.57 | sq ft | 1.2 | ft | 2026-02-13 | CD: 2026-03-25; CL: Jacob Perez; DD: 2026-03-25; DL: George Allahverdian |  |  | Not Passed | No |  | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-03-31 | N/A | N/A |  |  | 2026-04-01 | 2026-04-01 | 2026-04-01 |  |  |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 0% |  |  |  | 0%
C34-S258649 | 26003H | 5406J | LP1Y-AI(100)-034008-02-1 | LP1Y-AI(100)-034008-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS AI(100) (315) 034008 | AI(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034008 |  | TFS00I005YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258650 | 26003H | 5407J | LP1Y-AI(100)-034008-02-2 | LP1Y-AI(100)-034008-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS AI(100) (315) 034008 | AI(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034008 |  | TFS00I005YSPP |  | 315-AI(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258651 | 26003H | 5408J | LP1Y-APL(100)-034006-02-1 | LP1Y-APL(100)-034006-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 0.75" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258652 | 26003H | 5409J | LP1Y-APL(100)-034006-02-2 | LP1Y-APL(100)-034006-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 0.75" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258653 | 26003H | 5410J | LP1Y-APL(100)-034006-02-3 | LP1Y-APL(100)-034006-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 0.75" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258654 | 26003H | 5411J | LP1Y-APL(100)-034006-03-1 | LP1Y-APL(100)-034006-03 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258655 | 26003H | 5412J | LP1Y-APL(100)-034006-03-2 | LP1Y-APL(100)-034006-03 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258656 | 26003H | 5413J | LP1Y-APL(100)-034006-05-1 | LP1Y-APL(100)-034006-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258657 | 26003H | 5414J | LP1Y-APL(100)-034006-05-2 | LP1Y-APL(100)-034006-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS APL(100) (315) 034006 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034006 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258658 | 26003H | 5415J | LP1Y-APL(100)-357005-01-1 | LP1Y-APL(100)-357005-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS APL(100) (315) 357005 | APL(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-357005 |  | TFS00I005YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258659 | 26003H | 5416J | LP1Y-N2(100)-034005-01-1 | LP1Y-N2(100)-034005-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 034005 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034005 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258660 | 26003H | 5417J | LP1Y-N2(100)-034005-01-2 | LP1Y-N2(100)-034005-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 034005 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034005 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258662 | 26003H | 5419J | LP1Y-N2(100)-350016-01-2 | LP1Y-N2(100)-350016-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350016 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350016 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258661 | 26003H | 5418J | LP1Y-N2(100)-350016-01-1 | LP1Y-N2(100)-350016-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350016 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350016 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258663 | 26003H | 5420J | LP1Y-N2(100)-350016-02-1 | LP1Y-N2(100)-350016-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350016 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350016 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258664 | 26003H | 5421J | LP1Y-N2(100)-350040-01-1 | LP1Y-N2(100)-350040-01 | 2 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350040 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258665 | 26003H | 5422J | LP1Y-N2(100)-350040-01-2 | LP1Y-N2(100)-350040-01 | 2 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350040 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258666 | 26003H | 5423J | LP1Y-N2(100)-350040-01-3 | LP1Y-N2(100)-350040-01 | 2 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350040 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258667 | 26003H | 5424J | LP1Y-N2(100)-350040-01-4 | LP1Y-N2(100)-350040-01 | 2 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350040 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258668 | 26003H | 5425J | LP1Y-N2(100)-350040-01-5 | LP1Y-N2(100)-350040-01 | 2 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E 350040 | N2(100) |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258669 | 26003H | 5426J | LP1Y-N2(100)-350040-02-1 | LP1Y-N2(100)-350040-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350040 | N2(100) |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258670 | 26003H | 5427J | LP1Y-N2(100)-350040-02-2 | LP1Y-N2(100)-350040-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350040 | N2(100) |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258671 | 26003H | 5428J | LP1Y-N2(100)-350040-02-3 | LP1Y-N2(100)-350040-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350040 | N2(100) |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350040 |  | TFS00I005YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258672 | 26003H | 5429J | LP1Y-N2-350017-01-1 | LP1Y-N2-350017-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2 (315) E 350017 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350017 |  | TFS00I005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258673 | 26003H | 5430J | LP1Y-N2-350017-01-2 | LP1Y-N2-350017-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2 (315) E 350017 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350017 |  | TFS00I005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258674 | 26003H | 5431J | LP1Y-N2-350017-01-3 | LP1Y-N2-350017-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS N2 (315) E 350017 | N2 |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350017 |  | TFS00I005YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258676 | 26003H | 5433J | LP1Y-PV-302061-01-2 | LP1Y-PV-302061-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS PV (315) (108) 302061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302061 |  | TFS00I005YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258675 | 26003H | 5432J | LP1Y-PV-302061-01-1 | LP1Y-PV-302061-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS PV (315) (108) 302061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302061 |  | TFS00I005YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258677 | 26003H | 5434J | LP1Y-PV-302061-02-1 | LP1Y-PV-302061-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS PV (315) (108) 302061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302061 |  | TFS00I005YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258678 | 26003H | 5435J | LP1Y-PV-302061-02-2 | LP1Y-PV-302061-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS PV (315) (108) 302061 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302061 |  | TFS00I005YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258679 | 26003H | 5436J | LP1Y-PV-302112-01-1 | LP1Y-PV-302112-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS PV (315) (108) 302112 | PV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302112 |  | TFS00I005YSPP |  | 315-PV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258680 | 26003H | 5437J | LP1Y-RV-302102-01-1 | LP1Y-RV-302102-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS RV (315) (108) 302102 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302102 |  | TFS00I005YSPP |  | 315-RV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258681 | 26003H | 5438J | LP1Y-RV-302102-01-2 | LP1Y-RV-302102-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS RV (315) (108) 302102 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302102 |  | TFS00I005YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258682 | 26003H | 5439J | LP1Y-RV-302102-01-3 | LP1Y-RV-302102-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS RV (315) (108) 302102 | RV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302102 |  | TFS00I005YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258683 | 26003H | 5440J | LP1Y-RV-302108-01-1 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258684 | 26003H | 5441J | LP1Y-RV-302108-01-2 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258685 | 26003H | 5442J | LP1Y-RV-302108-01-3 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258686 | 26003H | 5443J | LP1Y-RV-302108-01-4 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258687 | 26003H | 5444J | LP1Y-RV-302108-01-5 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258688 | 26003H | 5445J | LP1Y-RV-302108-01-6 | LP1Y-RV-302108-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS RV (315) (108) 302108 | RV |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302108 |  | TFS00I005YSPP |  | 315-RV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258689 | 26003H | 5446C | LP1Y-S(130)-034053-01-1 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258691 | 26003H | 5448C | LP1Y-S(130)-034053-01-3 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258692 | 26003H | 5449C | LP1Y-S(130)-034053-01-4 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258693 | 26003H | 5450C | LP1Y-S(130)-034053-01-5 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258694 | 26003H | 5451C | LP1Y-S(130)-034053-01-6 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258690 | 26003H | 5447C | LP1Y-S(130)-034053-01-2 | LP1Y-S(130)-034053-01 | 3 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258695 | 26003H | 5452C | LP1Y-S(130)-034053-03-1 | LP1Y-S(130)-034053-03 | 1 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258696 | 26003H | 5453C | LP1Y-S(130)-034053-03-2 | LP1Y-S(130)-034053-03 | 1 | N | PRI-3-2 | 2026-04-30 |  | releasing |  |  | Releasing from Hold | P032 |  |  | LP1Y 2" CS S(130) (2) (103) 034053 | S(130) |  | 103 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034053 |  | TFS00I005YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258697 | 26003H | 5454J | LP1Y-S(130)-365205-01-1 | LP1Y-S(130)-365205-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 1" SS S(130) (315) (103) 365205 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365205 |  | TFS00I005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258698 | 26003H | 5455J | LP1Y-S(130)-365205-01-2 | LP1Y-S(130)-365205-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 1" SS S(130) (315) (103) 365205 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365205 |  | TFS00I005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258699 | 26003H | 5456J | LP1Y-S(130)-365205-01-3 | LP1Y-S(130)-365205-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 1" SS S(130) (315) (103) 365205 | S(130) |  | 103,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365205 |  | TFS00I005YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258700 | 26003H | 5457J | LP1Y-STORMP-037007-01-1 | LP1Y-STORMP-037007-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258701 | 26003H | 5458J | LP1Y-STORMP-037007-01-2 | LP1Y-STORMP-037007-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 037007 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037007 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258702 | 26003H | 5459J | LP1Y-STORMP-365214-03-1 | LP1Y-STORMP-365214-03 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 365214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365214 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258703 | 26003H | 5460J | LP1Y-STORMP-365214-03-2 | LP1Y-STORMP-365214-03 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 365214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365214 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258704 | 26003H | 5461J | LP1Y-STORMP-365214-07-1 | LP1Y-STORMP-365214-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 365214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365214 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258706 | 26003H | 5463J | LP1Y-STORMP-365214-08-2 | LP1Y-STORMP-365214-08 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 365214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365214 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258705 | 26003H | 5462J | LP1Y-STORMP-365214-08-1 | LP1Y-STORMP-365214-08 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS STORMP (315) (108) 365214 | STORMP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365214 |  | TFS00I005YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258707 | 26003H | 5464J | LP1Y-SW-365202-01-1 | LP1Y-SW-365202-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SW (315) 365202 | SW |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365202 |  | TFS00I005YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258708 | 26003H | 5465J | LP1Y-SWP-036045-13-1 | LP1Y-SWP-036045-13 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 036045 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036045 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258709 | 26003H | 5466J | LP1Y-SWP-036045-13-2 | LP1Y-SWP-036045-13 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 036045 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036045 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258710 | 26003H | 5467J | LP1Y-SWP-036048-13-1 | LP1Y-SWP-036048-13 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 036048 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036048 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258711 | 26003H | 5468J | LP1Y-SWP-036048-13-2 | LP1Y-SWP-036048-13 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 036048 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036048 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258712 | 26003H | 5469J | LP1Y-SWP-036050-01-1 | LP1Y-SWP-036050-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 036050 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-036050 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258713 | 26003H | 5470J | LP1Y-SWP-365213-02-1 | LP1Y-SWP-365213-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258714 | 26003H | 5471J | LP1Y-SWP-365213-02-2 | LP1Y-SWP-365213-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258715 | 26003H | 5472J | LP1Y-SWP-365213-05-1 | LP1Y-SWP-365213-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258716 | 26003H | 5473J | LP1Y-SWP-365213-06-1 | LP1Y-SWP-365213-06 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258717 | 26003H | 5474J | LP1Y-SWP-365213-06-2 | LP1Y-SWP-365213-06 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258718 | 26003H | 5475J | LP1Y-SWP-365213-07-1 | LP1Y-SWP-365213-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258719 | 26003H | 5476J | LP1Y-SWP-365213-07-2 | LP1Y-SWP-365213-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258720 | 26003H | 5477J | LP1Y-SWP-365213-07-3 | LP1Y-SWP-365213-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS SWP (315) (108) 365213 | SWP |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365213 |  | TFS00I005YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258721 | 26003H | 5478J | LP1Y-WFO-033010-05-1 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258722 | 26003H | 5479J | LP1Y-WFO-033010-05-2 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258723 | 26003H | 5480J | LP1Y-WFO-033010-05-3 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258724 | 26003H | 5481J | LP1Y-WFO-033010-05-4 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258725 | 26003H | 5482J | LP1Y-WFO-033010-05-5 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258726 | 26003H | 5483J | LP1Y-WFO-033010-05-6 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258727 | 26003H | 5484J | LP1Y-WFO-033010-05-7 | LP1Y-WFO-033010-05 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 033010 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033010 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258728 | 26003H | 5485J | LP1Y-WFO-302110-02-1 | LP1Y-WFO-302110-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 302110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302110 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258729 | 26003H | 5486J | LP1Y-WFO-302110-02-2 | LP1Y-WFO-302110-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 302110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302110 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258730 | 26003H | 5487J | LP1Y-WFO-302110-02-3 | LP1Y-WFO-302110-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 302110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302110 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258731 | 26003H | 5488J | LP1Y-WFO-302110-02-4 | LP1Y-WFO-302110-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 302110 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302110 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258732 | 26003H | 5489J | LP1Y-WFO-370013-02-1 | LP1Y-WFO-370013-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 370013 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370013 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258733 | 26003H | 5490J | LP1Y-WFO-370013-02-2 | LP1Y-WFO-370013-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 370013 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370013 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258734 | 26003H | 5491J | LP1Y-WFO-370013-02-3 | LP1Y-WFO-370013-03 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WFO (36) 370013 | WFO |  | NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370013 |  | TFS00I005YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258735 | 26003H | 5492J | LP1Y-WI-037001-01-1 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258736 | 26003H | 5493J | LP1Y-WI-037001-01-2 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258737 | 26003H | 5494J | LP1Y-WI-037001-01-3 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258738 | 26003H | 5495J | LP1Y-WI-037001-01-4 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258739 | 26003H | 5496J | LP1Y-WI-037001-01-5 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258740 | 26003H | 5497J | LP1Y-WI-037001-01-6 | LP1Y-WI-037001-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 037001 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-037001 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258741 | 26003H | 5498J | LP1Y-WI-302105-01-1 | LP1Y-WI-302105-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258742 | 26003H | 5499J | LP1Y-WI-302105-01-2 | LP1Y-WI-302105-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258743 | 26003H | 5500J | LP1Y-WI-302105-01-3 | LP1Y-WI-302105-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258744 | 26003H | 5501J | LP1Y-WI-302105-02-1 | LP1Y-WI-302105-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258745 | 26003H | 5502J | LP1Y-WI-302105-02-2 | LP1Y-WI-302105-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258746 | 26003H | 5503J | LP1Y-WI-302105-02-3 | LP1Y-WI-302105-02 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302105 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302105 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258747 | 26003H | 5504J | LP1Y-WI-302106-01-1 | LP1Y-WI-302106-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258748 | 26003H | 5505J | LP1Y-WI-302106-01-2 | LP1Y-WI-302106-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258749 | 26003H | 5506J | LP1Y-WI-302106-01-3 | LP1Y-WI-302106-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258750 | 26003H | 5507J | LP1Y-WI-302106-02-1 | LP1Y-WI-302106-02 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258751 | 26003H | 5508J | LP1Y-WI-302106-02-2 | LP1Y-WI-302106-02 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258752 | 26003H | 5509J | LP1Y-WI-302106-03-1 | LP1Y-WI-302106-03 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258753 | 26003H | 5510J | LP1Y-WI-302106-03-2 | LP1Y-WI-302106-03 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258754 | 26003H | 5511J | LP1Y-WI-302106-03-3 | LP1Y-WI-302106-03 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258755 | 26003H | 5512J | LP1Y-WI-302106-03-4 | LP1Y-WI-302106-03 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108,NI | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258758 | 26003H | 5515J | LP1Y-WI-302106-07-3 | LP1Y-WI-302106-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258756 | 26003H | 5513J | LP1Y-WI-302106-07-1 | LP1Y-WI-302106-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258757 | 26003H | 5514J | LP1Y-WI-302106-07-2 | LP1Y-WI-302106-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258759 | 26003H | 5516J | LP1Y-WI-302106-07-4 | LP1Y-WI-302106-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258760 | 26003H | 5517J | LP1Y-WI-302106-07-5 | LP1Y-WI-302106-07 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258761 | 26003H | 5518J | LP1Y-WI-302106-09-1 | LP1Y-WI-302106-09 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258762 | 26003H | 5519J | LP1Y-WI-302106-09-2 | LP1Y-WI-302106-09 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WI (315) (108) 302106 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302106 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258763 | 26003H | 5520J | LP1Y-WI-302107-01-1 | LP1Y-WI-302107-01 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS WI (315) (108) 302107 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302107 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258764 | 26003H | 5521J | LP1Y-WI-302107-01-2 | LP1Y-WI-302107-01 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS WI (315) (108) 302107 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302107 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258765 | 26003H | 5522J | LP1Y-WI-302107-01-3 | LP1Y-WI-302107-01 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS WI (315) (108) 302107 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302107 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258766 | 26003H | 5523J | LP1Y-WI-302107-01-4 | LP1Y-WI-302107-01 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS WI (315) (108) 302107 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302107 |  | TFS00I005YSPP |  | 315-WI | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258767 | 26003H | 5524J | LP1Y-WI-302107-01-5 | LP1Y-WI-302107-01 | 3 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 4" SS WI (315) (108) 302107 | WI |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-302107 |  | TFS00I005YSPP |  | 315-WI | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258768 | 26003H | 5525J | LP1Y-WPC-033029-02-1 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258769 | 26003H | 5526J | LP1Y-WPC-033029-02-2 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258770 | 26003H | 5527J | LP1Y-WPC-033029-02-3 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258771 | 26003H | 5528J | LP1Y-WPC-033029-02-4 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258772 | 26003H | 5529J | LP1Y-WPC-033029-02-5 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258773 | 26003H | 5530J | LP1Y-WPC-033029-02-6 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258774 | 26003H | 5531J | LP1Y-WPC-033029-02-7 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258775 | 26003H | 5532J | LP1Y-WPC-033029-02-8 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258776 | 26003H | 5533J | LP1Y-WPC-033029-02-9 | LP1Y-WPC-033029-02 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 033029 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033029 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258777 | 26003H | 5534J | LP1Y-WPC-375004-01-1 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258778 | 26003H | 5535J | LP1Y-WPC-375004-01-2 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258779 | 26003H | 5536J | LP1Y-WPC-375004-01-3 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258780 | 26003H | 5537J | LP1Y-WPC-375004-01-4 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258781 | 26003H | 5538J | LP1Y-WPC-375004-01-5 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258782 | 26003H | 5539J | LP1Y-WPC-375004-01-6 | LP1Y-WPC-375004-01 | 1 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 2" SS WPC (36) (108) 375004 | WPC |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375004 |  | TFS00I005YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258783 | 26003H | 5540J | LP1Y-WV-321011-01-1 | LP1Y-WV-321011-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WV (315) (108) 321011 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321011 |  | TFS00I005YSPP |  | 315-WV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258784 | 26003H | 5541J | LP1Y-WV-321011-01-2 | LP1Y-WV-321011-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WV (315) (108) 321011 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321011 |  | TFS00I005YSPP |  | 315-WV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258785 | 26003H | 5542J | LP1Y-WV-321011-01-3 | LP1Y-WV-321011-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WV (315) (108) 321011 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321011 |  | TFS00I005YSPP |  | 315-WV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258786 | 26003H | 5543J | LP1Y-WV-321011-01-4 | LP1Y-WV-321011-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WV (315) (108) 321011 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321011 |  | TFS00I005YSPP |  | 315-WV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258787 | 26003H | 5544J | LP1Y-WV-321011-01-5 | LP1Y-WV-321011-01 | 0 | N | PRI-3-2 | [5 empty] | In Engineering | P032 |  |  | LP1Y 3" SS WV (315) (108) 321011 | WV |  | 108 | 98.6 F |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-321011 |  | TFS00I005YSPP |  | 315-WV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258788 | 26003H | 5545J | LP1Y-APL(100)-034014-01-1 | LP1Y-APL(100)-034014-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 0.75" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258789 | 26003H | 5546J | LP1Y-APL(100)-034014-02-1 | LP1Y-APL(100)-034014-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258790 | 26003H | 5547J | LP1Y-APL(100)-034014-02-2 | LP1Y-APL(100)-034014-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258791 | 26003H | 5548J | LP1Y-APL(100)-034014-02-3 | LP1Y-APL(100)-034014-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258792 | 26003H | 5549J | LP1Y-APL(100)-034014-04-1 | LP1Y-APL(100)-034014-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 0.75" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258793 | 26003H | 5550J | LP1Y-APL(100)-034014-04-2 | LP1Y-APL(100)-034014-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 0.75" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258794 | 26003H | 5551J | LP1Y-APL(100)-034014-04-3 | LP1Y-APL(100)-034014-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 0.75" SS APL(100) (315) 034014 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034014 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 3/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258795 | 26003H | 5552J | LP1Y-APL(100)-357006-02-1 | LP1Y-APL(100)-357006-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS APL(100) (315) 357006 | APL(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-357006 |  | TFS00I007YSPP |  | 315-APL(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258796 | 26003H | 5553J | LP1Y-AWNP-301091-01-1 | LP1Y-AWNP-301091-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS AWNP (315) (108) 301091 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301091 |  | TFS00I007YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258797 | 26003H | 5554J | LP1Y-AWNP-301091-02-1 | LP1Y-AWNP-301091-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS AWNP (315) (108) 301091 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301091 |  | TFS00I007YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258798 | 26003H | 5555J | LP1Y-AWNP-301091-02-2 | LP1Y-AWNP-301091-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS AWNP (315) (108) 301091 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301091 |  | TFS00I007YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258799 | 26003H | 5556J | LP1Y-AWNP-301091-05-1 | LP1Y-AWNP-301091-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS AWNP (315) (108) 301091 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301091 |  | TFS00I007YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258800 | 26003H | 5557J | LP1Y-AWNP-301091-05-2 | LP1Y-AWNP-301091-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS AWNP (315) (108) 301091 | AWNP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301091 |  | TFS00I007YSPP |  | 315-AWNP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258801 | 26003H | 5558J | LP1Y-N2(100)-034013-01-1 | LP1Y-N2(100)-034013-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 034013 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034013 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258802 | 26003H | 5559J | LP1Y-N2(100)-034013-01-2 | LP1Y-N2(100)-034013-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 034013 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034013 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258803 | 26003H | 5560J | LP1Y-N2(100)-034013-01-3 | LP1Y-N2(100)-034013-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 034013 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034013 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258804 | 26003H | 5561J | LP1Y-N2(100)-350005-01-1 | LP1Y-N2(100)-350005-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350005 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350005 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258805 | 26003H | 5562J | LP1Y-N2(100)-350005-01-2 | LP1Y-N2(100)-350005-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350005 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350005 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258806 | 26003H | 5563J | LP1Y-N2(100)-350005-01-3 | LP1Y-N2(100)-350005-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350005 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350005 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258807 | 26003H | 5564J | LP1Y-N2(100)-350005-01-4 | LP1Y-N2(100)-350005-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E (108) 350005 | N2(100) |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350005 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258808 | 26003H | 5565J | LP1Y-N2(100)-350006-01-1 | LP1Y-N2(100)-350006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350006 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350006 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258809 | 26003H | 5566J | LP1Y-N2(100)-350006-01-2 | LP1Y-N2(100)-350006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350006 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350006 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258810 | 26003H | 5567J | LP1Y-N2(100)-350006-01-3 | LP1Y-N2(100)-350006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350006 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350006 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258811 | 26003H | 5568J | LP1Y-N2(100)-350007-01-1 | LP1Y-N2(100)-350007-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350007 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350007 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258812 | 26003H | 5569J | LP1Y-N2(100)-350007-01-2 | LP1Y-N2(100)-350007-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350007 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350007 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258813 | 26003H | 5570J | LP1Y-N2(100)-350007-01-3 | LP1Y-N2(100)-350007-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350007 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350007 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258814 | 26003H | 5571J | LP1Y-N2(100)-350018-02-1 | LP1Y-N2(100)-350018-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350018 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350018 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258815 | 26003H | 5572J | LP1Y-N2(100)-350018-02-2 | LP1Y-N2(100)-350018-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350018 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350018 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258816 | 26003H | 5573J | LP1Y-N2(100)-350041-01-1 | LP1Y-N2(100)-350041-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258817 | 26003H | 5574J | LP1Y-N2(100)-350041-01-2 | LP1Y-N2(100)-350041-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258818 | 26003H | 5575J | LP1Y-N2(100)-350041-01-3 | LP1Y-N2(100)-350041-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258819 | 26003H | 5576J | LP1Y-N2(100)-350041-01-4 | LP1Y-N2(100)-350041-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258820 | 26003H | 5577J | LP1Y-N2(100)-350041-01-5 | LP1Y-N2(100)-350041-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258821 | 26003H | 5578J | LP1Y-N2(100)-350041-03-1 | LP1Y-N2(100)-350041-03 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258822 | 26003H | 5579J | LP1Y-N2(100)-350041-03-2 | LP1Y-N2(100)-350041-03 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258823 | 26003H | 5580J | LP1Y-N2(100)-350041-03-3 | LP1Y-N2(100)-350041-03 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2(100) (315) E 350041 | N2(100) |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350041 |  | TFS00I007YSPP |  | 315-N2(100) | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258824 | 26003H | 5581J | LP1Y-N2-350019-01-1 | LP1Y-N2-350019-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2 (315) E 350019 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350019 |  | TFS00I007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258825 | 26003H | 5582J | LP1Y-N2-350019-01-2 | LP1Y-N2-350019-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2 (315) E 350019 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350019 |  | TFS00I007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258826 | 26003H | 5583J | LP1Y-N2-350019-01-3 | LP1Y-N2-350019-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS N2 (315) E 350019 | N2 |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-350019 |  | TFS00I007YSPP |  | 315-N2 | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258827 | 26003H | 5584J | LP1Y-PV-301061-01-1 | LP1Y-PV-301061-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301061 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258828 | 26003H | 5585J | LP1Y-PV-301061-01-2 | LP1Y-PV-301061-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301061 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258829 | 26003H | 5586J | LP1Y-PV-301061-02-1 | LP1Y-PV-301061-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301061 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301061 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258830 | 26003H | 5587J | LP1Y-PV-301062-01-1 | LP1Y-PV-301062-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301062 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258831 | 26003H | 5588J | LP1Y-PV-301062-01-2 | LP1Y-PV-301062-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301062 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258832 | 26003H | 5589J | LP1Y-PV-301062-01-3 | LP1Y-PV-301062-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301062 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301062 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258833 | 26003H | 5590J | LP1Y-PV-301063-01-1 | LP1Y-PV-301063-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301063 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301063 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258834 | 26003H | 5591J | LP1Y-PV-301063-01-2 | LP1Y-PV-301063-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301063 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301063 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258835 | 26003H | 5592J | LP1Y-PV-301063-02-1 | LP1Y-PV-301063-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301063 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301063 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258836 | 26003H | 5593J | LP1Y-PV-301063-02-2 | LP1Y-PV-301063-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301063 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301063 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258837 | 26003H | 5594J | LP1Y-PV-301064-01-1 | LP1Y-PV-301064-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301064 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258838 | 26003H | 5595J | LP1Y-PV-301064-01-2 | LP1Y-PV-301064-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301064 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258839 | 26003H | 5596J | LP1Y-PV-301064-01-3 | LP1Y-PV-301064-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) 301064 | PV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258840 | 26003H | 5597J | LP1Y-PV-301064-02-1 | LP1Y-PV-301064-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301064 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258841 | 26003H | 5598J | LP1Y-PV-301064-02-2 | LP1Y-PV-301064-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301064 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258842 | 26003H | 5599J | LP1Y-PV-301064-02-3 | LP1Y-PV-301064-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PV (315) (108) 301064 | PV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301064 |  | TFS00I007YSPP |  | 315-PV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258843 | 26003H | 5600J | LP1Y-PVP-301109-01-1 | LP1Y-PVP-301109-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258844 | 26003H | 5601J | LP1Y-PVP-301109-01-2 | LP1Y-PVP-301109-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258845 | 26003H | 5602J | LP1Y-PVP-301109-01-3 | LP1Y-PVP-301109-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258846 | 26003H | 5603J | LP1Y-PVP-301109-01-4 | LP1Y-PVP-301109-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301109 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301109 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258847 | 26003H | 5604J | LP1Y-PVP-301111-01-1 | LP1Y-PVP-301111-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301111 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301111 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258848 | 26003H | 5605J | LP1Y-PVP-301111-01-2 | LP1Y-PVP-301111-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P (108) 301111 | PVP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301111 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258849 | 26003H | 5606J | LP1Y-PVP-301209-01-1 | LP1Y-PVP-301209-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258850 | 26003H | 5607J | LP1Y-PVP-301209-01-2 | LP1Y-PVP-301209-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258851 | 26003H | 5608J | LP1Y-PVP-301209-01-3 | LP1Y-PVP-301209-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258852 | 26003H | 5609J | LP1Y-PVP-301209-06-1 | LP1Y-PVP-301209-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258853 | 26003H | 5610J | LP1Y-PVP-301209-06-2 | LP1Y-PVP-301209-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301209 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301209 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258854 | 26003H | 5611J | LP1Y-PVP-301211-01-1 | LP1Y-PVP-301211-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301211 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301211 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258855 | 26003H | 5612J | LP1Y-PVP-301211-01-2 | LP1Y-PVP-301211-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301211 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301211 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258856 | 26003H | 5613J | LP1Y-PVP-301309-01-1 | LP1Y-PVP-301309-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258857 | 26003H | 5614J | LP1Y-PVP-301309-01-2 | LP1Y-PVP-301309-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258858 | 26003H | 5615J | LP1Y-PVP-301309-06-1 | LP1Y-PVP-301309-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258859 | 26003H | 5616J | LP1Y-PVP-301309-06-2 | LP1Y-PVP-301309-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301309 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301309 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258860 | 26003H | 5617J | LP1Y-PVP-301311-01-1 | LP1Y-PVP-301311-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301311 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301311 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258861 | 26003H | 5618J | LP1Y-PVP-301311-01-2 | LP1Y-PVP-301311-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301311 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301311 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258862 | 26003H | 5619J | LP1Y-PVP-301409-01-1 | LP1Y-PVP-301409-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258863 | 26003H | 5620J | LP1Y-PVP-301409-01-2 | LP1Y-PVP-301409-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258864 | 26003H | 5621J | LP1Y-PVP-301409-06-1 | LP1Y-PVP-301409-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258865 | 26003H | 5622J | LP1Y-PVP-301409-06-2 | LP1Y-PVP-301409-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301409 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301409 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258866 | 26003H | 5623J | LP1Y-PVP-301411-01-1 | LP1Y-PVP-301411-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301411 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301411 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258867 | 26003H | 5624J | LP1Y-PVP-301411-01-2 | LP1Y-PVP-301411-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PVP (315) P 301411 | PVP |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301411 |  | TFS00I007YSPP |  | 315-PVP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258868 | 26003H | 5625J | LP1Y-PWP-301071-01-1 | LP1Y-PWP-301071-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258869 | 26003H | 5626J | LP1Y-PWP-301071-01-2 | LP1Y-PWP-301071-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258870 | 26003H | 5627J | LP1Y-PWP-301071-02-1 | LP1Y-PWP-301071-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258871 | 26003H | 5628J | LP1Y-PWP-301071-04-1 | LP1Y-PWP-301071-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258872 | 26003H | 5629J | LP1Y-PWP-301071-04-2 | LP1Y-PWP-301071-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258873 | 26003H | 5630J | LP1Y-PWP-301071-04-3 | LP1Y-PWP-301071-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258874 | 26003H | 5631J | LP1Y-PWP-301071-06-1 | LP1Y-PWP-301071-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258875 | 26003H | 5632J | LP1Y-PWP-301071-06-2 | LP1Y-PWP-301071-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258876 | 26003H | 5633J | LP1Y-PWP-301071-06-3 | LP1Y-PWP-301071-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS PWP (315) (108) 301071 | PWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301071 |  | TFS00I007YSPP |  | 315-PWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258877 | 26003H | 5634J | LP1Y-RV-301105-01-1 | LP1Y-RV-301105-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P (108) 301105 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301105 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258878 | 26003H | 5635J | LP1Y-RV-301107-01-1 | LP1Y-RV-301107-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) (108) 301107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301107 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258879 | 26003H | 5636J | LP1Y-RV-301107-01-2 | LP1Y-RV-301107-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) (108) 301107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301107 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258880 | 26003H | 5637J | LP1Y-RV-301107-01-3 | LP1Y-RV-301107-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) (108) 301107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301107 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258881 | 26003H | 5638J | LP1Y-RV-301107-01-4 | LP1Y-RV-301107-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) (108) 301107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301107 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258882 | 26003H | 5639J | LP1Y-RV-301107-01-5 | LP1Y-RV-301107-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) (108) 301107 | RV |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301107 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258883 | 26003H | 5640J | LP1Y-RV-301116-01-1 | LP1Y-RV-301116-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P (108) 301116 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301116 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258884 | 26003H | 5641J | LP1Y-RV-301116-01-2 | LP1Y-RV-301116-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P (108) 301116 | RV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301116 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258885 | 26003H | 5642J | LP1Y-RV-301207-01-1 | LP1Y-RV-301207-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301207 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258886 | 26003H | 5643J | LP1Y-RV-301207-01-2 | LP1Y-RV-301207-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301207 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258887 | 26003H | 5644J | LP1Y-RV-301207-01-3 | LP1Y-RV-301207-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301207 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258888 | 26003H | 5645J | LP1Y-RV-301207-01-4 | LP1Y-RV-301207-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301207 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258889 | 26003H | 5646J | LP1Y-RV-301207-01-5 | LP1Y-RV-301207-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301207 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301207 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258890 | 26003H | 5647J | LP1Y-RV-301216-01-1 | LP1Y-RV-301216-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301216 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301216 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258891 | 26003H | 5648J | LP1Y-RV-301216-01-2 | LP1Y-RV-301216-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301216 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301216 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258892 | 26003H | 5649J | LP1Y-RV-301300-01-1 | LP1Y-RV-301300-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301300 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301300 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258893 | 26003H | 5650J | LP1Y-RV-301300-01-2 | LP1Y-RV-301300-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301300 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301300 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258894 | 26003H | 5651J | LP1Y-RV-301307-01-1 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258895 | 26003H | 5652J | LP1Y-RV-301307-01-2 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258896 | 26003H | 5653J | LP1Y-RV-301307-01-3 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258897 | 26003H | 5654J | LP1Y-RV-301307-01-4 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258898 | 26003H | 5655J | LP1Y-RV-301307-01-5 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258899 | 26003H | 5656J | LP1Y-RV-301307-01-6 | LP1Y-RV-301307-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301307 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301307 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258900 | 26003H | 5657J | LP1Y-RV-301402-01-1 | LP1Y-RV-301402-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301402 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301402 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258901 | 26003H | 5658J | LP1Y-RV-301402-01-2 | LP1Y-RV-301402-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS RV (315) P 301402 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301402 |  | TFS00I007YSPP |  | 315-RV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258902 | 26003H | 5659J | LP1Y-RV-301407-01-1 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258903 | 26003H | 5660J | LP1Y-RV-301407-01-2 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258904 | 26003H | 5661J | LP1Y-RV-301407-01-3 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258905 | 26003H | 5662J | LP1Y-RV-301407-01-4 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258906 | 26003H | 5663J | LP1Y-RV-301407-01-5 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258907 | 26003H | 5664J | LP1Y-RV-301407-01-6 | LP1Y-RV-301407-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS RV (315) 301407 | RV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301407 |  | TFS00I007YSPP |  | 315-RV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258908 | 26003H | 5665C | LP1Y-S(130)-034035-12-1 | LP1Y-S(130)-034035-12 | 2 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034035 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034035 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258909 | 26003H | 5666C | LP1Y-S(130)-034035-12-2 | LP1Y-S(130)-034035-12 | 2 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034035 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034035 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258910 | 26003H | 5667C | LP1Y-S(130)-034054-01-1 | LP1Y-S(130)-034054-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034054 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034054 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258911 | 26003H | 5668C | LP1Y-S(130)-034054-01-2 | LP1Y-S(130)-034054-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034054 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034054 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258912 | 26003H | 5669C | LP1Y-S(130)-034054-01-3 | LP1Y-S(130)-034054-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034054 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034054 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258913 | 26003H | 5670C | LP1Y-S(130)-034054-03-1 | LP1Y-S(130)-034054-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034054 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034054 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258914 | 26003H | 5671C | LP1Y-S(130)-034054-03-2 | LP1Y-S(130)-034054-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" CS S(130) (2) (103) 034054 | S(130) |  | 103 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-034054 |  | TFS00I007YSPP |  | 2-S(130) | P-5 | 2" | CS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258915 | 26003H | 5672J | LP1Y-S(130)-365305-01-1 | LP1Y-S(130)-365305-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 1" SS S(130) (315) (103) 365305 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365305 |  | TFS00I007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258916 | 26003H | 5673J | LP1Y-S(130)-365305-01-2 | LP1Y-S(130)-365305-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 1" SS S(130) (315) (103) 365305 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365305 |  | TFS00I007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258917 | 26003H | 5674J | LP1Y-S(130)-365305-01-3 | LP1Y-S(130)-365305-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 1" SS S(130) (315) (103) 365305 | S(130) |  | 103,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365305 |  | TFS00I007YSPP |  | 315-S(130) | NONE | 1" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258918 | 26003H | 5675J | LP1Y-SOLV-030003-04-1 | LP1Y-SOLV-030003-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 030003 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-030003 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258919 | 26003H | 5676J | LP1Y-SOLV-030003-04-2 | LP1Y-SOLV-030003-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 030003 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-030003 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258920 | 26003H | 5677J | LP1Y-SOLV-030003-04-3 | LP1Y-SOLV-030003-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 030003 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-030003 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258921 | 26003H | 5678J | LP1Y-SOLV-030003-04-4 | LP1Y-SOLV-030003-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 030003 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-030003 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258922 | 26003H | 5679J | LP1Y-SOLV-030003-04-5 | LP1Y-SOLV-030003-04 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 030003 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-030003 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258923 | 26003H | 5680J | LP1Y-SOLV-301103-01-1 | LP1Y-SOLV-301103-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS SOLV (315) P (108) 301103 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301103 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258924 | 26003H | 5681J | LP1Y-SOLV-301103-01-2 | LP1Y-SOLV-301103-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS SOLV (315) P (108) 301103 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301103 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258925 | 26003H | 5682J | LP1Y-SOLV-301103-02-1 | LP1Y-SOLV-301103-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS SOLV (315) P (108) 301103 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301103 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258926 | 26003H | 5683J | LP1Y-SOLV-301103-02-2 | LP1Y-SOLV-301103-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 6" SS SOLV (315) P (108) 301103 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301103 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 6" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258927 | 26003H | 5684J | LP1Y-SOLV-301104-04-1 | LP1Y-SOLV-301104-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258928 | 26003H | 5685J | LP1Y-SOLV-301104-04-2 | LP1Y-SOLV-301104-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258929 | 26003H | 5686J | LP1Y-SOLV-301104-04-3 | LP1Y-SOLV-301104-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258930 | 26003H | 5687J | LP1Y-SOLV-301104-04-4 | LP1Y-SOLV-301104-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258931 | 26003H | 5688J | LP1Y-SOLV-301104-04-5 | LP1Y-SOLV-301104-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258932 | 26003H | 5689J | LP1Y-SOLV-301104-05-1 | LP1Y-SOLV-301104-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258933 | 26003H | 5690J | LP1Y-SOLV-301104-06-1 | LP1Y-SOLV-301104-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258934 | 26003H | 5691J | LP1Y-SOLV-301104-06-2 | LP1Y-SOLV-301104-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258935 | 26003H | 5692J | LP1Y-SOLV-301104-06-3 | LP1Y-SOLV-301104-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301104 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301104 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258936 | 26003H | 5693J | LP1Y-SOLV-301106-01-1 | LP1Y-SOLV-301106-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301106 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301106 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258937 | 26003H | 5694J | LP1Y-SOLV-301106-01-2 | LP1Y-SOLV-301106-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301106 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301106 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258938 | 26003H | 5695J | LP1Y-SOLV-301106-01-3 | LP1Y-SOLV-301106-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301106 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301106 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258939 | 26003H | 5696J | LP1Y-SOLV-301106-01-4 | LP1Y-SOLV-301106-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301106 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301106 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258940 | 26003H | 5697J | LP1Y-SOLV-301106-01-5 | LP1Y-SOLV-301106-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P (108) 301106 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301106 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258941 | 26003H | 5698J | LP1Y-SOLV-301115-01-1 | LP1Y-SOLV-301115-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301115 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301115 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258942 | 26003H | 5699J | LP1Y-SOLV-301115-01-2 | LP1Y-SOLV-301115-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301115 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301115 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258943 | 26003H | 5700J | LP1Y-SOLV-301115-02-1 | LP1Y-SOLV-301115-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301115 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301115 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258944 | 26003H | 5701J | LP1Y-SOLV-301115-02-2 | LP1Y-SOLV-301115-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301115 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301115 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258945 | 26003H | 5702J | LP1Y-SOLV-301117-01-1 | LP1Y-SOLV-301117-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301117 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301117 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258946 | 26003H | 5703J | LP1Y-SOLV-301117-01-2 | LP1Y-SOLV-301117-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301117 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301117 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258947 | 26003H | 5704J | LP1Y-SOLV-301117-01-3 | LP1Y-SOLV-301117-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301117 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301117 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258948 | 26003H | 5705J | LP1Y-SOLV-301117-02-1 | LP1Y-SOLV-301117-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301117 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301117 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258949 | 26003H | 5706J | LP1Y-SOLV-301117-02-2 | LP1Y-SOLV-301117-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 301117 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301117 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258950 | 26003H | 5707J | LP1Y-SOLV-301203-01-1 | LP1Y-SOLV-301203-01 | 2 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301203 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301203 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258951 | 26003H | 5708J | LP1Y-SOLV-301203-02-1 | LP1Y-SOLV-301203-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301203 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301203 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258952 | 26003H | 5709J | LP1Y-SOLV-301203-02-2 | LP1Y-SOLV-301203-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301203 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301203 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258953 | 26003H | 5710J | LP1Y-SOLV-301204-04-1 | LP1Y-SOLV-301204-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258954 | 26003H | 5711J | LP1Y-SOLV-301204-04-2 | LP1Y-SOLV-301204-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258955 | 26003H | 5712J | LP1Y-SOLV-301204-04-3 | LP1Y-SOLV-301204-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258956 | 26003H | 5713J | LP1Y-SOLV-301204-04-4 | LP1Y-SOLV-301204-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258957 | 26003H | 5714J | LP1Y-SOLV-301204-04-5 | LP1Y-SOLV-301204-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258958 | 26003H | 5715J | LP1Y-SOLV-301204-05-1 | LP1Y-SOLV-301204-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258959 | 26003H | 5716J | LP1Y-SOLV-301204-06-1 | LP1Y-SOLV-301204-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258960 | 26003H | 5717J | LP1Y-SOLV-301204-06-2 | LP1Y-SOLV-301204-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258961 | 26003H | 5718J | LP1Y-SOLV-301204-06-3 | LP1Y-SOLV-301204-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258962 | 26003H | 5719J | LP1Y-SOLV-301204-06-4 | LP1Y-SOLV-301204-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301204 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301204 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258963 | 26003H | 5720J | LP1Y-SOLV-301206-01-1 | LP1Y-SOLV-301206-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258964 | 26003H | 5721J | LP1Y-SOLV-301206-01-2 | LP1Y-SOLV-301206-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258965 | 26003H | 5722J | LP1Y-SOLV-301206-01-3 | LP1Y-SOLV-301206-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258966 | 26003H | 5723J | LP1Y-SOLV-301206-03-1 | LP1Y-SOLV-301206-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258967 | 26003H | 5724J | LP1Y-SOLV-301206-03-3 | LP1Y-SOLV-301206-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258968 | 26003H | 5725J | LP1Y-SOLV-301206-03-2 | LP1Y-SOLV-301206-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258969 | 26003H | 5726J | LP1Y-SOLV-301206-04-1 | LP1Y-SOLV-301206-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258970 | 26003H | 5727J | LP1Y-SOLV-301206-04-2 | LP1Y-SOLV-301206-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258971 | 26003H | 5728J | LP1Y-SOLV-301206-04-3 | LP1Y-SOLV-301206-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258972 | 26003H | 5729J | LP1Y-SOLV-301206-04-4 | LP1Y-SOLV-301206-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258973 | 26003H | 5730J | LP1Y-SOLV-301206-04-5 | LP1Y-SOLV-301206-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301206 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301206 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258974 | 26003H | 5731J | LP1Y-SOLV-301215-01-1 | LP1Y-SOLV-301215-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301215 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301215 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258975 | 26003H | 5732J | LP1Y-SOLV-301215-01-2 | LP1Y-SOLV-301215-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301215 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301215 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258976 | 26003H | 5733J | LP1Y-SOLV-301215-03-1 | LP1Y-SOLV-301215-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301215 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301215 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258977 | 26003H | 5734J | LP1Y-SOLV-301215-03-2 | LP1Y-SOLV-301215-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301215 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301215 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258978 | 26003H | 5735J | LP1Y-SOLV-301215-03-3 | LP1Y-SOLV-301215-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301215 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301215 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258979 | 26003H | 5736J | LP1Y-SOLV-301217-01-1 | LP1Y-SOLV-301217-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301217 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301217 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258980 | 26003H | 5737J | LP1Y-SOLV-301217-01-2 | LP1Y-SOLV-301217-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301217 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301217 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258981 | 26003H | 5738J | LP1Y-SOLV-301217-01-3 | LP1Y-SOLV-301217-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301217 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301217 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258982 | 26003H | 5739J | LP1Y-SOLV-301217-01-4 | LP1Y-SOLV-301217-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301217 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301217 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258983 | 26003H | 5740J | LP1Y-SOLV-301217-03-1 | LP1Y-SOLV-301217-03 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301217 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301217 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258984 | 26003H | 5741J | LP1Y-SOLV-301303-01-1 | LP1Y-SOLV-301303-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301303 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301303 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258985 | 26003H | 5742J | LP1Y-SOLV-301303-01-2 | LP1Y-SOLV-301303-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301303 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301303 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258986 | 26003H | 5743J | LP1Y-SOLV-301303-01-3 | LP1Y-SOLV-301303-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301303 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301303 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258987 | 26003H | 5744J | LP1Y-SOLV-301304-04-1 | LP1Y-SOLV-301304-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258988 | 26003H | 5745J | LP1Y-SOLV-301304-04-2 | LP1Y-SOLV-301304-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258989 | 26003H | 5746J | LP1Y-SOLV-301304-04-3 | LP1Y-SOLV-301304-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258990 | 26003H | 5747J | LP1Y-SOLV-301304-04-4 | LP1Y-SOLV-301304-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258991 | 26003H | 5748J | LP1Y-SOLV-301304-04-5 | LP1Y-SOLV-301304-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258992 | 26003H | 5749J | LP1Y-SOLV-301304-05-1 | LP1Y-SOLV-301304-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258993 | 26003H | 5750J | LP1Y-SOLV-301304-06-1 | LP1Y-SOLV-301304-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258994 | 26003H | 5751J | LP1Y-SOLV-301304-06-2 | LP1Y-SOLV-301304-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258995 | 26003H | 5752J | LP1Y-SOLV-301304-06-3 | LP1Y-SOLV-301304-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301304 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301304 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258996 | 26003H | 5753J | LP1Y-SOLV-301306-01-1 | LP1Y-SOLV-301306-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258997 | 26003H | 5754J | LP1Y-SOLV-301306-01-2 | LP1Y-SOLV-301306-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258998 | 26003H | 5755J | LP1Y-SOLV-301306-03-1 | LP1Y-SOLV-301306-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S258999 | 26003H | 5756J | LP1Y-SOLV-301306-03-2 | LP1Y-SOLV-301306-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259000 | 26003H | 5757J | LP1Y-SOLV-301306-03-3 | LP1Y-SOLV-301306-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259001 | 26003H | 5758J | LP1Y-SOLV-301306-04-1 | LP1Y-SOLV-301306-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259002 | 26003H | 5759J | LP1Y-SOLV-301306-04-2 | LP1Y-SOLV-301306-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259003 | 26003H | 5760J | LP1Y-SOLV-301306-04-3 | LP1Y-SOLV-301306-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259004 | 26003H | 5761J | LP1Y-SOLV-301306-04-4 | LP1Y-SOLV-301306-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301306 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301306 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259005 | 26003H | 5762J | LP1Y-SOLV-301315-01-1 | LP1Y-SOLV-301315-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301315 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301315 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259006 | 26003H | 5763J | LP1Y-SOLV-301315-01-2 | LP1Y-SOLV-301315-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301315 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301315 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259007 | 26003H | 5764J | LP1Y-SOLV-301315-01-3 | LP1Y-SOLV-301315-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301315 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301315 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259008 | 26003H | 5765J | LP1Y-SOLV-301315-03-1 | LP1Y-SOLV-301315-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301315 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301315 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259009 | 26003H | 5766J | LP1Y-SOLV-301316-01-1 | LP1Y-SOLV-301316-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301316 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301316 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259010 | 26003H | 5767J | LP1Y-SOLV-301316-01-2 | LP1Y-SOLV-301316-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301316 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301316 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259011 | 26003H | 5768J | LP1Y-SOLV-301316-03-1 | LP1Y-SOLV-301316-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301316 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301316 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259012 | 26003H | 5769J | LP1Y-SOLV-301316-03-2 | LP1Y-SOLV-301316-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301316 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301316 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259013 | 26003H | 5770J | LP1Y-SOLV-301316-03-3 | LP1Y-SOLV-301316-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301316 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301316 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259014 | 26003H | 5771J | LP1Y-SOLV-301403-01-1 | LP1Y-SOLV-301403-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301403 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301403 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259015 | 26003H | 5772J | LP1Y-SOLV-301403-02-1 | LP1Y-SOLV-301403-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301403 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301403 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259016 | 26003H | 5773J | LP1Y-SOLV-301403-02-2 | LP1Y-SOLV-301403-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301403 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301403 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259017 | 26003H | 5774J | LP1Y-SOLV-301403-02-3 | LP1Y-SOLV-301403-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301403 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301403 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259018 | 26003H | 5775J | LP1Y-SOLV-301404-04-1 | LP1Y-SOLV-301404-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259019 | 26003H | 5776J | LP1Y-SOLV-301404-04-2 | LP1Y-SOLV-301404-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259020 | 26003H | 5777J | LP1Y-SOLV-301404-04-3 | LP1Y-SOLV-301404-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259021 | 26003H | 5778J | LP1Y-SOLV-301404-04-4 | LP1Y-SOLV-301404-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259022 | 26003H | 5779J | LP1Y-SOLV-301404-04-5 | LP1Y-SOLV-301404-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259023 | 26003H | 5780J | LP1Y-SOLV-301404-05-1 | LP1Y-SOLV-301404-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 4" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259024 | 26003H | 5781J | LP1Y-SOLV-301404-06-1 | LP1Y-SOLV-301404-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259025 | 26003H | 5782J | LP1Y-SOLV-301404-06-2 | LP1Y-SOLV-301404-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259026 | 26003H | 5783J | LP1Y-SOLV-301404-06-3 | LP1Y-SOLV-301404-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 3" SS SOLV (315) P 301404 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301404 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 3" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259027 | 26003H | 5784J | LP1Y-SOLV-301406-01-1 | LP1Y-SOLV-301406-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259028 | 26003H | 5785J | LP1Y-SOLV-301406-01-2 | LP1Y-SOLV-301406-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259029 | 26003H | 5786J | LP1Y-SOLV-301406-01-3 | LP1Y-SOLV-301406-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259030 | 26003H | 5787J | LP1Y-SOLV-301406-03-1 | LP1Y-SOLV-301406-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259031 | 26003H | 5788J | LP1Y-SOLV-301406-03-2 | LP1Y-SOLV-301406-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259032 | 26003H | 5789J | LP1Y-SOLV-301406-04-1 | LP1Y-SOLV-301406-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259033 | 26003H | 5790J | LP1Y-SOLV-301406-04-2 | LP1Y-SOLV-301406-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259034 | 26003H | 5791J | LP1Y-SOLV-301406-04-3 | LP1Y-SOLV-301406-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259035 | 26003H | 5792J | LP1Y-SOLV-301406-04-4 | LP1Y-SOLV-301406-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301406 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301406 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259036 | 26003H | 5793J | LP1Y-SOLV-301415-01-1 | LP1Y-SOLV-301415-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301415 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301415 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259037 | 26003H | 5794J | LP1Y-SOLV-301415-01-2 | LP1Y-SOLV-301415-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301415 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301415 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259038 | 26003H | 5795J | LP1Y-SOLV-301415-01-3 | LP1Y-SOLV-301415-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301415 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301415 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259039 | 26003H | 5796J | LP1Y-SOLV-301415-03-1 | LP1Y-SOLV-301415-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) 301415 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301415 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259040 | 26003H | 5797J | LP1Y-SOLV-301416-01-1 | LP1Y-SOLV-301416-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301416 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301416 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259041 | 26003H | 5798J | LP1Y-SOLV-301416-01-2 | LP1Y-SOLV-301416-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301416 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301416 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259042 | 26003H | 5799J | LP1Y-SOLV-301416-03-1 | LP1Y-SOLV-301416-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301416 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301416 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259043 | 26003H | 5800J | LP1Y-SOLV-301416-03-2 | LP1Y-SOLV-301416-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301416 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301416 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259044 | 26003H | 5801J | LP1Y-SOLV-301416-03-3 | LP1Y-SOLV-301416-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 301416 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301416 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259045 | 26003H | 5802J | LP1Y-SOLV-320102-02-1 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259046 | 26003H | 5803J | LP1Y-SOLV-320102-02-2 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259047 | 26003H | 5804J | LP1Y-SOLV-320102-02-3 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259048 | 26003H | 5805J | LP1Y-SOLV-320102-02-4 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259049 | 26003H | 5806J | LP1Y-SOLV-320102-02-5 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259050 | 26003H | 5807J | LP1Y-SOLV-320102-02-6 | LP1Y-SOLV-320102-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P (108) 320102 | SOLV |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320102 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259051 | 26003H | 5808J | LP1Y-SOLV-320202-01-1 | LP1Y-SOLV-320202-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259052 | 26003H | 5809J | LP1Y-SOLV-320202-01-2 | LP1Y-SOLV-320202-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259053 | 26003H | 5810J | LP1Y-SOLV-320202-01-3 | LP1Y-SOLV-320202-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259054 | 26003H | 5811J | LP1Y-SOLV-320202-04-1 | LP1Y-SOLV-320202-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259055 | 26003H | 5812J | LP1Y-SOLV-320202-04-2 | LP1Y-SOLV-320202-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259056 | 26003H | 5813J | LP1Y-SOLV-320202-04-3 | LP1Y-SOLV-320202-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259057 | 26003H | 5814J | LP1Y-SOLV-320202-04-4 | LP1Y-SOLV-320202-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320202 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320202 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259058 | 26003H | 5815J | LP1Y-SOLV-320302-01-1 | LP1Y-SOLV-320302-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259059 | 26003H | 5816J | LP1Y-SOLV-320302-01-3 | LP1Y-SOLV-320302-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259060 | 26003H | 5817J | LP1Y-SOLV-320302-01-2 | LP1Y-SOLV-320302-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259061 | 26003H | 5818J | LP1Y-SOLV-320302-04-1 | LP1Y-SOLV-320302-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259062 | 26003H | 5819J | LP1Y-SOLV-320302-04-2 | LP1Y-SOLV-320302-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259063 | 26003H | 5820J | LP1Y-SOLV-320302-04-3 | LP1Y-SOLV-320302-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259064 | 26003H | 5821J | LP1Y-SOLV-320302-04-4 | LP1Y-SOLV-320302-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320302 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320302 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259065 | 26003H | 5822J | LP1Y-SOLV-320402-01-1 | LP1Y-SOLV-320402-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259066 | 26003H | 5823J | LP1Y-SOLV-320402-01-3 | LP1Y-SOLV-320402-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259067 | 26003H | 5824J | LP1Y-SOLV-320402-01-2 | LP1Y-SOLV-320402-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259068 | 26003H | 5825J | LP1Y-SOLV-320402-06-1 | LP1Y-SOLV-320402-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259069 | 26003H | 5826J | LP1Y-SOLV-320402-06-2 | LP1Y-SOLV-320402-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259070 | 26003H | 5827J | LP1Y-SOLV-320402-06-3 | LP1Y-SOLV-320402-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259071 | 26003H | 5828J | LP1Y-SOLV-320402-06-4 | LP1Y-SOLV-320402-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SOLV (315) P 320402 | SOLV |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-320402 |  | TFS00I007YSPP |  | 315-SOLV | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259072 | 26003H | 5829J | LP1Y-STORMP-365304-01-1 | LP1Y-STORMP-365304-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259073 | 26003H | 5830J | LP1Y-STORMP-365304-01-2 | LP1Y-STORMP-365304-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259074 | 26003H | 5831J | LP1Y-STORMP-365304-02-1 | LP1Y-STORMP-365304-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259075 | 26003H | 5832J | LP1Y-STORMP-365304-02-2 | LP1Y-STORMP-365304-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259076 | 26003H | 5833J | LP1Y-STORMP-365304-05-1 | LP1Y-STORMP-365304-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259077 | 26003H | 5834J | LP1Y-STORMP-365304-05-2 | LP1Y-STORMP-365304-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS STORMP (315) (108) 365304 | STORMP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365304 |  | TFS00I007YSPP |  | 315-STORMP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259078 | 26003H | 5835J | LP1Y-SW-365302-01-1 | LP1Y-SW-365302-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SW (315) 365302 | SW |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365302 |  | TFS00I007YSPP |  | 315-SW | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259079 | 26003H | 5836J | LP1Y-SWP-301081-02-1 | LP1Y-SWP-301081-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 301081 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301081 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259080 | 26003H | 5837J | LP1Y-SWP-301081-02-2 | LP1Y-SWP-301081-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 301081 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301081 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259081 | 26003H | 5838J | LP1Y-SWP-301081-03-1 | LP1Y-SWP-301081-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 301081 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301081 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259082 | 26003H | 5839J | LP1Y-SWP-301081-05-1 | LP1Y-SWP-301081-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 301081 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301081 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259083 | 26003H | 5840J | LP1Y-SWP-301081-05-2 | LP1Y-SWP-301081-05 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 301081 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301081 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259084 | 26003H | 5841J | LP1Y-SWP-365303-03-1 | LP1Y-SWP-365303-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259085 | 26003H | 5842J | LP1Y-SWP-365303-03-2 | LP1Y-SWP-365303-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 1 1/2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259086 | 26003H | 5843J | LP1Y-SWP-365303-03-3 | LP1Y-SWP-365303-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108,NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259087 | 26003H | 5844J | LP1Y-SWP-365303-04-1 | LP1Y-SWP-365303-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259088 | 26003H | 5845J | LP1Y-SWP-365303-04-2 | LP1Y-SWP-365303-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259089 | 26003H | 5846J | LP1Y-SWP-365303-04-3 | LP1Y-SWP-365303-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259090 | 26003H | 5847J | LP1Y-SWP-365303-06-1 | LP1Y-SWP-365303-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259091 | 26003H | 5848J | LP1Y-SWP-365303-06-2 | LP1Y-SWP-365303-06 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS SWP (315) (108) 365303 | SWP |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-365303 |  | TFS00I007YSPP |  | 315-SWP | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259092 | 26003H | 5849J | LP1Y-WFO-033014-08-1 | LP1Y-WFO-033014-08 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259093 | 26003H | 5850J | LP1Y-WFO-033014-08-2 | LP1Y-WFO-033014-08 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259094 | 26003H | 5851J | LP1Y-WFO-033014-09-1 | LP1Y-WFO-033014-09 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259095 | 26003H | 5852J | LP1Y-WFO-033014-09-2 | LP1Y-WFO-033014-09 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259096 | 26003H | 5853J | LP1Y-WFO-033014-09-3 | LP1Y-WFO-033014-09 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259097 | 26003H | 5854J | LP1Y-WFO-033014-09-4 | LP1Y-WFO-033014-09 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259098 | 26003H | 5855J | LP1Y-WFO-033014-10-1 | LP1Y-WFO-033014-10 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259099 | 26003H | 5856J | LP1Y-WFO-033014-10-2 | LP1Y-WFO-033014-10 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259100 | 26003H | 5857J | LP1Y-WFO-033014-10-3 | LP1Y-WFO-033014-10 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259101 | 26003H | 5858J | LP1Y-WFO-033014-10-4 | LP1Y-WFO-033014-10 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259102 | 26003H | 5859J | LP1Y-WFO-033014-10-5 | LP1Y-WFO-033014-10 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 033014 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033014 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259103 | 26003H | 5860J | LP1Y-WFO-301110-02-1 | LP1Y-WFO-301110-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301110 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259104 | 26003H | 5861J | LP1Y-WFO-301110-02-2 | LP1Y-WFO-301110-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301110 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259105 | 26003H | 5862J | LP1Y-WFO-301110-02-3 | LP1Y-WFO-301110-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301110 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259106 | 26003H | 5863J | LP1Y-WFO-301110-02-4 | LP1Y-WFO-301110-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301110 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259107 | 26003H | 5864J | LP1Y-WFO-301110-02-5 | LP1Y-WFO-301110-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301110 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301110 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259108 | 26003H | 5865J | LP1Y-WFO-301210-02-1 | LP1Y-WFO-301210-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301210 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259109 | 26003H | 5866J | LP1Y-WFO-301210-02-2 | LP1Y-WFO-301210-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301210 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259110 | 26003H | 5867J | LP1Y-WFO-301210-02-3 | LP1Y-WFO-301210-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301210 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259111 | 26003H | 5868J | LP1Y-WFO-301210-02-4 | LP1Y-WFO-301210-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301210 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259112 | 26003H | 5869J | LP1Y-WFO-301210-02-5 | LP1Y-WFO-301210-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301210 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301210 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259113 | 26003H | 5870J | LP1Y-WFO-301310-02-1 | LP1Y-WFO-301310-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301310 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301310 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259114 | 26003H | 5871J | LP1Y-WFO-301310-02-2 | LP1Y-WFO-301310-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301310 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301310 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259115 | 26003H | 5872J | LP1Y-WFO-301310-02-3 | LP1Y-WFO-301310-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301310 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301310 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259116 | 26003H | 5873J | LP1Y-WFO-301310-02-4 | LP1Y-WFO-301310-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301310 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301310 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259117 | 26003H | 5874J | LP1Y-WFO-301310-02-5 | LP1Y-WFO-301310-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301310 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301310 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259118 | 26003H | 5875J | LP1Y-WFO-301410-02-1 | LP1Y-WFO-301410-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301410 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301410 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259119 | 26003H | 5876J | LP1Y-WFO-301410-02-2 | LP1Y-WFO-301410-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301410 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301410 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259120 | 26003H | 5877J | LP1Y-WFO-301410-02-3 | LP1Y-WFO-301410-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301410 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301410 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259121 | 26003H | 5878J | LP1Y-WFO-301410-02-4 | LP1Y-WFO-301410-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301410 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301410 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259122 | 26003H | 5879J | LP1Y-WFO-301410-02-5 | LP1Y-WFO-301410-02 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 301410 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-301410 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259123 | 26003H | 5880J | LP1Y-WFO-370005-04-1 | LP1Y-WFO-370005-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370005 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370005 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259124 | 26003H | 5881J | LP1Y-WFO-370005-04-2 | LP1Y-WFO-370005-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370005 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370005 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259125 | 26003H | 5882J | LP1Y-WFO-370005-04-3 | LP1Y-WFO-370005-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370005 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370005 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259126 | 26003H | 5883J | LP1Y-WFO-370006-04-1 | LP1Y-WFO-370006-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370006 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259127 | 26003H | 5884J | LP1Y-WFO-370006-04-2 | LP1Y-WFO-370006-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370006 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259128 | 26003H | 5885J | LP1Y-WFO-370006-04-3 | LP1Y-WFO-370006-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370006 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370006 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259129 | 26003H | 5886J | LP1Y-WFO-370007-04-1 | LP1Y-WFO-370007-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370007 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259130 | 26003H | 5887J | LP1Y-WFO-370007-04-2 | LP1Y-WFO-370007-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370007 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259131 | 26003H | 5888J | LP1Y-WFO-370007-04-3 | LP1Y-WFO-370007-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370007 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259132 | 26003H | 5889J | LP1Y-WFO-370007-04-4 | LP1Y-WFO-370007-04 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WFO (36) 370007 | WFO |  | NI |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-370007 |  | TFS00I007YSPP |  | 36-WFO | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259133 | 26003H | 5890J | LP1Y-WPC-033015-03-1 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259134 | 26003H | 5891J | LP1Y-WPC-033015-03-2 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259135 | 26003H | 5892J | LP1Y-WPC-033015-03-3 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259136 | 26003H | 5893J | LP1Y-WPC-033015-03-4 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259137 | 26003H | 5894J | LP1Y-WPC-033015-03-5 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259138 | 26003H | 5895J | LP1Y-WPC-033015-03-6 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259139 | 26003H | 5896J | LP1Y-WPC-033015-03-7 | LP1Y-WPC-033015-03 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033015 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033015 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259140 | 26003H | 5897J | LP1Y-WPC-033069-01-1 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259141 | 26003H | 5898J | LP1Y-WPC-033069-01-2 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259142 | 26003H | 5899J | LP1Y-WPC-033069-01-3 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259143 | 26003H | 5900J | LP1Y-WPC-033069-01-4 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259144 | 26003H | 5901J | LP1Y-WPC-033069-01-5 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259145 | 26003H | 5902J | LP1Y-WPC-033069-01-6 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259146 | 26003H | 5903J | LP1Y-WPC-033069-01-7 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259147 | 26003H | 5904J | LP1Y-WPC-033069-01-8 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259148 | 26003H | 5905J | LP1Y-WPC-033069-01-9 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259149 | 26003H | 5906J | LP1Y-WPC-033069-01-10 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259150 | 26003H | 5907J | LP1Y-WPC-033069-01-11 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259151 | 26003H | 5908J | LP1Y-WPC-033069-01-12 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259152 | 26003H | 5909J | LP1Y-WPC-033069-01-13 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259153 | 26003H | 5910J | LP1Y-WPC-033069-01-14 | LP1Y-WPC-033069-01 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 033069 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-033069 |  | TFS00I006YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259154 | 26003H | 5911J | LP1Y-WPC-375006-01-1 | LP1Y-WPC-375006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259155 | 26003H | 5912J | LP1Y-WPC-375006-01-2 | LP1Y-WPC-375006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259156 | 26003H | 5913J | LP1Y-WPC-375006-01-3 | LP1Y-WPC-375006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259157 | 26003H | 5914J | LP1Y-WPC-375006-01-4 | LP1Y-WPC-375006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259158 | 26003H | 5915J | LP1Y-WPC-375006-01-5 | LP1Y-WPC-375006-01 | 0 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 2" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 2" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259159 | 26003H | 5916J | LP1Y-WPC-375006-02-1 | LP1Y-WPC-375006-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 1.25" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%
C34-S259160 | 26003H | 5917J | LP1Y-WPC-375006-02-2 | LP1Y-WPC-375006-02 | 1 | N | PRI-3-3 | [5 empty] | In Engineering | P033 |  |  | LP1Y 1.25" SS WPC (36) (108) 375006 | WPC |  | 108 |  |  |  | NONE |  | NONE | Amelia |  |  | LP1Y-375006 |  | TFS00I007YSPP |  | 36-WPC | NONE | 1 1/4" | 316 SS | 0 | 0 | 0 | 0 | 0 | sq ft | 0 | ft | 2026-02-13 | [14 empty] | Not Passed | No |  | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | 0% |  |  |  | 0%