## Main
Line No. | Priority | CWA | Dike | CWP | Module Yard | Node | Size (in) | Insulated | Quantity | PTP Tag | Client Tag | Job No. | Item No. | Status | Shipped QTY | Remaining QTY | Estimated Ready for Shipment Date | Actual Ship Date | PO Need By Date | Comment on Schedule | Comment on Shipment
119 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5UG-02 | TFS00D001YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 1 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
28 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5US-75 | TFS00D001YS18 ¦ PO LINE NO. 28 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 2 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
65 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00D001YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 3 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
122 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5US-02 | TFS00D001YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 4 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
27 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5UGSP-75-50 | TFS00D001YS18 ¦ PO LINE NO. 27 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 5 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
26 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-15 | TFS00D001YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 6 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
64 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5UGSP-01-50 | TFS00D001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 7 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
30 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1.25IN | YES | 1 | 5UGSP-11-01 | TFS00D001YS18 ¦ PO LINE NO. 30 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216611 | 8 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
120 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5UGSP-02-01 | TFS00D001YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 9 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
148 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 3IN | YES | 9 | 5UGSP-03-01 | TFS00D001YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 10 | Shipped | 9 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
14 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5C-75-50 | TFS00D001YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 11 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
13 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5C-75-15 | TFS00D001YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 12 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
55 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5C-01-50 | TFS00D001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 13 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
53 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00D001YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 14 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
29 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1.25IN | YES | 5 | 5C-11-01 | TFS00D001YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216611 | 15 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
16 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00D001YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 16 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
56 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00D001YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 17 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
76 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 23 | 5CI-02 | TFS00D001YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 18 | Shipped | 23 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
22 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00D001YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 19 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
95 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G1-1 | TFS00D001YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 20 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
138 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5G1-1 | TFS00D001YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 21 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
164 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5G1-1 | TFS00D001YS18 ¦ PO LINE NO. 164 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 22 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
96 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G2 | TFS00D001YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 23 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
108 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00D001YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 24 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
114 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C6S | TFS00D001YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 25 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
10 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5ABS1 | TFS00D001YS18 ¦ PO LINE NO. 10 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 26 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
49 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00D001YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 27 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
68 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS3 | TFS00D001YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 28 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
89 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-1 | TFS00D001YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 29 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
136 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00D001YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 30 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
159 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5FSS5-L-1 | TFS00D001YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 31 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
74 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 2IN | YES | 16 | 5CC-02-01 | TFS00D001YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 32 | Shipped | 16 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
127 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 3IN | YES | 22 | 5CC-03-01 | TFS00D001YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 33 | Shipped | 22 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
155 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 4IN | YES | 5 | 5CC-04-01 | TFS00D001YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 34 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
23 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5UG-75 | TFS00D002YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 35 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
61 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5UG-01 | TFS00D002YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 36 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
119 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 21 | 5UG-02 | TFS00D002YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 37 | Shipped | 21 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
43 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5US-15 | TFS00D002YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 38 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
122 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 9 | 5US-02 | TFS00D002YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 39 | Shipped | 9 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
120 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 39 | 5UGSP-02-01 | TFS00D002YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 40 | Shipped | 39 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
121 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5UGSP-02-15 | TFS00D002YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 41 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
148 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | YES | 4 | 5UGSP-03-01 | TFS00D002YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 42 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
171 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | YES | 10 | 5UGSP-04-01 | TFS00D002YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 43 | Shipped | 10 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
53 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00D002YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 44 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
16 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 0.75IN | NO | 6 | 5CI-75 | TFS00D002YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 45 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
56 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1IN | NO | 12 | 5CI-01 | TFS00D002YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 46 | Shipped | 12 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
35 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5CI-15 | TFS00D002YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 47 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
76 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 52 | 5CI-02 | TFS00D002YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 48 | Shipped | 52 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
128 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5CI-03 | TFS00D002YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 49 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
20 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5FS1S1 | TFS00D002YS18 ¦ PO LINE NO. 20 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 50 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
36 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FS1S1 | TFS00D002YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 51 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
81 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FS1S1 | TFS00D002YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 52 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
77 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00D002YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 53 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
95 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G1-1 | TFS00D002YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 54 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
138 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5G1-1 | TFS00D002YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 55 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
164 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5G1-1 | TFS00D002YS18 ¦ PO LINE NO. 164 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 56 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
96 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5G2 | TFS00D002YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 57 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
97 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G3-02 | TFS00D002YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 58 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
110 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 9 | 5S1C4S | TFS00D002YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 59 | Shipped | 9 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
114 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00D002YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 60 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
50 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS2 | TFS00D002YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 61 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
67 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5ABS2 | TFS00D002YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 62 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
68 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 15 | 5ABS3 | TFS00D002YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 63 | Shipped | 15 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
150 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 9 | 5ABS3 | TFS00D002YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 64 | Shipped | 9 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
89 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5FSS5-L-1 | TFS00D002YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 65 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
137 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-M-1 | TFS00D002YS18 ¦ PO LINE NO. 137 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 66 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
162 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5FSS5-M-5 | TFS00D002YS18 ¦ PO LINE NO. 162 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 67 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
134 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-H-7 | TFS00D002YS18 ¦ PO LINE NO. 134 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 68 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
75 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5CH-02-15 | TFS00D002YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 69 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
74 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 89 | 5CC-02-01 | TFS00D002YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 70 | Shipped | 89 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
127 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | YES | 14 | 5CC-03-01 | TFS00D002YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 71 | Shipped | 14 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
155 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | YES | 23 | 5CC-04-01 | TFS00D002YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 72 | Shipped | 23 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
104 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5ISC-02-01 | TFS00D002YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 73 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
102 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5IAC-02-01-M | TFS00D002YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 74 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
141 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5IAC-03-01-M | TFS00D002YS18 ¦ PO LINE NO. 141 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 75 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
166 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5IAC-04-01-M | TFS00D002YS18 ¦ PO LINE NO. 166 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 76 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
41 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5UG-15 | TFS00D003YS18 ¦ PO LINE NO. 41 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 78 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
119 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5UG-02 | TFS00D003YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 79 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
170 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5UG-04 | TFS00D003YS18 ¦ PO LINE NO. 170 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 80 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
46 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 10IN | YES | 2 | 5UG-10 | TFS00D003YS18 ¦ PO LINE NO. 46 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 10IN | 216611 | 81 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
28 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5US-75 | TFS00D003YS18 ¦ PO LINE NO. 28 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 82 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
43 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5US-15 | TFS00D003YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 83 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
122 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5US-02 | TFS00D003YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 84 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
172 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5US-04 | TFS00D003YS18 ¦ PO LINE NO. 172 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 85 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
62 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5UGSP-01-01 | TFS00D003YS18 ¦ PO LINE NO. 62 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 86 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
120 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5UGSP-02-01 | TFS00D003YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 87 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
121 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-15 | TFS00D003YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 88 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
148 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 3IN | YES | 5 | 5UGSP-03-01 | TFS00D003YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 89 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
171 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | YES | 5 | 5UGSP-04-01 | TFS00D003YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 90 | Shipped | 5 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
200 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | YES | 11 | 5UGSP-06-01 | TFS00D003YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 91 | Shipped | 11 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
53 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1IN | YES | 8 | 5C-01-01 | TFS00D003YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 92 | Shipped | 8 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
16 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 10 | 5CI-75 | TFS00D003YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 93 | Shipped | 10 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
56 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5CI-01 | TFS00D003YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 94 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
35 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5CI-15 | TFS00D003YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 95 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
76 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 27 | 5CI-02 | TFS00D003YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 96 | Shipped | 27 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
156 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5CI-04 | TFS00D003YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 97 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
44 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 10IN | NO | 2 | 5CI-10 | TFS00D003YS18 ¦ PO LINE NO. 44 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 10IN | 216611 | 98 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
36 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5FS1S1 | TFS00D003YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216611 | 99 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
81 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00D003YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 100 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
180 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FS1S2 | TFS00D003YS18 ¦ PO LINE NO. 180 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 101 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
83 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS1-L-1-2 | TFS00D003YS18 ¦ PO LINE NO. 83 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 102 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
154 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSG-2 | TFS00D003YS18 ¦ PO LINE NO. 154 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 103 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
77 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5DA3-C | TFS00D003YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 104 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
138 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5G1-1 | TFS00D003YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 105 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
96 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 7 | 5G2 | TFS00D003YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 106 | Shipped | 7 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
110 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 13 | 5S1C4S | TFS00D003YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 107 | Shipped | 13 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
112 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5S | TFS00D003YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 108 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
114 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00D003YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 109 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
66 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00D003YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 110 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
50 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 1IN | NO | 8 | 5ABS2 | TFS00D003YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216611 | 111 | Shipped | 8 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
11 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5ABS3 | TFS00D003YS18 ¦ PO LINE NO. 11 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216611 | 112 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
68 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS3 | TFS00D003YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 113 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
184 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 6 | 5FSS5-L-1 | TFS00D003YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 114 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
185 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5FSS5-L-2 | TFS00D003YS18 ¦ PO LINE NO. 185 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 115 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
186 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-M-1 | TFS00D003YS18 ¦ PO LINE NO. 186 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 116 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
187 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5FSS5-M-2 | TFS00D003YS18 ¦ PO LINE NO. 187 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 117 | Shipped | 3 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
160 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5FSS5-M-3 | TFS00D003YS18 ¦ PO LINE NO. 160 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 118 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
47 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 12IN | NO | 2 | 5FSS5-H-5 | TFS00D003YS18 ¦ PO LINE NO. 47 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 12IN | 216611 | 119 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
183 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-H-7 | TFS00D003YS18 ¦ PO LINE NO. 183 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 120 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
75 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00D003YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 121 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
74 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | YES | 31 | 5CC-02-01 | TFS00D003YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 122 | Shipped | 31 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
127 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 3IN | YES | 19 | 5CC-03-01 | TFS00D003YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216611 | 123 | Shipped | 19 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
155 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | YES | 9 | 5CC-04-01 | TFS00D003YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216611 | 124 | Shipped | 9 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
177 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | YES | 33 | 5CC-06-01 | TFS00D003YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 125 | Shipped | 33 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
48 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 12IN | YES | 2 | 5IGC-12-01 | TFS00D003YS18 ¦ PO LINE NO. 48 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 12IN | 216611 | 126 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
193 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5IAC-06-01-M | TFS00D003YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216611 | 127 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
120 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5UGSP-02-01 | TFS00D004YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 128 | Shipped | 4 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
80 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00D004YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 129 | Shipped | 2 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
81 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00D004YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 130 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
97 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00D004YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 131 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
66 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00D004YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 132 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
74 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5CC-02-01 | TFS00D004YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 133 | Shipped | 6 | 0 | 2026-01-09 | 2026-01-07 | 2026-02-04
102 | 1 | TFS00D | 4 | TFS00D004YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00D004YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216611 | 134 | Shipped | 1 | 0 | 2026-01-09 | 2026-01-06 | 2026-02-04
119 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 9 | 5UG-02 | TFS00I001YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 1 | Shipped | 9 | 0 |  |  | 2026-02-04
146 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5UG-03 | TFS00I001YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 2 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
65 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00I001YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 3 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
122 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5US-02 | TFS00I001YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 4 | Shipped | 8 | 0 | 2026-01-16 |  | 2026-02-04
26 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-15 | TFS00I001YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 5 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
64 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5UGSP-01-50 | TFS00I001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 6 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
30 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1.25IN | YES | 1 | 5UGSP-11-01 | TFS00I001YS18 ¦ PO LINE NO. 30 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216612 | 7 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
120 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 7 | 5UGSP-02-01 | TFS00I001YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 8 | Shipped | 7 | 0 | 2026-01-16 |  | 2026-02-04
14 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5C-75-50 | TFS00I001YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 9 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
13 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5C-75-15 | TFS00I001YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 10 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
55 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-50 | TFS00I001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 11 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
53 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00I001YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 12 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
29 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1.25IN | YES | 5 | 5C-11-01 | TFS00I001YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216612 | 13 | Shipped | 5 | 0 | 2026-01-16 |  | 2026-02-04
16 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00I001YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 14 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
56 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00I001YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 15 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
76 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 41 | 5CI-02 | TFS00I001YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 16 | Shipped | 41 | 0 | 2026-01-16 |  | 2026-02-04
128 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 3IN | NO | 7 | 5CI-03 | TFS00I001YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 17 | Shipped | 7 | 0 | 2026-01-16 |  | 2026-02-04
130 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5DA1-M | TFS00I001YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 18 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
22 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00I001YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 19 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
95 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G1-1 | TFS00I001YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 20 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
96 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G2 | TFS00I001YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 21 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
105 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5PU1-1 | TFS00I001YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 22 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
108 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00I001YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 23 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
112 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C5S | TFS00I001YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 24 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
114 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00I001YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 25 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
49 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00I001YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 26 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
68 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS3 | TFS00I001YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 27 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
123 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5ABS3 | TFS00I001YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 28 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
74 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 17 | 5CC-02-01 | TFS00I001YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 29 | Shipped | 17 | 0 | 2026-01-16 |  | 2026-02-04
103 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IGC-02-01 | TFS00I001YS18 ¦ PO LINE NO. 103 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 30 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
102 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00I001YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 31 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
146 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5UG-03 | TFS00I002YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 32 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
9 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 0.5IN | YES | 3 | 5UGSP-50-01 | TFS00I002YS18 ¦ PO LINE NO. 9 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 216612 | 33 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
64 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00I002YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 34 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
6 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 0.5IN | YES | 5 | 5C-50-01 | TFS00I002YS18 ¦ PO LINE NO. 6 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 216612 | 35 | Shipped | 5 | 0 | 2026-01-16 |  | 2026-02-04
55 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00I002YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 36 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
76 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5CI-02 | TFS00I002YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 37 | Shipped | 5 | 0 | 2026-01-16 |  | 2026-02-04
128 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 20 | 5CI-03 | TFS00I002YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 38 | Shipped | 20 | 0 | 2026-01-16 |  | 2026-02-04
130 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5DA1-M | TFS00I002YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 39 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
5 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 0.5IN | NO | 2 | 5ABS3 | TFS00I002YS18 ¦ PO LINE NO. 5 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 216612 | 40 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
123 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5ABS3 | TFS00I002YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 41 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
136 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00I002YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 42 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
133 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-H-4 | TFS00I002YS18 ¦ PO LINE NO. 133 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 43 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
119 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | YES | 23 | 5UG-02 | TFS00I003YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 44 | Shipped | 23 | 0 | 2026-01-16 |  | 2026-02-04
146 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 3IN | YES | 10 | 5UG-03 | TFS00I003YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 45 | Shipped | 10 | 0 | 2026-01-16 |  | 2026-02-04
65 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00I003YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 46 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
122 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 11 | 5US-02 | TFS00I003YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 47 | Shipped | 11 | 0 | 2026-01-16 |  | 2026-02-04
25 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-01 | TFS00I003YS18 ¦ PO LINE NO. 25 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 48 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
64 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00I003YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 49 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
30 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1.25IN | YES | 1 | 5UGSP-11-01 | TFS00I003YS18 ¦ PO LINE NO. 30 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216612 | 50 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
120 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | YES | 15 | 5UGSP-02-01 | TFS00I003YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 51 | Shipped | 15 | 0 | 2026-01-16 |  | 2026-02-04
148 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 3IN | YES | 9 | 5UGSP-03-01 | TFS00I003YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 52 | Shipped | 9 | 0 | 2026-01-16 |  | 2026-02-04
14 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5C-75-50 | TFS00I003YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 53 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
12 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5C-75-01 | TFS00I003YS18 ¦ PO LINE NO. 12 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 54 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
13 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5C-75-15 | TFS00I003YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 55 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
55 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00I003YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 56 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
53 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00I003YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 57 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
29 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1.25IN | YES | 5 | 5C-11-01 | TFS00I003YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 216612 | 58 | Shipped | 5 | 0 | 2026-01-16 |  | 2026-02-04
16 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00I003YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 59 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
56 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00I003YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 60 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
76 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 70 | 5CI-02 | TFS00I003YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 61 | Shipped | 70 | 0 | 2026-01-16 |  | 2026-02-04
128 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 3IN | NO | 22 | 5CI-03 | TFS00I003YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 62 | Shipped | 22 | 0 | 2026-01-16 |  | 2026-02-04
84 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FSS3-L-1-1 | TFS00I003YS18 ¦ PO LINE NO. 84 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 63 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
130 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5DA1-M | TFS00I003YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 64 | Shipped | 3 | 0 | 2026-01-16 |  | 2026-02-04
22 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00I003YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 216612 | 65 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
95 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00I003YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 66 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
96 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G2 | TFS00I003YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 67 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
105 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5PU1-1 | TFS00I003YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 68 | Shipped | 2 | 0 | 2026-01-16 |  | 2026-02-04
108 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5S1C3S | TFS00I003YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 69 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
110 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4S | TFS00I003YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 70 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
49 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00I003YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216612 | 71 | Shipped | 1 | 0 | 2026-01-16 |  | 2026-02-04
68 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5ABS3 | TFS00I003YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 72 | Shipped | 4 | 0 | 2026-01-16 |  | 2026-02-04
74 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | YES | 33 | 5CC-02-01 | TFS00I003YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216612 | 73 | Shipped | 33 | 0 | 2026-01-16 |  | 2026-02-04
127 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 3IN | YES | 23 | 5CC-03-01 | TFS00I003YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216612 | 74 | Shipped | 23 | 0 | 2026-01-16 |  | 2026-02-04
69 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BA1 | TFS00E015YS18 ¦ PO LINE NO. 69 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 1 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
151 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BA2 | TFS00E010YS18 ¦ PO LINE NO. 151 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 2 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
52 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | NO | 0 | 5BS1 | TFS00E015YS18 ¦ PO LINE NO. 52 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 216616 | 3 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00E007YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00I005YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00E003YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00E006YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00E016YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BS1 | TFS00E011YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 4 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00I005YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00D003YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00I004YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00D007YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00D005YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00D002YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00E011YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00E010YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00D006YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BS2 | TFS00E009YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 5 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
152 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BS2 | TFS00D003YS18 ¦ PO LINE NO. 152 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 6 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
152 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BS2 | TFS00D007YS18 ¦ PO LINE NO. 152 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 6 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
174 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BS2 | TFS00D006YS18 ¦ PO LINE NO. 174 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 7 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00E007YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00I003YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00I001YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00D001YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00E016YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00E015YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00D007YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5BSA1 | TFS00E010YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 8 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BSA1 | TFS00I003YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 9 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BSA1 | TFS00E016YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 9 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BSA1 | TFS00E015YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 9 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5BSA1 | TFS00E003YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 9 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E007YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00I005YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00D002YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E010YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E003YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E011YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E009YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5BSA1 | TFS00E005YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 10 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00D003YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00E006YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00I004YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00I007YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00I008YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00D002YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00E011YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00E009YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00D006YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00E010YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5BSA2 | TFS00E005YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 11 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00D005YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00I007YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00I008YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00D006YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00D003YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | NO | 0 | 5BSA2 | TFS00E005YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 216616 | 12 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00I006YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00D002YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E015YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E003YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E005YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00D005YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00D003YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00I007YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00I008YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E011YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00D006YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E007YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E010YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E006YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
79 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5DS1-02 | TFS00E009YS18 ¦ PO LINE NO. 79 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 13 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00D007YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00I007YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00I008YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00D002YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00E011YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
131 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5DS1-03 | TFS00E014YS18 ¦ PO LINE NO. 131 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 14 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
158 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5DS1-04 | TFS00E010YS18 ¦ PO LINE NO. 158 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 15 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
158 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5DS1-04 | TFS00E014YS18 ¦ PO LINE NO. 158 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 15 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
158 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5DS1-04 | TFS00E015YS18 ¦ PO LINE NO. 158 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 15 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E003YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E016YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E010YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E005YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E007YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
40 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1.5IN | NO | 0 | 5ST-15 | TFS00E011YS18 ¦ PO LINE NO. 40 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 216616 | 16 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
118 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5ST-15 | TFS00E006YS18 ¦ PO LINE NO. 118 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 17 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
117 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 0 | 5ST-02 | TFS00I006YS18 ¦ PO LINE NO. 117 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 216616 | 18 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
145 | 2 | TFS00I | 2 | TFS00I002YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5ST-02 | TFS00I002YS18 ¦ PO LINE NO. 145 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 19 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
145 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 3IN | NO | 0 | 5ST-02 | TFS00E014YS18 ¦ PO LINE NO. 145 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 216616 | 19 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
169 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 0 | 5ST-03 | TFS00D002YS18 ¦ PO LINE NO. 169 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 216616 | 20 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
45 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 10IN | NO | 0 | 5ST-06 | TFS00D003YS18 ¦ PO LINE NO. 45 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 10IN | 216616 | 21 | Deleted | 0 | 0 | Deleted |  | 2026-02-04 | Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
100 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5HR4-02 | TFS00E006YS18 ¦ PO LINE NO. 100 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 1 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
119 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 24 | 5UG-02 | TFS00E006YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 2 | Shipped | 24 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
122 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5US-02 | TFS00E006YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 3 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
9 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 0.5IN | YES | 8 | 5UGSP-50-01 | TFS00E006YS18 ¦ PO LINE NO. 9 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217380 | 4 | Shipped | 8 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
62 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 1IN | YES | 13 | 5UGSP-01-01 | TFS00E006YS18 ¦ PO LINE NO. 62 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 5 | Shipped | 13 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
120 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 48 | 5UGSP-02-01 | TFS00E006YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 6 | Shipped | 48 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
121 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UGSP-02-15 | TFS00E006YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 7 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
148 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 3IN | YES | 6 | 5UGSP-03-01 | TFS00E006YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 8 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
171 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | YES | 14 | 5UGSP-04-01 | TFS00E006YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 9 | Shipped | 14 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
200 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5UGSP-06-01 | TFS00E006YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 10 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
6 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 0.5IN | YES | 22 | 5C-50-01 | TFS00E006YS18 ¦ PO LINE NO. 6 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217380 | 11 | Shipped | 22 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
53 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 1IN | YES | 27 | 5C-01-01 | TFS00E006YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 12 | Shipped | 27 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
33 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 1.5IN | YES | 2 | 5C-15-15 | TFS00E006YS18 ¦ PO LINE NO. 33 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 13 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
16 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 0.75IN | NO | 7 | 5CI-75 | TFS00E006YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 14 | Shipped | 7 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
56 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5CI-01 | TFS00E006YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 15 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
35 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5CI-15 | TFS00E006YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 16 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
76 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 51 | 5CI-02 | TFS00E006YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 17 | Shipped | 51 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
77 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00E006YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 18 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
95 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G1-1 | TFS00E006YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 19 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
96 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G2 | TFS00E006YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 20 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
110 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5S1C4S | TFS00E006YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 21 | Shipped | 10 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
67 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5ABS2 | TFS00E006YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 22 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
68 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5ABS3 | TFS00E006YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 23 | Shipped | 10 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
150 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | NO | 6 | 5ABS3 | TFS00E006YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 24 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
89 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FSS5-L-1 | TFS00E006YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 25 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
159 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-L-1 | TFS00E006YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 26 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
91 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-3 | TFS00E006YS18 ¦ PO LINE NO. 91 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 27 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
163 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-M-6 | TFS00E006YS18 ¦ PO LINE NO. 163 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 28 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
75 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5CH-02-15 | TFS00E006YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 29 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
73 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CC, SUPPORT CRADLE COLD SERVICE 2" PIPE, 1" INS | TFS00E006YS18 ¦ PO LINE NO. 73 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 30 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
74 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | YES | 98 | 5CC-02-01 | TFS00E006YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 31 | Shipped | 98 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
127 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 3IN | YES | 6 | 5CC-03-01 | TFS00E006YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 32 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
155 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | YES | 30 | 5CC-04-01 | TFS00E006YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 33 | Shipped | 30 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
177 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 6IN | YES | 6 | 5CC-06-01 | TFS00E006YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 34 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
167 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5IGC-04-01 | TFS00E006YS18 ¦ PO LINE NO. 167 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 35 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
193 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5IAC-06-01-M | TFS00E006YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 36 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
99 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5HR2 | TFS00E007YS18 ¦ PO LINE NO. 99 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 37 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
101 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5HR4-05 | TFS00E007YS18 ¦ PO LINE NO. 101 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 38 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04 | Jan-19-26: Reponse for RFI Received Dec-4-25: On HOLD Due To RFI No. 4
61 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UG-01 | TFS00E007YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 39 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
119 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | YES | 27 | 5UG-02 | TFS00E007YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 40 | Shipped | 27 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
122 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5US-02 | TFS00E007YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 41 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
62 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5UGSP-01-01 | TFS00E007YS18 ¦ PO LINE NO. 62 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 42 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
42 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | YES | 7 | 5UGSP-15-01 | TFS00E007YS18 ¦ PO LINE NO. 42 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 43 | Shipped | 7 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
120 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | YES | 39 | 5UGSP-02-01 | TFS00E007YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 44 | Shipped | 39 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
121 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5UGSP-02-15 | TFS00E007YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 45 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
148 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5UGSP-03-01 | TFS00E007YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 46 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
171 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | YES | 5 | 5UGSP-04-01 | TFS00E007YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 47 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
53 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5C-01-01 | TFS00E007YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 48 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
32 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | YES | 14 | 5C-15-01 | TFS00E007YS18 ¦ PO LINE NO. 32 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 49 | Shipped | 14 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
16 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 6 | 5CI-75 | TFS00E007YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 50 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
56 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | NO | 9 | 5CI-01 | TFS00E007YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 51 | Shipped | 9 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
35 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5CI-15 | TFS00E007YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 52 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
76 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 62 | 5CI-02 | TFS00E007YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 53 | Shipped | 62 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
20 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5FS1S1 | TFS00E007YS18 ¦ PO LINE NO. 20 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 54 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
81 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5FS1S1 | TFS00E007YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 55 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
82 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S2 | TFS00E007YS18 ¦ PO LINE NO. 82 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 56 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
77 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00E007YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 57 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
78 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-M | TFS00E007YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 58 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
96 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G2 | TFS00E007YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 59 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
165 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5G3-04 | TFS00E007YS18 ¦ PO LINE NO. 165 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 60 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
108 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00E007YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 61 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
110 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5S1C4S | TFS00E007YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 62 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
112 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5S | TFS00E007YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 63 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
111 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5L | TFS00E007YS18 ¦ PO LINE NO. 111 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 64 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
114 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C6S | TFS00E007YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 65 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
66 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00E007YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 66 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
50 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5ABS2 | TFS00E007YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 67 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
67 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS2 | TFS00E007YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 68 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
68 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 19 | 5ABS3 | TFS00E007YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 69 | Shipped | 19 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
150 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5ABS3 | TFS00E007YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 70 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
60 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5FSS5-L-1 | TFS00E007YS18 ¦ PO LINE NO. 60 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 71 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
90 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-2 | TFS00E007YS18 ¦ PO LINE NO. 90 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 72 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
37 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FSS5-M-5 | TFS00E007YS18 ¦ PO LINE NO. 37 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 73 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
38 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FSS5-M-6 | TFS00E007YS18 ¦ PO LINE NO. 38 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 74 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
75 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5CH-02-15 | TFS00E007YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 75 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
74 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | YES | 88 | 5CC-02-01 | TFS00E007YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 76 | Shipped | 88 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
127 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 3IN | YES | 11 | 5CC-03-01 | TFS00E007YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 77 | Shipped | 11 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
155 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | YES | 6 | 5CC-04-01 | TFS00E007YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 78 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
168 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5ISC-04-01 | TFS00E007YS18 ¦ PO LINE NO. 168 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 79 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
141 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5IAC-03-01-M | TFS00E007YS18 ¦ PO LINE NO. 141 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 80 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
166 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 4IN | NO | 5 | 5IAC-04-01-M | TFS00E007YS18 ¦ PO LINE NO. 166 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 81 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
120 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5UGSP-02-01 | TFS00E008YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 82 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
80 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00E008YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 83 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
81 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00E008YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 84 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
97 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E008YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 85 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
66 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00E008YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 86 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
74 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | YES | 7 | 5CC-02-01 | TFS00E008YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 87 | Shipped | 7 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
102 | 3 | TFS00E | 8 | TFS00E008YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E008YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 88 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
100 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5HR4-02 | TFS00E009YS18 ¦ PO LINE NO. 100 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 89 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
8 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.5IN | YES | 1 | 5UG-50 | TFS00E009YS18 ¦ PO LINE NO. 8 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217380 | 90 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
23 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00E009YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 91 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
61 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UG-01 | TFS00E009YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 92 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
41 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5UG-15 | TFS00E009YS18 ¦ PO LINE NO. 41 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 93 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
119 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | YES | 14 | 5UG-02 | TFS00E009YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 94 | Shipped | 14 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
122 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 9 | 5US-02 | TFS00E009YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 95 | Shipped | 9 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
120 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | YES | 51 | 5UGSP-02-01 | TFS00E009YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 96 | Shipped | 51 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
148 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | YES | 9 | 5UGSP-03-01 | TFS00E009YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 97 | Shipped | 9 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
171 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | YES | 4 | 5UGSP-04-01 | TFS00E009YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 98 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
200 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5UGSP-06-01 | TFS00E009YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 99 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
2 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.25IN | NO | 1 | 5BSH10-23 | TFS00E009YS18 ¦ PO LINE NO. 2 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.25IN | 217380 | 100 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
3 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.25IN | NO | 2 | 5BSH8-A-23 | TFS00E009YS18 ¦ PO LINE NO. 3 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.25IN | 217380 | 101 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
17 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5CLH4-75 | TFS00E009YS18 ¦ PO LINE NO. 17 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 102 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
53 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00E009YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 103 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
7 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.5IN | NO | 1 | 5CI-50 | TFS00E009YS18 ¦ PO LINE NO. 7 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217380 | 104 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
16 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.75IN | NO | 5 | 5CI-75 | TFS00E009YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 105 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
56 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5CI-01 | TFS00E009YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 106 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
34 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-1.5 | TFS00E009YS18 ¦ PO LINE NO. 34 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 107 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
76 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 39 | 5CI-02 | TFS00E009YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 108 | Shipped | 39 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
128 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5CI-03 | TFS00E009YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 109 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
77 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00E009YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 110 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
95 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00E009YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 111 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
97 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G3-02 | TFS00E009YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 112 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
108 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5S1C3S | TFS00E009YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 113 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
107 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3L | TFS00E009YS18 ¦ PO LINE NO. 107 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 114 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
110 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C4S | TFS00E009YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 115 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
114 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00E009YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 116 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
4 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.5IN | NO | 1 | 5ABS1 | TFS00E009YS18 ¦ PO LINE NO. 4 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217380 | 117 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
10 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5ABS1 | TFS00E009YS18 ¦ PO LINE NO. 10 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 118 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
49 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5ABS1 | TFS00E009YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 119 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
66 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00E009YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 120 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
1 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 0.25IN | NO | 1 | 5ABS2 | TFS00E009YS18 ¦ PO LINE NO. 1 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.25IN | 217380 | 121 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
67 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5ABS2 | TFS00E009YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 122 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
68 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 29 | 5ABS3 | TFS00E009YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 123 | Shipped | 29 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
123 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 5 | 5ABS3 | TFS00E009YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 124 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
159 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-L-1 | TFS00E009YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 125 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
90 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-2 | TFS00E009YS18 ¦ PO LINE NO. 90 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 126 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
162 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-M-5 | TFS00E009YS18 ¦ PO LINE NO. 162 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 127 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
188 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-M-5 | TFS00E009YS18 ¦ PO LINE NO. 188 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 128 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
94 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-M-8 | TFS00E009YS18 ¦ PO LINE NO. 94 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 129 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
74 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | YES | 111 | 5CC-02-01 | TFS00E009YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 130 | Shipped | 111 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
127 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | YES | 30 | 5CC-03-01 | TFS00E009YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 131 | Shipped | 30 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
155 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | YES | 13 | 5CC-04-01 | TFS00E009YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 132 | Shipped | 13 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
177 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5CC-06-01 | TFS00E009YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 133 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
104 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5ISC-02-01 | TFS00E009YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 134 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
102 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E009YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 135 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
166 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5IAC-04-01-M | TFS00E009YS18 ¦ PO LINE NO. 166 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 136 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
193 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5IAC-06-01-M | TFS00E009YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 137 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
106 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5RC1-02 | TFS00E010YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 138 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
23 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00E010YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 139 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
61 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5UG-01 | TFS00E010YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 140 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
119 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | YES | 54 | 5UG-02 | TFS00E010YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 141 | Shipped | 54 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
146 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | YES | 6 | 5UG-03 | TFS00E010YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 142 | Shipped | 6 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
170 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5UG-04 | TFS00E010YS18 ¦ PO LINE NO. 170 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 143 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
199 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | YES | 5 | 5UG-06 | TFS00E010YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 144 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
43 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5US-15 | TFS00E010YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 145 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
122 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 16 | 5US-02 | TFS00E010YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 146 | Shipped | 16 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
120 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | YES | 29 | 5UGSP-02-01 | TFS00E010YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 147 | Shipped | 29 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
148 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5UGSP-03-01 | TFS00E010YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 148 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
53 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00E010YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 149 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
32 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5C-15-01 | TFS00E010YS18 ¦ PO LINE NO. 32 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 150 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
16 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00E010YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217380 | 151 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
56 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1IN | NO | 5 | 5CI-01 | TFS00E010YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 152 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
35 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00E010YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217380 | 153 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
76 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 99 | 5CI-02 | TFS00E010YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 154 | Shipped | 99 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
128 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 18 | 5CI-03 | TFS00E010YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 155 | Shipped | 18 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
156 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | NO | 5 | 5CI-04 | TFS00E010YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217380 | 156 | Shipped | 5 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
178 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | NO | 9 | 5CI-06 | TFS00E010YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 157 | Shipped | 9 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
130 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5DA1-M | TFS00E010YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 158 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
179 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5DA1-M | TFS00E010YS18 ¦ PO LINE NO. 179 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 159 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
77 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00E010YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 160 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
95 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00E010YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 161 | Shipped | 4 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
96 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G2 | TFS00E010YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 162 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
97 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E010YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 163 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
116 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5SLM-1 | TFS00E010YS18 ¦ PO LINE NO. 116 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 164 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
108 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00E010YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 165 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
110 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C4S | TFS00E010YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 166 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
109 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4L | TFS00E010YS18 ¦ PO LINE NO. 109 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 167 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
114 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00E010YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 168 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
50 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5ABS2 | TFS00E010YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217380 | 169 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
67 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 11 | 5ABS2 | TFS00E010YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 170 | Shipped | 11 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
68 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 14 | 5ABS3 | TFS00E010YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 171 | Shipped | 14 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
123 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5ABS3 | TFS00E010YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 172 | Shipped | 3 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
173 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5ABS3 | TFS00E010YS18 ¦ PO LINE NO. 173 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 173 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
89 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-1 | TFS00E010YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 174 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
136 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00E010YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 175 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
184 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-L-1 | TFS00E010YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 176 | Shipped | 2 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
188 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-M-5 | TFS00E010YS18 ¦ PO LINE NO. 188 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217380 | 177 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04
75 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CH-02-15 | TFS00E010YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 178 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
74 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | YES | 59 | 5CC-02-01 | TFS00E010YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 179 | Shipped | 59 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
127 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | YES | 10 | 5CC-03-01 | TFS00E010YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217380 | 180 | Shipped | 10 | 0 | 2026-01-23 | 2026-01-05 | 2026-02-04
102 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E010YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 181 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-23 | 2026-02-04
101 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5HR4-05 | TFS00D003YS18 ¦ PO LINE NO. 101 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217380 | 182 | Shipped | 1 | 0 | 2026-01-23 | 2026-01-21 | 2026-02-04 | Jan-19-26: Reponse for RFI Received Dec-4-25: On HOLD Due To RFI No. 4
100 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5HR4-02 | TFS00D005YS18 ¦ PO LINE NO. 100 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 1 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
106 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5RC1-02 | TFS00D005YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 2 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
23 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5UG-75 | TFS00D005YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 3 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
41 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5UG-15 | TFS00D005YS18 ¦ PO LINE NO. 41 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217381 | 4 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
119 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 27 | 5UG-02 | TFS00D005YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 5 | Shipped | 27 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
28 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5US-75 | TFS00D005YS18 ¦ PO LINE NO. 28 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 6 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
43 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 3 | 5US-15 | TFS00D005YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217381 | 7 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
122 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5US-02 | TFS00D005YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 8 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
62 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | YES | 14 | 5UGSP-01-01 | TFS00D005YS18 ¦ PO LINE NO. 62 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 9 | Shipped | 14 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
120 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 18 | 5UGSP-02-01 | TFS00D005YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 10 | Shipped | 18 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
121 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5UGSP-02-15 | TFS00D005YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 11 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
148 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | YES | 18 | 5UGSP-03-01 | TFS00D005YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 12 | Shipped | 18 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
171 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 4IN | YES | 11 | 5UGSP-04-01 | TFS00D005YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 13 | Shipped | 11 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
200 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | YES | 30 | 5UGSP-06-01 | TFS00D005YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 14 | Shipped | 30 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
53 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | YES | 23 | 5C-01-01 | TFS00D005YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 15 | Shipped | 23 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
16 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 16 | 5CI-75 | TFS00D005YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 16 | Shipped | 16 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
56 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | NO | 8 | 5CI-01 | TFS00D005YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 17 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
35 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 4 | 5CI-15 | TFS00D005YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217381 | 18 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
76 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 85 | 5CI-02 | TFS00D005YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 19 | Shipped | 85 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
59 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5FS1S1 | TFS00D005YS18 ¦ PO LINE NO. 59 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 20 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
36 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 4 | 5FS1S1 | TFS00D005YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217381 | 21 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
81 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FS1S1 | TFS00D005YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 22 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
180 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5FS1S2 | TFS00D005YS18 ¦ PO LINE NO. 180 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 23 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04 |  | (2) shipped on 1/28/26 (1) shipped on 1/29/26
181 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS1-M-1-1 | TFS00D005YS18 ¦ PO LINE NO. 181 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 24 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
182 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS2-M-1 | TFS00D005YS18 ¦ PO LINE NO. 182 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 25 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
126 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BSG-2 | TFS00D005YS18 ¦ PO LINE NO. 126 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 26 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
77 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5DA3-C | TFS00D005YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 27 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
96 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G2 | TFS00D005YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 28 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
97 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00D005YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 29 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
190 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5G3-06 | TFS00D005YS18 ¦ PO LINE NO. 190 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 30 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
197 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5PU3 | TFS00D005YS18 ¦ PO LINE NO. 197 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 31 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
108 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 7 | 5S1C3S | TFS00D005YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 32 | Shipped | 7 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
107 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C3L | TFS00D005YS18 ¦ PO LINE NO. 107 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 33 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
110 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 7 | 5S1C4S | TFS00D005YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 34 | Shipped | 7 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
111 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5L | TFS00D005YS18 ¦ PO LINE NO. 111 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 35 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
49 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5ABS1 | TFS00D005YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 36 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
50 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | NO | 11 | 5ABS2 | TFS00D005YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 37 | Shipped | 11 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
67 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5ABS2 | TFS00D005YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 38 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
11 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 11 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 39 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
51 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 51 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 40 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
68 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 41 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
123 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | NO | 12 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 42 | Shipped | 12 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
150 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 43 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
173 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5ABS3 | TFS00D005YS18 ¦ PO LINE NO. 173 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 44 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
184 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 10 | 5FSS5-L-1 | TFS00D005YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 45 | Shipped | 10 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
160 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5FSS5-M-3 | TFS00D005YS18 ¦ PO LINE NO. 160 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 46 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
161 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5FSS5-M-4 | TFS00D005YS18 ¦ PO LINE NO. 161 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 47 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
86 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FSS5-H-6 | TFS00D005YS18 ¦ PO LINE NO. 86 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 48 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
75 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5CH-02-15 | TFS00D005YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 49 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
74 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 62 | 5CC-02-01 | TFS00D005YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 50 | Shipped | 62 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04 |  | (61) shipped on 1/23/2026 (1) shipped on 1/29/2026
127 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | YES | 43 | 5CC-03-01 | TFS00D005YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 51 | Shipped | 43 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04 |  | (40) shipped on 1/23/2026 (3) shipped on 1/29/2026
155 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 4IN | YES | 27 | 5CC-04-01 | TFS00D005YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 52 | Shipped | 27 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04 |  | (24) shipped on 1/23/2026 (3) shipped on 1/28/2026
177 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | YES | 68 | 5CC-06-01 | TFS00D005YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 53 | Shipped | 68 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04 |  | (48) shipped on 1/22/2026 (8) shipped on 1/29/2026 (12) shipped on 1/30/2026
196 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5ISC-06-01-L | TFS00D005YS18 ¦ PO LINE NO. 196 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 54 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
102 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00D005YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 55 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
141 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5IAC-03-01-M | TFS00D005YS18 ¦ PO LINE NO. 141 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 56 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
193 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5IAC-06-01-M | TFS00D005YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 57 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
100 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5HR4-02 | TFS00D006YS18 ¦ PO LINE NO. 100 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 58 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
61 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5UG-01 | TFS00D006YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 59 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
119 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | YES | 48 | 5UG-02 | TFS00D006YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 60 | Shipped | 48 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
146 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | YES | 9 | 5UG-03 | TFS00D006YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 61 | Shipped | 9 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
170 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5UG-04 | TFS00D006YS18 ¦ PO LINE NO. 170 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 62 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
199 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5UG-06 | TFS00D006YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 63 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
122 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 13 | 5US-02 | TFS00D006YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 64 | Shipped | 13 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
149 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5US-03 | TFS00D006YS18 ¦ PO LINE NO. 149 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 65 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
120 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5UGSP-02-01 | TFS00D006YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 66 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
121 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-15 | TFS00D006YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 67 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
53 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00D006YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 68 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
15 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5CI-0.75 | TFS00D006YS18 ¦ PO LINE NO. 15 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 69 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
16 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 0.75IN | NO | 3 | 5CI-75 | TFS00D006YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 70 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
56 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 1IN | NO | 6 | 5CI-01 | TFS00D006YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 71 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
35 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00D006YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217381 | 72 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
76 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 85 | 5CI-02 | TFS00D006YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 73 | Shipped | 85 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
128 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | NO | 23 | 5CI-03 | TFS00D006YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 74 | Shipped | 23 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
156 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5CI-04 | TFS00D006YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 75 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
178 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 10 | 5CI-06 | TFS00D006YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 76 | Shipped | 10 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
59 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5FS1S1 | TFS00D006YS18 ¦ PO LINE NO. 59 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 77 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
154 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSG-2 | TFS00D006YS18 ¦ PO LINE NO. 154 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 78 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
176 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5BSG-2 | TFS00D006YS18 ¦ PO LINE NO. 176 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 79 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
77 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5DA3-C | TFS00D006YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 80 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
189 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5G1-2 | TFS00D006YS18 ¦ PO LINE NO. 189 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 81 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
96 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G2 | TFS00D006YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 82 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
110 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5S1C4S | TFS00D006YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 83 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
66 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00D006YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 84 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
67 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5ABS2 | TFS00D006YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 85 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
68 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5ABS3 | TFS00D006YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 86 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
123 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | NO | 6 | 5ABS3 | TFS00D006YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 87 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
173 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5ABS3 | TFS00D006YS18 ¦ PO LINE NO. 173 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 88 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
159 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-L-1 | TFS00D006YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 89 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
184 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-L-1 | TFS00D006YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 90 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
75 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5CH-02-15 | TFS00D006YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 91 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
74 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 2IN | YES | 23 | 5CC-02-01 | TFS00D006YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 92 | Shipped | 23 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
23 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00D007YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 93 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
119 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | YES | 9 | 5UG-02 | TFS00D007YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 94 | Shipped | 9 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
146 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | YES | 2 | 5UG-03 | TFS00D007YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 95 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
65 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00D007YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 96 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
122 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5US-02 | TFS00D007YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 97 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
27 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-50 | TFS00D007YS18 ¦ PO LINE NO. 27 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 98 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
26 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5UGSP-75-15 | TFS00D007YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 99 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
64 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | YES | 6 | 5UGSP-01-50 | TFS00D007YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 100 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
63 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-15 | TFS00D007YS18 ¦ PO LINE NO. 63 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 101 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
120 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-01 | TFS00D007YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 102 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
148 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | YES | 5 | 5UGSP-03-01 | TFS00D007YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 103 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
171 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5UGSP-04-01 | TFS00D007YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 104 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
200 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5UGSP-06-01 | TFS00D007YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 105 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
14 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5C-75-50 | TFS00D007YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 106 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
13 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | YES | 11 | 5C-75-15 | TFS00D007YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 107 | Shipped | 11 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
55 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | YES | 6 | 5C-01-50 | TFS00D007YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 108 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
53 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00D007YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 109 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
54 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5C-01-15 | TFS00D007YS18 ¦ PO LINE NO. 54 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 110 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
29 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1.25IN | YES | 5 | 5C-11-01 | TFS00D007YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 217381 | 111 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
16 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00D007YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 112 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
56 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00D007YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 113 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
76 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 38 | 5CI-02 | TFS00D007YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 114 | Shipped | 38 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
128 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 10 | 5CI-03 | TFS00D007YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 115 | Shipped | 10 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
20 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5FS1S1 | TFS00D007YS18 ¦ PO LINE NO. 20 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 116 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
81 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00D007YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 117 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
130 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5DA1-M | TFS00D007YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 118 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
18 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5DA3-C | TFS00D007YS18 ¦ PO LINE NO. 18 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 119 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
22 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00D007YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 120 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
95 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G1-1 | TFS00D007YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 121 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
138 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5G1-1 | TFS00D007YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 122 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
96 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G2 | TFS00D007YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 123 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
97 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G3-02 | TFS00D007YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 124 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
105 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5PU1-1 | TFS00D007YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 125 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
108 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00D007YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 126 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
110 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4S | TFS00D007YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 127 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
114 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C6S | TFS00D007YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 128 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
10 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5ABS1 | TFS00D007YS18 ¦ PO LINE NO. 10 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217381 | 129 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
49 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00D007YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217381 | 130 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
68 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5ABS3 | TFS00D007YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 131 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
150 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5ABS3 | TFS00D007YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 132 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
136 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5FSS5-L-1 | TFS00D007YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 133 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
93 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-M-5 | TFS00D007YS18 ¦ PO LINE NO. 93 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 134 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
74 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | YES | 16 | 5CC-02-01 | TFS00D007YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 135 | Shipped | 16 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
127 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | YES | 7 | 5CC-03-01 | TFS00D007YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217381 | 136 | Shipped | 7 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
155 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5CC-04-01 | TFS00D007YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217381 | 137 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
177 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5CC-06-01 | TFS00D007YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 138 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
195 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5ISC-06-01 | TFS00D007YS18 ¦ PO LINE NO. 195 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 139 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
102 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5IAC-02-01-M | TFS00D007YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217381 | 140 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
192 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5IAC-06-01-D | TFS00D007YS18 ¦ PO LINE NO. 192 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217381 | 141 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
120 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UGSP-02-01 | TFS00E001YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 1 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
80 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00E001YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 2 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
81 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00E001YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 3 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
97 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E001YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 4 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
66 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00E001YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 5 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
74 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5CC-02-01 | TFS00E001YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 6 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
102 |  | TFS00E | 1 | TFS00E001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E001YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 7 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
191 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5HR1-06 | TFS00E003YS18 ¦ PO LINE NO. 191 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 8 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
23 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00E003YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217382 | 9 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
61 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5UG-01 | TFS00E003YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 10 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
119 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 38 | 5UG-02 | TFS00E003YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 11 | Shipped | 38 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
122 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5US-02 | TFS00E003YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 12 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
9 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.5IN | YES | 13 | 5UGSP-50-01 | TFS00E003YS18 ¦ PO LINE NO. 9 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217382 | 13 | Shipped | 13 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
42 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1.5IN | YES | 4 | 5UGSP-15-01 | TFS00E003YS18 ¦ PO LINE NO. 42 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217382 | 14 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 70 | 5UGSP-02-01 | TFS00E003YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 15 | Shipped | 70 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
6 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.5IN | YES | 31 | 5C-50-01 | TFS00E003YS18 ¦ PO LINE NO. 6 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217382 | 16 | Shipped | 31 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
53 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5C-01-01 | TFS00E003YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 17 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
32 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1.5IN | YES | 8 | 5C-15-01 | TFS00E003YS18 ¦ PO LINE NO. 32 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217382 | 18 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
16 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 5 | 5CI-75 | TFS00E003YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217382 | 19 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
56 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1IN | NO | 6 | 5CI-01 | TFS00E003YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 20 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
76 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 84 | 5CI-02 | TFS00E003YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 21 | Shipped | 84 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
20 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5FS1S1 | TFS00E003YS18 ¦ PO LINE NO. 20 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217382 | 22 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
36 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FS1S1 | TFS00E003YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217382 | 23 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
81 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 9 | 5FS1S1 | TFS00E003YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 24 | Shipped | 9 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
72 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5BSG-1 | TFS00E003YS18 ¦ PO LINE NO. 72 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 25 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
77 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5DA3-C | TFS00E003YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 26 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
78 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5DA3-M | TFS00E003YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 27 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
96 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5G2 | TFS00E003YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 28 | Shipped | 10 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
139 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5G2 | TFS00E003YS18 ¦ PO LINE NO. 139 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 29 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
97 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E003YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 30 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
98 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5GS2C | TFS00E003YS18 ¦ PO LINE NO. 98 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 31 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
115 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5SH-1 | TFS00E003YS18 ¦ PO LINE NO. 115 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 32 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
108 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5S1C3S | TFS00E003YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 33 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
110 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 9 | 5S1C4S | TFS00E003YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 34 | Shipped | 9 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
144 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5S1C4S | TFS00E003YS18 ¦ PO LINE NO. 144 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 35 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
198 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5S1C4S | TFS00E003YS18 ¦ PO LINE NO. 198 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 36 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
109 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4L | TFS00E003YS18 ¦ PO LINE NO. 109 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 37 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
112 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C5S | TFS00E003YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 38 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
114 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5S1C6S | TFS00E003YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 39 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
113 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6L | TFS00E003YS18 ¦ PO LINE NO. 113 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 40 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
49 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00E003YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 41 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
67 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS2 | TFS00E003YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 42 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
5 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 0.5IN | NO | 1 | 5ABS3 | TFS00E003YS18 ¦ PO LINE NO. 5 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217382 | 43 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
68 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS3 | TFS00E003YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 44 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-28 | 2026-02-04
89 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-1 | TFS00E003YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 45 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
92 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-5 | TFS00E003YS18 ¦ PO LINE NO. 92 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 46 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
93 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-M-5 | TFS00E003YS18 ¦ PO LINE NO. 93 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 47 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
75 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CH-02-15 | TFS00E003YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 48 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
74 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 140 | 5CC-02-01 | TFS00E003YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 49 | Shipped | 140 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
127 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 3IN | YES | 2 | 5CC-03-01 | TFS00E003YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 50 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
103 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5IGC-02-01 | TFS00E003YS18 ¦ PO LINE NO. 103 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 51 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
104 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5ISC-02-01 | TFS00E003YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 52 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5UGSP-02-01 | TFS00E004YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 53 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
80 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00E004YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 54 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
81 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00E004YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 55 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
97 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E004YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 56 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
66 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00E004YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 57 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
74 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | YES | 7 | 5CC-02-01 | TFS00E004YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 58 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
102 |  | TFS00E | 4 | TFS00E004YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E004YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 59 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
61 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1IN | YES | 4 | 5UG-01 | TFS00E005YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 60 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
119 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 27 | 5UG-02 | TFS00E005YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 61 | Shipped | 27 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
146 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | YES | 9 | 5UG-03 | TFS00E005YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 62 | Shipped | 9 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
199 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5UG-06 | TFS00E005YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 63 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
122 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 12 | 5US-02 | TFS00E005YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 64 | Shipped | 12 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 33 | 5UGSP-02-01 | TFS00E005YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 65 | Shipped | 33 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
121 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-15 | TFS00E005YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 66 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
148 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | YES | 7 | 5UGSP-03-01 | TFS00E005YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 67 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
200 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5UGSP-06-01 | TFS00E005YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 68 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
53 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00E005YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 69 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
33 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1.5IN | YES | 2 | 5C-15-15 | TFS00E005YS18 ¦ PO LINE NO. 33 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217382 | 70 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
16 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 5 | 5CI-75 | TFS00E005YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217382 | 71 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
56 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1IN | NO | 6 | 5CI-01 | TFS00E005YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 72 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
35 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00E005YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217382 | 73 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
76 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 70 | 5CI-02 | TFS00E005YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 74 | Shipped | 70 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
128 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 11 | 5CI-03 | TFS00E005YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 75 | Shipped | 11 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
156 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 4IN | NO | 8 | 5CI-04 | TFS00E005YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217382 | 76 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
178 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | NO | 4 | 5CI-06 | TFS00E005YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 77 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
81 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5FS1S1 | TFS00E005YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 78 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
132 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FS1S2 | TFS00E005YS18 ¦ PO LINE NO. 132 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 79 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
132 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FS1S2 | TFS00E005YS18 ¦ PO LINE NO. 132 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 79 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
179 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5DA1-M | TFS00E005YS18 ¦ PO LINE NO. 179 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 80 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
77 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5DA3-C | TFS00E005YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 81 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
78 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5DA3-M | TFS00E005YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 82 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
95 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G1-1 | TFS00E005YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 83 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
96 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G2 | TFS00E005YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 84 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
97 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E005YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 85 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
107 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3L | TFS00E005YS18 ¦ PO LINE NO. 107 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 86 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
110 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5S1C4S | TFS00E005YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 87 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
49 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5ABS1 | TFS00E005YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217382 | 88 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
66 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00E005YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 89 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
67 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 15 | 5ABS2 | TFS00E005YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 90 | Shipped | 15 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
68 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 17 | 5ABS3 | TFS00E005YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 91 | Shipped | 17 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
123 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5ABS3 | TFS00E005YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 92 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
89 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-1 | TFS00E005YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 93 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
136 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00E005YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 94 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
184 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-L-1 | TFS00E005YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 95 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
87 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-H-8 | TFS00E005YS18 ¦ PO LINE NO. 87 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 96 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
88 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FSS5-H-9 | TFS00E005YS18 ¦ PO LINE NO. 88 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 97 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04 |  | (1) shipped on 1/29/2026 (3) shipped on 1/31/2026
135 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5FSS5-H-9 | TFS00E005YS18 ¦ PO LINE NO. 135 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 98 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-29 | 2026-02-04
75 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00E005YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 99 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
74 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 78 | 5CC-02-01 | TFS00E005YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 100 | Shipped | 78 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (30) shipped on 1/23/2026 (38) shipped on 1/28/2026 (1) shipped on 2/3/2026
127 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | YES | 25 | 5CC-03-01 | TFS00E005YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 101 | Shipped | 25 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (17) shipped on 1/28/2026 (8) shipped on 2/3/2026
155 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 4IN | YES | 6 | 5CC-04-01 | TFS00E005YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217382 | 102 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
177 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 5 | 5CC-06-01 | TFS00E005YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 103 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (3) shipped on 1/28/2026 (2) shipped on 2/3/26
142 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5IGC-03-01-L | TFS00E005YS18 ¦ PO LINE NO. 142 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217382 | 104 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
194 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5IGC-06-01 | TFS00E005YS18 ¦ PO LINE NO. 194 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 105 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
195 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 4 | 5ISC-06-01 | TFS00E005YS18 ¦ PO LINE NO. 195 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 106 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
102 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E005YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217382 | 107 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
193 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5IAC-06-01-M | TFS00E005YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217382 | 108 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
106 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5RC1-02 | TFS00E011YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 1 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
61 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5UG-01 | TFS00E011YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 2 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
119 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 38 | 5UG-02 | TFS00E011YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 3 | Shipped | 38 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
146 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | YES | 10 | 5UG-03 | TFS00E011YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 4 | Shipped | 10 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
199 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5UG-06 | TFS00E011YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217383 | 5 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
122 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5US-02 | TFS00E011YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 6 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 24 | 5UGSP-02-01 | TFS00E011YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 7 | Shipped | 24 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
147 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5UGSP-02-01 | TFS00E011YS18 ¦ PO LINE NO. 147 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 8 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
121 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UGSP-02-15 | TFS00E011YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 9 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00E011YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 10 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
32 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5C-15-01 | TFS00E011YS18 ¦ PO LINE NO. 32 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217383 | 11 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
16 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 0.75IN | NO | 14 | 5CI-75 | TFS00E011YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 12 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
56 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1IN | NO | 5 | 5CI-01 | TFS00E011YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 13 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
35 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5CI-15 | TFS00E011YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217383 | 14 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
76 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 83 | 5CI-02 | TFS00E011YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 15 | Shipped | 83 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
128 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 22 | 5CI-03 | TFS00E011YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 16 | Shipped | 22 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
156 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5CI-04 | TFS00E011YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 17 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
178 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 6IN | NO | 4 | 5CI-06 | TFS00E011YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217383 | 18 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
81 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1S1 | TFS00E011YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 19 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
126 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BSG-2 | TFS00E011YS18 ¦ PO LINE NO. 126 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 20 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
130 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 4 | 5DA1-M | TFS00E011YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 21 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
179 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5DA1-M | TFS00E011YS18 ¦ PO LINE NO. 179 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217383 | 22 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
77 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00E011YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 23 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
78 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-M | TFS00E011YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 24 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
39 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5G1-1 | TFS00E011YS18 ¦ PO LINE NO. 39 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217383 | 25 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
138 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5G1-1 | TFS00E011YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 26 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
96 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G2 | TFS00E011YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 27 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
97 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5G3-02 | TFS00E011YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 28 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
165 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5G3-04 | TFS00E011YS18 ¦ PO LINE NO. 165 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 29 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
116 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5SLM-1 | TFS00E011YS18 ¦ PO LINE NO. 116 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 30 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
108 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C3S | TFS00E011YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 31 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
110 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5S1C4S | TFS00E011YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 32 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
49 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00E011YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 33 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
66 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00E011YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 34 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
67 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5ABS2 | TFS00E011YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 35 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5ABS3 | TFS00E011YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 36 | Shipped | 8 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
123 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5ABS3 | TFS00E011YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 37 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
89 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-1 | TFS00E011YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 38 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
136 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00E011YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 39 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
184 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-L-1 | TFS00E011YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217383 | 40 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
188 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-M-5 | TFS00E011YS18 ¦ PO LINE NO. 188 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217383 | 41 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5CH-02-15 | TFS00E011YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 42 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
74 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 60 | 5CC-02-01 | TFS00E011YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 43 | Shipped | 60 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
127 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | YES | 10 | 5CC-03-01 | TFS00E011YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 44 | Shipped | 10 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
155 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | YES | 4 | 5CC-04-01 | TFS00E011YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 45 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
104 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 4 | 5ISC-02-01 | TFS00E011YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 46 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
168 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5ISC-04-01 | TFS00E011YS18 ¦ PO LINE NO. 168 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 47 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5IAC-02-01-M | TFS00E011YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 48 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
141 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5IAC-03-01-M | TFS00E011YS18 ¦ PO LINE NO. 141 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 49 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UGSP-02-01 | TFS00E012YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 50 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
80 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00E012YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 51 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
81 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00E012YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 52 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
97 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E012YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 53 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
66 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00E012YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 54 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
74 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5CC-02-01 | TFS00E012YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 55 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00E | 12 | TFS00E012YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E012YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 56 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
119 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UG-02 | TFS00E014YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 57 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
146 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 3IN | YES | 5 | 5UG-03 | TFS00E014YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 58 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
170 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | YES | 4 | 5UG-04 | TFS00E014YS18 ¦ PO LINE NO. 170 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 59 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
64 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 1IN | YES | 5 | 5UGSP-01-50 | TFS00E014YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 60 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
6 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 0.5IN | YES | 3 | 5C-50-01 | TFS00E014YS18 ¦ PO LINE NO. 6 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217383 | 61 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
55 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 1IN | YES | 5 | 5C-01-50 | TFS00E014YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 62 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
76 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5CI-02 | TFS00E014YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 63 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
128 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 3IN | NO | 12 | 5CI-03 | TFS00E014YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 64 | Shipped | 12 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
156 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | NO | 6 | 5CI-04 | TFS00E014YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 65 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
157 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5DA1-M | TFS00E014YS18 ¦ PO LINE NO. 157 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 66 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
5 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 0.5IN | NO | 2 | 5ABS3 | TFS00E014YS18 ¦ PO LINE NO. 5 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.5IN | 217383 | 67 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5ABS3 | TFS00E014YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 68 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
123 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 3IN | NO | 4 | 5ABS3 | TFS00E014YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 69 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
150 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5ABS3 | TFS00E014YS18 ¦ PO LINE NO. 150 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 70 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
89 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FSS5-L-1 | TFS00E014YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 71 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
159 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5FSS5-L-1 | TFS00E014YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 72 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
74 |  | TFS00E | 14 | TFS00E014YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CC-02-01 | TFS00E014YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 73 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
119 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 14 | 5UG-02 | TFS00E015YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 74 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
65 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00E015YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 75 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
122 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5US-02 | TFS00E015YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 76 | Shipped | 10 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
26 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-15 | TFS00E015YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 77 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
64 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5UGSP-01-50 | TFS00E015YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 78 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 14 | 5UGSP-02-01 | TFS00E015YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 79 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
121 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5UGSP-02-15 | TFS00E015YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 80 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
148 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 3IN | YES | 2 | 5UGSP-03-01 | TFS00E015YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 81 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
171 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5UGSP-04-01 | TFS00E015YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 82 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
14 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5C-75-50 | TFS00E015YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 83 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
12 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5C-75-01 | TFS00E015YS18 ¦ PO LINE NO. 12 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 84 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
13 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5C-75-15 | TFS00E015YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 85 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
55 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5C-01-50 | TFS00E015YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 86 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
53 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5C-01-01 | TFS00E015YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 87 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
29 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1.25IN | YES | 4 | 5C-11-01 | TFS00E015YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 217383 | 88 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
16 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00E015YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 89 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
56 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00E015YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 90 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
76 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 58 | 5CI-02 | TFS00E015YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 91 | Shipped | 58 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
81 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1S1 | TFS00E015YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 92 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
77 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5DA3-C | TFS00E015YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 93 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
78 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5DA3-M | TFS00E015YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 94 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
22 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00E015YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 95 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
95 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5G1-1 | TFS00E015YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 96 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
96 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G2 | TFS00E015YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 97 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
97 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E015YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 98 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
105 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5PU1-1 | TFS00E015YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 99 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
108 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00E015YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 100 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
110 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C4S | TFS00E015YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 101 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
114 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C6S | TFS00E015YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 102 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
49 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00E015YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 103 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
66 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00E015YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 104 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS3 | TFS00E015YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 105 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
89 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-1 | TFS00E015YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 106 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00E015YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 107 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 38 | 5CC-02-01 | TFS00E015YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 108 | Shipped | 38 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (30) shipped on 1/30/2026 (8) shipped on 2/3/2026
127 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 3IN | YES | 8 | 5CC-03-01 | TFS00E015YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 109 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
155 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5CC-04-01 | TFS00E015YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217383 | 110 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
103 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5IGC-02-01 | TFS00E015YS18 ¦ PO LINE NO. 103 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 111 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
102 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5IAC-02-01-M | TFS00E015YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 112 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
119 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 24 | 5UG-02 | TFS00E016YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 113 | Shipped | 24 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
146 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | YES | 8 | 5UG-03 | TFS00E016YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 114 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
65 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5US-01 | TFS00E016YS18 ¦ PO LINE NO. 65 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 115 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
122 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5US-02 | TFS00E016YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 116 | Shipped | 10 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
149 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5US-03 | TFS00E016YS18 ¦ PO LINE NO. 149 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 117 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
27 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-50 | TFS00E016YS18 ¦ PO LINE NO. 27 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 118 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
26 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-75-15 | TFS00E016YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 119 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
64 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00E016YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 120 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
120 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5UGSP-02-01 | TFS00E016YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 121 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
121 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5UGSP-02-15 | TFS00E016YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 122 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
148 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | YES | 4 | 5UGSP-03-01 | TFS00E016YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 123 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
14 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | YES | 2 | 5C-75-50 | TFS00E016YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 124 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
13 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | YES | 3 | 5C-75-15 | TFS00E016YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 125 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00E016YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 126 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00E016YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 127 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
29 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1.25IN | YES | 4 | 5C-11-01 | TFS00E016YS18 ¦ PO LINE NO. 29 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.25IN | 217383 | 128 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
32 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1.5IN | YES | 1 | 5C-15-01 | TFS00E016YS18 ¦ PO LINE NO. 32 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217383 | 129 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
16 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00E016YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 130 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
56 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00E016YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 131 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 68 | 5CI-02 | TFS00E016YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 132 | Shipped | 68 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
128 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | NO | 33 | 5CI-03 | TFS00E016YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 133 | Shipped | 33 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
19 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5FS1C1 | TFS00E016YS18 ¦ PO LINE NO. 19 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 134 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
81 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00E016YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 135 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
85 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS3-M-1-2 | TFS00E016YS18 ¦ PO LINE NO. 85 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 136 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
130 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | NO | 5 | 5DA1-M | TFS00E016YS18 ¦ PO LINE NO. 130 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 137 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
18 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5DA3-C | TFS00E016YS18 ¦ PO LINE NO. 18 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 138 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
77 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5DA3-C | TFS00E016YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 139 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
78 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5DA3-M | TFS00E016YS18 ¦ PO LINE NO. 78 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 140 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
22 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5G1-1 | TFS00E016YS18 ¦ PO LINE NO. 22 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217383 | 141 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
95 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00E016YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 142 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
138 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5G1-1 | TFS00E016YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 143 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
96 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G2 | TFS00E016YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 144 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
97 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00E016YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 145 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
105 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5PU1-1 | TFS00E016YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 146 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
108 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C3S | TFS00E016YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 147 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
110 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C4S | TFS00E016YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 148 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
112 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5S | TFS00E016YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 149 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
114 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C6S | TFS00E016YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 150 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
49 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS1 | TFS00E016YS18 ¦ PO LINE NO. 49 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217383 | 151 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
67 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS2 | TFS00E016YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 152 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5ABS3 | TFS00E016YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 153 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
136 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5FSS5-L-1 | TFS00E016YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 154 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
93 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-M-5 | TFS00E016YS18 ¦ PO LINE NO. 93 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 155 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CH-02-15 | TFS00E016YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 156 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 23 | 5CC-02-01 | TFS00E016YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 157 | Shipped | 23 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
127 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 3IN | YES | 12 | 5CC-03-01 | TFS00E016YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217383 | 158 | Shipped | 12 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
102 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00E016YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217383 | 159 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
106 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5RC1-02 | TFS00I004YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 1 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
23 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00I004YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 2 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
61 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5UG-01 | TFS00I004YS18 ¦ PO LINE NO. 61 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 3 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
119 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 30 | 5UG-02 | TFS00I004YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 4 | Shipped | 30 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
146 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 3IN | YES | 2 | 5UG-03 | TFS00I004YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 5 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
199 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5UG-06 | TFS00I004YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 6 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
43 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5US-15 | TFS00I004YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 7 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
122 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5US-02 | TFS00I004YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 8 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
62 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5UGSP-01-01 | TFS00I004YS18 ¦ PO LINE NO. 62 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 9 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 22 | 5UGSP-02-01 | TFS00I004YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 10 | Shipped | 22 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
121 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5UGSP-02-15 | TFS00I004YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 11 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00I004YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 12 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
16 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 0.75IN | NO | 3 | 5CI-75 | TFS00I004YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 13 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
56 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5CI-01 | TFS00I004YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 14 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
35 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00I004YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 15 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 58 | 5CI-02 | TFS00I004YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 16 | Shipped | 58 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
128 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 3IN | NO | 4 | 5CI-03 | TFS00I004YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 17 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
156 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5CI-04 | TFS00I004YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 18 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
178 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5CI-06 | TFS00I004YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 19 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
36 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FS1S1 | TFS00I004YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 20 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
81 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5FS1S1 | TFS00I004YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 21 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
179 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5DA1-M | TFS00I004YS18 ¦ PO LINE NO. 179 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 22 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
77 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5DA3-C | TFS00I004YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 23 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
95 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G1-1 | TFS00I004YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 24 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
189 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5G1-2 | TFS00I004YS18 ¦ PO LINE NO. 189 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 25 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
96 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5G2 | TFS00I004YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 26 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
97 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G3-02 | TFS00I004YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 27 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
116 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5SLM-1 | TFS00I004YS18 ¦ PO LINE NO. 116 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 28 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
108 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5S1C3S | TFS00I004YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 29 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
110 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4S | TFS00I004YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 30 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
112 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C5S | TFS00I004YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 31 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
10 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5ABS1 | TFS00I004YS18 ¦ PO LINE NO. 10 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 32 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
50 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS2 | TFS00I004YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 33 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
67 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5ABS2 | TFS00I004YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 34 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5ABS3 | TFS00I004YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 35 | Shipped | 6 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
89 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-1 | TFS00I004YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 36 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
136 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5FSS5-L-1 | TFS00I004YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 37 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
186 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-M-1 | TFS00I004YS18 ¦ PO LINE NO. 186 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 38 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
93 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-M-5 | TFS00I004YS18 ¦ PO LINE NO. 93 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 39 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00I004YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 40 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
74 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 55 | 5CC-02-01 | TFS00I004YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 41 | Shipped | 55 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04 |  | (25) shipped on 1/30/2026 (30) shipped on 1/31/2026
102 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5IAC-02-01-M | TFS00I004YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 42 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-30 | 2026-02-04
106 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5RC1-02 | TFS00I005YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 43 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
23 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UG-75 | TFS00I005YS18 ¦ PO LINE NO. 23 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 44 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
119 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 14 | 5UG-02 | TFS00I005YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 45 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
43 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5US-15 | TFS00I005YS18 ¦ PO LINE NO. 43 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 46 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
122 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5US-02 | TFS00I005YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 47 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 24 | 5UGSP-02-01 | TFS00I005YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 48 | Shipped | 24 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
121 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-15 | TFS00I005YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 49 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
171 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5UGSP-04-01 | TFS00I005YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 50 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-01 | TFS00I005YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 51 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
16 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 3 | 5CI-75 | TFS00I005YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 52 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
56 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5CI-01 | TFS00I005YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 53 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
35 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00I005YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 54 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 37 | 5CI-02 | TFS00I005YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 55 | Shipped | 37 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
20 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5FS1S1 | TFS00I005YS18 ¦ PO LINE NO. 20 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 56 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
36 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5FS1S1 | TFS00I005YS18 ¦ PO LINE NO. 36 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 57 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
81 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00I005YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 58 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
126 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BSG-2 | TFS00I005YS18 ¦ PO LINE NO. 126 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 59 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
77 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5DA3-C | TFS00I005YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 60 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
95 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5G1-1 | TFS00I005YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 61 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
96 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G2 | TFS00I005YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 62 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
97 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G3-02 | TFS00I005YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 63 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
165 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5G3-04 | TFS00I005YS18 ¦ PO LINE NO. 165 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 64 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
116 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5SLM-1 | TFS00I005YS18 ¦ PO LINE NO. 116 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 65 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
108 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5S1C3S | TFS00I005YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 66 | Shipped | 3 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
110 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C4S | TFS00I005YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 67 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
112 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C5S | TFS00I005YS18 ¦ PO LINE NO. 112 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 68 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
114 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5S1C6S | TFS00I005YS18 ¦ PO LINE NO. 114 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 69 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
50 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5ABS2 | TFS00I005YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 70 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
67 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS2 | TFS00I005YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 71 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
68 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5ABS3 | TFS00I005YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 72 | Shipped | 5 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
89 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FSS5-L-1 | TFS00I005YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 73 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
159 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5FSS5-L-1 | TFS00I005YS18 ¦ PO LINE NO. 159 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 74 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00I005YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 75 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
74 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 50 | 5CC-02-01 | TFS00I005YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 76 | Shipped | 50 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (30) shipped on 1/30/2026 (20) shipped on 2/3/2026
127 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5CC-03-01 | TFS00I005YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 77 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
155 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5CC-04-01 | TFS00I005YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 78 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
103 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IGC-02-01 | TFS00I005YS18 ¦ PO LINE NO. 103 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 79 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
167 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5IGC-04-01 | TFS00I005YS18 ¦ PO LINE NO. 167 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 80 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
104 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5ISC-02-01 | TFS00I005YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 81 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
168 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5ISC-04-01 | TFS00I005YS18 ¦ PO LINE NO. 168 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 82 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5IAC-02-01-M | TFS00I005YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 83 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
166 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5IAC-04-01-M | TFS00I005YS18 ¦ PO LINE NO. 166 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 84 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | YES | 3 | 5UGSP-02-01 | TFS00I006YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 85 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
80 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00I006YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 86 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
81 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00I006YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 87 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
97 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00I006YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 88 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
66 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00I006YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 89 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
74 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | YES | 8 | 5CC-02-01 | TFS00I006YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 90 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00I | 6 | TFS00I006YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00I006YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 91 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
106 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5RC1-02 | TFS00I007YS18 ¦ PO LINE NO. 106 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 92 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
119 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | YES | 63 | 5UG-02 | TFS00I007YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 93 | Shipped | 63 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
146 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5UG-03 | TFS00I007YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 94 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
199 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | YES | 3 | 5UG-06 | TFS00I007YS18 ¦ PO LINE NO. 199 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 95 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
122 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 25 | 5US-02 | TFS00I007YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 96 | Shipped | 25 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | YES | 39 | 5UGSP-02-01 | TFS00I007YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 97 | Shipped | 39 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
121 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5UGSP-02-15 | TFS00I007YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 98 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
148 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | YES | 4 | 5UGSP-03-01 | TFS00I007YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 99 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
171 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5UGSP-04-01 | TFS00I007YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 100 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
200 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5UGSP-06-01 | TFS00I007YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 101 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00I007YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 102 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
16 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00I007YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 103 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
56 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 1IN | NO | 6 | 5CI-01 | TFS00I007YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 104 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
35 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00I007YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 105 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 144 | 5CI-02 | TFS00I007YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 106 | Shipped | 144 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
128 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | NO | 7 | 5CI-03 | TFS00I007YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 107 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
156 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 4IN | NO | 6 | 5CI-04 | TFS00I007YS18 ¦ PO LINE NO. 156 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 108 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
178 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 6 | 5CI-06 | TFS00I007YS18 ¦ PO LINE NO. 178 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 109 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
81 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5FS1S1 | TFS00I007YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 110 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
179 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5DA1-M | TFS00I007YS18 ¦ PO LINE NO. 179 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 111 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
77 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5DA3-C | TFS00I007YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 112 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
95 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00I007YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 113 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
189 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 3 | 5G1-2 | TFS00I007YS18 ¦ PO LINE NO. 189 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 114 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
96 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G2 | TFS00I007YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 115 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
116 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5SLM-1 | TFS00I007YS18 ¦ PO LINE NO. 116 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 116 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
108 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5S1C3S | TFS00I007YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 117 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
110 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5S1C4S | TFS00I007YS18 ¦ PO LINE NO. 110 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 118 | Shipped | 2 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
66 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00I007YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 119 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
50 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5ABS2 | TFS00I007YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 120 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
67 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 7 | 5ABS2 | TFS00I007YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 121 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
68 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 23 | 5ABS3 | TFS00I007YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 122 | Shipped | 23 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (4) shipped on 1/31/2026 (19) shipped on 2/3/2026
123 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5ABS3 | TFS00I007YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 123 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
89 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5FSS5-L-1 | TFS00I007YS18 ¦ PO LINE NO. 89 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 124 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
136 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | NO | 4 | 5FSS5-L-1 | TFS00I007YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 125 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
184 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5FSS5-L-1 | TFS00I007YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 126 | Shipped | 1 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
186 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 4 | 5FSS5-M-1 | TFS00I007YS18 ¦ PO LINE NO. 186 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 127 | Shipped | 4 | 0 | 2026-02-04 | 2026-01-31 | 2026-02-04
75 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5CH-02-15 | TFS00I007YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 128 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 2IN | YES | 81 | 5CC-02-01 | TFS00I007YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 129 | Shipped | 81 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04 |  | (30) shipped on 1/30/2026 (30) shipped on 1/31/2026 (21) shipped on 2/3/2026
127 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | YES | 7 | 5CC-03-01 | TFS00I007YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 130 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
155 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 4IN | YES | 1 | 5CC-04-01 | TFS00I007YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 131 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
177 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5CC-06-01 | TFS00I007YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 132 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
142 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5IGC-03-01-L | TFS00I007YS18 ¦ PO LINE NO. 142 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 133 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
193 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | YES | 1 | 5IAC-06-01-M | TFS00I007YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 134 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
119 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | YES | 14 | 5UG-02 | TFS00I008YS18 ¦ PO LINE NO. 119 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 135 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
122 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 6 | 5US-02 | TFS00I008YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 136 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | YES | 46 | 5UGSP-02-01 | TFS00I008YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 137 | Shipped | 46 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
121 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5UGSP-02-15 | TFS00I008YS18 ¦ PO LINE NO. 121 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 138 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
148 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | YES | 8 | 5UGSP-03-01 | TFS00I008YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 139 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
171 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5UGSP-04-01 | TFS00I008YS18 ¦ PO LINE NO. 171 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 140 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
200 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5UGSP-06-01 | TFS00I008YS18 ¦ PO LINE NO. 200 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 141 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
53 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 1IN | YES | 1 | 5C-01-01 | TFS00I008YS18 ¦ PO LINE NO. 53 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 142 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
16 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 0.75IN | NO | 4 | 5CI-75 | TFS00I008YS18 ¦ PO LINE NO. 16 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217384 | 143 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
56 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 1IN | NO | 4 | 5CI-01 | TFS00I008YS18 ¦ PO LINE NO. 56 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 144 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
35 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5CI-15 | TFS00I008YS18 ¦ PO LINE NO. 35 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 217384 | 145 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 34 | 5CI-02 | TFS00I008YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 146 | Shipped | 34 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
77 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5DA3-C | TFS00I008YS18 ¦ PO LINE NO. 77 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 147 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
95 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G1-1 | TFS00I008YS18 ¦ PO LINE NO. 95 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 148 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
96 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 4 | 5G2 | TFS00I008YS18 ¦ PO LINE NO. 96 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 149 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
108 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 5 | 5S1C3S | TFS00I008YS18 ¦ PO LINE NO. 108 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 150 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
66 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS1 | TFS00I008YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 151 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
50 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5ABS2 | TFS00I008YS18 ¦ PO LINE NO. 50 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217384 | 152 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
67 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5ABS2 | TFS00I008YS18 ¦ PO LINE NO. 67 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 153 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
68 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | NO | 10 | 5ABS3 | TFS00I008YS18 ¦ PO LINE NO. 68 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 154 | Shipped | 10 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
123 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5ABS3 | TFS00I008YS18 ¦ PO LINE NO. 123 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 155 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
136 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | NO | 6 | 5FSS5-L-1 | TFS00I008YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 156 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
184 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-L-1 | TFS00I008YS18 ¦ PO LINE NO. 184 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 157 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
186 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5FSS5-M-1 | TFS00I008YS18 ¦ PO LINE NO. 186 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 158 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-03 | 2026-02-04
75 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5CH-02-15 | TFS00I008YS18 ¦ PO LINE NO. 75 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 159 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 2IN | YES | 89 | 5CC-02-01 | TFS00I008YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217384 | 160 | Shipped | 89 | 0 | 2026-02-04 | 2026-01-23 | 2026-02-04
127 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | YES | 22 | 5CC-03-01 | TFS00I008YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 161 | Shipped | 22 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
155 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 4IN | YES | 2 | 5CC-04-01 | TFS00I008YS18 ¦ PO LINE NO. 155 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 217384 | 162 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
177 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | YES | 4 | 5CC-06-01 | TFS00I008YS18 ¦ PO LINE NO. 177 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 163 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
143 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 3IN | YES | 2 | 5ISC-03-01-L | TFS00I008YS18 ¦ PO LINE NO. 143 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217384 | 164 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
193 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | YES | 2 | 5IAC-06-01-M | TFS00I008YS18 ¦ PO LINE NO. 193 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 217384 | 165 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5UGSP-01-50 | TFS00B001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 1 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
148 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 3IN | YES | 1 | 5UGSP-03-01 | TFS00B001YS18 ¦ PO LINE NO. 148 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 2 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 1IN | YES | 3 | 5C-01-50 | TFS00B001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 3 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
128 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5CI-03 | TFS00B001YS18 ¦ PO LINE NO. 128 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 4 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
59 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5FS1S1 | TFS00B001YS18 ¦ PO LINE NO. 59 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 5 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
127 |  | TFS00B | 1 | TFS00B001YS18 | TFS Mechanical | TFS | 3IN | YES | 3 | 5CC-03-01 | TFS00B001YS18 ¦ PO LINE NO. 127 ¦ CWA TFS00B ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 6 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00F | 1 | TFS00F001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00F001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00F ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 7 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00F | 1 | TFS00F001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00F001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00F ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 8 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00J | 1 | TFS00J001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00J001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00J ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 9 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
63 |  | TFS00J | 1 | TFS00J001YS18 | TFS Mechanical | TFS | 1IN | YES | 5 | 5UGSP-01-15 | TFS00J001YS18 ¦ PO LINE NO. 63 ¦ CWA TFS00J ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 10 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00J | 1 | TFS00J001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00J001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00J ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 11 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
54 |  | TFS00J | 1 | TFS00J001YS18 | TFS Mechanical | TFS | 1IN | YES | 14 | 5C-01-15 | TFS00J001YS18 ¦ PO LINE NO. 54 ¦ CWA TFS00J ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 12 | Shipped | 14 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
57 |  | TFS00J | 1 | TFS00J001YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5DA3-C | TFS00J001YS18 ¦ PO LINE NO. 57 ¦ CWA TFS00J ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 13 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00K | 1 | TFS00K001YS18 | TFS Mechanical | TFS | 1IN | YES | 12 | 5UGSP-01-50 | TFS00K001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00K ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 14 | Shipped | 12 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
63 |  | TFS00K | 1 | TFS00K001YS18 | TFS Mechanical | TFS | 1IN | YES | 28 | 5UGSP-01-15 | TFS00K001YS18 ¦ PO LINE NO. 63 ¦ CWA TFS00K ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 15 | Shipped | 28 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00K | 1 | TFS00K001YS18 | TFS Mechanical | TFS | 1IN | YES | 12 | 5C-01-50 | TFS00K001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00K ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 16 | Shipped | 12 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
54 |  | TFS00K | 1 | TFS00K001YS18 | TFS Mechanical | TFS | 1IN | YES | 72 | 5C-01-15 | TFS00K001YS18 ¦ PO LINE NO. 54 ¦ CWA TFS00K ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 17 | Shipped | 72 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
57 |  | TFS00K | 1 | TFS00K001YS18 | TFS Mechanical | TFS | 1IN | NO | 12 | 5DA3-C | TFS00K001YS18 ¦ PO LINE NO. 57 ¦ CWA TFS00K ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 18 | Shipped | 12 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
27 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 4 | 5UGSP-75-50 | TFS00L001YS18 ¦ PO LINE NO. 27 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 19 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
26 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 13 | 5UGSP-75-15 | TFS00L001YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 20 | Shipped | 13 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | YES | 6 | 5UGSP-02-01 | TFS00L001YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 21 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
14 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 4 | 5C-75-50 | TFS00L001YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 22 | Shipped | 4 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
13 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 31 | 5C-75-15 | TFS00L001YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 23 | Shipped | 31 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
19 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5FS1C1 | TFS00L001YS18 ¦ PO LINE NO. 19 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 24 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
80 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00L001YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 25 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
21 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 1 | 5FS3C | TFS00L001YS18 ¦ PO LINE NO. 21 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 26 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
18 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 7 | 5DA3-C | TFS00L001YS18 ¦ PO LINE NO. 18 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 27 | Shipped | 7 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
97 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | NO | 3 | 5G3-02 | TFS00L001YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 28 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
66 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00L001YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 29 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | YES | 11 | 5CC-02-01 | TFS00L001YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 30 | Shipped | 11 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
104 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5ISC-02-01 | TFS00L001YS18 ¦ PO LINE NO. 104 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 31 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00L | 1 | TFS00L001YS18 | TFS Mechanical | TFS | 2IN | YES | 2 | 5IAC-02-01-M | TFS00L001YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00L ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 32 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
122 |  | TFS00R | 1 | TFS00R001YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5US-02 | TFS00R001YS18 ¦ PO LINE NO. 122 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 33 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00R | 1 | TFS00R001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00R001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 34 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00R | 1 | TFS00R001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00R001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 35 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
76 |  | TFS00R | 1 | TFS00R001YS18 | TFS Mechanical | TFS | 2IN | NO | 8 | 5CI-02 | TFS00R001YS18 ¦ PO LINE NO. 76 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 36 | Shipped | 8 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
105 |  | TFS00R | 1 | TFS00R001YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5PU1-1 | TFS00R001YS18 ¦ PO LINE NO. 105 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 37 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
120 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | YES | 5 | 5UGSP-02-01 | TFS00R002YS18 ¦ PO LINE NO. 120 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 38 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
80 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1C1 | TFS00R002YS18 ¦ PO LINE NO. 80 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 39 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
81 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5FS1S1 | TFS00R002YS18 ¦ PO LINE NO. 81 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 40 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
97 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5G3-02 | TFS00R002YS18 ¦ PO LINE NO. 97 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 41 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
66 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5ABS1 | TFS00R002YS18 ¦ PO LINE NO. 66 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 42 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
74 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | YES | 9 | 5CC-02-01 | TFS00R002YS18 ¦ PO LINE NO. 74 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 43 | Shipped | 9 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
102 |  | TFS00R | 2 | TFS00R002YS18 | TFS Mechanical | TFS | 2IN | YES | 1 | 5IAC-02-01-M | TFS00R002YS18 ¦ PO LINE NO. 102 ¦ CWA TFS00R ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 217385 | 44 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
64 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5UGSP-01-50 | TFS00S001YS18 ¦ PO LINE NO. 64 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 45 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
63 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | YES | 5 | 5UGSP-01-15 | TFS00S001YS18 ¦ PO LINE NO. 63 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 46 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
55 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | YES | 2 | 5C-01-50 | TFS00S001YS18 ¦ PO LINE NO. 55 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 47 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
54 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | YES | 15 | 5C-01-15 | TFS00S001YS18 ¦ PO LINE NO. 54 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 48 | Shipped | 15 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
58 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | NO | 2 | 5FS1C1 | TFS00S001YS18 ¦ PO LINE NO. 58 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 49 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
57 |  | TFS00S | 1 | TFS00S001YS18 | TFS Mechanical | TFS | 1IN | NO | 3 | 5DA3-C | TFS00S001YS18 ¦ PO LINE NO. 57 ¦ CWA TFS00S ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 217385 | 50 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
140 |  | TFS00T | 1 | TFS00T001YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5HR4-03 | TFS00T001YS18 ¦ PO LINE NO. 140 ¦ CWA TFS00T ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 51 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
146 |  | TFS00T | 1 | TFS00T001YS18 | TFS Mechanical | TFS | 3IN | YES | 11 | 5UG-03 | TFS00T001YS18 ¦ PO LINE NO. 146 ¦ CWA TFS00T ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 52 | Shipped | 11 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
129 |  | TFS00T | 1 | TFS00T001YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5DA1-C | TFS00T001YS18 ¦ PO LINE NO. 129 ¦ CWA TFS00T ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 53 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
138 |  | TFS00T | 1 | TFS00T001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5G1-1 | TFS00T001YS18 ¦ PO LINE NO. 138 ¦ CWA TFS00T ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 54 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
27 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 5 | 5UGSP-75-50 | TFS00W001YS18 ¦ PO LINE NO. 27 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 55 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
26 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 15 | 5UGSP-75-15 | TFS00W001YS18 ¦ PO LINE NO. 26 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 56 | Shipped | 15 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
24 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 1 | 5UGSP-01-50 | TFS00W001YS18 ¦ PO LINE NO. 24 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 57 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
14 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 6 | 5C-75-50 | TFS00W001YS18 ¦ PO LINE NO. 14 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 58 | Shipped | 6 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
13 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | YES | 30 | 5C-75-15 | TFS00W001YS18 ¦ PO LINE NO. 13 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 59 | Shipped | 30 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
19 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 3 | 5FS1C1 | TFS00W001YS18 ¦ PO LINE NO. 19 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 60 | Shipped | 3 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
18 |  | TFS00W | 1 | TFS00W001YS18 | TFS Mechanical | TFS | 0.75IN | NO | 2 | 5DA3-C | TFS00W001YS18 ¦ PO LINE NO. 18 ¦ CWA TFS00W ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 0.75IN | 217385 | 61 | Shipped | 2 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
129 |  | TFS00X | 1 | TFS00X001YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5DA1-C | TFS00X001YS18 ¦ PO LINE NO. 129 ¦ CWA TFS00X ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 62 | Shipped | 1 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
136 |  | TFS00X | 1 | TFS00X001YS18 | TFS Mechanical | TFS | 3IN | NO | 5 | 5FSS5-L-1 | TFS00X001YS18 ¦ PO LINE NO. 136 ¦ CWA TFS00X ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 217385 | 63 | Shipped | 5 | 0 | 2026-02-04 | 2026-02-04 | 2026-02-04
52 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1IN | NO | 1 | 5BS1 | TFS00E015YS18 ¦ PO LINE NO. 52 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1IN | 218889 | 1 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BS1 | TFS00E007YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 2 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BS1 | TFS00I005YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 3 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 7 | 5BS1 | TFS00E003YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 4 | In PT&P Engineering /Waitn RFI Reponse |  | 7 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 2IN | NO | 2 | 5BS1 | TFS00E006YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 5 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BS1 | TFS00E016YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 6 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
70 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BS1 | TFS00E011YS18 ¦ PO LINE NO. 70 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 7 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00I005YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 8 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00D003YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 9 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00I004YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 10 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00D007YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 11 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5BS2 | TFS00D005YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 12 | In PT&P Engineering /Waitn RFI Reponse |  | 3 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00D002YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 13 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5BS2 | TFS00E011YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 14 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00E010YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 15 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 3IN | NO | 4 | 5BS2 | TFS00D006YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 16 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
124 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BS2 | TFS00E009YS18 ¦ PO LINE NO. 124 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 17 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
152 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BS2 | TFS00D003YS18 ¦ PO LINE NO. 152 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 18 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
152 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5BS2 | TFS00D007YS18 ¦ PO LINE NO. 152 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 19 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
174 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5BS2 | TFS00D006YS18 ¦ PO LINE NO. 174 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 20 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 3 | 5BSA1 | TFS00E007YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 21 | In PT&P Engineering /Waitn RFI Reponse |  | 3 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 1.5IN | NO | 11 | 5BSA1 | TFS00I003YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 22 | In PT&P Engineering /Waitn RFI Reponse |  | 11 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 2 | TFS00I | 1 | TFS00I001YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5BSA1 | TFS00I001YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 23 | In PT&P Engineering /Waitn RFI Reponse | 0 | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 1 | TFS00D | 1 | TFS00D001YS18 | TFS Mechanical | TFS | 1.5IN | NO | 4 | 5BSA1 | TFS00D001YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 24 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 1.5IN | NO | 7 | 5BSA1 | TFS00E016YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 25 | In PT&P Engineering /Waitn RFI Reponse |  | 7 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5BSA1 | TFS00E015YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 26 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 |  | TFS00D | 7 | TFS00D007YS18 | TFS Mechanical | TFS | 1.5IN | NO | 2 | 5BSA1 | TFS00D007YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 27 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
31 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 1.5IN | NO | 1 | 5BSA1 | TFS00E010YS18 ¦ PO LINE NO. 31 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 1.5IN | 218889 | 28 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 | 2 | TFS00I | 3 | TFS00I003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BSA1 | TFS00I003YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 29 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 16 | TFS00E016YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BSA1 | TFS00E016YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 30 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 15 | TFS00E015YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BSA1 | TFS00E015YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 31 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
71 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 2IN | NO | 1 | 5BSA1 | TFS00E003YS18 ¦ PO LINE NO. 71 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 2IN | 218889 | 32 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 7 | TFS00E007YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BSA1 | TFS00E007YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 33 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00I | 5 | TFS00I005YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5BSA1 | TFS00I005YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 34 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5BSA1 | TFS00D002YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 35 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5BSA1 | TFS00E010YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 36 | In PT&P Engineering /Waitn RFI Reponse |  | 3 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 3 | TFS00E003YS18 | TFS Mechanical | TFS | 3IN | NO | 1 | 5BSA1 | TFS00E003YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 37 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5BSA1 | TFS00E011YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 38 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 3IN | NO | 2 | 5BSA1 | TFS00E009YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 39 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
125 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 3IN | NO | 3 | 5BSA1 | TFS00E005YS18 ¦ PO LINE NO. 125 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 3IN | 218889 | 40 | In PT&P Engineering /Waitn RFI Reponse |  | 3 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 4IN | NO | 3 | 5BSA2 | TFS00D003YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 41 | In PT&P Engineering /Waitn RFI Reponse |  | 3 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 6 | TFS00E006YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5BSA2 | TFS00E006YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 42 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 4 | TFS00I004YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSA2 | TFS00I004YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 43 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 4IN | NO | 7 | 5BSA2 | TFS00I007YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 44 | In PT&P Engineering /Waitn RFI Reponse |  | 7 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSA2 | TFS00I008YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 45 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 1 | TFS00D | 2 | TFS00D002YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSA2 | TFS00D002YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 46 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00E | 11 | TFS00E011YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5BSA2 | TFS00E011YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 47 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 9 | TFS00E009YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5BSA2 | TFS00E009YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 48 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 4IN | NO | 2 | 5BSA2 | TFS00D006YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 49 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 | 3 | TFS00E | 10 | TFS00E010YS18 | TFS Mechanical | TFS | 4IN | NO | 1 | 5BSA2 | TFS00E010YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 50 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
153 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 4IN | NO | 4 | 5BSA2 | TFS00E005YS18 ¦ PO LINE NO. 153 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 4IN | 218889 | 51 | In PT&P Engineering /Waitn RFI Reponse |  | 4 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00D | 5 | TFS00D005YS18 | TFS Mechanical | TFS | 6IN | NO | 6 | 5BSA2 | TFS00D005YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 52 | In PT&P Engineering /Waitn RFI Reponse |  | 6 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00I | 7 | TFS00I007YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5BSA2 | TFS00I007YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 53 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00I | 8 | TFS00I008YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5BSA2 | TFS00I008YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00I ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 54 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00D | 6 | TFS00D006YS18 | TFS Mechanical | TFS | 6IN | NO | 2 | 5BSA2 | TFS00D006YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 55 | In PT&P Engineering /Waitn RFI Reponse |  | 2 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 | 1 | TFS00D | 3 | TFS00D003YS18 | TFS Mechanical | TFS | 6IN | NO | 8 | 5BSA2 | TFS00D003YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00D ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 56 | In PT&P Engineering /Waitn RFI Reponse |  | 8 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
175 |  | TFS00E | 5 | TFS00E005YS18 | TFS Mechanical | TFS | 6IN | NO | 1 | 5BSA2 | TFS00E005YS18 ¦ PO LINE NO. 175 ¦ CWA TFS00E ¦ NODE TFS ¦ MODULE TFS Mechanical ¦ SIZE 6IN | 218889 | 57 | In PT&P Engineering /Waitn RFI Reponse |  | 1 | RFI - Pending |  | 2026-02-04 | Feb-19-26: Still in Scope of Supply. Confirmed by PO CO-1 Feb-5-26: : Support deleted per Summit’s instruction. Dec-4-25: On HOLD Due To RFI No. 3
Total | [14 empty] | 0 | 2