## Summary
Job | masterPhase | Phase | JCJP.Description | ERROR DESCRIPTION | Est Units | Est Hours | ACT QTY | ACT MH | Wk Units | Wk ACT MH | Wk ERN MH | JTD ERN | PJTD HR | EXTP HR | % | wk PF | JTD PF | WK PR TE | REM BDGT | Vtg Budget | Vtg Earned
24.005. | 30 | 30.100. . | Structural Steel Labor (Holding Code) |  | 94 | 2493 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0009e-11 | 2.0009e-11 | 0% | 0 | 0 | 0 | 2493 | Not Found | Not Found
24.005. | 30 | 30.CUB.100. 1 | CUB Structural Steel Labor |  | 952 | 16255 | 952 | 11157.5 | 0 | 0 | 0 | 16255 | 11157.5 | 11157.5 | 100% | 0 | 1.46 | 0 | 5097.5 | 14441.389 | 14441.389
24.005. | 30 | 30.TFS.100. 1 | TFS Structural Steel Labor | EARN NO BURN | 5368 | 88558 | 5368 | 48440.5 | 755.278 | 0 | 12460.1172 | 88558 | 50000 | 48440.5 | 100% | 0 | 1.83 | 0 | 40117.5 | 76099.239 | 76099.239
24.005. | 30 | 30. PP.100. 1 | PP Structural Steel Labor |  | 113 | 1729 | 113 | 863.75 | 0 | 0 | 0 | 1729 | 863.75 | 863.75 | 100% | 0 | 2 | 0 | 865.25 | Not Found | Not Found
24.005. | 31 | 31.CUB.100. 1 | CUB Misc. Steel Labor (Grating, Catwalks, Railing, Ladders.. |  | 48 | 1143 | 48 | 402.5 | 0 | 0 | 0 | 1143 | 402.5 | 402.5 | 100% | 0 | 2.84 | 0 | 740.5 | 668.904 | 668.904
24.005. | 31 | 31.TFS.100. 1 | TFS Misc. Steel Labor (Grating, Catwalks, Railing, Ladders.. | EARN NO BURN | 3.04 | 9671 | 3.04 | 1371.75 | 1.735 | 0 | 5519.4688 | 9671 | 1371.75 | 1371.75 | 100% | 0 | 7.05 | 0 | 8299.25 | 4151.319 | 4151.319
24.005. | 31 | 31. PP.100. 1 | PP Misc. Steel Labor (Grating, Catwalks, Railing, Ladders.. |  | 1 | 10 | 1 | 12 | 0 | 0 | 0 | 10 | 12 | 12 | 100% | 0 | 0.83 | 0 | -2 | Not Found | Not Found
24.005. | 45 | 45.100. 1. | Module Load Out onto SPMT Labor (Holding Code) |  | 4 | 180 | 0 | 182.5 | 0 | 0 | 0 | 0 | 182.5 | 182.5 | 0% | 0 | 0 | 0 | -2.5 | Not Found | Not Found
24.005. | 45 | 45.100. 2. | Module Stacking Labor (Holding Code) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 50 | 50.100. . | Pipe Labor (Holding Code) | CODE NOT PROGRESSABLE | 0 | -1.0914e-11 | 0 | 0 | 0 | 0 | 0 | 0 | -1.0914e-11 | -1.0914e-11 | 0% | 0 | 0 | 0 | -1.0914e-11 | Not Found | Not Found
24.005. | 50 | 50.CUB.100. 1 | Shop CUB CS Pipe Fabrication |  | 13077 | 14103 | 13077 | 13750.5 | 0 | 0 | 0 | 14103 | 13750.5 | 13750.5 | 100% | 0 | 1.03 | 0 | 352.5 | 14135.39 | 14135.39
24.005. | 51 | 51.CUB.100. 1 | Field CUB CS Pipe Fabrication & Assembly |  | 12870 | 18126 | 12870 | 19704 | 0 | 0 | 0 | 18126 | 19704 | 19704 | 100% | 0 | 0.92 | 0 | -1578 | 18153.199 | 18153.199
24.005. | 51 | 51.TFS.100. 1 | Field TFS CS Pipe Fabrication & Assembly | PF CHECK | 25527 | 34249 | 23295.94 | 25269.25 | 291.008 | 95 | 390.4389 | 31255.6371 | 34249 | 27689.2946 | 91% | 4.11 | 1.24 | 95 | 8884.75 | 32093.114 | 31256.162
24.005. | 51 | 51. PP.100. 1 | Field PP CS Pipe Fabrication & Assembly | OVERRUNNING PROJECTION | 2486 | 1474 | 1657.168 | 711.75 | 0 | 0 | 0 | 982.5686 | 711.75 | 1067.7315 | 67% | 0 | 1.38 | 0 | 762.25 | Not Found | Not Found
24.005. | 52 | 52.100. . | Aboveground Hydrotest & Flush | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 53 | 53.CUB.100. 1 | Field CUB SS, 2205, Hastelloy Pipe Fabrication & Assembly |  | 4813 | 3176 | 4813 | 2987.5 | 0 | 0 | 0 | 3176 | 2987.5 | 2987.5 | 100% | 0 | 1.06 | 0 | 188.5 | 3159.558 | 3159.558
24.005. | 53 | 53.TFS.100. 1 | Field TFS SS, 2205, Hastelloy Pipe Fabrication & Assembly | PF CHECK | 101368 | 68680 | 83821.199 | 50024.25 | 2149.001 | 257 | 1456.0156 | 56791.4919 | 68680 | 60496.1303 | 83% | 5.67 | 1.14 | 257 | 18398.75 | 57603.828 | 56800.424
24.005. | 53 | 53. PP.100. 1 | Field PP SS, 2205, Hastelloy Pipe Fabrication & Assembly | OVERRUNNING PROJECTION | 3052 | 1676 | 2567.648 | 1082.5 | 0 | 0 | 0 | 1410.019 | 1082.5 | 1286.699 | 84% | 0 | 1.3 | 0 | 593.5 | Not Found | Not Found
24.005. | 55 | 55.100. . | Pipe Support Labor - (ALLOWANCE Holding Code) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 57 | 57. PP.100. 1 | Field PP CPVC Pipe Fabrication & Assembly | OVERRUNNING PROJECTION | 196 | 139 | 83.182 | 23 | 0 | 0 | 0 | 58.9913 | 23 | 54.1944 | 42% | 0 | 2.56 | 0 | 116 | Not Found | Not Found
24.005. | 57 | 57.TFS.100. 1 | Field TFS CPVC Pipe Fabrication & Assembly | OVERRUNNING PROJECTION | 1127 | 412 | 1007.989 | 314.75 | 0 | 0 | 0 | 368.4929 | 314.75 | 351.9118 | 89% | 0 | 1.17 | 0 | 97.25 | 374.064 | 374.064
24.005. | 58 | 58.CUB.100. 1 | Shop CUB Pipe Supports |  | 86 | 130 | 86 | 78 | 0 | 0 | 0 | 130 | 78 | 78 | 100% | 0 | 1.67 | 0 | 52 | 414.377 | 414.377
24.005. | 59 | 59.CUB.100. 1 | Field CUB Pipe Supports |  | 1468 | 5490 | 1468 | 5664 | 0 | 0 | 0 | 5490 | 5664 | 5664 | 100% | 0 | 0.97 | 0 | -174 | 5489.853 | 5489.853
24.005. | 59 | 59. PP.100. 1 | Field PP Pipe Supports | OVERRUNNING PROJECTION | 460 | 1312 | 388.7 | 807 | 0 | 0 | 0 | 1108.64 | 807 | 955.0296 | 85% | 0 | 1.37 | 0 | 505 | Not Found | Not Found
24.005. | 59 | 59.TFS.100. 1 | Field TFS Pipe Supports | PF CHECK | 14989 | 41113 | 13343.208 | 30590.25 | 391.213 | 23 | 1073.0496 | 36598.7931 | 41113 | 34363.3448 | 89% | 46.65 | 1.2 | 23 | 10499.75 | 36600.239 | 36600.239
24.005. | 75 | 75.100. . | Pressure Testing | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 90 | 90.001. 1. | Corporate Management | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 12389.7 | 0 | 15379.5 | 0 | 420 | 0 | 0 | 14263 | 14263 | 0% | 0 | 0 | 0 | -2989.8 | Not Found | Not Found
24.005. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 45942 | 0 | 52285.25 | 0 | 781 | 0 | 0 | 53519 | 53519 | 0% | 0 | 0 | 61 | -6404.25 | Not Found | Not Found
24.005. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 21888 | 0 | 20900.5 | 0 | 126 | 0 | 0 | 23063 | 23063 | 0% | 0 | 0 | 126 | 861.5 | Not Found | Not Found
24.005. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 51375 | 0 | 32977.25 | 0 | 473 | 0 | 0 | 63821 | 63821 | 0% | 0 | 0 | 60 | 18337.75 | Not Found | Not Found
24.005. | 90 | 90.005. 1. | HR Staff | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4218 | 0 | 4567.5 | 0 | 140 | 0 | 0 | 7151 | 7151 | 0% | 0 | 0 | 40 | -389.5 | Not Found | Not Found
24.005. | 90 | 90.008. 1. | Estimating Support for True Up | CODE NOT PROGRESSABLE | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 300 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 90 | 90.009. 1. | Onsite Engineering Management | CODE NOT PROGRESSABLE | 0 | 308 | 0 | 308 | 0 | 0 | 0 | 0 | 308 | 308 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 91 | 91.002. 1. | General Foreman | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 2565 | 0 | 1618.5 | 0 | 0 | 0 | 0 | 1618.5 | 1618.5 | 0% | 0 | 0 | 0 | 946.5 | Not Found | Not Found
24.005. | 91 | 91.002. 4. | Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 19038 | 0 | 32862.25 | 0 | 513 | 0 | 0 | 25232 | 25232 | 0% | 0 | 0 | 512.75 | -14337 | Not Found | Not Found
24.005. | 91 | 91.002. 5. | Crane Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 21261 | 0 | 23987.25 | 0 | 70 | 0 | 0 | 29526 | 29526 | 0% | 0 | 0 | 70 | -2796.25 | Not Found | Not Found
24.005. | 91 | 91.003. 1. | Tool Room Attendant | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 3192 | 0 | 4229 | 0 | 55 | 0 | 0 | 3814 | 3814 | 0% | 0 | 0 | 55 | -1092 | Not Found | Not Found
24.005. | 91 | 91.004. 1. | Orientation & Drug Testing Labor | CODE NOT PROGRESSABLE | 0 | 3408 | 0 | 3006.75 | 0 | 0 | 0 | 0 | 3006.75 | 3006.75 | 0% | 0 | 0 | 0 | 401.25 | Not Found | Not Found
24.005. | 91 | 91.005. 1. | Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 205 | 0 | 108 | 0 | 0 | 0 | 0 | 108 | 108 | 0% | 0 | 0 | 0 | 97 | Not Found | Not Found
24.005. | 91 | 91.006. 1. | OSHA 10/30 Training Labor Costs | CODE NOT PROGRESSABLE | 0 | 1300 | 0 | 1007 | 0 | 0 | 0 | 0 | 1007 | 1007 | 0% | 0 | 0 | 0 | 293 | Not Found | Not Found
24.005. | 91 | 91.007. 1. | Orbital Welding Coupon In/Out Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 91 | 91.004. 3. | Buggy Training | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 92 | 92.100. 1. | Job Set Up | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4500 | 0 | 4462 | 0 | 64 | 0 | 0 | 5000 | 5000 | 0% | 0 | 0 | 64 | -26 | Not Found | Not Found
24.005. | 93 | 93.006. 1. | Rig Welder Rig Rental | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 98 | 98.002. 1. | Preconstruction | CODE NOT PROGRESSABLE | 0 | 3005 | 0 | 3005 | 0 | 0 | 0 | 0 | 3005 | 3005 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 98 | 98.030. 1. | Steel - Fluor IFC Revision Rework | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 376.5 | 0 | 0 | 0 | 0 | 376.5 | 376.5 | 0% | 0 | 0 | 0 | -376.5 | Not Found | Not Found
24.005. | 98 | 98.050. 1. | Pipe - Fluor IFC Revision Rework | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 3658.75 | 0 | 0 | 0 | 0 | 3658.75 | 3658.75 | 0% | 0 | 0 | 0 | -3658.75 | Not Found | Not Found
24.005. | 98 | 98.100. 2. | (NR) - Holiday Per Diem Incentive | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 98 | 98.100. . | Orizon Structural Steel Rework & Mat'l Shorts | CODE NOT PROGRESSABLE | 0 | 416 | 0 | 674 | 0 | 0 | 0 | 0 | 674 | 674 | 0% | 0 | 0 | 0 | -258 | Not Found | Not Found
24.005. | 98 | 98.200. . | Pipe Supports Rework | CODE NOT PROGRESSABLE | 0 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 220 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 98 | 98.000. 3. | Pipe Labor to T&M (Holding Code) | CODE NOT PROGRESSABLE | 0 | 13628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 13628 | Not Found | Not Found
24.005. | 98 | 98.000. 4. | IFC Revision Rework - Offset | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 98 | 98.300.105. | TW105 Module Repair | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 128 | 128 | 0% | 0 | 0 | 0 | -128 | Not Found | Not Found
24.005. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.005. | 99 | 99.001. . | REWORK ONLY - Shoebox Module Leveling | CODE NOT PROGRESSABLE | 0 | 102 | 0 | 102 | 0 | 0 | 0 | 0 | 102 | 102 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 26 | 26.100. . | Grout Labor (per WP) | CODE NOT PROGRESSABLE | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 45 | 45.100. 0. | Mechanical Equipment Labor (per WP) | CODE NOT PROGRESSABLE | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 50 | 50.100. 1. | CS Pipe Aboveground Labor (per WP) | CODE NOT PROGRESSABLE | 6123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 50 | 50.100. 2. | SS Pipe Aboveground Labor (per WP) | CODE NOT PROGRESSABLE | 10158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 51 | 51.100. 1. | Hydrotest & Flush (per WP) | CODE NOT PROGRESSABLE | 4749.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 52 | 52.100. 1. | Line Labeling | CODE NOT PROGRESSABLE | 1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 52 | 52.100. 2. | Glycol Fill Budget (per WP) | CODE NOT PROGRESSABLE | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 52 | 52.100. 3. | Pipe Stress Allowance (per WP) | CODE NOT PROGRESSABLE | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 52 | 52.100. 4. | Instrumentation (per WP) | CODE NOT PROGRESSABLE | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 59 | 59.100. 1. | Pipe Support Labor (per WP) | CODE NOT PROGRESSABLE | 1085.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 59 | 59.100. 2. | Seismic Bracing Labor (per WP) | CODE NOT PROGRESSABLE | 652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 75 | 75.100. 1. | Startup & Commissioning Support | CODE NOT PROGRESSABLE | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | CODE NOT PROGRESSABLE | 0 | 22 | 0 | 22 | 0 | 0 | 0 | 0 | 22 | 22 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 90 | 90.004. 1. | Site HSE & QA/QC | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 90 | 90.005. 1. | HR Staff | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.002. 1. | General Foreman | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.002. 4. | Warehouse Crew | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.002. 5. | Operators | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.003. 1. | Tool Room Attendant | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.004. 1. | Orientation & Drug Testing Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 91 | 91.005. 1. | Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 92 | 92.100. 1. | Job Set Up | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
24.006. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.100. 1. | Combustion Piping - Labor | CODE NOT PROGRESSABLE | 9015.5 | 9015.5 | 0 | 9015.5 | 0 | 0 | 0 | 0 | 9015.5 | 9015.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.102. 1. | Quench Rings - Labor | CODE NOT PROGRESSABLE | 2525.5 | 2525.5 | 0 | 2525.5 | 0 | 0 | 0 | 0 | 2525.5 | 2525.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.105. 1. | Punch Items - Labor | CODE NOT PROGRESSABLE | 4450.75 | 4450.75 | 0 | 4450.75 | 0 | 0 | 0 | 0 | 4450.75 | 4450.75 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.100. 2. | Owner Change Requests | CODE NOT PROGRESSABLE | 152.5 | 152.5 | 0 | 152.5 | 0 | 0 | 0 | 0 | 152.5 | 152.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.103. 1. | Boiler Piping - Labor | CODE NOT PROGRESSABLE | 3762.75 | 3762.75 | 0 | 3762.75 | 0 | 0 | 0 | 0 | 3762.75 | 3762.75 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.104. 1. | CCU Piping - Labor | CODE NOT PROGRESSABLE | 2263.75 | 2263.75 | 0 | 2263.75 | 0 | 0 | 0 | 0 | 2263.75 | 2263.75 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.110. 1. | TBRC 1 Lance Final Alignment - Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.106. 1. | TBRC 2 Lance Recovery | CODE NOT PROGRESSABLE | 328.5 | 328.5 | 0 | 328.5 | 0 | 0 | 0 | 0 | 328.5 | 328.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.101. 1. | Urea Piping - Labor | CODE NOT PROGRESSABLE | 1458.25 | 1458.25 | 0 | 1458.25 | 0 | 0 | 0 | 0 | 1458.25 | 1458.25 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.107. 1. | Polypro Piping - Labor | CODE NOT PROGRESSABLE | 7107.25 | 7107.25 | 0 | 7107.25 | 0 | 0 | 0 | 0 | 7107.25 | 7107.25 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.108. 1. | TBRC 2 Lance Recovery Final Alignment - Labor | CODE NOT PROGRESSABLE | 4244.25 | 4244.25 | 0 | 4244.25 | 0 | 0 | 0 | 0 | 4244.25 | 4244.25 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.109. 1. | TBRC 2 Charging Lance Final Alignment - Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.002. | 99 | 99.605. . | Internal T&M Budgeting Placeholder | CODE NOT PROGRESSABLE | 0 | 37502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 37502 | Not Found | Not Found
25.002. | 99 | 99.111. 1. | WWT Flange Tie-Ins | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.001. | 20 | 20.100. . | Misc Rock Labor | CODE NOT PROGRESSABLE | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0% | 0 | 0 | 0 | 1000 | Not Found | Not Found
25.001. | 20 | 20.200. . | SWPPP Labor | CODE NOT PROGRESSABLE | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 1300 | 0% | 0 | 0 | 0 | 1300 | Not Found | Not Found
25.001. | 20 | 20.300. . | Finish Grade Sitework Labor | CODE NOT PROGRESSABLE | 0 | 1131.69 | 0 | 0 | 0 | 0 | 0 | 0 | 1131.69 | 1131.69 | 0% | 0 | 0 | 0 | 1131.69 | Not Found | Not Found
25.001. | 25 | 25.100. . | Foundations Labor (per work package) |  | 5392 | 38870.74 | 0 | 0 | 0 | 0 | 0 | 0 | 38870.74 | 38870.74 | 0% | 0 | 0 | 0 | 38870.74 | Not Found | Not Found
25.001. | 26 | 26.100. . | Grout Labor (per work package) |  | 129 | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 1548 | 1548 | 0% | 0 | 0 | 0 | 1548 | Not Found | Not Found
25.001. | 30 | 30.100. . | Structural Steel Labor (per work package) |  | 193.357 | 11280.84 | 0 | 0 | 0 | 0 | 0 | 0 | 11280.84 | 11280.84 | 0% | 0 | 0 | 0 | 11280.84 | Not Found | Not Found
25.001. | 30 | 30.300. . | Fire Water Pumps House Labor |  | 1 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0% | 0 | 0 | 0 | 240 | Not Found | Not Found
25.001. | 45 | 45.100. . | Mechanical Equipment Labor (per work package) |  | 10 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 3300 | 0% | 0 | 0 | 0 | 3300 | Not Found | Not Found
25.001. | 45 | 45.100. 1. | MAN Supplied Equipment Labor |  | 186 | 9520 | 0 | 0 | 0 | 0 | 0 | 0 | 9520 | 9520 | 0% | 0 | 0 | 0 | 9520 | Not Found | Not Found
25.001. | 50 | 50.100. . | Pipe Labor (per work package) |  | 12059.25 | 24666.93 | 0 | 0 | 0 | 0 | 0 | 0 | 24666.93 | 24666.93 | 0% | 0 | 0 | 0 | 24666.93 | Not Found | Not Found
25.001. | 50 | 50.700. . | Piping Support Labor Allowance |  | 2009.875 | 6532.09 | 0 | 0 | 0 | 0 | 0 | 0 | 6532.09 | 6532.09 | 0% | 0 | 0 | 0 | 6532.09 | Not Found | Not Found
25.001. | 52 | 52.100. . | Aboveground Hydrotest & Flush Labor Allowance |  | 12059.25 | 2887.68 | 0 | 0 | 0 | 0 | 0 | 0 | 2887.68 | 2887.68 | 0% | 0 | 0 | 0 | 2887.68 | Not Found | Not Found
25.001. | 75 | 75.100. 1. | Startup & Commissioning Support |  | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 1440 | 0% | 0 | 0 | 0 | 1440 | Not Found | Not Found
25.001. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 7028.7 | 0 | 2443 | 0 | 225 | 0 | 0 | 7028.7 | 7028.7 | 0% | 0 | 0 | 0 | 4585.7 | Not Found | Not Found
25.001. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 19680 | 0 | 450 | 0 | 25 | 0 | 0 | 19680 | 19680 | 0% | 0 | 0 | 0 | 19230 | Not Found | Not Found
25.001. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | CODE NOT PROGRESSABLE | 0 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 12180 | 12180 | 0% | 0 | 0 | 0 | 12180 | Not Found | Not Found
25.001. | 90 | 90.004. 1. | Site HSE & QA/QC | CODE NOT PROGRESSABLE | 0 | 10920 | 0 | 0 | 0 | 0 | 0 | 0 | 10920 | 10920 | 0% | 0 | 0 | 0 | 10920 | Not Found | Not Found
25.001. | 90 | 90.005. 1. | HR Staff | CODE NOT PROGRESSABLE | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0% | 0 | 0 | 0 | 1920 | Not Found | Not Found
25.001. | 91 | 91.002. 1. | General Foreman | CODE NOT PROGRESSABLE | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0% | 0 | 0 | 0 | 2100 | Not Found | Not Found
25.001. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 5460 | 5460 | 0% | 0 | 0 | 0 | 5460 | Not Found | Not Found
25.001. | 91 | 91.002. 4. | Warehouse Crew | CODE NOT PROGRESSABLE | 0 | 12240 | 0 | 0 | 0 | 0 | 0 | 0 | 12240 | 12240 | 0% | 0 | 0 | 0 | 12240 | Not Found | Not Found
25.001. | 91 | 91.002. 5. | Operators | CODE NOT PROGRESSABLE | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0% | 0 | 0 | 0 | 12000 | Not Found | Not Found
25.001. | 91 | 91.002. 6. | General Site Laborer (Fire Watch Ice/Water etcï¿½) | CODE NOT PROGRESSABLE | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0% | 0 | 0 | 0 | 1920 | Not Found | Not Found
25.001. | 91 | 91.003. 1. | Tool Room Attendant | CODE NOT PROGRESSABLE | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 3900 | 0% | 0 | 0 | 0 | 3900 | Not Found | Not Found
25.001. | 91 | 91.005. 1. | Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0% | 0 | 0 | 0 | 120 | Not Found | Not Found
25.001. | 92 | 92.100. 1. | Job Set Up Labor | CODE NOT PROGRESSABLE | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 1440 | 0% | 0 | 0 | 0 | 1440 | Not Found | Not Found
25.001. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 20 | 20.100. 1. | Civil - Excavation Labor | PF CHECK | 71981 | 18444 | 65862.615 | 14499 | 1079.715 | 325 | 276.66 | 16876.26 | 18444 | 15845.9016 | 92% | 0.85 | 1.16 | 326 | 3619 | 18306 | 15560.1
25.004. | 21 | 21.100. 1. | Civil - Backfill Labor | PF CHECK | 73212 | 33125 | 44476.29 | 15381.25 | 549.09 | 271 | 248.4375 | 20123.4375 | 33125 | 25318.93 | 61% | 0.92 | 1.31 | 271.5 | 17472.25 | 32844 | 17735.76
25.004. | 22 | 22.100. 1. | Civil Labor - Storm Drain Piping Installation | PF CHECK | 3061 | 2342 | 2280.445 | 685 | 45.915 | 41 | 35.13 | 1744.79 | 2342 | 919.4631 | 75% | 0.86 | 2.55 | 42 | 1615 | 2342 | 1873.6
25.004. | 23 | 23.100. 1. | Civil Labor - Storm Drains Catch Basins | PF CHECK OVERRUNNING PROJECTION | 18 | 486 | 17.64 | 681.5 | 1.08 | 104 | 29.16 | 476.28 | 603 | 695.4082 | 98% | 0.28 | 0.7 | 107 | -302.5 | 486 | 388.8
25.004. | 23 | 23.100. 2. | Civil Labor - UG Fire Water Thrust Blocks |  | 45 | 900 | 24.3 | 403 | 0 | 0 | 0 | 486 | 900 | 746.2963 | 54% | 0 | 1.21 | 0 | 497 | Not Found | Not Found
25.004. | 25 | 25.100. . | Foundations Labor (per work package) |  | 0.22 | 47.29 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7397e-13 | 8.7397e-13 | 0% | 0 | 0 | 0 | 47.29 | 47.29 | 0
25.004. | 25 | 25.100. 1. | Foundations Labor - Pipe Rack |  | 2704 | 11396 | 2704 | 12802.5 | 0 | 0 | 0 | 11396 | 13554 | 12802.5 | 100% | 0 | 0.89 | 0 | -1406.5 | 11396.318 | 11396.318
25.004. | 25 | 25.100. 2. | Foundations Labor - Addendum 3 |  | 40 | 4284 | 40 | 2296.5 | 0 | 0 | 0 | 4284 | 2296.5 | 2296.5 | 100% | 0 | 1.87 | 0 | 1987.5 | Not Found | Not Found
25.004. | 25 | 25.200. 1. | Civil - Duct Banks Concrete Labor |  | 7216 | 22601 | 7216 | 24155.9 | 0 | 0 | 0 | 22601 | 24256 | 24155.9 | 100% | 0 | 0.94 | 0 | -1554.9 | 22601 | 22601
25.004. | 25 | 25.200. 2. | Lunch Tent Pads - Concrete Labor |  | 1503 | 5336.01 | 1503 | 5156.9 | 0 | 0 | 0 | 5336.01 | 5156.9 | 5156.9 | 100% | 0 | 1.03 | 0 | 179.11 | 5336.01 | 5336.01
25.004. | 25 | 25.200. 3. | Admin Manholes |  | 12 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 0% | 0 | 0 | 0 | 720 | Not Found | Not Found
25.004. | 26 | 26.100. . | Grout Labor (per work package) |  | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 26 | 26.100. PR. 1 | Grout Labor - Pipe Rack | OVERRUNNING PROJECTION | 227.34 | 2866 | 181.872 | 4044 | 0 | 0 | 0 | 2292.8 | 4963 | 5055 | 80% | 0 | 0.57 | 0 | -1178 | 1342.004 | 1342.004
25.004. | 26 | 26.100.SUP. 1 | Grout Labor - Supp Steel |  | 195.66 | 2565 | 195.66 | 2650 | 0 | 0 | 0 | 2565 | 2650 | 2650 | 100% | 0 | 0.97 | 0 | -85 | 2564.89 | 2564.89
25.004. | 27 | 27.100. . | Anchor Bolts (per work package) | EARN NO BURN | 2704 | 15267 | 554.32 | 1326.5 | 13.52 | 0 | 76.335 | 3129.735 | 1550 | 1550 | 21% | 0 | 2.36 | 0 | 13940.5 | 15267 | 2290.05
25.004. | 30 | 30.100. . | Structural Steel Labor (per work package) |  | 23.99 | 464.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4779e-12 | 1.4779e-12 | 0% | 0 | 0 | 0 | 464.4 | Not Found | Not Found
25.004. | 30 | 30.100. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 30 | 30.100. 4. | Addendum 3 Steel |  | 12 | 360 | 12 | 394 | 0 | 0 | 0 | 360 | 394 | 394 | 100% | 0 | 0.91 | 0 | -34 | Not Found | Not Found
25.004. | 30 | 30.100. PR. 1 | Ext Pipe Rack - Steel Labor | PF CHECK OVERRUNNING PROJECTION | 1242.15 | 24214 | 1242.15 | 18068.5 | 6.211 | 328 | 121.0749 | 24214 | 17325 | 18068.5 | 100% | 0.37 | 1.34 | 328.5 | 5817 | 17681.152 | 17589.251
25.004. | 30 | 30.100.SUP. 1 | Data Halls - Supp Steel Labor |  | 589.45 | 11885.39 | 589.45 | 9200.5 | 0 | 0 | 0 | 11885.39 | 9200.5 | 9200.5 | 100% | 0 | 1.29 | 0 | 2684.89 | 14573.383 | 14573.369
25.004. | 30 | 30.100.SUP. 2 | VOID - DO NOT USE | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 30 | 30.100.SUP. 3 | VOID - DO NOT USE | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 30 | 30.100.COR. 1 | Core Blg - Steel Labor |  | 194 | 3752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 3752 | Not Found | Not Found
25.004. | 45 | 45.100. . | Mechanical Equipment Labor (per work package) | PF CHECK BURN NO EARN | 951 | 13803 | 475.5 | 1774 | 0 | 74 | 0 | 6901.5 | 5303 | 3548 | 50% | 0 | 3.89 | 74.5 | 11954.5 | 13803 | 4831.05
25.004. | 50 | 50.100. . | CS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 50 | 50.100. 2. | Chainwheels & Belimo Valves |  | 540 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 | 0% | 0 | 0 | 0 | 1260 | Not Found | Not Found
25.004. | 50 | 50.100. 3. | GPU Hoses |  | 528 | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 2640 | 2640 | 0% | 0 | 0 | 0 | 2640 | Not Found | Not Found
25.004. | 50 | 50.100.OSM. 1 | CS Pipe Fabrication Labor - OSM |  | 43957 | 73919 | 43957 | 59268.5 | 0 | 0 | 0 | 73919 | 59268.5 | 59268.5 | 100% | 0 | 1.25 | 0 | 14650.5 | 73919 | 73919
25.004. | 50 | 50.100.SIT. 1 | CS Pipe Installation Labor - SITE | PF CHECK | 43957 | 83691 | 40440.44 | 66172.5 | 2197.85 | 7261 | 4184.55 | 76995.72 | 83691 | 71926.6304 | 92% | 0.58 | 1.16 | 7256 | 10262.5 | 115603.33 | 0.09
25.004. | 50 | 50.100.TES. 1 | CS Pipe - Hunton Trane Bypass | CODE NOT PROGRESSABLE | 542 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 9000 | Not Found | Not Found
25.004. | 51 | 51.100. . | SS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3910 | -3910 | 0% | 0 | 0 | 0 | 0 | 24919 | 622.975
25.004. | 51 | 51.100.SIT. 1 | SS Pipe Installation Labor - SITE | PF CHECK OVERRUNNING PROJECTION | 12972 | 24919 | 12193.68 | 27654 | 1167.48 | 3043 | 2242.71 | 23423.86 | 24919 | 29419.1489 | 94% | 0.74 | 0.85 | 3046 | -5781 | 81674.34 | 0.76
25.004. | 52 | 52.100. . | Aboveground Hydrotest & Flush | CODE NOT PROGRESSABLE | 0 | -0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -0.2 | 21705.8 | 0
25.004. | 53 | 53.100. . | Ductwork Installation | OVERRUNNING PROJECTION | 71863 | 12490 | 44914.375 | 2941 | 0 | 0 | 0 | 7806.25 | 2941 | 4705.6 | 63% | 0 | 2.65 | 0 | 9549 | 12490.01 | 7369.1
25.004. | 55 | 55.100. . | Pipe Supports Labor (per work package) | CODE NOT PROGRESSABLE | 3189 | 1697.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1697.5 | 17398.03 | 15658.227
25.004. | 55 | 55.100.SIT. 1 | Pipe Support Installation Labor - SITE | PF CHECK OVERRUNNING PROJECTION | 4686 | 18500 | 4639.14 | 20968 | 164.01 | 721 | 647.5 | 18315 | 20500 | 21179.798 | 99% | 0.9 | 0.87 | 722.5 | -3190.5 | Not Found | Not Found
25.004. | 58 | 58.100. . | Pipe Labels Label (per work package) | CODE NOT PROGRESSABLE | 3071 | 2533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2533 | 2533 | 0
25.004. | 75 | 75.100. 1. | Startup & Commissioning Support | PF CHECK OVERRUNNING PROJECTION | 61412 | 26026 | 45444.88 | 22208 | 8597.68 | 3777 | 3643.64 | 19259.24 | 26026 | 30010.8108 | 74% | 0.96 | 0.87 | 3776.5 | 41.5 | 4320 | 0
25.004. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6832.2 | 0 | 7318 | 0 | 210 | 0 | 0 | 7000 | 7000 | 0% | 0 | 0 | 0 | -485.8 | Not Found | Not Found
25.004. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 49346 | 0 | 27462 | 0 | 405 | 0 | 0 | 27160 | 27160 | 0% | 0 | 0 | 212 | 21672 | Not Found | Not Found
25.004. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 10920 | 0 | 11384 | 0 | 472 | 0 | 0 | 10550 | 10550 | 0% | 0 | 0 | 473 | -937 | Not Found | Not Found
25.004. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 49560 | 0 | 37929 | 0 | 2655 | 0 | 0 | 30837 | 30837 | 0% | 0 | 0 | 1909 | 9722 | Not Found | Not Found
25.004. | 90 | 90.005. 1. | HR Staff | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 2940 | 0 | 892.5 | 0 | 25 | 0 | 0 | 900 | 900 | 0% | 0 | 0 | 0 | 2047.5 | Not Found | Not Found
25.004. | 91 | 91.002. 1. | General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 28644 | 0 | 8978.5 | 0 | 117 | 0 | 0 | 9730 | 9730 | 0% | 0 | 0 | 117.5 | 19548 | Not Found | Not Found
25.004. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 11676 | 0 | 7360.5 | 0 | 0 | 0 | 0 | 8116 | 8116 | 0% | 0 | 0 | 0 | 4315.5 | Not Found | Not Found
25.004. | 91 | 91.002. 4. | Warehouse Crew | CODE NOT PROGRESSABLE | 0 | 21168 | 0 | 28732 | 0 | 0 | 0 | 0 | 30175 | 30175 | 0% | 0 | 0 | 0 | -7564 | Not Found | Not Found
25.004. | 91 | 91.002. 5. | Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 15204 | 0 | 27568 | 0 | 320 | 0 | 0 | 30535 | 30535 | 0% | 0 | 0 | 321.5 | -12685.5 | Not Found | Not Found
25.004. | 91 | 91.002. 6. | General Site Laborer (Fire Watch Ice/Water etc) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 14364 | 0 | 15534.5 | 0 | 2 | 0 | 0 | 14364 | 14364 | 0% | 0 | 0 | 2 | -1172.5 | Not Found | Not Found
25.004. | 91 | 91.003. 1. | Tool Room Attendant | CODE NOT PROGRESSABLE | 0 | 4704 | 0 | 3668.5 | 0 | 0 | 0 | 0 | 4660 | 4660 | 0% | 0 | 0 | 0 | 1035.5 | Not Found | Not Found
25.004. | 91 | 91.004. 1. | Orientation & Drug Testing | CODE NOT PROGRESSABLE | 0 | 460 | 0 | 853.5 | 0 | 0 | 0 | 0 | 620 | 620 | 0% | 0 | 0 | 0 | -393.5 | Not Found | Not Found
25.004. | 91 | 91.005. 1. | Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 350 | 0 | 214 | 0 | 0 | 0 | 0 | 350 | 350 | 0% | 0 | 0 | 0 | 136 | Not Found | Not Found
25.004. | 92 | 92.100. 1. | Job Set Up Labor | CODE NOT PROGRESSABLE | 0 | 1400 | 0 | 181.5 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 1218.5 | Not Found | Not Found
25.004. | 93 | 93.006. 1. | RIG Welder Pay | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.100. 2. | Orizon Steel Rework | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.200. 1. | OSM - Salary Staff | CODE NOT PROGRESSABLE | 0 | 2626 | 0 | 6525 | 0 | 0 | 0 | 0 | 6525 | 6525 | 0% | 0 | 0 | 0 | -3899 | Not Found | Not Found
25.004. | 98 | 98.100. 3. | Hiring Office Setup Labor and Materials | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.100. 4. | DH Generator Setting |  | 26 | 8320 | 26 | 4288.5 | 0 | 0 | 0 | 8320 | 4288.5 | 4288.5 | 100% | 0 | 1.94 | 0 | 4031.5 | Not Found | Not Found
25.004. | 98 | 98.100. 5. | Colgan Rebar Rework | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 588.5 | 0 | 0 | 0 | 0 | 588.5 | 588.5 | 0% | 0 | 0 | 0 | -588.5 | Not Found | Not Found
25.004. | 98 | 98.100. 6. | Civil Additional Scope | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.100. 7. | Sequence 2 - Drilled Piers TOC Fix | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 30 | 0% | 0 | 0 | 0 | -30 | Not Found | Not Found
25.004. | 98 | 98.100. 8. | MER Setting |  | 28 | 1400 | 28 | 1597 | 0 | 0 | 0 | 1400 | 1597 | 1597 | 100% | 0 | 0.88 | 0 | -197 | Not Found | Not Found
25.004. | 98 | 98.200. 2. | OSM - Direct Support | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 5751.5 | 0 | 0 | 0 | 0 | 5751.5 | 5751.5 | 0% | 0 | 0 | 0 | -5751.5 | Not Found | Not Found
25.004. | 98 | 98.100. 9. | Pipe Clash Reroute | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 390.5 | 0 | 0 | 0 | 0 | 390.5 | 390.5 | 0% | 0 | 0 | 0 | -390.5 | Not Found | Not Found
25.004. | 98 | 98.100. 10. | H2 Data Hall Supp Steel Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.100. 11. | Tap Box Clashing | CODE NOT PROGRESSABLE | 700 | 2275 | 0 | 2114 | 0 | 0 | 0 | 0 | 2275 | 2275 | 0% | 0 | 0 | 0 | 161 | Not Found | Not Found
25.004. | 98 | 98.100. 12. | V-Loop Repair Welding | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 12 | 0% | 0 | 0 | 0 | -12 | Not Found | Not Found
25.004. | 98 | 98.100. 13. | PEMB Rigger Support | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 353.5 | 0 | 0 | 0 | 0 | 353.5 | 353.5 | 0% | 0 | 0 | 0 | -353.5 | Not Found | Not Found
25.004. | 98 | 98.100. 15. | MER Platform & U Supts | PF CHECK BURN NO EARN ACTUAL UNITS WITH NO EST UNITS | 0 | 5440 | 12.5 | 2114.5 | 3.75 | 104 | 0 | 0 | 2968 | 2968 | 0% | 0 | 0 | 103.5 | 3222 | Not Found | Not Found
25.004. | 98 | 98.100. 16. | Night Shift Premium & Per Diem Increase | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 98 | 98.100. 17. | H1 CUP Apron FDN & Pedestals | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 398 | 4300 | 0 | 3402.5 | 0 | 354 | 0 | 0 | 4300 | 4300 | 0% | 0 | 0 | 353.5 | 544 | Not Found | Not Found
25.004. | 98 | 98.100. 18. | H1 Telecom Extension Ductbank | CODE NOT PROGRESSABLE | 195 | 1154 | 0 | 521.5 | 0 | 0 | 0 | 0 | 521.5 | 521.5 | 0% | 0 | 0 | 0 | 632.5 | Not Found | Not Found
25.004. | 98 | 98.100. 19. | H1 Interconnects Supp Steel | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 14 | 3250 | 0 | 909.5 | 0 | 384 | 0 | 0 | 3520 | 3520 | 0% | 0 | 0 | 384 | 1956.5 | Not Found | Not Found
25.004. | 98 | 98.100. 20. | Site Cleanup Requested by IREN | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 819 | 0 | 0 | 0 | 0 | 819 | 819 | 0% | 0 | 0 | 0 | -819 | Not Found | Not Found
25.004. | 98 | 98.100. 21. | H1 DOAS Plenum Supports | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 1289.5 | 0 | 601 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 601 | -1890.5 | Not Found | Not Found
25.004. | 99 | 99.100. 1. | Summit T&M Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 2163.5 | 0 | 0 | 0 | 0 | 2163.5 | 2163.5 | 0% | 0 | 0 | 0 | -2163.5 | Not Found | Not Found
25.004. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.004. | 99 | 99.100. 2. | Steel Downtime Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 2565.5 | 0 | 0 | 0 | 0 | 2565.5 | 2565.5 | 0% | 0 | 0 | 0 | -2565.5 | Not Found | Not Found
25.005. | 26 | 26.100. . | Grout Labor (per work package) |  | 820 | 10820.47 | 0 | 0 | 0 | 0 | 0 | 0 | 10820.47 | 10820.47 | 0% | 0 | 0 | 0 | 10820.47 | Not Found | Not Found
25.005. | 26 | 26.TFS.203. 1 | ACN SRU - Grout Labor |  | 25 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 410 | 0% | 0 | 0 | 0 | 410 | Not Found | Not Found
25.005. | 26 | 26.CUB.200. | K214 - CUB Module Grout | PF CHECK OVERRUNNING PROJECTION | 135 | 1909 | 51.058 | 722 | 11.174 | 157 | 158.0086 | 721.9979 | 1909 | 1909.0054 | 38% | 1.01 | 1 | 158 | 1029 | 1975 | 1017.5
25.005. | 26 | 26.TFS.200. | K214 - TFS Module Grout | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 371.5 | 0 | 371 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 371.5 | -743 | 4605 | 385.505
25.005. | 26 | 26.TFS.201. | K210 - Module Grout | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 51 | 0 | 50 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 51 | -102 | 3699 | 69.793
25.005. | 30 | 30.100. . | Structural Steel Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 30 | 30.CUB.100. 1 | CUB Int - Steel Labor | OVERRUNNING PROJECTION | 55 | 1380 | 47.616 | 1551.75 | 0 | 0 | 0 | 1194.7287 | 1380 | 1792.386 | 87% | 0 | 0.77 | 0 | -171.75 | 787.077 | 751.919
25.005. | 30 | 30.CUB.200. 1 | CUB Ex - Vert Steel Labor |  | 166 | 5077 | 92.396 | 2350.5 | 0 | 0 | 0 | 2825.8704 | 5077 | 4222.9426 | 56% | 0 | 1.2 | 0 | 2726.5 | 7405.87 | 6351.43
25.005. | 30 | 30.PP1.200. 1 | PP1 Ex - Vert Steel Labor |  | 50 | 1512 | 18.092 | 547 | 0 | 0 | 0 | 547.1021 | 1512 | 1511.7179 | 36% | 0 | 1 | 0 | 965 | 724.14 | 724.14
25.005. | 30 | 30.TFS.200. 1 | TFS Ex - Vert Steel Labor | PF CHECK | 1229 | 37673 | 829.268 | 24807 | 53.671 | 1830 | 1645.1974 | 25419.8644 | 37673 | 36764.7166 | 67% | 0.9 | 1.02 | 1828 | 11038 | 46581.615 | 36001.475
25.005. | 30 | 30.TFS.201. 1 | TFS - K210 Module Steel Labor | PF CHECK OVERRUNNING PROJECTION | 784 | 21677.36 | 301.871 | 8346.75 | 44.296 | 1224 | 1224.7708 | 8346.6407 | 21677.36 | 21677.6438 | 39% | 1 | 1 | 1224.75 | 12105.86 | 19456.976 | 12137.54
25.005. | 30 | 30.TFS.202. 1 | TFS - SRU Steel Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 30 | 30.TFS.203. 1 | ACN SRU - Steel Erection Labor | PF CHECK OVERRUNNING PROJECTION | 38 | 7185 | 10.793 | 2040.75 | 0.028 | 5 | 5.2942 | 2040.7291 | 7185 | 7185.0737 | 28% | 1.06 | 1 | 5 | 5139.25 | 7184.966 | 4986.394
25.005. | 30 | 30.TFS.700. 1 | TFS Mech - Misc. Tray & Pipe Support Steel Labor |  | 48 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0% | 0 | 0 | 0 | 1920 | Not Found | Not Found
25.005. | 45 | 45.100. . | Shoebox Setting Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 45 | 45.CUB.100. 1 | CUB Int - Module Setting & Installation | OVERRUNNING PROJECTION | 11 | 1386 | 11 | 1472 | 0 | 0 | 0 | 1386 | 1386 | 1472 | 100% | 0 | 0.94 | 0 | -86 | 3168.516 | 3168.516
25.005. | 45 | 45.CUB.200. 1 | CUB Ex - Shoebox Setting & Installation | PF CHECK BURN NO EARN CHARGING AT 100% OVERRUNNING PROJECTION | 19 | 1111 | 19 | 1355.5 | 0 | 245 | 0 | 1111 | 1111 | 1355.5 | 100% | 0 | 0.82 | 244.5 | -489 | 1646.511 | 1646.511
25.005. | 45 | 45.PP1.200. 1 | PP1 Ex - Shoebox Setting & Installation |  | 4 | 234 | 2.12 | 124 | 0 | 0 | 0 | 124.02 | 234 | 233.9623 | 53% | 0 | 1 | 0 | 110 | 234 | 234
25.005. | 45 | 45.TFS.200. 1 | TFS Ex - Shoebox Setting & Installation | PF CHECK | 89 | 5204 | 78.369 | 4582.38 | 2.211 | 130 | 129.2814 | 4582.3851 | 5204 | 5203.9942 | 88% | 0.99 | 1 | 129.25 | 492.37 | 9752.89 | 8724.58
25.005. | 45 | 45.TFS.201. 1 | TFS - K210 Module Setting & Install |  | 178 | 10502 | 46.403 | 2491 | 0 | 0 | 0 | 2737.777 | 10502 | 9555.3736 | 26% | 0 | 1.1 | 0 | 8011 | 5939.795 | 3196.92
25.005. | 45 | 45.TFS.202. 1 | TFS E-Houses Installation |  | 8 | 900 | 7 | 620 | 0 | 0 | 0 | 787.5 | 900 | 708.5714 | 88% | 0 | 1.27 | 0 | 280 | 1714.25 | 1637.25
25.005. | 45 | 45.TFS.203. 1 | ACN SRU - Mod Receive, Install, Equip Labor |  | 6 | 2570 | 0.701 | 299.25 | 0 | 0 | 0 | 300.2617 | 2570 | 2570 | 12% | 0 | 1 | 0 | 2270.75 | Not Found | Not Found
25.005. | 45 | 45.TFS.700. 1 | TFS Mech - Truck Loading/Unloading |  | 6 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 4800 | 0% | 0 | 0 | 0 | 4800 | 9241 | 0
25.005. | 45 | 45.TFS.700. 2 | TFS Mech - Process Equipment Setting Labor |  | 157 | 5071 | 0 | 0 | 0 | 0 | 0 | 0 | 5071 | 5071 | 0% | 0 | 0 | 0 | 5071 | 930.5 | 0
25.005. | 50 | 50.100. . | Piping Spool Installation (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 50 | 50.100. 1. | Pipe Support Labor |  | 135 | 529.35 | 0 | 0 | 0 | 0 | 0 | 0 | 529.35 | 529.35 | 0% | 0 | 0 | 0 | 529.35 | Not Found | Not Found
25.005. | 50 | 50.CUB.100. 1 | CUB Int - Pipe Spool Install & Welding |  | 73 | 16825 | 64.267 | 14559 | 0 | 0 | 0 | 14812.2229 | 16825 | 16537.3675 | 88% | 0 | 1.02 | 0 | 2266 | 21767.78 | 21470.736
25.005. | 50 | 50.CUB.200. 1 | CUB Ex - Vert Pipe Spool Install & Welding | OVERRUNNING PROJECTION | 46 | 8258 | 22.929 | 4188.5 | 0 | 0 | 0 | 4116.254 | 8258 | 8402.9395 | 50% | 0 | 0.98 | 0 | 4069.5 | 10647.517 | 7145.895
25.005. | 50 | 50.PP1.200. 1 | PP1 Ex - Vert Pipe Spool Install & Welding |  | 2 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 419 | 0% | 0 | 0 | 0 | 419 | Not Found | Not Found
25.005. | 50 | 50.TFS.200. 1 | TFS Ex - Vert Pipe Spool Install & Welding | PF CHECK | 73 | 9426 | 51.792 | 6687.5 | 11.753 | 1517 | 1517.586 | 6687.5533 | 9426 | 9425.9249 | 71% | 1 | 1 | 1477.5 | 1261 | 53589.717 | 10883.143
25.005. | 50 | 50.CUB.300. 1 | CUB Ex - Horz Interconnect Welding |  | 153 | 10877 | 61.639 | 4382 | 0 | 0 | 0 | 4382.0092 | 10877 | 10876.9772 | 40% | 0 | 1 | 0 | 6495 | 10949.332 | 9381.832
25.005. | 50 | 50.PP1.300. 1 | PP1 Ex - Horz Interconnect Welding |  | 13 | 507 | 2.385 | 93 | 0 | 0 | 0 | 93.015 | 507 | 507 | 18% | 0 | 1 | 0 | 414 | Not Found | Not Found
25.005. | 50 | 50.TFS.201. 1 | TFS - K210 Module Pipe Labor | PF CHECK | 256 | 47010 | 26.542 | 4874 | 3.927 | 720 | 721.1261 | 4873.9821 | 47010 | 47010 | 10% | 1 | 1 | 720.75 | 41415.25 | 45266.718 | 6258.132
25.005. | 50 | 50.TFS.300. 1 | TFS Ex - Horz Interconnect Welding | PF CHECK | 782 | 25756 | 488.644 | 16094 | 65.175 | 2146 | 2146.6078 | 16094.0088 | 25756 | 25755.986 | 62% | 1 | 1 | 2146.5 | 7515.5 | 23801.529 | 17591.12
25.005. | 50 | 50.TFS.203. 1 | ACN SRU - Pipe & Pipe Support Labor |  | 476 | 2354 | 273.271 | 1351.25 | 0 | 0 | 0 | 1351.4284 | 2354 | 2353.6892 | 57% | 0 | 1 | 0 | 1002.75 | 2555.27 | 681.24
25.005. | 50 | 50.000. 3. | LP1X Accelerated Line & Valve - Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 51 | 51.TFS.700. 1 | TFS Mech - Pipe & Pipe Support Labor |  | 60073 | 163339 | 0 | 0 | 0 | 0 | 0 | 0 | 163339 | 163339 | 0% | 0 | 0 | 0 | 163339 | Not Found | Not Found
25.005. | 60 | 60.CUB.100. 1 | CUB Int - Cable Tray | CODE NOT PROGRESSABLE | 0 | 271.75 | 0 | 271.75 | 0 | 0 | 0 | 0 | 271.75 | 271.75 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 75 | 75.100. . | NSY - Pressure Testing - Holding | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 75 | 75.100. 1. | Pressure Testing Labor | OVERRUNNING PROJECTION | 151375 | 69496 | 54888.575 | 25997.75 | 0 | 0 | 0 | 25199.2496 | 69496 | 71698.1522 | 36% | 0 | 0.97 | 0 | 43498.25 | Not Found | Not Found
25.005. | 75 | 75.TFS.203. 1 | ACN SRU - Pressure Testing Labor |  | 2880 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 2880 | 0% | 0 | 0 | 0 | 2880 | Not Found | Not Found
25.005. | 75 | 75.TFS.700. 1 | TFS Mech - Pressure Testing Labor |  | 24999 | 24999 | 0 | 0 | 0 | 0 | 0 | 0 | 24999 | 24999 | 0% | 0 | 0 | 0 | 24999 | Not Found | Not Found
25.005. | 90 | 90.001. 1. | Corporate Management | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6686 | 0 | 3446.5 | 0 | 200 | 0 | 0 | 6686 | 6686 | 0% | 0 | 0 | 0 | 3239.5 | Not Found | Not Found
25.005. | 90 | 90.002. 1. | Site Management (CM, Supt, PE, FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 69752 | 0 | 22955.5 | 0 | 1714 | 0 | 0 | 69752 | 69752 | 0% | 0 | 0 | 259.25 | 46537.25 | Not Found | Not Found
25.005. | 90 | 90.003. 1. | Field Staff (Matl Manager, Office Manager, Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 20052 | 0 | 4386 | 0 | 221 | 0 | 0 | 20052 | 20052 | 0% | 0 | 0 | 221 | 15445 | Not Found | Not Found
25.005. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 46901 | 0 | 11098 | 0 | 1253 | 0 | 0 | 46901 | 46901 | 0% | 0 | 0 | 395 | 35408 | Not Found | Not Found
25.005. | 90 | 90.005. 1. | HR Staff | CODE NOT PROGRESSABLE | 0 | 6840 | 0 | 6 | 0 | 0 | 0 | 0 | 6840 | 6840 | 0% | 0 | 0 | 0 | 6834 | Not Found | Not Found
25.005. | 90 | 90.006. 1. | Estimating | CODE NOT PROGRESSABLE | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 0 | 1728 | 1728 | 0% | 0 | 0 | 0 | 1728 | Not Found | Not Found
25.005. | 91 | 91.002. 1. | General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 23721 | 0 | 3345.75 | 0 | 260 | 0 | 0 | 23721 | 23721 | 0% | 0 | 0 | 260.25 | 20115 | Not Found | Not Found
25.005. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 5466 | 0 | 2089 | 0 | 0 | 0 | 0 | 5466 | 5466 | 0% | 0 | 0 | 0 | 3377 | Not Found | Not Found
25.005. | 91 | 91.002. 4. | Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 40236 | 0 | 7653 | 0 | 649 | 0 | 0 | 40236 | 40236 | 0% | 0 | 0 | 647.5 | 31935.5 | Not Found | Not Found
25.005. | 91 | 91.002. 5. | Operators | CODE NOT PROGRESSABLE | 0 | 901 | 0 | 190.5 | 0 | 0 | 0 | 0 | 901 | 901 | 0% | 0 | 0 | 0 | 710.5 | Not Found | Not Found
25.005. | 91 | 91.002. 6. | General Site Laborer | CODE NOT PROGRESSABLE | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 1020 | 0% | 0 | 0 | 0 | 1020 | Not Found | Not Found
25.005. | 91 | 91.003. 1. | Tool Room Attendant | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 11283 | 0 | 2185.5 | 0 | 99 | 0 | 0 | 11283 | 11283 | 0% | 0 | 0 | 99 | 8998.5 | Not Found | Not Found
25.005. | 91 | 91.004. 1. | Orientation & Drug Testing | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4602 | 0 | 3706 | 0 | 117 | 0 | 0 | 4602 | 4602 | 0% | 0 | 0 | 117 | 779 | Not Found | Not Found
25.005. | 91 | 91.005. 1. | Welder Testing Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 820 | 0 | 155.5 | 0 | 5 | 0 | 0 | 820 | 820 | 0% | 0 | 0 | 5 | 659.5 | Not Found | Not Found
25.005. | 91 | 91.006. 1. | OSHA 10/30 Training | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 1960 | 0 | 1070 | 0 | 10 | 0 | 0 | 1960 | 1960 | 0% | 0 | 0 | 10 | 880 | Not Found | Not Found
25.005. | 91 | 91.002. 5. 1 | Operators - CUB | CODE NOT PROGRESSABLE | 0 | 8379 | 0 | 1815.5 | 0 | 0 | 0 | 0 | 8379 | 8379 | 0% | 0 | 0 | 0 | 6563.5 | Not Found | Not Found
25.005. | 91 | 91.002. 5. 2 | Operators - TFS | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 21725 | 0 | 8746.25 | 0 | 574 | 0 | 0 | 21725 | 21725 | 0% | 0 | 0 | 574.25 | 12404.5 | Not Found | Not Found
25.005. | 91 | 91.002. 5. 3 | Operators - PP1 | CODE NOT PROGRESSABLE | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 30 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 91 | 91.008. 1. | Accredited Training Costs | CODE NOT PROGRESSABLE | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 240 | 240 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 92 | 92.100. 1. | Job Set Up | CODE NOT PROGRESSABLE | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 0% | 0 | 0 | 0 | 1600 | Not Found | Not Found
25.005. | 92 | 92.100. 3. | Job Set Up | CODE NOT PROGRESSABLE | 0 | 900 | 0 | 50 | 0 | 0 | 0 | 0 | 900 | 900 | 0% | 0 | 0 | 0 | 850 | Not Found | Not Found
25.005. | 98 | 98.001. 2. | Fluor MOD.0003 Pressure Testing Funding Budget Delta Offset | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 98 | 98.300. 1. | PDN 420 - On Site ISO Fab/Install Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 479.75 | 0 | 832.5 | 0 | 65 | 0 | 0 | 479.75 | 479.75 | 0% | 0 | 0 | 104.75 | -457.5 | Not Found | Not Found
25.005. | 98 | 98.201. 1. | K210 E-House Funding Offset | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 98 | 98.CUB.100. | (NR) NON REIM CUB Int - Backing Bar Rework | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 3451.25 | 0 | 3995.5 | 0 | 153 | 0 | 0 | 3451.25 | 3451.25 | 0% | 0 | 0 | 153 | -697.25 | Not Found | Not Found
25.005. | 99 | 99.004. 1. | MOD.0004 - Weather & Safety Standdown | CODE NOT PROGRESSABLE | 0 | 261 | 0 | 261 | 0 | 0 | 0 | 0 | 261 | 261 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.004. 2. | MOD.0004 - Standby Due to Others | CODE NOT PROGRESSABLE | 0 | 719.75 | 0 | 719.75 | 0 | 0 | 0 | 0 | 719.75 | 719.75 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.005. 1. | MOD.0005 - Weather & Safety Standdown | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 836.25 | 0 | 957.25 | 0 | 33 | 0 | 0 | 836.25 | 836.25 | 0% | 0 | 0 | 33 | -154 | Not Found | Not Found
25.005. | 99 | 99.030. 1. | Steel IFC Revision Labor | CODE NOT PROGRESSABLE | 0 | 1094 | 0 | 1094 | 0 | 0 | 0 | 0 | 1094 | 1094 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.100. 1. | 12/2/25 - Weather Day Show Up | CODE NOT PROGRESSABLE | 0 | 720 | 0 | 720 | 0 | 0 | 0 | 0 | 720 | 720 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.100. 2. | (R) 25.005 - Holiday Per Diem Incentive | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.100. 3. | 3/11/26 - Tornado Warning Show Up | CODE NOT PROGRESSABLE | 0 | 244 | 0 | 244 | 0 | 0 | 0 | 0 | 244 | 244 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.015. 1. | SRU Preservation - Labor (MOD.0015) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.006. 1. | TFS - DWHU Horz Interconnect Welding | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 1868.5 | 0 | 2028.5 | 0 | 20 | 0 | 0 | 1868.5 | 1868.5 | 0% | 0 | 0 | 20 | -180 | Not Found | Not Found
25.005. | 99 | 99.004. 3. | MOD.0004 - Extra Work | CODE NOT PROGRESSABLE | 0 | 1302.25 | 0 | 1302.25 | 0 | 0 | 0 | 0 | 1302.25 | 1302.25 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.005. 2. | MOD.0005 - Standby Due to Others | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 1166.5 | 0 | 1263.5 | 0 | 33 | 0 | 0 | 1166.5 | 1166.5 | 0% | 0 | 0 | 33 | -130 | Not Found | Not Found
25.005. | 99 | 99.005. 3. | MOD.0005 - Extra Work | CODE NOT PROGRESSABLE | 0 | 5447.87 | 0 | 5455.87 | 0 | 0 | 0 | 0 | 5447.87 | 5447.87 | 0% | 0 | 0 | 0 | -8 | Not Found | Not Found
25.005. | 99 | 99.005. 4. | TFS - K210 Module Extra Work | CODE NOT PROGRESSABLE | 0 | 2650.25 | 0 | 2650.25 | 0 | 0 | 0 | 0 | 2650.25 | 2650.25 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.005. 5. | MOD.0005 - E-House Extra Work | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4132.75 | 0 | 4531.75 | 0 | 173 | 0 | 0 | 4132.75 | 4132.75 | 0% | 0 | 0 | 172.75 | -571.75 | 2750 | 2423.5
25.005. | 99 | 99.005. 6. | IFC Steel Revision Rework | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.006. 2. | MOD.0006 - Weather & Safety Standdown | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 530.75 | 0 | 706.75 | 0 | 150 | 0 | 0 | 530.75 | 530.75 | 0% | 0 | 0 | 150 | -326 | Not Found | Not Found
25.005. | 99 | 99.006. 3. | MOD.0006 - Extra Work - Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 3231 | 0 | 3708.25 | 0 | 411 | 0 | 0 | 3231 | 3231 | 0% | 0 | 0 | 411.25 | -888.5 | Not Found | Not Found
25.005. | 99 | 99.006. 5. | TFS Night Shift - Indirect/GC Labor & Material | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.006. 6. | MOD.0006 - Standby Due to Others | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 191 | 0 | 275 | 0 | 84 | 0 | 0 | 191 | 191 | 0% | 0 | 0 | 84 | -168 | Not Found | Not Found
25.005. | 99 | 99.030. 2. | IFC Revision Rework - Piping | CODE NOT PROGRESSABLE | 0 | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 60 | 60 | 0% | 0 | 0 | 0 | 0 | 1226.544 | 444.211
25.005. | 99 | 99.CUB.100. 1 | CB114 - W6 Beam - MOD.0006 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 74.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -74.5 | Not Found | Not Found
25.005. | 99 | 99.CUB.301. 1 | IFC Revision Rework - MOD.0006 Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.PP1.301. 1 | IFC Revision Rework - MOD.0006 Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.005. | 99 | 99.TFS.301. 1 | IFC Revision Rework - MOD.0006 Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 372.25 | 0 | 427.25 | 0 | 55 | 0 | 0 | 372.25 | 372.25 | 0% | 0 | 0 | 55 | -110 | Not Found | Not Found
25.006. | 25 | 25.100. 1. | Cast-On-Site Vaults |  | 10 | 2196.5 | 10 | 2196.5 | 0 | 0 | 0 | 2196.5 | 2196.5 | 2196.5 | 100% | 0 | 1 | 0 | 0 | 1680 | 1680
25.006. | 25 | 25.100. 2. | GN-1 Trestle Foundations |  | 16 | 360 | 16 | 200.5 | 0 | 0 | 0 | 360 | 360 | 200.5 | 100% | 0 | 1.8 | 0 | 159.5 | Not Found | Not Found
25.006. | 25 | 25.000. 3. | Sand Materials | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.100. . | MV Conduit Prep & Pre-Assembly (Holding) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.100. 1. | MV ALL Prep & Pre-Assembly | PF CHECK | 7136 | 71171 | 3539.456 | 28620 | 135.584 | 804 | 1352.249 | 35300.816 | 71171 | 57701.6129 | 50% | 1.68 | 1.23 | 803 | 41748 | 55367 | 20098.221
25.006. | 60 | 60.100. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.200. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.300. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.200. . | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.300. . | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.100. 3. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.200. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.300. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.400. . | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.400. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.400. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.500. . | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.500. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.500. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.600. . | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.600. 1. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.600. 2. | VOID | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 60 | 60.000. 6. | Primer/Cement Materials | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 61 | 61.100. 1. | MV Midnight North Conduit Install |  | 100 | 2227 | 100 | 2104.5 | 0 | 0 | 0 | 2227 | 2227 | 2104.5 | 100% | 0 | 1.06 | 0 | 122.5 | 2227 | 2227
25.006. | 61 | 61.100. . | MV Conduit Install (Holding) | CODE NOT PROGRESSABLE | 0 | -2.3306e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -2.3306e-12 | Not Found | Not Found
25.006. | 61 | 61.100. 2. | MV Midnight South Conduit Install |  | 150 | 3352 | 147.75 | 2288 | 0 | 0 | 0 | 3301.72 | 3352 | 2322.8426 | 99% | 0 | 1.44 | 0 | 1064 | 3352 | 3231.32
25.006. | 61 | 61.100. 9. | C-506 Conduit Install |  | 207 | 4606 | 207 | 4036 | 0 | 0 | 0 | 4606 | 4606 | 4036 | 100% | 0 | 1.14 | 0 | 570 | 4605.76 | 4605.76
25.006. | 61 | 61.100. 12. | C-509 Conduit Install | PF CHECK | 1854 | 42003 | 1545.494 | 29653.5 | 90.104 | 1966 | 2041.3367 | 35013.6917 | 42003 | 35572.8259 | 83% | 1.04 | 1.18 | 1962 | 10387.5 | 41323.05 | 21803.738
25.006. | 61 | 61.100. 24. | MV Midnight East Conduit Install |  | 455 | 10147 | 455 | 9915.5 | 0 | 0 | 0 | 10147 | 10147 | 9915.5 | 100% | 0 | 1.02 | 0 | 231.5 | 9147 | 9147
25.006. | 61 | 61.200. . | VOID | CODE NOT PROGRESSABLE | 0 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0.12 | 0% | 0 | 0 | 0 | 0.12 | Not Found | Not Found
25.006. | 61 | 61.300. . | VOID | CODE NOT PROGRESSABLE | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0% | 0 | 0 | 0 | 0.1 | Not Found | Not Found
25.006. | 61 | 61.400. . | VOID | CODE NOT PROGRESSABLE | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0% | 0 | 0 | 0 | 0.5 | Not Found | Not Found
25.006. | 61 | 61.500. . | VOID | CODE NOT PROGRESSABLE | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0% | 0 | 0 | 0 | 0.5 | Not Found | Not Found
25.006. | 61 | 61.600. . | VOID | CODE NOT PROGRESSABLE | 0 | -0.39 | 0 | 0 | 0 | 0 | 0 | 0 | -0.39 | -0.39 | 0% | 0 | 0 | 0 | -0.39 | Not Found | Not Found
25.006. | 61 | 61.100. 13. | C-510 Conduit Install |  | 465 | 10376 | 442.308 | 8838 | 0 | 0 | 0 | 9869.6512 | 10376 | 9291.4214 | 95% | 0 | 1.12 | 0 | 1538 | 10375.83 | 7207.88
25.006. | 61 | 61.100. 14. | C-511 Conduit Install |  | 114 | 2542 | 111.72 | 2105 | 0 | 0 | 0 | 2491.16 | 2542 | 2147.9592 | 98% | 0 | 1.18 | 0 | 437 | 2542.339 | 2021.16
25.006. | 61 | 61.100. 18. | C-515 Conduit Install |  | 327 | 7292 | 327 | 5296 | 0 | 0 | 0 | 7292 | 7292 | 5296 | 100% | 0 | 1.38 | 0 | 1996 | 7292.5 | 7292.5
25.006. | 61 | 61.100. 3. | Compressor Station - Conduit Install |  | 709 | 15811 | 0 | 60 | 0 | 0 | 0 | 0 | 15811 | 15811 | 0% | 0 | 0 | 0 | 15751 | 15811.566 | 0
25.006. | 61 | 61.100. 4. | C-501 Conduit Install | PF CHECK BURN NO EARN | 48 | 1070 | 0 | 50 | 0 | 50 | 0 | 0 | 1070 | 1070 | 0% | 0 | 0 | 50 | 970 | 1070.459 | 0
25.006. | 61 | 61.100. 5. | C-502 Conduit Install | PF CHECK | 648 | 14451 | 95.904 | 2048.5 | 38.102 | 778 | 849.7099 | 2138.748 | 14451 | 14451 | 15% | 1.09 | 1.04 | 781 | 11621.5 | 14451.192 | 0
25.006. | 61 | 61.100. 6. | C-503 Conduit Install |  | 132 | 2944 | 0 | 0 | 0 | 0 | 0 | 0 | 2944 | 2944 | 0% | 0 | 0 | 0 | 2944 | 2943.761 | 0
25.006. | 61 | 61.100. 7. | C-504 Conduit Install |  | 39 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 870 | 0% | 0 | 0 | 0 | 870 | 869.748 | 0
25.006. | 61 | 61.100. 8. | C-505 Conduit Install |  | 530 | 11820 | 0 | 0 | 0 | 0 | 0 | 0 | 11820 | 11820 | 0% | 0 | 0 | 0 | 11820 | 11819.648 | 0
25.006. | 61 | 61.100. 11. | C-508 Conduit Install |  | 117 | 2623 | 0 | 0 | 0 | 0 | 0 | 0 | 2623 | 2623 | 0% | 0 | 0 | 0 | 2623 | 2623.181 | 0
25.006. | 61 | 61.100. 15. | C-512 Conduit Install | PF CHECK | 101 | 2252 | 58.58 | 1148.5 | 14.898 | 289 | 332.1811 | 1306.16 | 2252 | 1980.1724 | 58% | 1.15 | 1.14 | 289 | 814.5 | 2252.423 | 112.621
25.006. | 61 | 61.100. 17. | MV C-514 Conduit Installation |  | 544 | 12135 | 337.28 | 6975 | 0 | 0 | 0 | 7523.7 | 12135 | 11250 | 62% | 0 | 1.08 | 0 | 5160 | 12135.21 | 4193.321
25.006. | 61 | 61.100. 19. | C-516 Conduit Install |  | 337 | 7516 | 0 | 0 | 0 | 0 | 0 | 0 | 7516 | 7516 | 0% | 0 | 0 | 0 | 7516 | 7515.512 | 0
25.006. | 61 | 61.100. 20. | C-517 Conduit Install |  | 138 | 3078 | 0 | 0 | 0 | 0 | 0 | 0 | 3078 | 3078 | 0% | 0 | 0 | 0 | 3078 | 3077.569 | 0
25.006. | 61 | 61.100. 25. | EX-43 Conduit Install | OVERRUNNING PROJECTION | 121 | 2698 | 121 | 2821 | 0 | 0 | 0 | 2698 | 2698 | 2821 | 100% | 0 | 0.96 | 0 | -123 | 2698.448 | 2118.282
25.006. | 62 | 62.100. . | MV Excavation (Holding) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 62 | 62.100. 1. | MV Midnight North Excavation |  | 12885 | 3633 | 12885 | 1717 | 0 | 0 | 0 | 3633 | 3633 | 1717 | 100% | 0 | 2.12 | 0 | 1916 | 4314 | 4314
25.006. | 62 | 62.100. 2. | MV Midnight South Excavation |  | 9983 | 2815 | 9983 | 1026 | 0 | 0 | 0 | 2815 | 2815 | 1026 | 100% | 0 | 2.74 | 0 | 1789 | 3343 | 3343
25.006. | 62 | 62.100. 9. | C-506 Excavation |  | 9903 | 2792 | 9903 | 1072 | 0 | 0 | 0 | 2792 | 2792 | 1072 | 100% | 0 | 2.6 | 0 | 1720 | 2792.421 | 2792.421
25.006. | 62 | 62.100. 12. | C-509 Excavation | PF CHECK | 108252 | 30675 | 76296.01 | 17445.5 | 2576.398 | 648 | 730.0651 | 21619.7401 | 30675 | 24752.4119 | 70% | 1.13 | 1.24 | 649.5 | 12580 | 27140.686 | 14345.453
25.006. | 62 | 62.100. 24. | MV Midnight East Excavation |  | 23503 | 6626 | 23503 | 3032.5 | 0 | 0 | 0 | 6626 | 6626 | 3032.5 | 100% | 0 | 2.18 | 0 | 3593.5 | 7871 | 7871
25.006. | 62 | 62.100. 13. | C-510 Excavation |  | 25866 | 7294 | 24642.538 | 5324 | 0 | 0 | 0 | 6948.9937 | 7294 | 5588.328 | 95% | 0 | 1.31 | 0 | 1970 | 7293.294 | 5785.937
25.006. | 62 | 62.100. 14. | C-511 Excavation |  | 6162 | 1738 | 6162 | 1684 | 0 | 0 | 0 | 1738 | 1738 | 1684 | 100% | 0 | 1.03 | 0 | 54 | 1737.541 | 1737.541
25.006. | 62 | 62.100. 18. | C-515 Excavation | PF CHECK BURN NO EARN | 13810 | 3894 | 13119.5 | 2145 | 0 | 48 | 0 | 3699.3 | 3894 | 2257.8947 | 95% | 0 | 1.72 | 48.5 | 1700.5 | 3894.051 | 3699.348
25.006. | 62 | 62.100. 3. | Compressor Station Excavation |  | 41672 | 11751 | 0 | 0 | 0 | 0 | 0 | 0 | 11751 | 11751 | 0% | 0 | 0 | 0 | 11751 | 11750.691 | 0
25.006. | 62 | 62.100. 4. | C-501 Excavation | PF CHECK | 5658 | 1595 | 1753.98 | 415 | 1527.66 | 374 | 430.65 | 494.45 | 1595 | 1338.7097 | 31% | 1.15 | 1.19 | 375 | 805 | 1595.314 | 0
25.006. | 62 | 62.100. 5. | C-502 Excavation | PF CHECK | 43263 | 12199 | 8933.809 | 1842 | 627.313 | 171 | 176.8854 | 2519.0934 | 12199 | 12199 | 21% | 1.03 | 1.37 | 171.5 | 10185.5 | 12199.14 | 0
25.006. | 62 | 62.100. 6. | C-503 Excavation |  | 12341 | 3480 | 0 | 0 | 0 | 0 | 0 | 0 | 3480 | 3480 | 0% | 0 | 0 | 0 | 3480 | 3479.798 | 0
25.006. | 62 | 62.100. 7. | C-504 Excavation |  | 4685 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 1321 | 1321 | 0% | 0 | 0 | 0 | 1321 | 1320.948 | 0
25.006. | 62 | 62.100. 8. | C-505 Excavation |  | 65966 | 18601 | 0 | 0 | 0 | 0 | 0 | 0 | 18601 | 18601 | 0% | 0 | 0 | 0 | 18601 | 18601.012 | 0
25.006. | 62 | 62.100. 11. | C-508 Excavation |  | 12663 | 3571 | 0 | 0 | 0 | 0 | 0 | 0 | 3571 | 3571 | 0% | 0 | 0 | 0 | 3571 | 3570.65 | 0
25.006. | 62 | 62.100. 15. | C-512 Excavation | PF CHECK OVERRUNNING PROJECTION | 752 | 212 | 684.32 | 922.5 | 7.52 | 372 | 2.12 | 192.92 | 212 | 1013.7363 | 91% | 0.01 | 0.21 | 372 | -1082.5 | 212.025 | 21.203
25.006. | 62 | 62.100. 17. | MV C-514 Excavation |  | 25846 | 7288 | 6608.822 | 1383.5 | 0 | 0 | 0 | 1863.5415 | 7288 | 5410.6376 | 26% | 0 | 1.35 | 0 | 5904.5 | 7287.913 | 1627.433
25.006. | 62 | 62.100. 19. | C-516 Excavation |  | 24006 | 6769 | 0 | 0 | 0 | 0 | 0 | 0 | 6769 | 6769 | 0% | 0 | 0 | 0 | 6769 | 6769.228 | 0
25.006. | 62 | 62.100. 20. | C-517 Excavation |  | 11799 | 3327 | 0 | 0 | 0 | 0 | 0 | 0 | 3327 | 3327 | 0% | 0 | 0 | 0 | 3327 | 3326.933 | 0
25.006. | 62 | 62.100. 25. | EX-43 Excavation | OVERRUNNING PROJECTION | 6087 | 1716 | 6087 | 2059.5 | 0 | 0 | 0 | 1716 | 1716 | 2059.5 | 100% | 0 | 0.83 | 0 | -343.5 | 1716.341 | 858.171
25.006. | 63 | 63.100. . | MV Backfill (Holding) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 63 | 63.100. 1. | MV Midnight North Backfill |  | 1289 | 303 | 1289 | 198.5 | 0 | 0 | 0 | 303 | 303 | 198.5 | 100% | 0 | 1.53 | 0 | 104.5 | 303 | 303
25.006. | 63 | 63.100. 2. | MV Midnight South Backfill | OVERRUNNING PROJECTION | 998 | 235 | 678.54 | 208 | 0 | 0 | 0 | 159.7765 | 235 | 305.9274 | 68% | 0 | 0.77 | 0 | 27 | 234 | 159.1
25.006. | 63 | 63.100. 9. | C-506 Backfill |  | 743 | 175 | 743 | 116.5 | 0 | 0 | 0 | 175 | 175 | 116.5 | 100% | 0 | 1.5 | 0 | 58.5 | 174.632 | 174.632
25.006. | 63 | 63.100. 12. | C-509 Backfill | PF CHECK | 11681 | 2747 | 7544.758 | 1497.5 | 536.158 | 90 | 126.0873 | 1774.2873 | 2747 | 2318.4703 | 65% | 1.4 | 1.18 | 90.5 | 1159 | 2534.916 | 1226.043
25.006. | 63 | 63.100. 24. | MV Midnight East Backfill | OVERRUNNING PROJECTION | 2530 | 553 | 1583.78 | 603 | 0 | 0 | 0 | 346.178 | 553 | 963.2588 | 63% | 0 | 0.57 | 0 | -50 | 553 | 346.178
25.006. | 63 | 63.100. 13. | C-510 Backfill |  | 1940 | 456 | 1940 | 316.5 | 0 | 0 | 0 | 456 | 456 | 316.5 | 100% | 0 | 1.44 | 0 | 139.5 | 456.149 | 456.149
25.006. | 63 | 63.100. 14. | C-511 Backfill |  | 462 | 109 | 462 | 92.5 | 0 | 0 | 0 | 109 | 109 | 92.5 | 100% | 0 | 1.18 | 0 | 16.5 | 108.662 | 108.662
25.006. | 63 | 63.100. 18. | C-515 Backfill | OVERRUNNING PROJECTION | 1036 | 244 | 1036 | 395 | 0 | 0 | 0 | 244 | 244 | 395 | 100% | 0 | 0.62 | 0 | -151 | 243.525 | 224.043
25.006. | 63 | 63.100. 3. | Compressor Station Backfill |  | 3125 | 735 | 0 | 0 | 0 | 0 | 0 | 0 | 735 | 735 | 0% | 0 | 0 | 0 | 735 | 734.862 | 0
25.006. | 63 | 63.100. 4. | C-501 Backfill |  | 424 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0% | 0 | 0 | 0 | 100 | 99.767 | 0
25.006. | 63 | 63.100. 5. | C-502 Backfill |  | 3245 | 763 | 0 | 0 | 0 | 0 | 0 | 0 | 763 | 763 | 0% | 0 | 0 | 0 | 763 | 762.907 | 0
25.006. | 63 | 63.100. 6. | C-503 Backfill |  | 926 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 218 | 218 | 0% | 0 | 0 | 0 | 218 | 217.619 | 0
25.006. | 63 | 63.100. 7. | C-504 Backfill |  | 351 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 83 | 0% | 0 | 0 | 0 | 83 | 82.609 | 0
25.006. | 63 | 63.100. 8. | C-505 Backfill |  | 4947 | 1163 | 0 | 0 | 0 | 0 | 0 | 0 | 1163 | 1163 | 0% | 0 | 0 | 0 | 1163 | 1163.266 | 0
25.006. | 63 | 63.100. 11. | C-508 Backfill |  | 950 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 223 | 0% | 0 | 0 | 0 | 223 | 223.301 | 0
25.006. | 63 | 63.100. 15. | C-512 Backfill |  | 56 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0% | 0 | 0 | 0 | 13 | 13.26 | 0
25.006. | 63 | 63.100. 17. | MV C-514 Backfill |  | 1938 | 456.01 | 530.624 | 91 | 0 | 0 | 0 | 124.8554 | 456.01 | 332.3596 | 27% | 0 | 1.37 | 0 | 365.01 | 455.77 | 0
25.006. | 63 | 63.100. 19. | C-516 Backfill |  | 1800 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 423 | 0% | 0 | 0 | 0 | 423 | 423.333 | 0
25.006. | 63 | 63.100. 20. | C-517 Backfill |  | 885 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 208 | 0% | 0 | 0 | 0 | 208 | 208.059 | 0
25.006. | 63 | 63.100. 25. | EX-43 Backfill | OVERRUNNING PROJECTION | 457 | 107.01 | 228.5 | 111 | 0 | 0 | 0 | 53.505 | 107.01 | 222 | 50% | 0 | 0.48 | 0 | -3.99 | 107.336 | 0
25.006. | 64 | 64.100. . | MV MH Installation (Holding) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 64 | 64.100. 1. | MV Midnight North MH Installation |  | 9 | 793 | 7 | 280.5 | 0 | 0 | 0 | 616.7778 | 793 | 360.6429 | 78% | 0 | 2.2 | 0 | 512.5 | 617 | 617
25.006. | 64 | 64.100. 2. | MV Midnight South MH Installation |  | 6 | 528 | 6 | 325.5 | 0 | 0 | 0 | 528 | 528 | 325.5 | 100% | 0 | 1.62 | 0 | 202.5 | 528 | 528
25.006. | 64 | 64.100. 9. | C-506 MH Installation | >100% | 14 | 1233 | 15 | 948.5 | 0 | 0 | 0 | 1321.0714 | 1233 | 885.2667 | 107% | 0 | 1.39 | 0 | 284.5 | 1321.189 | 1321.189
25.006. | 64 | 64.100. 12. | C-509 MH Installation | PF CHECK OVERRUNNING PROJECTION | 153 | 14620 | 63.77 | 6887.5 | -22.216 | 262 | -2122.8622 | 6093.5778 | 14620 | 16524.8157 | 42% | -8.1 | 0.88 | 261.5 | 7471 | 9160.244 | 5355.218
25.006. | 64 | 64.100. 24. | MV Midnight North MH Installation | PF CHECK BURN NO EARN | 35 | 3083 | 24 | 1154.5 | 0 | 100 | 0 | 2114.0571 | 3083 | 1683.6458 | 69% | 0 | 1.83 | 100.5 | 1828 | 2114.003 | 2114
25.006. | 64 | 64.100. 13. | C-510 MH Installation |  | 45 | 3963 | 20.7 | 1520.5 | 0 | 0 | 0 | 1822.98 | 3963 | 3305.4348 | 46% | 0 | 1.2 | 0 | 2442.5 | 2378.507 | 1672.727
25.006. | 64 | 64.100. 14. | C-511 MH Installation |  | 10 | 881 | 10 | 784 | 0 | 0 | 0 | 881 | 881 | 784 | 100% | 0 | 1.12 | 0 | 97 | 880.792 | 880.792
25.006. | 64 | 64.100. 18. | C-515 MH Installation |  | 32 | 2819 | 28.16 | 1632 | 0 | 0 | 0 | 2480.72 | 2819 | 1854.5455 | 88% | 0 | 1.52 | 0 | 1187 | 2818.536 | 2423.941
25.006. | 64 | 64.100. 3. | Compressor Station MH Installation |  | 41 | 3611 | 0 | 0 | 0 | 0 | 0 | 0 | 3611 | 3611 | 0% | 0 | 0 | 0 | 3611 | 3523.171 | 0
25.006. | 64 | 64.100. 4. | C-501 MH Installation |  | 9 | 793 | 0 | 0 | 0 | 0 | 0 | 0 | 793 | 793 | 0% | 0 | 0 | 0 | 793 | 704.634 | 0
25.006. | 64 | 64.100. 5. | C-502 MH Installation | PF CHECK | 54 | 4756 | 5.168 | 338.5 | 0.74 | 50 | 65.1748 | 455.1668 | 4756 | 4756 | 10% | 1.3 | 1.34 | 50 | 4367.5 | 4668.2 | 0
25.006. | 64 | 64.100. 6. | C-503 MH Installation |  | 11 | 969 | 0 | 0 | 0 | 0 | 0 | 0 | 969 | 969 | 0% | 0 | 0 | 0 | 969 | 704.634 | 0
25.006. | 64 | 64.100. 7. | C-504 MH Installation |  | 1 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 88 | 0% | 0 | 0 | 0 | 88 | 88.079 | 0
25.006. | 64 | 64.100. 8. | C-505 MH Installation |  | 72 | 6342 | 0 | 0 | 0 | 0 | 0 | 0 | 6342 | 6342 | 0% | 0 | 0 | 0 | 6342 | 6694.022 | 0
25.006. | 64 | 64.100. 11. | C-508 MH Installation |  | 12 | 1057 | 0 | 0 | 0 | 0 | 0 | 0 | 1057 | 1057 | 0% | 0 | 0 | 0 | 1057 | 968.871 | 0
25.006. | 64 | 64.100. 15. | C-512 MH Installation |  | 5 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 0% | 0 | 0 | 0 | 440 | 176.158 | 0
25.006. | 64 | 64.100. 17. | MV C-514 MH Installation |  | 45 | 3963 | 16.281 | 1028.5 | 0 | 0 | 0 | 1433.8134 | 3963 | 2842.7308 | 36% | 0 | 1.39 | 0 | 2934.5 | 3435.09 | 673.806
25.006. | 64 | 64.100. 19. | C-516 MH Installation |  | 31 | 2730 | 0 | 0 | 0 | 0 | 0 | 0 | 2730 | 2730 | 0% | 0 | 0 | 0 | 2730 | 2378.139 | 0
25.006. | 64 | 64.100. 20. | C-517 MH Installation |  | 15 | 1321 | 0 | 0 | 0 | 0 | 0 | 0 | 1321 | 1321 | 0% | 0 | 0 | 0 | 1321 | 968.871 | 0
25.006. | 64 | 64.100. 25. | EX-43 MH Installation |  | 14 | 1233 | 6.02 | 494 | 0 | 0 | 0 | 530.19 | 1233 | 1148.8372 | 43% | 0 | 1.07 | 0 | 739 | 1233.109 | 530.237
25.006. | 65 | 65.100. . | MV Jetline, Mandrels & Mule Tape (Holding) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 65 | 65.100. 1. | MV Midnight North Jet Line, Mandrels & Mule Tape |  | 23997 | 376 | 23997 | 361.5 | 0 | 0 | 0 | 376 | 376 | 361.5 | 100% | 0 | 1.04 | 0 | 14.5 | 376 | 376
25.006. | 65 | 65.100. 2. | MV Midnight South Jet Line, Mandrels & Mules Tape |  | 36072 | 565 | 34217.899 | 526.5 | 0 | 0 | 0 | 535.959 | 565 | 555.0285 | 95% | 0 | 1.02 | 0 | 38.5 | 566 | 536.9
25.006. | 65 | 65.100. 9. | C-506 Jet Line, Mandrels & Mules Tape |  | 49566 | 777 | 7434.9 | 100 | 0 | 0 | 0 | 116.55 | 777 | 777 | 15% | 0 | 1.17 | 0 | 677 | 776.948 | 116.542
25.006. | 65 | 65.100. 12. | C-509 Jet Line, Mandrels & Mules Tape | PF CHECK | 444708 | 6971 | 66839.612 | 863 | 12318.411 | 148 | 193.0967 | 1047.7413 | 6971 | 6971 | 15% | 1.3 | 1.21 | 148.5 | 5959.5 | 6970.801 | 624.799
25.006. | 65 | 65.100. 24. | MV Midnight South Jet Line, Mandrels & Mules Tape |  | 109200 | 1712 | 44509.92 | 678 | 0 | 0 | 0 | 697.8112 | 1712 | 1663.3955 | 41% | 0 | 1.03 | 0 | 1034 | 1712 | 697.811
25.006. | 65 | 65.100. 13. | C-510 Jet Line, Mandrels & Mules Tape | PF CHECK | 97892 | 1534 | 18433.064 | 243 | 2770.344 | 32 | 43.4122 | 288.8522 | 1534 | 1534 | 19% | 1.36 | 1.19 | 32.5 | 1258.5 | 1534.253 | 0
25.006. | 65 | 65.100. 14. | C-511 Jet Line, Mandrels & Mules Tape |  | 24658 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 387 | 387 | 0% | 0 | 0 | 0 | 387 | 386.514 | 0
25.006. | 65 | 65.100. 18. | C-515 Jet Line, Mandrels & Mules Tape |  | 71940 | 1128 | 41005.8 | 518.5 | 0 | 0 | 0 | 642.96 | 1128 | 909.6491 | 57% | 0 | 1.24 | 0 | 609.5 | 1127.66 | 146.596
25.006. | 65 | 65.100. 3. | Compressor Station Jet Line, Mandrels & Mules Tape |  | 170280 | 2669 | 0 | 0 | 0 | 0 | 0 | 0 | 2669 | 2669 | 0% | 0 | 0 | 0 | 2669 | 2669.141 | 0
25.006. | 65 | 65.100. 4. | C-501 Jet Line, Mandrels & Mules Tape |  | 11736 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 184 | 0% | 0 | 0 | 0 | 184 | 183.962 | 0
25.006. | 65 | 65.100. 5. | C-502 Jet Line, Mandrels & Mules Tape |  | 155728 | 2441 | 0 | 0 | 0 | 0 | 0 | 0 | 2441 | 2441 | 0% | 0 | 0 | 0 | 2441 | 2441.038 | 0
25.006. | 65 | 65.100. 6. | C-503 Jet Line, Mandrels & Mules Tape |  | 31788 | 498 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 498 | 0% | 0 | 0 | 0 | 498 | 498.277 | 0
25.006. | 65 | 65.100. 7. | C-504 Jet Line, Mandrels & Mules Tape |  | 9240 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 145 | 0% | 0 | 0 | 0 | 145 | 144.837 | 0
25.006. | 65 | 65.100. 8. | C-505 Jet Line, Mandrels & Mules Tape |  | 127320 | 1996 | 0 | 0 | 0 | 0 | 0 | 0 | 1996 | 1996 | 0% | 0 | 0 | 0 | 1996 | 1995.742 | 0
25.006. | 65 | 65.100. 11. | C-508 Jet Line, Mandrels & Mules Tape |  | 26116 | 409 | 2170.24 | 0 | 0 | 0 | 0 | 33.9879 | 409 | 409 | 8% | 0 | 0 | 0 | 409 | 409.369 | 34.009
25.006. | 65 | 65.100. 15. | C-512 Jet Line, Mandrels & Mules Tape |  | 24240 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 380 | 0% | 0 | 0 | 0 | 380 | 379.962 | 0
25.006. | 65 | 65.100. 17. | MV C-514 Jet Line, Mandrels & Mule Tape |  | 130596 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 2047 | 0% | 0 | 0 | 0 | 2047 | 2047.093 | 0
25.006. | 65 | 65.100. 19. | C-516 Jet Line, Mandrels & Mules Tape |  | 81030 | 1270 | 0 | 0 | 0 | 0 | 0 | 0 | 1270 | 1270 | 0% | 0 | 0 | 0 | 1270 | 1270.146 | 0
25.006. | 65 | 65.100. 20. | C-517 Jet Line, Mandrels & Mules Tape |  | 33438 | 524 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 524 | 0% | 0 | 0 | 0 | 524 | 524.141 | 0
25.006. | 65 | 65.100. 25. | EX-43 Jet Line, Mandrels & Mules Tape |  | 17157 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 269 | 269 | 0% | 0 | 0 | 0 | 269 | 268.936 | 0
25.006. | 70 | 70.100. . | LV Conduit Prep & Preassembly (Holding) |  | 1201 | 10931.94 | 0 | 0 | 0 | 0 | 0 | 0 | 10931.94 | 10931.94 | 0% | 0 | 0 | 0 | 10931.94 | Not Found | Not Found
25.006. | 70 | 70.200. 1. | TBD | CODE NOT PROGRESSABLE | 0 | 131488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 131488 | Not Found | Not Found
25.006. | 71 | 71.100. . | LV Conduit Installation (Holding) | CODE NOT PROGRESSABLE | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | Not Found | Not Found
25.006. | 71 | 71.200. 1. | Security Conduit Installation | PF CHECK | 111920 | 38511 | 9345.32 | 2287.5 | 2227.208 | 691 | 766.3689 | 3215.6685 | 38511 | 38511 | 8% | 1.11 | 1.41 | 691 | 35532.5 | 38511 | 995.248
25.006. | 72 | 72.100. . | LV Excavation (Holding) |  | 13961 | 1.91 | 0 | 0 | 0 | 0 | 0 | 0 | 1.91 | 1.91 | 0% | 0 | 0 | 0 | 1.91 | Not Found | Not Found
25.006. | 72 | 72.200. 1. | Security Excavation | PF CHECK BURN NO EARN | 5600 | 3753 | 5096 | 3159 | 0 | 192 | 0 | 3415.23 | 3753 | 3471.4286 | 91% | 0 | 1.08 | 192 | 402 | 3753 | 1088.37
25.006. | 72 | 72.100. 1. | ZCV-1 Excavation | OVERRUNNING PROJECTION | 104 | 100 | 104 | 264.5 | 0 | 0 | 0 | 100 | 100 | 264.5 | 100% | 0 | 0.38 | 0 | -164.5 | 100 | 100
25.006. | 72 | 72.100. 2. | ZCV-2 Excavation | OVERRUNNING PROJECTION | 1000 | 900 | 956 | 1082.5 | 0 | 0 | 0 | 860.4 | 900 | 1132.3222 | 96% | 0 | 0.79 | 0 | -182.5 | 75 | 75
25.006. | 72 | 72.100. 3. | ZCV-3 Excavation |  | 44 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0% | 0 | 0 | 0 | 75 | 75 | 0
25.006. | 72 | 72.100. 6. | LV - B1 Excavation | PF CHECK >100% | 2792 | 3308 | 10760.922 | 6347 | 750.762 | 452 | 889.5131 | 12749.6884 | 3308 | 1646.7756 | 385% | 1.97 | 2.01 | 447 | -3486 | 8897.92 | 2402.438
25.006. | 72 | 72.100. 7. | LV-B2 Excavation | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 73 | 73.100. . | LV Backfill (Holding) | CODE NOT PROGRESSABLE | 0 | 0.49 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2737e-13 | -2.2737e-13 | 0% | 0 | 0 | 0 | 0.49 | Not Found | Not Found
25.006. | 73 | 73.200. 1. | Security Backfill | PF CHECK | 5254 | 5167 | 609.464 | 494 | 57.794 | 50 | 56.837 | 599.372 | 5167 | 5167 | 12% | 1.14 | 1.21 | 50.5 | 4622.5 | 5167 | 271.268
25.006. | 73 | 73.100. 1. | ZCV-1 Backfill |  | 28 | 75 | 28 | 65 | 0 | 0 | 0 | 75 | 75 | 65 | 100% | 0 | 1.15 | 0 | 10 | 75 | 15
25.006. | 73 | 73.100. 2. | ZCV-2 Backfill | OVERRUNNING PROJECTION | 12 | 50 | 12 | 284.5 | 0 | 0 | 0 | 50 | 50 | 284.5 | 100% | 0 | 0.18 | 0 | -234.5 | 50 | 25
25.006. | 73 | 73.100. 3. | ZCV-3 Backfill |  | 12 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0% | 0 | 0 | 0 | 50 | 50 | 0
25.006. | 73 | 73.100. 6. | LV - B1 Backfill | PF CHECK >100% | 2459 | 6973 | 4186.854 | 3009.5 | 496.314 | 400 | 1407.4004 | 11872.6852 | 6973 | 1767.5229 | 170% | 3.52 | 3.95 | 398 | 3565.5 | 5026.77 | 829.417
25.006. | 73 | 73.100. 7. | LV-B2 Backfill | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 74 | 74.100. . | LV MH Installation (Holding) | CODE NOT PROGRESSABLE | 0 | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -0.5 | Not Found | Not Found
25.006. | 74 | 74.200. 1. | Security Poles | PF CHECK | 195 | 9106 | 62.205 | 2403.5 | 5.655 | 236 | 264.074 | 2904.814 | 9106 | 7534.4828 | 32% | 1.12 | 1.21 | 236 | 6466.5 | 9106 | 364.24
25.006. | 74 | 74.100. 1. | ZCV-1 MH Installation | PF CHECK | 10 | 3750 | 5.75 | 1679.5 | 0.55 | 192 | 206.25 | 2156.25 | 3750 | 2920.8696 | 58% | 1.07 | 1.28 | 192.5 | 1878 | 864.634 | 25.939
25.006. | 74 | 74.100. 2. | ZCV-2 MH Installation | PF CHECK | 8 | 3000 | 6.44 | 2229 | 0.64 | 232 | 240 | 2415 | 3000 | 2768.9441 | 81% | 1.03 | 1.08 | 232 | 539 | 540.396 | 216.158
25.006. | 74 | 74.100. 3. | ZCV-3 MH Installation | PF CHECK | 5 | 1875 | 2.6 | 798.5 | 0.65 | 211 | 243.75 | 975 | 1875 | 1535.5769 | 52% | 1.16 | 1.22 | 211.5 | 865 | 540.396 | 0
25.006. | 74 | 74.100. 6. | LV - B1 Manhole Installation |  | 22 | 3441 | 10.12 | 746 | 0 | 0 | 0 | 1582.86 | 3441 | 1621.7391 | 46% | 0 | 2.12 | 0 | 2695 | 1931.6 | 57.948
25.006. | 74 | 74.200. 2. | Security Hand Holes | PF CHECK | 29 | 4634 | 5.307 | 609.5 | 1.827 | 265 | 291.942 | 848.022 | 4634 | 4634 | 18% | 1.1 | 1.39 | 264.5 | 3760 | 4634 | 0
25.006. | 74 | 74.100. 7. | LV-B2 Manhole Installation | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 75 | 75.100. . | LV Precast Trench |  | 288162 | 0.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0.39 | Not Found | Not Found
25.006. | 75 | 75.200. 1. | TBD | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 75 | 75.100. 6. | LV - B1 Precast Trench |  | 4167 | 9278.08 | 1834.47 | 2076.5 | 0 | 0 | 0 | 4084.5595 | 9278.08 | 4716.7713 | 44% | 0 | 1.97 | 0 | 7201.58 | 10791 | 0
25.006. | 75 | 75.100. 7. | LV-B2 Precast Trench | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 76 | 76.100. 6. | LV - B1 CIP Trench | PF CHECK BURN NO EARN | 3397.62 | 32957 | 412.02 | 5467.5 | 0 | 951 | 0 | 3996.6044 | 32957 | 32957 | 12% | 0 | 0.73 | 951 | 26538.5 | 3318.281 | 759.514
25.006. | 76 | 76.100. 7. | LV - B2 CIP Trench | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 77 | 77.100. 6. | LV - B1 Drainage | PF CHECK OVERRUNNING PROJECTION | 7925 | 5030 | 4007.916 | 4223.5 | 325.826 | 341 | 206.8019 | 2543.8255 | 5030 | 8351.2822 | 51% | 0.61 | 0.6 | 340 | 466.5 | 10211.2 | 1156.795
25.006. | 77 | 77.100. 7. | LV-B2 Drainage | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 14879.6 | 0 | 12595 | 0 | 595 | 0 | 0 | 14879.6 | 14879.6 | 0% | 0 | 0 | 0 | 2284.6 | Not Found | Not Found
25.006. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 53238 | 0 | 17371 | 0 | 1438 | 0 | 0 | 53238 | 53238 | 0% | 0 | 0 | 67.5 | 35799.5 | Not Found | Not Found
25.006. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 19950 | 0 | 6264 | 0 | 215 | 0 | 0 | 19950 | 19950 | 0% | 0 | 0 | 215 | 13471 | Not Found | Not Found
25.006. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 61275 | 0 | 14043.5 | 0 | 1003 | 0 | 0 | 61275 | 61275 | 0% | 0 | 0 | 513.5 | 46718 | Not Found | Not Found
25.006. | 90 | 90.005. 1. | HR Staff | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6669 | 0 | 1494 | 0 | 38 | 0 | 0 | 6669 | 6669 | 0% | 0 | 0 | 38 | 5137 | Not Found | Not Found
25.006. | 90 | 90.008. 1. | Estimating Support | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 1480 | 0 | 300 | 0 | 50 | 0 | 0 | 1480 | 1480 | 0% | 0 | 0 | 0 | 1180 | Not Found | Not Found
25.006. | 90 | 90.007. 1. | IT Support | CODE NOT PROGRESSABLE | 0 | 1480.01 | 0 | 1050 | 0 | 0 | 0 | 0 | 1480.01 | 1480.01 | 0% | 0 | 0 | 0 | 430.01 | Not Found | Not Found
25.006. | 91 | 91.002. 1. | General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 27140 | 0 | 10715.5 | 0 | 398 | 0 | 0 | 27140 | 27140 | 0% | 0 | 0 | 397.5 | 16027 | Not Found | Not Found
25.006. | 91 | 91.002. 3. | Survey Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 16644 | 0 | 12291 | 0 | 643 | 0 | 0 | 16644 | 16644 | 0% | 0 | 0 | 643 | 3710 | Not Found | Not Found
25.006. | 91 | 91.002. 4. | Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 37791 | 0 | 10467.5 | 0 | 239 | 0 | 0 | 37791 | 37791 | 0% | 0 | 0 | 238.5 | 27085 | Not Found | Not Found
25.006. | 91 | 91.002. 5. | Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 37620 | 0 | 14223.5 | 0 | 683 | 0 | 0 | 37620 | 37620 | 0% | 0 | 0 | 683 | 22713.5 | Not Found | Not Found
25.006. | 91 | 91.002. 6. | General Site Laborer (FireWatch Ice/Water etc) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 100719 | 0 | 26422.5 | 0 | 1335 | 0 | 0 | 100719 | 100719 | 0% | 0 | 0 | 1335.5 | 72961 | Not Found | Not Found
25.006. | 91 | 91.003. 1. | Tool Room Attendant | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 3306 | 0 | 1472 | 0 | 61 | 0 | 0 | 3306 | 3306 | 0% | 0 | 0 | 61 | 1773 | Not Found | Not Found
25.006. | 91 | 91.004. 1. | Orientation & Drug Testing Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 8820 | 0 | 1773.5 | 0 | 15 | 0 | 0 | 8820 | 8820 | 0% | 0 | 0 | 15 | 7031.5 | Not Found | Not Found
25.006. | 92 | 92.100. 1. | Job Set Up | CODE NOT PROGRESSABLE | 0 | 4000 | 0 | 716.5 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0% | 0 | 0 | 0 | 3283.5 | Not Found | Not Found
25.006. | 98 | 98.000. 1. | TBD Buyout | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 98 | 98.100. 3. | Hiring Office Setup Labor and Materials | CODE NOT PROGRESSABLE | 0 | 500.01 | 0 | 324 | 0 | 0 | 0 | 0 | 500.01 | 500.01 | 0% | 0 | 0 | 0 | 176.01 | Not Found | Not Found
25.006. | 98 | 98.000. 2. | Internal Offset | CODE NOT PROGRESSABLE | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0.01 | Not Found | Not Found
25.006. | 98 | 98.100. 4. | Cast-On-Site Vault Pad Prep | CODE NOT PROGRESSABLE | 0 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 300 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 98 | 98.000. 3. | Pre-IFC Conduit Assembly | CODE NOT PROGRESSABLE | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 98 | 98.100. 5. | Tent Foundation | CODE NOT PROGRESSABLE | 0 | 1155.5 | 0 | 1155.5 | 0 | 0 | 0 | 0 | 1155.5 | 1155.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 98 | 98.100. 6. | Houston Office Buildout | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 98 | 98.000. 4. | LV True Up | CODE NOT PROGRESSABLE | 0 | 28373 | 0 | 0 | 0 | 0 | 0 | 0 | 28373 | 28373 | 0% | 0 | 0 | 0 | 28373 | Not Found | Not Found
25.006. | 98 | 98.000. 5. | MV True Up | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351697 | 351697 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 99 | 99.100. 1. | Bell End - Temp. (Email Approval) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 99 | 99.200. 1. | Weather Shut Down - 1/23/26 | CODE NOT PROGRESSABLE | 0 | 744 | 0 | 744 | 0 | 0 | 0 | 0 | 744 | 744 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 99 | 99.100. 2. | GN-1 Serena Work Around (Email Approval) | CODE NOT PROGRESSABLE | 0 | 1726.5 | 0 | 1726.5 | 0 | 0 | 0 | 0 | 1726.5 | 1726.5 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.006. | 99 | 99.100. 3. | Temp (Security) Fiber Conduits | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6900 | 0 | 585 | 0 | 542 | 0 | 0 | 6900 | 6900 | 0% | 0 | 0 | 545 | 5770 | Not Found | Not Found
25.006. | 99 | 99.100. 4. | GN-1 Trestle Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 1319 | 0 | 572 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 571.5 | -1890.5 | Not Found | Not Found
25.006. | 99 | 99.100. 5. | B1.B2 BESSUP Security Scope | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.007. | 20 | 20.100. 1. | H2 Civil - Excavation Labor | PF CHECK | 30882 | 10261.78 | 20382.12 | 6473 | 1235.28 | 515 | 410.4712 | 6772.7748 | 10261.78 | 9807.5758 | 66% | 0.8 | 1.05 | 516.5 | 3272.28 | Not Found | Not Found
25.007. | 21 | 21.100. 1. | H2 Civil - Backfill/Finish/Fine Grading Labor | PF CHECK | 235355 | 15168.58 | 115323.95 | 6676 | 5883.875 | 535 | 379.2145 | 7432.6042 | 15168.58 | 13624.4898 | 49% | 0.71 | 1.11 | 536 | 7956.58 | Not Found | Not Found
25.007. | 22 | 22.100. 1. | Civil Labor - Storm Drain Piping & Catch Basin Installation | PF CHECK | 2983 | 3089.55 | 357.96 | 416.5 | 149.15 | 243 | 154.4775 | 370.746 | 3089.55 | 3089.55 | 12% | 0.64 | 0.89 | 244 | 2429.05 | Not Found | Not Found
25.007. | 25 | 25.100. 1. | H2 Civil - Foundations Concrete & Rebar Labor | PF CHECK | 1630 | 18483.64 | 1124.7 | 9531 | 32.6 | 398 | 369.6728 | 12753.7116 | 18483.64 | 13813.0435 | 69% | 0.93 | 1.34 | 399 | 8553.64 | Not Found | Not Found
25.007. | 25 | 25.200. 1. | H2 Civil - Duct Banks Concrete & Rebar Labor | PF CHECK OVERRUNNING PROJECTION | 3695 | 9111.37 | 3140.75 | 8191.5 | 73.9 | 239 | 182.2274 | 7744.6645 | 9111.37 | 9637.0588 | 85% | 0.76 | 0.95 | 238.5 | 681.37 | Not Found | Not Found
25.007. | 25 | 25.300. 1. | H2 Civil - Precast Manholes/ Vaults Labor | PF CHECK BURN NO EARN | 269 | 2719.6 | 0 | 24 | 0 | 24 | 0 | 0 | 2719.6 | 2719.6 | 0% | 0 | 0 | 24 | 2671.6 | Not Found | Not Found
25.007. | 26 | 26.100. . | H2 Grout Labor (per work package) |  | 15 | 619.25 | 0 | 166 | 0 | 0 | 0 | 0 | 619.25 | 619.25 | 0% | 0 | 0 | 0 | 453.25 | Not Found | Not Found
25.007. | 26 | 26.100. PR. 1 | Grout Labor - H2 Pipe Rack | PF CHECK OVERRUNNING PROJECTION | 114 | 1029 | 74.1 | 1009 | 22.8 | 484 | 205.8 | 668.85 | 1029 | 1552.3077 | 65% | 0.43 | 0.66 | 486.5 | -466.5 | Not Found | Not Found
25.007. | 26 | 26.100.SUP. 1 | Grout Labor - H2 Supp Steel |  | 155 | 1818 | 155 | 171 | 0 | 0 | 0 | 1818 | 1818 | 171 | 100% | 0 | 10.63 | 0 | 1647 | Not Found | Not Found
25.007. | 27 | 27.100. . | H2 Anchor Bolts (per work package) | PF CHECK OVERRUNNING PROJECTION | 4708 | 4725 | 2401.08 | 2446.5 | 376.64 | 329 | 378 | 2409.75 | 4725 | 4797.0588 | 51% | 1.15 | 0.98 | 330 | 1948.5 | Not Found | Not Found
25.007. | 30 | 30.100. . | H2 Structural Steel Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.007. | 30 | 30.100. PR. 1 | H2 Ext Pipe Rack - Steel Labor | PF CHECK | 1336 | 24270.29 | 507.68 | 8007 | 106.88 | 911 | 1941.6232 | 9222.7102 | 24270.29 | 21071.0526 | 38% | 2.13 | 1.15 | 909 | 15354.29 | Not Found | Not Found
25.007. | 30 | 30.100.SUP. 1 | H2 Data Halls - Supp Steel Labor | PF CHECK BURN NO EARN CHARGING AT 100% | 589 | 11024 | 589 | 6633 | 0 | 234 | 0 | 11024 | 11024 | 6633 | 100% | 0 | 1.66 | 260 | 4131 | Not Found | Not Found
25.007. | 30 | 30.100.SUP. 3 | H3 Data Halls - Supp Steel Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | -5949 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.007. | 30 | 30.100.SUP. 4 | H4 Data Halls - Supp Steel Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 94.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -94.5 | Not Found | Not Found
25.007. | 45 | 45.100. . | H2 Mechanical Equipment Labor (per work package) | EARN NO BURN | 768 | 11868 | 7.68 | 72 | 3.84 | 0 | 59.34 | 118.68 | 11868 | 11868 | 1% | 0 | 1.65 | 0 | 11796 | Not Found | Not Found
25.007. | 45 | 45.200. . | H2 Expansion Loops and Dog Legs Labor | PF CHECK | 534 | 5440 | 8.01 | 84 | 6.408 | 72 | 65.28 | 81.6 | 5440 | 5440 | 2% | 0.91 | 0.97 | 72 | 5284 | Not Found | Not Found
25.007. | 45 | 45.300. . | H2 Set & Install MER Buildings and Generators | PF CHECK | 48 | 8880 | 7.2 | 909 | 1.44 | 287 | 266.4 | 1332 | 8880 | 8880 | 15% | 0.93 | 1.47 | 288 | 7683 | Not Found | Not Found
25.007. | 50 | 50.100. . | H2 CS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 171.79 | 0 | 0 | 0 | 0 | 0 | 0 | 114697.5 | 114697.5 | 0% | 0 | 0 | 0 | 171.79 | Not Found | Not Found
25.007. | 50 | 50.100.OSM. 1 | H2 CS Pipe Fabrication Labor - OSM | PF CHECK OVERRUNNING PROJECTION | 60267 | 47318.15 | 30133.5 | 27433.5 | 30133.5 | 5739 | 23659.075 | 23659.075 | 47318.15 | 54867 | 50% | 4.12 | 0.86 | 5700 | 14184.65 | Not Found | Not Found
25.007. | 50 | 50.100.SIT. 1 | H2 CS Pipe Installation Labor - SITE | PF CHECK | 60267 | 106753.7 | 4821.36 | 8102 | 4821.36 | 4218 | 8540.296 | 8540.296 | 106753.7 | 106753.7 | 8% | 2.02 | 1.05 | 4219 | 94432.7 | Not Found | Not Found
25.007. | 51 | 51.100. . | H2 SS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | -46.34 | 0 | 0 | 0 | 0 | 0 | 0 | 43331.8 | 43331.8 | 0% | 0 | 0 | 0 | -46.34 | Not Found | Not Found
25.007. | 51 | 51.100.SIT. 1 | H2 SS Pipe Installation Labor | PF CHECK | 15409 | 53553.39 | 77.045 | 240.5 | 77.045 | 120 | 267.767 | 267.767 | 53553.39 | 53553.39 | 1% | 2.23 | 1.11 | 120 | 53192.89 | Not Found | Not Found
25.007. | 52 | 52.100. . | H2 MER Fire Water Risers Labor |  | 26 | 1222 | 0 | 0 | 0 | 0 | 0 | 0 | 1222 | 1222 | 0% | 0 | 0 | 0 | 1222 | Not Found | Not Found
25.007. | 53 | 53.100. . | H2 Ductwork Installation (per work package) | CODE NOT PROGRESSABLE | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0.06 | Not Found | Not Found
25.007. | 55 | 55.100. . | H2 Pipe Supports Labor (per work package) |  | 6456 | 17259.82 | 0 | 0 | 0 | 0 | 0 | 0 | 17259.82 | 17259.82 | 0% | 0 | 0 | 0 | 17259.82 | Not Found | Not Found
25.007. | 55 | 55.100.SIT. 1 | H2 Pipe Support Installation Labor - SITE | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 7039.5 | 0 | 3021 | 0 | 0 | 1108.5 | 1108.5 | 0% | 0 | 0 | 3021 | -10060.5 | Not Found | Not Found
25.007. | 58 | 58.100. . | H2 Pipe Labels Labor (per work package) |  | 2873 | 2370.19 | 0 | 0 | 0 | 0 | 0 | 0 | 2370.19 | 2370.19 | 0% | 0 | 0 | 0 | 2370.19 | Not Found | Not Found
25.007. | 75 | 75.100. 1. 1 | H2 Pressure Testing Labor |  | 18761 | 18573.16 | 0 | 0 | 0 | 0 | 0 | 0 | 18573.16 | 18573.16 | 0% | 0 | 0 | 0 | 18573.16 | Not Found | Not Found
25.007. | 75 | 75.100. 1. 2 | H2 Start-Up Support Labor | CODE NOT PROGRESSABLE | 0 | 3456 | 0 | 0 | 0 | 0 | 0 | 0 | 3456 | 3456 | 0% | 0 | 0 | 0 | 3456 | Not Found | Not Found
25.007. | 90 | 90.001. 1. | H2 Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4257.98 | 0 | 1612 | 0 | 285 | 0 | 0 | 4257.98 | 4257.98 | 0% | 0 | 0 | 0 | 2645.98 | Not Found | Not Found
25.007. | 90 | 90.002. 1. | H2 Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 29904 | 0 | 5435 | 0 | 894 | 0 | 0 | 29904 | 29904 | 0% | 0 | 0 | 40 | 24429 | Not Found | Not Found
25.007. | 90 | 90.003. 1. | H2 Field Staff (Matl Manager Office Manager Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 9828 | 0 | 433.5 | 0 | 102 | 0 | 0 | 9828 | 9828 | 0% | 0 | 0 | 102 | 9292.5 | Not Found | Not Found
25.007. | 90 | 90.004. 1. | H2 Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 34188 | 0 | 4476.5 | 0 | 1472 | 0 | 0 | 34188 | 34188 | 0% | 0 | 0 | 437 | 29274.5 | Not Found | Not Found
25.007. | 90 | 90.005. 1. | H2 HR Staff | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 2184 | 0 | 270 | 0 | 94 | 0 | 0 | 2184 | 2184 | 0% | 0 | 0 | 43.5 | 1870.5 | Not Found | Not Found
25.007. | 90 | 90.950. 1. | H2 Relocation Expenses | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.007. | 91 | 91.002. 1. | H2 General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 12516 | 0 | 3456.5 | 0 | 484 | 0 | 0 | 12516 | 12516 | 0% | 0 | 0 | 484.5 | 8575 | Not Found | Not Found
25.007. | 91 | 91.002. 3. | H2 Survey Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4368 | 0 | 4475.5 | 0 | 57 | 0 | 0 | 5368 | 5368 | 0% | 0 | 0 | 58.5 | -166 | Not Found | Not Found
25.007. | 91 | 91.002. 4. | H2 Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 15288 | 0 | 17667.5 | 0 | 1143 | 0 | 0 | 15288 | 15288 | 0% | 0 | 0 | 1141 | -3520.5 | Not Found | Not Found
25.007. | 91 | 91.002. 5. | H2 Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 12768 | 0 | 15639.5 | 0 | 1267 | 0 | 0 | 12768 | 12768 | 0% | 0 | 0 | 1268 | -4139.5 | Not Found | Not Found
25.007. | 91 | 91.002. 6. | H2 General Site Labor (Fire Watch Ice/Water etc) | CODE NOT PROGRESSABLE | 0 | 4368 | 0 | 10016.5 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0% | 0 | 0 | 0 | -5648.5 | Not Found | Not Found
25.007. | 91 | 91.003. 1. | H2 Tool Room Attendant | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4368 | 0 | 1096.5 | 0 | 13 | 0 | 0 | 4368 | 4368 | 0% | 0 | 0 | 13 | 3258.5 | Not Found | Not Found
25.007. | 91 | 91.004. 1. | H2 Orientation & Drug Testing | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -25 | Not Found | Not Found
25.007. | 91 | 91.005. 1. | H2 Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 350 | 0 | 26 | 0 | 0 | 0 | 0 | 350 | 350 | 0% | 0 | 0 | 0 | 324 | Not Found | Not Found
25.007. | 92 | 92.100. 1. | H2 Job Set Up Labor | CODE NOT PROGRESSABLE | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 0% | 0 | 0 | 0 | 900 | Not Found | Not Found
25.007. | 93 | 93.006. 1. | RIG Welder Pay | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.007. | 97 | 97.100. 1. | Incorrect Generator Demob | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -251 | Not Found | Not Found
25.007. | 98 | 98.100. 3. | H2 Ground Lug Welding | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -44 | Not Found | Not Found
25.007. | 98 | 98.100. 4. | H3 Ductbank (35kV MER Pad T&M ) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 1796.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -1796.5 | Not Found | Not Found
25.007. | 98 | 98. H2. DB. 1 | H2 LS Ductbank (35kV/Telecom) - Labor | PF CHECK | 668 | 25119.82 | 227.12 | 5027.5 | 5.01 | 135 | 188.3987 | 8540.7388 | 25119.82 | 14786.7647 | 34% | 1.4 | 1.7 | 135.5 | 19956.82 | Not Found | Not Found
25.007. | 98 | 98. H2.CUP. 1 | H2 LS CUP FNDs - Labor |  | 1928 | 7253.28 | 1928 | 4597.5 | 0 | 0 | 0 | 7253.28 | 7253.28 | 4597.5 | 100% | 0 | 1.58 | 0 | 2655.78 | Not Found | Not Found
25.007. | 98 | 98.200. 6. | H2 OSM Yard Mob/Demob & Maintenance | CODE NOT PROGRESSABLE | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | Not Found | Not Found
25.007. | 99 | 99.601. . | H2 Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 20 | 20.100. . | Sitewide Dewatering Budget | CODE NOT PROGRESSABLE | 0 | 2880 | 0 | 50 | 0 | 0 | 0 | 0 | 2880 | 2880 | 0% | 0 | 0 | 0 | 2830 | Not Found | Not Found
25.008. | 22 | 22.100. . | Direct Burial Conduit (2") - Labor | CODE NOT PROGRESSABLE | 0 | 9540.8 | 0 | 0 | 0 | 0 | 0 | 0 | 9540.8 | 9540.8 | 0% | 0 | 0 | 0 | 9540.8 | Not Found | Not Found
25.008. | 26 | 26.100. . | Grout Labor (per work package) |  | 33 | 1551.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1551.6 | 1551.6 | 0% | 0 | 0 | 0 | 1551.6 | Not Found | Not Found
25.008. | 26 | 26.105. 1. | Grout - C-9105 - Bldg. 01 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 26 | 26.101. 1. | Grout - C-9101 - Bldg. 01 |  | 8 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0% | 0 | 0 | 0 | 80 | 80 | 0
25.008. | 26 | 26.102. 1. | Grout - C-9102 - Bldg. 01 |  | 22 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 0% | 0 | 0 | 0 | 220 | 220 | 0
25.008. | 26 | 26.103. 1. | Grout - C-9103 - Bldg. 01 |  | 12 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0% | 0 | 0 | 0 | 120 | 120 | 0
25.008. | 26 | 26.106. 1. | Grout - C-9106 - Bldg. 01 |  | 36 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 0% | 0 | 0 | 0 | 360 | 360 | 0
25.008. | 26 | 26.107. 1. | Grout - C-9107 - Bldg. 01 |  | 24 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0% | 0 | 0 | 0 | 240 | 240 | 0
25.008. | 26 | 26.109. 1. | Grout - C-9109 - Bldg. 01 |  | 8 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0% | 0 | 0 | 0 | 80 | 80 | 0
25.008. | 26 | 26.109. 2. | Grout - C-9109 - Bldg. 02 |  | 18 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 0% | 0 | 0 | 0 | 180 | 180 | 0
25.008. | 26 | 26.110. 1. | Grout - C-9110 - Bldg. 01 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 26 | 26.110. 2. | Grout - C-9110 - Bldg. 02 |  | 48 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0% | 0 | 0 | 0 | 480 | 480 | 0
25.008. | 26 | 26.111. 1. | Grout - C-9111 - Bldg. 01 |  | 44 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 0% | 0 | 0 | 0 | 440 | 440 | 0
25.008. | 26 | 26.111. 2. | Grout - C-9112 - Bldg. 02 |  | 8 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0% | 0 | 0 | 0 | 80 | 80 | 0
25.008. | 26 | 26.113. 2. | Grout - C-9113 - Bldg. 02 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 26 | 26.114. 2. | Grout - C-9114 - Bldg. 02 |  | 68 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 680 | 0% | 0 | 0 | 0 | 680 | 680 | 0
25.008. | 26 | 26.115. 2. | Grout - C-9115 - Bldg. 02 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 26 | 26.117. 3. | Grout - C-9117 - Bldg. 03 |  | 18 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 0% | 0 | 0 | 0 | 180 | 180 | 0
25.008. | 26 | 26.118. 3. | Grout - C-9118 - Bldg. 03 |  | 64 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 640 | 0% | 0 | 0 | 0 | 640 | 640 | 0
25.008. | 26 | 26.119. 2. | Grout - C-9119 - Bldg. 02 |  | 8 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0% | 0 | 0 | 0 | 80 | 80 | 0
25.008. | 26 | 26.119. 3. | Grout - C-9119 - Bldg. 03 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 26 | 26.121. 3. | Grout - C-9121 - Bldg. 03 |  | 18 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 0% | 0 | 0 | 0 | 180 | 180 | 0
25.008. | 26 | 26.122. 3. | Grout - C-9122 - Bldg. 03 |  | 50 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0% | 0 | 0 | 0 | 500 | 500 | 0
25.008. | 26 | 26.123. 3. | Grout - C-9123 - Bldg. 03 |  | 20 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200 | 0
25.008. | 60 | 60.100. . | MVDB - Cast-In-Place Labor (per WP) |  | 611 | 747.33 | 0 | 0 | 0 | 0 | 0 | 0 | 747.33 | 747.33 | 0% | 0 | 0 | 0 | 747.33 | Not Found | Not Found
25.008. | 60 | 60.101. 1. | MV: CIP DB - C-9101 - Bldg. 01 | PF CHECK | 228 | 171 | 140.904 | 60 | 9.804 | 40 | 7.353 | 105.678 | 171 | 97.0874 | 62% | 0.18 | 1.76 | 40 | 71 | 171 | 105.75
25.008. | 60 | 60.102. 1. | MV: CIP DB - C-9102 - Bldg. 01 |  | 789 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 592 | 592 | 0% | 0 | 0 | 0 | 592 | 591.75 | 0
25.008. | 60 | 60.103. 1. | MV: CIP DB - C-9103 - Bldg. 01 | PF CHECK OVERRUNNING PROJECTION | 232 | 174 | 64.96 | 60.5 | 64.96 | 60 | 48.72 | 48.72 | 174 | 216.0714 | 28% | 0.81 | 0.81 | 60.5 | 53 | 174 | 48.75
25.008. | 60 | 60.105. 1. | MV: CIP DB - C-9105 - Bldg. 01 | PF CHECK OVERRUNNING PROJECTION | 109 | 82 | 99.19 | 76 | 2.18 | 10 | 1.64 | 74.62 | 82 | 83.5165 | 91% | 0.16 | 0.98 | 10 | -4 | 81.75 | 55.425
25.008. | 60 | 60.106. 1. | MV: CIP DB - C-9106 - Bldg. 01 |  | 166 | 125 | 4.482 | 10 | 0 | 0 | 0 | 3.375 | 125 | 125 | 3% | 0 | 0.34 | 0 | 115 | 124.5 | 3
25.008. | 60 | 60.107. 1. | MV: CIP DB - C-9107 - Bldg. 01 | PF CHECK | 998 | 749 | 524.948 | 256.25 | 19.96 | 39 | 14.98 | 393.974 | 749 | 487.1673 | 53% | 0.38 | 1.54 | 39.25 | 453.5 | 748.5 | 393.5
25.008. | 60 | 60.109. 1. | MV: CIP DB - C-9109 - Bldg. 01 |  | 267 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0% | 0 | 0 | 0 | 200 | 200.25 | 0
25.008. | 60 | 60.109. 2. | MV: CIP DB - C-9109 - Bldg. 02 |  | 217 | 163 | 6.076 | 7 | 0 | 0 | 0 | 4.564 | 163 | 163 | 3% | 0 | 0.65 | 0 | 156 | 162.75 | 0
25.008. | 60 | 60.110. 1. | MV: CIP DB - C-9110 - Bldg. 01 |  | 955 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0% | 0 | 0 | 0 | 716 | 716.25 | 0
25.008. | 60 | 60.110. 2. | MV: CIP DB - C-9110 - Bldg. 02 |  | 762 | 572 | 18.288 | 110 | 0 | 0 | 0 | 13.728 | 572 | 572 | 2% | 0 | 0.12 | 0 | 462 | 571.5 | 10.05
25.008. | 60 | 60.111. 1. | MV: CIP DB - C-9111 - Bldg. 01 |  | 1846 | 1385 | 0 | 0 | 0 | 0 | 0 | 0 | 1385 | 1385 | 0% | 0 | 0 | 0 | 1385 | 1384.5 | 0
25.008. | 60 | 60.111. 2. | MV: CIP DB - C-9111 - Bldg. 02 |  | 249 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 187 | 0% | 0 | 0 | 0 | 187 | 186.75 | 0
25.008. | 60 | 60.113. 2. | MV: CIP DB - C-9113 - Bldg. 02 |  | 197 | 148 | 9.456 | 9 | 0 | 0 | 0 | 7.104 | 148 | 148 | 5% | 0 | 0.79 | 0 | 139 | 147.75 | 3.75
25.008. | 60 | 60.114. 2. | MV: CIP DB - C-9114 - Bldg. 02 |  | 1242 | 932 | 43.47 | 79.5 | 0 | 0 | 0 | 32.62 | 932 | 932 | 4% | 0 | 0.41 | 0 | 852.5 | 931.5 | 33
25.008. | 60 | 60.115. 2. | MV: CIP DB - C-9115 - Bldg. 02 |  | 1805 | 1354 | 0 | 0 | 0 | 0 | 0 | 0 | 1354 | 1354 | 0% | 0 | 0 | 0 | 1354 | 1353.75 | 0
25.008. | 60 | 60.117. 3. | MV: CIP DB - C-9117 - Bldg. 03 |  | 207 | 155.25 | 0 | 30 | 0 | 0 | 0 | 0 | 155.25 | 155.25 | 0% | 0 | 0 | 0 | 125.25 | 155.25 | 0
25.008. | 60 | 60.118. 2. | MV: CIP DB - C-9118 - Bldg. 02 |  | 19 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0% | 0 | 0 | 0 | 14 | 14.25 | 0
25.008. | 60 | 60.118. 3. | MV: CIP DB - C-9118 - Bldg. 03 | PF CHECK | 866 | 649.5 | 19.918 | 20.5 | 19.918 | 20 | 14.9385 | 14.9385 | 649.5 | 649.5 | 2% | 0.75 | 0.73 | 20.5 | 608.5 | 649.5 | 15
25.008. | 60 | 60.119. 2. | MV: CIP DB - C-9119 - Bldg. 02 |  | 261 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 196 | 0% | 0 | 0 | 0 | 196 | 195.75 | 0
25.008. | 60 | 60.119. 3. | MV: CIP DB - C-9119 - Bldg. 03 |  | 1154 | 865.5 | 0 | 0 | 0 | 0 | 0 | 0 | 865.5 | 865.5 | 0% | 0 | 0 | 0 | 865.5 | 865.5 | 0
25.008. | 60 | 60.121. 3. | MV: CIP DB - C-9121 - Bldg. 03 |  | 291 | 218.25 | 0 | 34.5 | 0 | 0 | 0 | 0 | 218.25 | 218.25 | 0% | 0 | 0 | 0 | 183.75 | 218.25 | 0
25.008. | 60 | 60.122. 3. | MV: CIP DB - C-9122 - Bldg. 03 |  | 1109 | 831.75 | 0 | 10 | 0 | 0 | 0 | 0 | 831.75 | 831.75 | 0% | 0 | 0 | 0 | 821.75 | 831.75 | 9
25.008. | 60 | 60.123. 3. | MV: CIP DB - C-9123 - Bldg. 03 |  | 762 | 571.5 | 0 | 0 | 0 | 0 | 0 | 0 | 571.5 | 571.5 | 0% | 0 | 0 | 0 | 571.5 | 571.5 | 0
25.008. | 60 | 60.999. 1. | Prefab Conduit Bends - Bldg. 1 |  | 2496 | 1872 | 449.28 | 61 | 0 | 0 | 0 | 336.96 | 1872 | 1872 | 18% | 0 | 5.52 | 0 | 1811 | 1872 | 396.15
25.008. | 60 | 60.999. 2. | Prefab Conduit Bends - Bldg. 2 |  | 1372 | 1029 | 23.324 | 20 | 0 | 0 | 0 | 17.493 | 1029 | 1029 | 2% | 0 | 0.87 | 0 | 1009 | 1029 | 12
25.008. | 60 | 60.999. 3. | Prefab Conduit Bends - Bldg. 3 |  | 1712 | 1284 | 0 | 0 | 0 | 0 | 0 | 0 | 1284 | 1284 | 0% | 0 | 0 | 0 | 1284 | 1284 | 0
25.008. | 61 | 61.100. . | MVDB - Precast Ductbank Labor (per WP) |  | 1320 | 16384.4 | 0 | 0 | 0 | 0 | 0 | 0 | 16384.4 | 16384.4 | 0% | 0 | 0 | 0 | 16384.4 | Not Found | Not Found
25.008. | 61 | 61.101. 1. | MV: Precast DB - C-9101 - Bldg. 01 | PF CHECK | 1100 | 495 | 640.2 | 101 | 160.6 | 30 | 72.27 | 288.09 | 495 | 173.5395 | 58% | 2.41 | 2.85 | 30.5 | 363.5 | 495 | 288
25.008. | 61 | 61.102. 1. | MV: Precast DB - C-9102 - Bldg. 01 |  | 3900 | 1755 | 0 | 0 | 0 | 0 | 0 | 0 | 1755 | 1755 | 0% | 0 | 0 | 0 | 1755 | 1755 | 0
25.008. | 61 | 61.103. 1. | MV: Precast DB - C-9103 - Bldg. 01 |  | 780 | 351 | 208.26 | 20 | 0 | 0 | 0 | 93.717 | 351 | 74.9064 | 27% | 0 | 4.69 | 0 | 331 | 351 | 90
25.008. | 61 | 61.105. 1. | MV: Precast DB - C-9105 - Bldg. 01 |  | 240 | 108 | 199.92 | 58.5 | 0 | 0 | 0 | 89.964 | 108 | 70.2281 | 83% | 0 | 1.54 | 0 | 49.5 | 108 | 73.8
25.008. | 61 | 61.106. 1. | MV: Precast DB - C-9106 - Bldg. 01 |  | 480 | 216 | 349.92 | 28 | 0 | 0 | 0 | 157.464 | 216 | 38.4088 | 73% | 0 | 5.62 | 0 | 188 | 216 | 90
25.008. | 61 | 61.107. 1. | MV: Precast DB - C-9107 - Bldg. 01 | PF CHECK | 4060 | 1827 | 2634.94 | 621 | 85.26 | 30 | 38.367 | 1185.723 | 1827 | 956.8567 | 65% | 1.28 | 1.91 | 31 | 1175 | 1827 | 1185.3
25.008. | 61 | 61.109. 1. | MV: Precast DB - C-9109 - Bldg. 01 |  | 1180 | 531 | 0 | 0 | 0 | 0 | 0 | 0 | 531 | 531 | 0% | 0 | 0 | 0 | 531 | 531 | 0
25.008. | 61 | 61.109. 2. | MV: Precast DB - C-9109 - Bldg. 02 |  | 1320 | 594 | 58.08 | 17 | 0 | 0 | 0 | 26.136 | 594 | 594 | 4% | 0 | 1.54 | 0 | 577 | 594 | 27
25.008. | 61 | 61.110. 1. | MV: Precast DB - C-9110 - Bldg. 01 |  | 3860 | 1737 | 19.3 | 17 | 0 | 0 | 0 | 8.685 | 1737 | 1737 | 1% | 0 | 0.51 | 0 | 1720 | 1737 | 0
25.008. | 61 | 61.110. 2. | MV: Precast DB - C-9110 - Bldg. 02 |  | 5080 | 2286 | 208.28 | 60.5 | 0 | 0 | 0 | 93.726 | 2286 | 2286 | 4% | 0 | 1.55 | 0 | 2225.5 | 2286 | 81
25.008. | 61 | 61.111. 1. | MV: Precast DB - C-9111 - Bldg. 01 |  | 5160 | 2322 | 0 | 0 | 0 | 0 | 0 | 0 | 2322 | 2322 | 0% | 0 | 0 | 0 | 2322 | 2322 | 0
25.008. | 61 | 61.111. 2. | MV: Precast DB - C-9111 - Bldg. 02 |  | 1000 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 0% | 0 | 0 | 0 | 450 | 450.002 | 0
25.008. | 61 | 61.113. 2. | MV: Precast DB - C-9113 - Bldg. 02 |  | 1320 | 594 | 39.6 | 9 | 0 | 0 | 0 | 17.82 | 594 | 594 | 3% | 0 | 1.98 | 0 | 585 | 594 | 18
25.008. | 61 | 61.114. 2. | MV: Precast DB - C-9114 - Bldg. 02 |  | 5460 | 2457 | 283.92 | 52 | 0 | 0 | 0 | 127.764 | 2457 | 2457 | 5% | 0 | 2.46 | 0 | 2405 | 2457.006 | 117
25.008. | 61 | 61.115. 2. | MV: Precast DB - C-9115 - Bldg. 02 |  | 4160 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 | 1872 | 1872 | 0% | 0 | 0 | 0 | 1872 | 1872.001 | 0
25.008. | 61 | 61.117. 3. | MV: Precast DB - C-9117 - Bldg. 03 |  | 1320 | 594 | 0 | 12 | 0 | 0 | 0 | 0 | 594 | 594 | 0% | 0 | 0 | 0 | 582 | 594 | 9
25.008. | 61 | 61.118. 2. | MV: Precast DB - C-9118 - Bldg. 02 |  | 40 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0% | 0 | 0 | 0 | 18 | 18 | 0
25.008. | 61 | 61.118. 3. | MV: Precast DB - C-9118 - Bldg. 03 |  | 5480 | 2466 | 0 | 16.5 | 0 | 0 | 0 | 0 | 2466 | 2466 | 0% | 0 | 0 | 0 | 2449.5 | 2466 | 27
25.008. | 61 | 61.119. 2. | MV: Precast DB - C-9119 - Bldg. 02 |  | 700 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 315 | 0% | 0 | 0 | 0 | 315 | 315 | 0
25.008. | 61 | 61.119. 3. | MV: Precast DB - C-9119 - Bldg. 03 |  | 3320 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 1494 | 1494 | 0% | 0 | 0 | 0 | 1494 | 1494 | 0
25.008. | 61 | 61.121. 3. | MV: Precast DB - C-9121 - Bldg. 03 |  | 1240 | 558 | 0 | 12 | 0 | 0 | 0 | 0 | 558 | 558 | 0% | 0 | 0 | 0 | 546 | 558 | 9
25.008. | 61 | 61.122. 3. | MV: Precast DB - C-9122 - Bldg. 03 |  | 4460 | 2007 | 187.32 | 50.5 | 0 | 0 | 0 | 84.294 | 2007 | 2007 | 4% | 0 | 1.67 | 0 | 1956.5 | 2007 | 68.401
25.008. | 61 | 61.123. 3. | MV: Precast DB - C-9123 - Bldg. 03 |  | 1900 | 855 | 0 | 0 | 0 | 0 | 0 | 0 | 855 | 855 | 0% | 0 | 0 | 0 | 855 | 855 | 0
25.008. | 61 | 61.999. 1. | Receive & Inspect Precast DB - Bldg. 1 | PF CHECK | 1038 | 1038 | 285.45 | 116 | 49.824 | 30 | 49.824 | 285.45 | 1038 | 421.8182 | 28% | 1.66 | 2.46 | 30 | 892 | 1038 | 285
25.008. | 61 | 61.999. 2. | Receive & Inspect Precast DB - Bldg. 2 |  | 954 | 954 | 56.286 | 3 | 0 | 0 | 0 | 56.286 | 954 | 954 | 6% | 0 | 18.76 | 0 | 951 | 954.009 | 56
25.008. | 61 | 61.999. 3. | Receive & Inspect Precast DB - Bldg. 3 |  | 886 | 886 | 0 | 30.5 | 0 | 0 | 0 | 0 | 886 | 886 | 0% | 0 | 0 | 0 | 855.5 | 886 | 10
25.008. | 62 | 62.100. . | MVDB - Excavation (per WP) |  | 88934.8 | 3081.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3081.5 | 3081.5 | 0% | 0 | 0 | 0 | 3081.5 | Not Found | Not Found
25.008. | 62 | 62.101. 1. | MV: Excavation - C-9101 - Bldg. 01 | PF CHECK | 3853.3 | 1255.8 | 2570.151 | 360.5 | 493.222 | 148 | 160.7423 | 837.6186 | 1255.8 | 540.4798 | 67% | 1.09 | 2.32 | 148 | 747.3 | 1255.846 | 837.51
25.008. | 62 | 62.102. 1. | MV: Excavation - C-9102 - Bldg. 01 |  | 9994.9 | 3243 | 0 | 0 | 0 | 0 | 0 | 0 | 3243 | 3243 | 0% | 0 | 0 | 0 | 3243 | 3243.01 | 0
25.008. | 62 | 62.103. 1. | MV: Excavation - C-9103 - Bldg. 01 | PF CHECK | 3185.8 | 975.9 | 1468.654 | 253.5 | 200.706 | 50 | 61.4819 | 449.89 | 975.9 | 549.8915 | 46% | 1.23 | 1.77 | 50 | 672.4 | 975.907 | 450.075
25.008. | 62 | 62.105. 1. | MV: Excavation - C-9105 - Bldg. 01 |  | 3081.8 | 875.4 | 1488.509 | 218.5 | 0 | 0 | 0 | 422.8181 | 875.4 | 452.3811 | 48% | 0 | 1.94 | 0 | 656.9 | 875.409 | 351.532
25.008. | 62 | 62.106. 1. | MV: Excavation - C-9106 - Bldg. 01 | PF CHECK | 4366.7 | 1197.1 | 1091.675 | 302.25 | 222.702 | 186 | 61.0522 | 299.275 | 1197.1 | 1197.1 | 25% | 0.33 | 0.99 | 187.75 | 707.1 | 1197.134 | 298.761
25.008. | 62 | 62.107. 1. | MV: Excavation - C-9107 - Bldg. 01 | PF CHECK | 11424.9 | 3720.3 | 6409.369 | 893 | 708.344 | 261 | 230.6587 | 2087.0883 | 3720.3 | 1591.8003 | 56% | 0.88 | 2.34 | 261.5 | 2565.8 | 3720.275 | 2085.84
25.008. | 62 | 62.109. 1. | MV: Excavation - C-9109 - Bldg. 01 |  | 4172.4 | 1367.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1367.6 | 1367.6 | 0% | 0 | 0 | 0 | 1367.6 | 1367.581 | 0
25.008. | 62 | 62.109. 2. | MV: Excavation - C-9109 - Bldg. 02 |  | 5441.7 | 1710.2 | 43.534 | 30 | 0 | 0 | 0 | 13.6817 | 1710.2 | 1710.2 | 1% | 0 | 0.46 | 0 | 1680.2 | 1710.199 | 12.912
25.008. | 62 | 62.110. 1. | MV: Excavation - C-9110 - Bldg. 01 |  | 9978.9 | 3260.7 | 0 | 0 | 0 | 0 | 0 | 0 | 3260.7 | 3260.7 | 0% | 0 | 0 | 0 | 3260.7 | 3260.656 | 0
25.008. | 62 | 62.110. 2. | MV: Excavation - C-9110 - Bldg. 02 |  | 14618.1 | 4602.7 | 745.523 | 113 | 0 | 0 | 0 | 234.7377 | 4602.7 | 4602.7 | 5% | 0 | 2.08 | 0 | 4489.7 | 4602.713 | 205.346
25.008. | 62 | 62.111. 1. | MV: Excavation - C-9111 - Bldg. 01 |  | 17927.9 | 5764.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5764.5 | 5764.5 | 0% | 0 | 0 | 0 | 5764.5 | 5764.453 | 0
25.008. | 62 | 62.111. 2. | MV: Excavation - C-9111 - Bldg. 02 |  | 3007.1 | 959.7 | 0 | 0 | 0 | 0 | 0 | 0 | 959.7 | 959.7 | 0% | 0 | 0 | 0 | 959.7 | 959.729 | 0
25.008. | 62 | 62.113. 2. | MV: Excavation - C-9113 - Bldg. 02 |  | 5665.5 | 1765.3 | 75.119 | 10 | 0 | 0 | 0 | 23.4062 | 1765.3 | 1765.3 | 1% | 0 | 2.34 | 0 | 1755.3 | 1765.305 | 15.566
25.008. | 62 | 62.114. 2. | MV: Excavation - C-9114 - Bldg. 02 |  | 18062.8 | 5576.4 | 1174.082 | 87.5 | 0 | 0 | 0 | 362.466 | 5576.4 | 5576.4 | 7% | 0 | 4.14 | 0 | 5488.9 | 5576.373 | 332.087
25.008. | 62 | 62.115. 2. | MV: Excavation - C-9115 - Bldg. 02 |  | 15127.1 | 5062.4 | 166.398 | 20.5 | 0 | 0 | 0 | 55.6864 | 5062.4 | 5062.4 | 1% | 0 | 2.72 | 0 | 5041.9 | 5062.42 | 58
25.008. | 62 | 62.117. 3. | MV: Excavation - C-9117 - Bldg. 03 |  | 7456.8 | 2415.5 | 0 | 27.5 | 0 | 0 | 0 | 0 | 2415.5 | 2415.5 | 0% | 0 | 0 | 0 | 2388 | 2415.473 | 18.081
25.008. | 62 | 62.118. 2. | MV: Excavation - C-9118 - Bldg. 02 |  | 98.8 | 34.6 | 0 | 0 | 0 | 0 | 0 | 0 | 34.6 | 34.6 | 0% | 0 | 0 | 0 | 34.6 | 34.573 | 0
25.008. | 62 | 62.118. 3. | MV: Excavation - C-9118 - Bldg. 03 | PF CHECK | 24053 | 7719.4 | 1419.127 | 96 | 553.219 | 40 | 177.5462 | 455.4446 | 7719.4 | 7719.4 | 6% | 4.44 | 4.74 | 40.5 | 7582.9 | 7719.422 | 455.008
25.008. | 62 | 62.119. 2. | MV: Excavation - C-9119 - Bldg. 02 |  | 3309.6 | 1065.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1065.5 | 1065.5 | 0% | 0 | 0 | 0 | 1065.5 | 1065.525 | 0
25.008. | 62 | 62.119. 3. | MV: Excavation - C-9119 - Bldg. 03 |  | 16773.8 | 5638.8 | 0 | 0 | 0 | 0 | 0 | 0 | 5638.8 | 5638.8 | 0% | 0 | 0 | 0 | 5638.8 | 5638.785 | 0
25.008. | 62 | 62.121. 3. | MV: Excavation - C-9121 - Bldg. 03 |  | 8736.8 | 2863.5 | 0 | 21 | 0 | 0 | 0 | 0 | 2863.5 | 2863.5 | 0% | 0 | 0 | 0 | 2842.5 | 2863.473 | 30.197
25.008. | 62 | 62.122. 3. | MV: Excavation - C-9122 - Bldg. 03 |  | 20515.3 | 6643.7 | 0 | 28.5 | 0 | 0 | 0 | 0 | 6643.7 | 6643.7 | 0% | 0 | 0 | 0 | 6615.2 | 6643.69 | 97.449
25.008. | 62 | 62.123. 3. | MV: Excavation - C-9123 - Bldg. 03 |  | 11972.2 | 3958.3 | 0 | 0 | 0 | 0 | 0 | 0 | 3958.3 | 3958.3 | 0% | 0 | 0 | 0 | 3958.3 | 3958.285 | 0
25.008. | 63 | 63.100. . | MVDB - Backfill & Compaction (per WP) |  | 74925.9 | 38101.2 | 0 | 0 | 0 | 0 | 0 | 0 | 38101.2 | 38101.2 | 0% | 0 | 0 | 0 | 38101.2 | Not Found | Not Found
25.008. | 63 | 63.101. 1. | MV: Backfill - C-9101 - Bldg. 01 | PF CHECK | 6055 | 2119 | 3487.68 | 346 | 2173.745 | 244 | 760.721 | 1220.544 | 2119 | 600.6944 | 58% | 3.12 | 3.53 | 245 | 1528 | 2119.352 | 1220.243
25.008. | 63 | 63.102. 1. | MV: Backfill - C-9102 - Bldg. 01 |  | 15622 | 5468 | 0 | 0 | 0 | 0 | 0 | 0 | 5468 | 5468 | 0% | 0 | 0 | 0 | 5468 | 5467.655 | 0
25.008. | 63 | 63.103. 1. | MV: Backfill - C-9103 - Bldg. 01 | PF CHECK | 4521 | 1582 | 646.503 | 101 | 63.294 | 50 | 22.148 | 226.226 | 1582 | 1582 | 14% | 0.44 | 2.24 | 51 | 1430 | 1582.436 | 225.493
25.008. | 63 | 63.105. 1. | MV: Backfill - C-9105 - Bldg. 01 | PF CHECK | 4028 | 1410 | 1647.452 | 194.5 | 426.968 | 44 | 149.46 | 576.69 | 1410 | 475.5501 | 41% | 3.4 | 2.96 | 43.5 | 1172 | 1409.962 | 577.191
25.008. | 63 | 63.106. 1. | MV: Backfill - C-9106 - Bldg. 01 |  | 5537 | 1938 | 902.531 | 116.5 | 0 | 0 | 0 | 315.894 | 1938 | 1938 | 16% | 0 | 2.71 | 0 | 1821.5 | 1937.879 | 194.951
25.008. | 63 | 63.107. 1. | MV: Backfill - C-9107 - Bldg. 01 |  | 17894 | 6263 | 6245.006 | 536 | 0 | 0 | 0 | 2185.787 | 6263 | 1535.8166 | 35% | 0 | 4.08 | 0 | 5727 | 6262.749 | 2185.666
25.008. | 63 | 63.109. 1. | MV: Backfill - C-9109 - Bldg. 01 |  | 6605 | 2312 | 0 | 0 | 0 | 0 | 0 | 0 | 2312 | 2312 | 0% | 0 | 0 | 0 | 2312 | 2311.608 | 0
25.008. | 63 | 63.109. 2. | MV: Backfill - C-9109 - Bldg. 02 |  | 8153 | 2853 | 81.53 | 18 | 0 | 0 | 0 | 28.53 | 2853 | 2853 | 1% | 0 | 1.59 | 0 | 2835 | 2853.391 | 21.437
25.008. | 63 | 63.110. 1. | MV: Backfill - C-9110 - Bldg. 01 |  | 15734 | 5507 | 0 | 0 | 0 | 0 | 0 | 0 | 5507 | 5507 | 0% | 0 | 0 | 0 | 5507 | 5506.878 | 0
25.008. | 63 | 63.110. 2. | MV: Backfill - C-9110 - Bldg. 02 |  | 21994 | 7698 | 395.892 | 53 | 0 | 0 | 0 | 138.564 | 7698 | 7698 | 2% | 0 | 2.61 | 0 | 7645 | 7697.827 | 140.876
25.008. | 63 | 63.111. 1. | MV: Backfill - C-9111 - Bldg. 01 |  | 27555 | 9644 | 0 | 0 | 0 | 0 | 0 | 0 | 9644 | 9644 | 0% | 0 | 0 | 0 | 9644 | 9644.12 | 0
25.008. | 63 | 63.111. 2. | MV: Backfill - C-9111 - Bldg. 02 |  | 4578 | 1602 | 0 | 0 | 0 | 0 | 0 | 0 | 1602 | 1602 | 0% | 0 | 0 | 0 | 1602 | 1602.312 | 0
25.008. | 63 | 63.113. 2. | MV: Backfill - C-9113 - Bldg. 02 |  | 8379 | 2933 | 75.411 | 39 | 0 | 0 | 0 | 26.397 | 2933 | 2933 | 1% | 0 | 0.68 | 0 | 2894 | 2932.665 | 25.976
25.008. | 63 | 63.114. 2. | MV: Backfill - C-9114 - Bldg. 02 |  | 26371 | 9230 | 606.533 | 60.5 | 0 | 0 | 0 | 212.29 | 9230 | 9230 | 2% | 0 | 3.51 | 0 | 9169.5 | 9229.754 | 207.648
25.008. | 63 | 63.115. 2. | MV: Backfill - C-9115 - Bldg. 02 |  | 24698 | 8644 | 0 | 0 | 0 | 0 | 0 | 0 | 8644 | 8644 | 0% | 0 | 0 | 0 | 8644 | 8644.375 | 3.5
25.008. | 63 | 63.117. 3. | MV: Backfill - C-9117 - Bldg. 03 |  | 7880 | 2758 | 0 | 14 | 0 | 0 | 0 | 0 | 2758 | 2758 | 0% | 0 | 0 | 0 | 2744 | 2757.923 | 0
25.008. | 63 | 63.118. 2. | MV: Backfill - C-9118 - Bldg. 02 |  | 168 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 59 | 0% | 0 | 0 | 0 | 59 | 58.942 | 0
25.008. | 63 | 63.118. 3. | MV: Backfill - C-9118 - Bldg. 03 |  | 25348 | 8872 | 0 | 14 | 0 | 0 | 0 | 0 | 8872 | 8872 | 0% | 0 | 0 | 0 | 8858 | 8871.837 | 51.294
25.008. | 63 | 63.119. 2. | MV: Backfill - C-9119 - Bldg. 02 |  | 5106 | 1787 | 0 | 0 | 0 | 0 | 0 | 0 | 1787 | 1787 | 0% | 0 | 0 | 0 | 1787 | 1787.032 | 0
25.008. | 63 | 63.119. 3. | MV: Backfill - C-9119 - Bldg. 03 |  | 17720 | 6202 | 0 | 0 | 0 | 0 | 0 | 0 | 6202 | 6202 | 0% | 0 | 0 | 0 | 6202 | 6202.06 | 0
25.008. | 63 | 63.121. 3. | MV: Backfill - C-9121 - Bldg. 03 |  | 9246 | 3236 | 0 | 14.5 | 0 | 0 | 0 | 0 | 3236 | 3236 | 0% | 0 | 0 | 0 | 3221.5 | 3235.953 | 31.86
25.008. | 63 | 63.122. 3. | MV: Backfill - C-9122 - Bldg. 03 |  | 21699 | 7595 | 260.388 | 34 | 0 | 0 | 0 | 91.14 | 7595 | 7595 | 1% | 0 | 2.68 | 0 | 7561 | 7594.855 | 58.727
25.008. | 63 | 63.123. 3. | MV: Backfill - C-9123 - Bldg. 03 |  | 12595 | 4408 | 0 | 0 | 0 | 0 | 0 | 0 | 4408 | 4408 | 0% | 0 | 0 | 0 | 4408 | 4408.3 | 0
25.008. | 64 | 64.100. . | MVDB - Precast Manholes Labor (per WP) |  | 41 | 7842.3 | 0 | 0 | 0 | 0 | 0 | 0 | 7842.3 | 7842.3 | 0% | 0 | 0 | 0 | 7842.3 | Not Found | Not Found
25.008. | 64 | 64.101. 1. | MV: Vault Installation - C-9101 - Bldg. 01 |  | 4 | 368 | 0.912 | 20 | 0 | 0 | 0 | 83.904 | 368 | 368 | 23% | 0 | 4.2 | 0 | 348 | 368 | 168
25.008. | 64 | 64.102. 1. | MV: Vault Installation - C-9102 - Bldg. 01 |  | 11 | 1012 | 0 | 0 | 0 | 0 | 0 | 0 | 1012 | 1012 | 0% | 0 | 0 | 0 | 1012 | 1012 | 0
25.008. | 64 | 64.103. 1. | MV: Vault Installation - C-9103 - Bldg. 01 |  | 6 | 552 | 1.824 | 40.5 | 0 | 0 | 0 | 167.808 | 552 | 133.2237 | 30% | 0 | 4.14 | 0 | 511.5 | 552 | 210
25.008. | 64 | 64.105. 1. | MV: Vault Installation - C-9105 - Bldg. 01 |  | 8 | 736 | 1.888 | 50.5 | 0 | 0 | 0 | 173.696 | 736 | 736 | 24% | 0 | 3.44 | 0 | 685.5 | 736 | 174
25.008. | 64 | 64.106. 1. | MV: Vault Installation - C-9106 - Bldg. 01 | PF CHECK | 12 | 1104 | 1.368 | 49.5 | 1.368 | 40 | 125.856 | 125.856 | 1104 | 1104 | 11% | 3.15 | 2.54 | 41 | 1013.5 | 1104 | 126
25.008. | 64 | 64.107. 1. | MV: Vault Installation - C-9107 - Bldg. 01 |  | 12 | 1104 | 1.896 | 71.5 | 0 | 0 | 0 | 174.432 | 1104 | 1104 | 16% | 0 | 2.44 | 0 | 1032.5 | 1104 | 174
25.008. | 64 | 64.109. 1. | MV: Vault Installation - C-9109 - Bldg. 01 |  | 4 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 368 | 0% | 0 | 0 | 0 | 368 | 368 | 0
25.008. | 64 | 64.109. 2. | MV: Vault Installation - C-9109 - Bldg. 02 |  | 8 | 736 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 736 | 0% | 0 | 0 | 0 | 736 | 736 | 0
25.008. | 64 | 64.110. 1. | MV: Vault Installation - C-9110 - Bldg. 01 |  | 10 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0% | 0 | 0 | 0 | 920 | 920 | 0
25.008. | 64 | 64.110. 2. | MV: Vault Installation - C-9110 - Bldg. 02 |  | 21 | 1932 | 1.89 | 120 | 0 | 0 | 0 | 173.88 | 1932 | 1932 | 9% | 0 | 1.45 | 0 | 1812 | 1932 | 174
25.008. | 64 | 64.111. 1. | MV: Vault Installation - C-9111 - Bldg. 01 |  | 22 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0% | 0 | 0 | 0 | 2024 | 2024 | 0
25.008. | 64 | 64.111. 2. | MV: Vault Installation - C-9111 - Bldg. 02 |  | 4 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 368 | 0% | 0 | 0 | 0 | 368 | 368 | 0
25.008. | 64 | 64.113. 2. | MV: Vault Installation - C-9113 - Bldg. 02 |  | 8 | 736 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 736 | 0% | 0 | 0 | 0 | 736 | 828 | 0
25.008. | 64 | 64.114. 2. | MV: Vault Installation - C-9114 - Bldg. 02 |  | 31 | 2852 | 2.852 | 48.5 | 0 | 0 | 0 | 262.384 | 2852 | 2852 | 9% | 0 | 5.41 | 0 | 2803.5 | 2852 | 303
25.008. | 64 | 64.115. 2. | MV: Vault Installation - C-9115 - Bldg. 02 |  | 10 | 920 | 0.45 | 50.5 | 0 | 0 | 0 | 41.4 | 920 | 920 | 5% | 0 | 0.82 | 0 | 869.5 | 920 | 42
25.008. | 64 | 64.117. 3. | MV: Vault Installation - C-9117 - Bldg. 03 |  | 8 | 736 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 736 | 0% | 0 | 0 | 0 | 736 | 750 | 0
25.008. | 64 | 64.118. 3. | MV: Vault Installation - C-9118 - Bldg. 03 | PF CHECK | 29 | 2668 | 3.277 | 95 | 1.392 | 62 | 128.064 | 301.484 | 2668 | 2668 | 11% | 2.07 | 3.17 | 62.5 | 2510.5 | 2726 | 308
25.008. | 64 | 64.119. 2. | MV: Vault Installation - C-9119 - Bldg. 02 |  | 4 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 368 | 0% | 0 | 0 | 0 | 368 | 368 | 0
25.008. | 64 | 64.119. 3. | MV: Vault Installation - C-9119 - Bldg. 03 |  | 10 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0% | 0 | 0 | 0 | 920 | 940 | 0
25.008. | 64 | 64.121. 3. | MV: Vault Installation - C-9121 - Bldg. 03 |  | 8 | 736 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 736 | 0% | 0 | 0 | 0 | 736 | 752 | 0
25.008. | 64 | 64.122. 3. | MV: Vault Installation - C-9122 - Bldg. 03 |  | 22 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 2024 | 0% | 0 | 0 | 0 | 2024 | 2068 | 0
25.008. | 64 | 64.123. 3. | MV: Vault Installation - C-9123 - Bldg. 03 |  | 10 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 920 | 0% | 0 | 0 | 0 | 920 | 940 | 0
25.008. | 64 | 64.999. 1. | Receive & Inspect Manholes - Bldg. 1 | PF CHECK OVERRUNNING PROJECTION | 89 | 178 | 24.03 | 97 | 14.062 | 60 | 28.124 | 48.06 | 178 | 359.2593 | 27% | 0.47 | 0.5 | 60 | 21 | 178 | 48
25.008. | 64 | 64.999. 2. | Receive & Inspect Manholes - Bldg. 2 |  | 86 | 172 | 6.966 | 15.5 | 0 | 0 | 0 | 13.932 | 172 | 172 | 8% | 0 | 0.9 | 0 | 156.5 | 172 | 14
25.008. | 64 | 64.999. 3. | Receive & Inspect Manholes - Bldg. 3 |  | 87 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 174 | 0% | 0 | 0 | 0 | 174 | 2 | 0
25.008. | 65 | 65.100. . | MVDB - Testing Labor (per WP) |  | 295520 | 9382.7 | 0 | 0 | 0 | 0 | 0 | 0 | 9382.7 | 9382.7 | 0% | 0 | 0 | 0 | 9382.7 | Not Found | Not Found
25.008. | 65 | 65.101. 1. | MV: Testing - C-9101 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 119.52 | 0
25.008. | 65 | 65.102. 1. | MV: Testing - C-9102 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 422.01 | 0
25.008. | 65 | 65.103. 1. | MV: Testing - C-9103 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 91.08 | 0
25.008. | 65 | 65.105. 1. | MV: Testing - C-9105 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 29.34 | 0
25.008. | 65 | 65.106. 1. | MV: Testing - C-9106 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 54.54 | 0
25.008. | 65 | 65.107. 1. | MV: Testing - C-9107 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 453.42 | 0
25.008. | 65 | 65.109. 1. | MV: Testing - C-9109 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 130.23 | 0
25.008. | 65 | 65.109. 2. | MV: Testing - C-9109 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 138.33 | 0
25.008. | 65 | 65.110. 1. | MV: Testing - C-9110 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 433.35 | 0
25.008. | 65 | 65.110. 2. | MV: Testing - C-9110 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 525.78 | 0
25.008. | 65 | 65.111. 1. | MV: Testing - C-9111 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 623.34 | 0
25.008. | 65 | 65.111. 2. | MV: Testing - C-9111 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 112.41 | 0
25.008. | 65 | 65.113. 2. | MV: Testing - C-9113 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 136.53 | 0
25.008. | 65 | 65.114. 2. | MV: Testing - C-9114 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 603.18 | 0
25.008. | 65 | 65.115. 2. | MV: Testing - C-9115 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 536.85 | 0
25.008. | 65 | 65.117. 3. | MV: Testing - C-9117 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 137.43 | 0
25.008. | 65 | 65.118. 3. | MV: Testing - C-9118 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 571.14 | 0
25.008. | 65 | 65.119. 2. | MV: Testing - C-9119 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 86.49 | 0
25.008. | 65 | 65.119. 3. | MV: Testing - C-9119 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 402.66 | 0
25.008. | 65 | 65.121. 3. | MV: Testing - C-9121 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 137.79 | 0
25.008. | 65 | 65.122. 3. | MV: Testing - C-9122 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 501.21 | 0
25.008. | 65 | 65.123. 3. | MV: Testing - C-9123 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 239.58 | 0
25.008. | 66 | 66.100. . | MVDB - Locate Labor (per WP) |  | 73880 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 1341 | 0% | 0 | 0 | 0 | 1341 | Not Found | Not Found
25.008. | 66 | 66.101. 1. | MV: Locate Labor - C-9101 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.102. 1. | MV: Locate Labor - C-9102 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.103. 1. | MV: Locate Labor - C-9103 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.105. 1. | MV: Locate Labor - C-9105 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.106. 1. | MV: Locate Labor - C-9106 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.107. 1. | MV: Locate Labor - C-9107 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.109. 1. | MV: Locate Labor - C-9109 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.109. 2. | MV: Locate Labor - C-9109 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.110. 1. | MV: Locate Labor - C-9110 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.110. 2. | MV: Locate Labor - C-9110 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.111. 1. | MV: Locate Labor - C-9111 - Bldg. 01 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.111. 2. | MV: Locate Labor - C-9111 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.113. 2. | MV: Locate Labor - C-9113 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.114. 2. | MV: Locate Labor - C-9114 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.115. 2. | MV: Locate Labor - C-9115 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.117. 3. | MV: Locate Labor - C-9117 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.118. 3. | MV: Locate Labor - C-9118 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.119. 2. | MV: Locate Labor - C-9119 - Bldg. 02 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.119. 3. | MV: Locate Labor - C-9119 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.121. 3. | MV: Locate Labor - C-9121 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.122. 3. | MV: Locate Labor - C-9122 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 66 | 66.123. 3. | MV: Locate Labor - C-9123 - Bldg. 03 | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 71 | 71.100. . | Telecoms Systems - Precast Trench Install (per WP) |  | 219.9 | 1198.1 | 0 | 0 | 0 | 0 | 0 | 0 | 1198.1 | 1198.1 | 0% | 0 | 0 | 0 | 1198.1 | Not Found | Not Found
25.008. | 71 | 71.101. 1. | Telecoms - Precast Trench - C-8101 - Bldg. 01 |  | 743 | 1697.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1697.25 | 1697.25 | 0% | 0 | 0 | 0 | 1697.25 | 3684.097 | 0
25.008. | 71 | 71.102. 1. | Telecoms - Precast Trench - C-8102 - Bldg. 01 |  | 1144 | 2625 | 0 | 0 | 0 | 0 | 0 | 0 | 2625 | 2625 | 0% | 0 | 0 | 0 | 2625 | 5701.004 | 0
25.008. | 71 | 71.103. 1. | Telecoms - Precast Trench - C-8103 - Bldg. 01 |  | 600 | 1376.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1376.25 | 1376.25 | 0% | 0 | 0 | 0 | 1376.25 | 2988.392 | 0
25.008. | 71 | 71.105. 1. | Telecoms - Precast Trench - C-8105 - Bldg. 01 |  | 669 | 1557.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.5 | 1557.5 | 0% | 0 | 0 | 0 | 1557.5 | 3389.781 | 0
25.008. | 71 | 71.106. 1. | Telecoms - Precast Trench - C-8106 - Bldg. 01 |  | 58 | 130.5 | 0 | 0 | 0 | 0 | 0 | 0 | 130.5 | 130.5 | 0% | 0 | 0 | 0 | 130.5 | 284.238 | 0
25.008. | 71 | 71.107. 1. | Telecoms - Precast Trench - C-8107 - Bldg. 01 |  | 653 | 1599.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1599.25 | 1599.25 | 0% | 0 | 0 | 0 | 1599.25 | 3498.388 | 0
25.008. | 71 | 71.109. 1. | Telecoms - Precast Trench - C-8109 - Bldg. 01 |  | 882 | 1987 | 0 | 0 | 0 | 0 | 0 | 0 | 1987 | 1987 | 0% | 0 | 0 | 0 | 1987 | 4304.719 | 0
25.008. | 71 | 71.109. 2. | Telecoms - Precast Trench - C-8109 - Bldg. 02 |  | 386 | 922 | 0 | 0 | 0 | 0 | 0 | 0 | 922 | 922 | 0% | 0 | 0 | 0 | 922 | 2012.703 | 0
25.008. | 71 | 71.110. 1. | Telecoms - Precast Trench - C-8110 - Bldg. 01 |  | 731 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 1646 | 1646 | 0% | 0 | 0 | 0 | 1646 | 3569.125 | 0
25.008. | 71 | 71.110. 2. | Telecoms - Precast Trench - C-8110 - Bldg. 02 |  | 29 | 65.25 | 0 | 0 | 0 | 0 | 0 | 0 | 65.25 | 65.25 | 0% | 0 | 0 | 0 | 65.25 | 142.767 | 0
25.008. | 71 | 71.111. 1. | Telecoms - Precast Trench - C-8111 - Bldg. 01 |  | 388 | 926.25 | 0 | 0 | 0 | 0 | 0 | 0 | 926.25 | 926.25 | 0% | 0 | 0 | 0 | 926.25 | 1987.701 | 0
25.008. | 71 | 71.111. 2. | Telecoms - Precast Trench - C-8111 - Bldg. 02 |  | 377 | 925.25 | 0 | 0 | 0 | 0 | 0 | 0 | 925.25 | 925.25 | 0% | 0 | 0 | 0 | 925.25 | 2058.889 | 0
25.008. | 71 | 71.113. 2. | Telecoms - Precast Trench - C-8113 - Bldg. 02 |  | 579 | 1329.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1329.75 | 1329.75 | 0% | 0 | 0 | 0 | 1329.75 | 2893.018 | 0
25.008. | 71 | 71.114. 2. | Telecoms - Precast Trench - C-8114 - Bldg. 02 |  | 40 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 0% | 0 | 0 | 0 | 90 | 195.539 | 0
25.008. | 71 | 71.115. 2. | Telecoms - Precast Trench - C-8115 - Bldg. 02 |  | 559 | 1284.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1284.5 | 1284.5 | 0% | 0 | 0 | 0 | 1284.5 | 2791.572 | 0
25.008. | 71 | 71.117. 2. | Telecoms - Precast Trench - C-8117 - Bldg. 02 |  | 656 | 1501.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1501.25 | 1501.25 | 0% | 0 | 0 | 0 | 1501.25 | 3256.414 | 0
25.008. | 71 | 71.117. 3. | Telecoms - Precast Trench - C-8117 - Bldg. 03 |  | 573 | 1316.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1316.75 | 1316.75 | 0% | 0 | 0 | 0 | 1316.75 | 2863.472 | 0
25.008. | 71 | 71.118. 2. | Telecoms - Precast Trench - C-8118 - Bldg. 02 |  | 731 | 1646 | 0 | 0 | 0 | 0 | 0 | 0 | 1646 | 1646 | 0% | 0 | 0 | 0 | 1646 | 3569.191 | 0
25.008. | 71 | 71.118. 3. | Telecoms - Precast Trench - C-8118 - Bldg. 03 |  | 29 | 65.25 | 0 | 0 | 0 | 0 | 0 | 0 | 65.25 | 65.25 | 0% | 0 | 0 | 0 | 65.25 | 142.111 | 0
25.008. | 71 | 71.119. 2. | Telecoms - Precast Trench - C-8119 - Bldg. 02 |  | 143 | 347.25 | 0 | 0 | 0 | 0 | 0 | 0 | 347.25 | 347.25 | 0% | 0 | 0 | 0 | 347.25 | 761.81 | 0
25.008. | 71 | 71.119. 3. | Telecoms - Precast Trench - C-8119 - Bldg. 03 |  | 635 | 1453.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1453.5 | 1453.5 | 0% | 0 | 0 | 0 | 1453.5 | 3158.029 | 0
25.008. | 71 | 71.121. 3. | Telecoms - Precast Trench - C-8121 - Bldg. 03 |  | 965 | 2224 | 0 | 0 | 0 | 0 | 0 | 0 | 2224 | 2224 | 0% | 0 | 0 | 0 | 2224 | 4832.391 | 0
25.008. | 71 | 71.122. 3. | Telecoms - Precast Trench - C-8122 - Bldg. 03 |  | 874 | 1966.75 | 0 | 0 | 0 | 0 | 0 | 0 | 1966.75 | 1966.75 | 0% | 0 | 0 | 0 | 1966.75 | 4258.095 | 0
25.008. | 71 | 71.123. 3. | Telecoms - Precast Trench - C-8123 - Bldg. 03 |  | 618 | 1444.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1444.5 | 1444.5 | 0% | 0 | 0 | 0 | 1444.5 | 3141.825 | 0
25.008. | 72 | 72.100. . | Telecoms Systems - Excavation & Sub Grade (per WP) |  | 0.4 | -0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 5137 | 5137 | 0% | 0 | 0 | 0 | -0.02 | Not Found | Not Found
25.008. | 72 | 72.101. 1. | Telecoms - Excavation - C-8101 - Bldg. 01 | CODE NOT PROGRESSABLE | 3904 | 642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 642 | 641.709 | 0
25.008. | 72 | 72.102. 1. | Telecoms - Excavation - C-8102 - Bldg. 01 | CODE NOT PROGRESSABLE | 1520 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 296 | 296.328 | 0
25.008. | 72 | 72.103. 1. | Telecoms - Excavation - C-8103 - Bldg. 01 | CODE NOT PROGRESSABLE | 638 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 129 | 129.329 | 0
25.008. | 72 | 72.105. 1. | Telecoms - Excavation - C-8105 - Bldg. 01 | CODE NOT PROGRESSABLE | 513 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 111 | 111.406 | 0
25.008. | 72 | 72.106. 1. | Telecoms - Excavation - C-8106 - Bldg. 01 | CODE NOT PROGRESSABLE | 42 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 9 | 9.388 | 0
25.008. | 72 | 72.107. 1. | Telecoms - Excavation - C-8107 - Bldg. 01 | CODE NOT PROGRESSABLE | 3990 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 668 | 668.257 | 0
25.008. | 72 | 72.109. 1. | Telecoms - Excavation - C-8109 - Bldg. 01 | CODE NOT PROGRESSABLE | 3624 | 617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 617 | 616.616 | 0
25.008. | 72 | 72.109. 2. | Telecoms - Excavation - C-8109 - Bldg. 02 | CODE NOT PROGRESSABLE | 381 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 82 | 81.806 | 0
25.008. | 72 | 72.110. 1. | Telecoms - Excavation - C-8110 - Bldg. 01 | CODE NOT PROGRESSABLE | 677 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 148 | 147.838 | 0
25.008. | 72 | 72.110. 2. | Telecoms - Excavation - C-8110 - Bldg. 10 | CODE NOT PROGRESSABLE | 22 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5 | 4.892 | 0
25.008. | 72 | 72.111. 1. | Telecoms - Excavation - C-8111 - Bldg. 01 | CODE NOT PROGRESSABLE | 2833 | 476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 476 | 476.366 | 0
25.008. | 72 | 72.111. 2. | Telecoms - Excavation - C-8111 - Bldg. 02 | CODE NOT PROGRESSABLE | 367 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 79 | 78.623 | 0
25.008. | 72 | 72.113. 2. | Telecoms - Excavation - C-8113 - Bldg. 02 | CODE NOT PROGRESSABLE | 515 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 111 | 110.871 | 0
25.008. | 72 | 72.113. 3. | Telecoms - Excavation - C-8113 - Bldg. 03 | CODE NOT PROGRESSABLE | 2253 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 361 | 360.806 | 0
25.008. | 72 | 72.114. 2. | Telecoms - Excavation - C-8114 - Bldg. 02 | CODE NOT PROGRESSABLE | 28 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 6 | 6.264 | 0
25.008. | 72 | 72.115. 1. | Telecoms - Excavation - C-8115 - Bldg. 01 | CODE NOT PROGRESSABLE | 3340 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 522 | 522.12 | 0
25.008. | 72 | 72.115. 2. | Telecoms - Excavation - C-8115 - Bldg. 02 | CODE NOT PROGRESSABLE | 850 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 175 | 175.073 | 0
25.008. | 72 | 72.115. 3. | Telecoms - Excavation - C-8115 - Bldg. 03 | CODE NOT PROGRESSABLE | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 3 | 2.7 | 0
25.008. | 72 | 72.117. 2. | Telecoms - Excavation - C-8117 - Bldg. 02 | CODE NOT PROGRESSABLE | 469 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 103 | 102.563 | 0
25.008. | 72 | 72.117. 3. | Telecoms - Excavation - C-8117 - Bldg. 03 | CODE NOT PROGRESSABLE | 2591 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 439 | 439.327 | 0
25.008. | 72 | 72.118. 2. | Telecoms - Excavation - C-8118 - Bldg. 02 | CODE NOT PROGRESSABLE | 696 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 151 | 150.648 | 0
25.008. | 72 | 72.118. 3. | Telecoms - Excavation - C-8118 - Bldg. 03 | CODE NOT PROGRESSABLE | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5 | 4.686 | 0
25.008. | 72 | 72.119. 1. | Telecoms - Excavation - C-8119 - Bldg. 01 | CODE NOT PROGRESSABLE | 2651 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 415 | 414.586 | 0
25.008. | 72 | 72.119. 2. | Telecoms - Excavation - C-8119 - Bldg. 02 | CODE NOT PROGRESSABLE | 197 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 42 | 42.019 | 0
25.008. | 72 | 72.119. 3. | Telecoms - Excavation - C-8119 - Bldg. 03 | CODE NOT PROGRESSABLE | 647 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 140 | 139.695 | 0
25.008. | 72 | 72.121. 3. | Telecoms - Excavation - C-8121 - Bldg. 03 | CODE NOT PROGRESSABLE | 3436 | 589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 589 | 589.456 | 0
25.008. | 72 | 72.122. 3. | Telecoms - Excavation - C-8122 - Bldg. 03 | CODE NOT PROGRESSABLE | 591 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 131 | 130.57 | 0
25.008. | 72 | 72.123. 1. | Telecoms - Excavation - C-8123 - Bldg. 01 | CODE NOT PROGRESSABLE | 2301 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 363 | 362.662 | 0
25.008. | 72 | 72.123. 3. | Telecoms - Excavation - C-8123 - Bldg. 03 | CODE NOT PROGRESSABLE | 611 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 129 | 129.226 | 0
25.008. | 72 | 72.125. 3. | Telecoms - Excavation - C-8125 - Bldg. 03 | CODE NOT PROGRESSABLE | 7837 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1215 | 1214.582 | 0
25.008. | 72 | 72.127. 1. | Telecoms - Excavation - C-8127 - Bldg. 01 | CODE NOT PROGRESSABLE | 573 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 88 | 88.334 | 0
25.008. | 72 | 72.128. 1. | Telecoms - Excavation - C-8128 - Bldg. 01 | CODE NOT PROGRESSABLE | 2445 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 384 | 384.454 | 0
25.008. | 72 | 72.129. 3. | Telecoms - Excavation - C-8129 - Bldg. 03 | CODE NOT PROGRESSABLE | 1708 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 270 | 269.896 | 0
25.008. | 72 | 72.132. 1. | Telecoms - Excavation - C-8132 - Bldg. 01 | CODE NOT PROGRESSABLE | 1709 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 270 | 270.046 | 0
25.008. | 72 | 72.133. 3. | Telecoms - Excavation - C-8133 - Bldg. 03 | CODE NOT PROGRESSABLE | 1089 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 168 | 167.526 | 0
25.008. | 72 | 72.136. 1. | Telecoms - Excavation - C-8136 - Bldg. 01 | CODE NOT PROGRESSABLE | 2031 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 318 | 318.218 | 0
25.008. | 73 | 73.100. . | Telecoms Systems - Backfill & Compaction (per WP) |  | -0.2 | 44.07 | 0 | 0 | 0 | 0 | 0 | 0 | 23281.9 | 23281.9 | 0% | 0 | 0 | 0 | 44.07 | Not Found | Not Found
25.008. | 73 | 73.101. 1. | Telecoms - Backfill - C-8101 - Bldg. 01 | CODE NOT PROGRESSABLE | 4314 | 1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1788 | 1788.1 | 0
25.008. | 73 | 73.102. 1. | Telecoms - Backfill - C-8102 - Bldg. 01 | CODE NOT PROGRESSABLE | 1233 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 583 | 583.07 | 0
25.008. | 73 | 73.103. 1. | Telecoms - Backfill - C-8103 - Bldg. 01 | CODE NOT PROGRESSABLE | 468 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 233 | 232.895 | 0
25.008. | 73 | 73.105. 1. | Telecoms - Backfill - C-8105 - Bldg. 01 | CODE NOT PROGRESSABLE | 314 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 174 | 173.675 | 0
25.008. | 73 | 73.106. 1. | Telecoms - Backfill - C-8106 - Bldg. 01 | CODE NOT PROGRESSABLE | 24 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 14 | 13.85 | 0
25.008. | 73 | 73.107. 1. | Telecoms - Backfill - C-8107 - Bldg. 01 | CODE NOT PROGRESSABLE | 4201 | 1738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1738 | 1737.735 | 0
25.008. | 73 | 73.109. 1. | Telecoms - Backfill - C-8109 - Bldg. 01 | CODE NOT PROGRESSABLE | 3734 | 1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1564 | 1564.46 | 0
25.008. | 73 | 73.109. 2. | Telecoms - Backfill - C-8109 - Bldg. 02 | CODE NOT PROGRESSABLE | 220 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 120 | 119.9 | 0
25.008. | 73 | 73.110. 1. | Telecoms - Backfill - C-8110 - Bldg. 01 | CODE NOT PROGRESSABLE | 358 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 205 | 205.35 | 0
25.008. | 73 | 73.110. 2. | Telecoms - Backfill - C-8110 - Bldg. 02 | CODE NOT PROGRESSABLE | 13 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 7 | 7.375 | 0
25.008. | 73 | 73.111. 1. | Telecoms - Backfill - C-8111 - Bldg. 01 | CODE NOT PROGRESSABLE | 2954 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1223 | 1222.845 | 0
25.008. | 73 | 73.111. 2. | Telecoms - Backfill - C-8111 - Bldg. 02 | CODE NOT PROGRESSABLE | 211 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 115 | 114.925 | 0
25.008. | 73 | 73.113. 2. | Telecoms - Backfill - C-8113 - Bldg. 02 | CODE NOT PROGRESSABLE | 303 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 167 | 166.9 | 0
25.008. | 73 | 73.113. 3. | Telecoms - Backfill - C-8113 - Bldg. 03 | CODE NOT PROGRESSABLE | 2536 | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1019 | 1018.88 | 0
25.008. | 73 | 73.114. 2. | Telecoms - Backfill - C-8114 - Bldg. 02 | CODE NOT PROGRESSABLE | 16 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 9 | 9.275 | 0
25.008. | 73 | 73.115. 1. | Telecoms - Backfill - C-8115 - Bldg. 01 | CODE NOT PROGRESSABLE | 3880 | 1556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1556 | 1556.39 | 0
25.008. | 73 | 73.115. 2. | Telecoms - Backfill - C-8115 - Bldg. 02 | CODE NOT PROGRESSABLE | 512 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 265 | 264.5 | 0
25.008. | 73 | 73.115. 3. | Telecoms - Backfill - C-8115 - Bldg. 03 | CODE NOT PROGRESSABLE | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 8 | 8 | 0
25.008. | 73 | 73.117. 2. | Telecoms - Backfill - C-8117 - Bldg. 02 | CODE NOT PROGRESSABLE | 278 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 158 | 157.8 | 0
25.008. | 73 | 73.117. 3. | Telecoms - Backfill - C-8117 - Bldg. 03 | CODE NOT PROGRESSABLE | 2685 | 1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1124 | 1123.84 | 0
25.008. | 73 | 73.118. 2. | Telecoms - Backfill - C-8118 - Bldg. 02 | CODE NOT PROGRESSABLE | 380 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 214 | 214.15 | 0
25.008. | 73 | 73.118. 3. | Telecoms - Backfill - C-8118 - Bldg. 03 | CODE NOT PROGRESSABLE | 12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 7 | 6.925 | 0
25.008. | 73 | 73.119. 1. | Telecoms - Backfill - C-8119 - Bldg. 01 | CODE NOT PROGRESSABLE | 3085 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1239 | 1238.62 | 0
25.008. | 73 | 73.119. 2. | Telecoms - Backfill - C-8119 - Bldg. 02 | CODE NOT PROGRESSABLE | 103 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 56 | 56.25 | 0
25.008. | 73 | 73.119. 3. | Telecoms - Backfill - C-8119 - Bldg. 03 | CODE NOT PROGRESSABLE | 347 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 195 | 195 | 0
25.008. | 73 | 73.121. 3. | Telecoms - Backfill - C-8121 - Bldg. 03 | CODE NOT PROGRESSABLE | 3518 | 1487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1487 | 1486.705 | 0
25.008. | 73 | 73.122. 3. | Telecoms - Backfill - C-8122 - Bldg. 03 | CODE NOT PROGRESSABLE | 345 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 199 | 199.375 | 0
25.008. | 73 | 73.123. 1. | Telecoms - Backfill - C-8123 - Bldg. 01 | CODE NOT PROGRESSABLE | 2684 | 1078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1078 | 1078.26 | 0
25.008. | 73 | 73.123. 3. | Telecoms - Backfill - C-8123 - Bldg. 03 | CODE NOT PROGRESSABLE | 379 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 202 | 201.585 | 0
25.008. | 73 | 73.125. 3. | Telecoms - Backfill - C-8125 - Bldg. 03 | CODE NOT PROGRESSABLE | 9376 | 3765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 3765 | 3765.47 | 0
25.008. | 73 | 73.127. 1. | Telecoms - Backfill - C-8127 - Bldg. 01 | CODE NOT PROGRESSABLE | 691 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 277 | 276.88 | 0
25.008. | 73 | 73.128. 1. | Telecoms - Backfill - C-8128 - Bldg. 01 | CODE NOT PROGRESSABLE | 2882 | 1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1158 | 1158.46 | 0
25.008. | 73 | 73.129. 3. | Telecoms - Backfill - C-8129 - Bldg. 03 | CODE NOT PROGRESSABLE | 2001 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 805 | 804.99 | 0
25.008. | 73 | 73.132. 1. | Telecoms - Backfill - C-8132 - Bldg. 01 | CODE NOT PROGRESSABLE | 2002 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 805 | 805.39 | 0
25.008. | 73 | 73.133. 3. | Telecoms - Backfill - C-8133 - Bldg. 03 | CODE NOT PROGRESSABLE | 1316 | 527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 527 | 527.13 | 0
25.008. | 73 | 73.136. 1. | Telecoms - Backfill - C-8136 - Bldg. 01 | CODE NOT PROGRESSABLE | 2404 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 966 | 965.75 | 0
25.008. | 74 | 74.100. . | Telecoms Systems - Precast Manhole Install (per WP) | CODE NOT PROGRESSABLE | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.7 | 2159.7 | 0% | 0 | 0 | 0 | 0.36 | Not Found | Not Found
25.008. | 74 | 74.101. 1. | Telecoms - Manholes - C-8101 - Bldg. 01 | CODE NOT PROGRESSABLE | 4 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 276 | 1618.2 | 0
25.008. | 74 | 74.107. 1. | Telecoms - Manholes - C-8107 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 1052.404 | 0
25.008. | 74 | 74.109. 1. | Telecoms - Manholes - C-8109 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 1052.404 | 0
25.008. | 74 | 74.111. 1. | Telecoms - Manholes - C-8111 - Bldg. 01 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 526.202 | 0
25.008. | 74 | 74.113. 3. | Telecoms - Manholes - C-8113 - Bldg. 03 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 69 | 0
25.008. | 74 | 74.115. 1. | Telecoms - Manholes - C-8115 - Bldg. 01 | CODE NOT PROGRESSABLE | 3 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 207 | 1578.606 | 0
25.008. | 74 | 74.117. 3. | Telecoms - Manholes - C-8117 - Bldg. 03 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 69 | 0
25.008. | 74 | 74.119. 1. | Telecoms - Manholes - C-8119 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 1052.404 | 0
25.008. | 74 | 74.121. 3. | Telecoms - Manholes - C-8121 - Bldg. 03 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 69 | 0
25.008. | 74 | 74.123. 1. | Telecoms - Manholes - C-8123 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 809.1 | 0
25.008. | 74 | 74.125. 3. | Telecoms - Manholes - C-8125 - Bldg. 03 | CODE NOT PROGRESSABLE | 9 | 621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 621 | 3884.254 | 0
25.008. | 74 | 74.127. 1. | Telecoms - Manholes - C-8127 - Bldg. 01 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 69 | 0
25.008. | 74 | 74.128. 1. | Telecoms - Manholes - C-8128 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 138 | 0
25.008. | 74 | 74.129. 3. | Telecoms - Manholes - C-8129 - Bldg. 03 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 404.55 | 0
25.008. | 74 | 74.132. 1. | Telecoms - Manholes - C-8132 - Bldg. 01 | CODE NOT PROGRESSABLE | 1 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 69 | 69 | 0
25.008. | 74 | 74.133. 3. | Telecoms - Manholes - C-8133 - Bldg. 03 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 809.1 | 0
25.008. | 74 | 74.136. 1. | Telecoms - Manholes - C-8136 - Bldg. 01 | CODE NOT PROGRESSABLE | 2 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 138 | 138 | 0
25.008. | 75 | 75.100. . | Telecoms Systems - UG CIP Ductbank Labor (per WP) | CODE NOT PROGRESSABLE | 0 | 31.86 | 0 | 0 | 0 | 0 | 0 | 0 | 6893.8 | 6893.8 | 0% | 0 | 0 | 0 | 31.86 | Not Found | Not Found
25.008. | 75 | 75.101. 1. | Telecoms - Duct Banks (CIP) - C-8101 - Bldg. 01 | CODE NOT PROGRESSABLE | 10555 | 479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 479 | 2255.954 | 0
25.008. | 75 | 75.102. 1. | Telecoms - Duct Banks (CIP) - C-8102 - Bldg. 01 | CODE NOT PROGRESSABLE | 2590 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 122 | 675.14 | 0
25.008. | 75 | 75.103. 1. | Telecoms - Duct Banks (CIP) - C-8103 - Bldg. 01 | CODE NOT PROGRESSABLE | 740 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 35 | 193.23 | 0
25.008. | 75 | 75.107. 1. | Telecoms - Duct Banks (CIP) - C-8107 - Bldg. 01 | CODE NOT PROGRESSABLE | 33155 | 1437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1437 | 4974.252 | 0
25.008. | 75 | 75.109. 1. | Telecoms - Duct Banks (CIP) - C-8109 - Bldg. 01 | CODE NOT PROGRESSABLE | 29580 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1280 | 4309.67 | 0
25.008. | 75 | 75.111. 1. | Telecoms - Duct Banks (CIP) - C-8111 - Bldg. 01 | CODE NOT PROGRESSABLE | 23990 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1045 | 3748.984 | 0
25.008. | 75 | 75.113. 3. | Telecoms - Duct Banks (CIP) - C-8113 - Bldg. 03 | CODE NOT PROGRESSABLE | 26460 | 1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1146 | 1146.39 | 0
25.008. | 75 | 75.115. 1. | Telecoms - Duct Banks (CIP) - C-8115 - Bldg. 01 | CODE NOT PROGRESSABLE | 19285 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 842 | 3103.028 | 0
25.008. | 75 | 75.115. 2. | Telecoms - Duct Banks (CIP) - C-8115 - Bldg. 02 | CODE NOT PROGRESSABLE | 465 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 22 | 78.912 | 0
25.008. | 75 | 75.117. 3. | Telecoms - Duct Banks (CIP) - C-8117 - Bldg. 03 | CODE NOT PROGRESSABLE | 18025 | 788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 788 | 2920.246 | 0
25.008. | 75 | 75.119. 1. | Telecoms - Duct Banks (CIP) - C-8119 - Bldg. 01 | CODE NOT PROGRESSABLE | 15385 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 675 | 2596.272 | 0
25.008. | 75 | 75.121. 3. | Telecoms - Duct Banks (CIP) - C-8121 - Bldg. 03 | CODE NOT PROGRESSABLE | 21290 | 936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 936 | 3643.148 | 0
25.008. | 75 | 75.123. 1. | Telecoms - Duct Banks (CIP) - C-8123 - Bldg. 01 | CODE NOT PROGRESSABLE | 16295 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 715 | 2729.892 | 0
25.008. | 75 | 75.123. 3. | Telecoms - Duct Banks (CIP) - C-8123 - Bldg. 03 | CODE NOT PROGRESSABLE | 275 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 13 | 71.968 | 0
25.008. | 75 | 75.125. 3. | Telecoms - Duct Banks (CIP) - C-8125 - Bldg. 03 | CODE NOT PROGRESSABLE | 23560 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1073 | 5049.928 | 0
25.008. | 75 | 75.127. 1. | Telecoms - Duct Banks (CIP) - C-8127 - Bldg. 01 | CODE NOT PROGRESSABLE | 1330 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 60 | 59.58 | 0
25.008. | 75 | 75.128. 1. | Telecoms - Duct Banks (CIP) - C-8128 - Bldg. 01 | CODE NOT PROGRESSABLE | 13515 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 602 | 601.625 | 0
25.008. | 75 | 75.129. 3. | Telecoms - Duct Banks (CIP) - C-8129 - Bldg. 03 | CODE NOT PROGRESSABLE | 10815 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 481 | 2029.956 | 0
25.008. | 75 | 75.132. 1. | Telecoms - Duct Banks (CIP) - C-8132 - Bldg. 01 | CODE NOT PROGRESSABLE | 10820 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 482 | 481.51 | 0
25.008. | 75 | 75.133. 3. | Telecoms - Duct Banks (CIP) - C-8133 - Bldg. 03 | CODE NOT PROGRESSABLE | 2160 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 96 | 405.786 | 0
25.008. | 75 | 75.136. 1. | Telecoms - Duct Banks (CIP) - C-8136 - Bldg. 01 | CODE NOT PROGRESSABLE | 10045 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 447 | 447.175 | 0
25.008. | 76 | 76.100. . | Telecoms Systems - CIP Trench Labor (per WP) | CODE NOT PROGRESSABLE | 0 | 580.72 | 0 | 0 | 0 | 0 | 0 | 0 | 5525 | 5525 | 0% | 0 | 0 | 0 | 580.72 | Not Found | Not Found
25.008. | 76 | 76.101. 1. | Telecoms - Trenches (CIP) - C-8101 - Bldg. 01 | CODE NOT PROGRESSABLE | 453 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 154 | 330.612 | 0
25.008. | 76 | 76.102. 1. | Telecoms - Trenches (CIP) - C-8102 - Bldg. 01 | CODE NOT PROGRESSABLE | 837 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 286 | 615.454 | 0
25.008. | 76 | 76.103. 1. | Telecoms - Trenches (CIP) - C-8103 - Bldg. 01 | CODE NOT PROGRESSABLE | 300 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 102 | 220.46 | 0
25.008. | 76 | 76.107. 1. | Telecoms - Trenches (CIP) - C-8107 - Bldg. 01 | CODE NOT PROGRESSABLE | 399 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 135 | 291.428 | 0
25.008. | 76 | 76.109. 1. | Telecoms - Trenches (CIP) - C-8109 - Bldg. 01 | CODE NOT PROGRESSABLE | 540 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 184 | 395.205 | 0
25.008. | 76 | 76.109. 2. | Telecoms - Trenches (CIP) - C-8109 - Bldg. 02 | CODE NOT PROGRESSABLE | 540 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 184 | 395.205 | 0
25.008. | 76 | 76.110. 1. | Telecoms - Trenches (CIP) - C-8110 - Bldg. 01 | CODE NOT PROGRESSABLE | 1462 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 494 | 1062.831 | 0
25.008. | 76 | 76.111. 1. | Telecoms - Trenches (CIP) - C-8111 - Bldg. 01 | CODE NOT PROGRESSABLE | 1033 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 351 | 755.701 | 0
25.008. | 76 | 76.111. 2. | Telecoms - Trenches (CIP) - C-8111 - Bldg. 02 | CODE NOT PROGRESSABLE | 402 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 136 | 293.253 | 0
25.008. | 76 | 76.113. 2. | Telecoms - Trenches (CIP) - C-8113 - Bldg. 02 | CODE NOT PROGRESSABLE | 540 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 184 | 395.117 | 0
25.008. | 76 | 76.115. 2. | Telecoms - Trenches (CIP) - C-8115 - Bldg. 02 | CODE NOT PROGRESSABLE | 2648 | 895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 895 | 1925.285 | 0
25.008. | 76 | 76.117. 3. | Telecoms - Trenches (CIP) - C-8117 - Bldg. 03 | CODE NOT PROGRESSABLE | 567 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 193 | 415.685 | 0
25.008. | 76 | 76.118. 2. | Telecoms - Trenches (CIP) - C-8118 - Bldg. 02 | CODE NOT PROGRESSABLE | 1453 | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 491 | 1055.673 | 0
25.008. | 76 | 76.119. 2. | Telecoms - Trenches (CIP) - C-8119 - Bldg. 02 | CODE NOT PROGRESSABLE | 603 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 204 | 439.818 | 0
25.008. | 76 | 76.119. 3. | Telecoms - Trenches (CIP) - C-8119 - Bldg. 03 | CODE NOT PROGRESSABLE | 1509 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 513 | 1104.5 | 0
25.008. | 76 | 76.121. 3. | Telecoms - Trenches (CIP) - C-8121 - Bldg. 03 | CODE NOT PROGRESSABLE | 521 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 177 | 380.198 | 0
25.008. | 76 | 76.123. 3. | Telecoms - Trenches (CIP) - C-8123 - Bldg. 03 | CODE NOT PROGRESSABLE | 760 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 259 | 557.362 | 0
25.008. | 77 | 77.100. . | Telecoms Systems - French Drain Install (per WP) |  | 19946 | 6786.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6786.5 | 6786.5 | 0% | 0 | 0 | 0 | 6786.5 | Not Found | Not Found
25.008. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6472.8 | 0 | 1625 | 0 | 345 | 0 | 0 | 6472.8 | 6472.8 | 0% | 0 | 0 | 0 | 4847.8 | Not Found | Not Found
25.008. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 26733 | 0 | 5058 | 0 | 710 | 0 | 0 | 26733 | 26733 | 0% | 0 | 0 | 50.5 | 21624.5 | Not Found | Not Found
25.008. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 5700 | 0 | 472.5 | 0 | 48 | 0 | 0 | 5700 | 5700 | 0% | 0 | 0 | 48 | 5179.5 | Not Found | Not Found
25.008. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 22230 | 0 | 604 | 0 | 148 | 0 | 0 | 22230 | 22230 | 0% | 0 | 0 | 48 | 21578 | Not Found | Not Found
25.008. | 90 | 90.005. 1. | HR Staff | CODE NOT PROGRESSABLE | 0 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 2736 | 2736 | 0% | 0 | 0 | 0 | 2736 | Not Found | Not Found
25.008. | 90 | 90.008. 1. | Estimating Support | CODE NOT PROGRESSABLE | 0 | 649.5 | 0 | 225 | 0 | 0 | 0 | 0 | 649.5 | 649.5 | 0% | 0 | 0 | 0 | 424.5 | Not Found | Not Found
25.008. | 91 | 91.002. 1. | General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 8580 | 0 | 278 | 0 | 46 | 0 | 0 | 8580 | 8580 | 0% | 0 | 0 | 46.5 | 8255.5 | Not Found | Not Found
25.008. | 91 | 91.002. 3. | Survey Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 17160 | 0 | 1892.5 | 0 | 265 | 0 | 0 | 17160 | 17160 | 0% | 0 | 0 | 265 | 15002.5 | Not Found | Not Found
25.008. | 91 | 91.002. 4. | Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 20100 | 0 | 3209 | 0 | 490 | 0 | 0 | 20100 | 20100 | 0% | 0 | 0 | 490.5 | 16400.5 | Not Found | Not Found
25.008. | 91 | 91.002. 5. | Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 20040 | 0 | 483 | 0 | 96 | 0 | 0 | 20040 | 20040 | 0% | 0 | 0 | 96 | 19461 | Not Found | Not Found
25.008. | 91 | 91.002. 6. | General Site Laborer (Fire Watch Ice/Water etc) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 28560 | 0 | 891 | 0 | 252 | 0 | 0 | 28560 | 28560 | 0% | 0 | 0 | 251.5 | 27417.5 | Not Found | Not Found
25.008. | 91 | 91.004. 1. | Orientation & Drug Testing Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 6992 | 0 | 776 | 0 | 284 | 0 | 0 | 6992 | 6992 | 0% | 0 | 0 | 283.5 | 5932.5 | Not Found | Not Found
25.008. | 92 | 92.100. 1. | Job Set Up | CODE NOT PROGRESSABLE | 0 | 1600 | 0 | 1254 | 0 | 0 | 0 | 0 | 1600 | 1600 | 0% | 0 | 0 | 0 | 346 | Not Found | Not Found
25.008. | 92 | 92.004. 2. | Communication and IT Services (Labor) | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.008. | 99 | 99.000. 1. | Mobilization Delays | CODE NOT PROGRESSABLE | 0 | 4500 | 0 | 886.5 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0% | 0 | 0 | 0 | 3613.5 | Not Found | Not Found
25.008. | 99 | 99.999. 8. | True-Up Budget Offset | CODE NOT PROGRESSABLE | 0 | -60657 | 0 | 0 | 0 | 0 | 0 | 0 | -60657 | -60657 | 0% | 0 | 0 | 0 | -60657 | Not Found | Not Found
25.008. | 99 | 99.999. 7. | Bulletin #1 Budget Offset | CODE NOT PROGRESSABLE | 0 | -12566.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -12566.6 | Not Found | Not Found
25.011. | 20 | 20.100. 1. | Civil - Excavation Labor | PF CHECK | 64530 | 21142.58 | 5162.4 | 2102.5 | 1290.6 | 522 | 422.8516 | 1691.4064 | 21142.58 | 21142.58 | 8% | 0.81 | 0.8 | 522.5 | 18517.58 | Not Found | Not Found
25.011. | 21 | 21.100. 1. | Civil - Backfill/Finish/Fine Grading Labor | PF CHECK | 45585.66 | 31264.96 | 2735.14 | 2160 | 911.714 | 813 | 625.2997 | 1875.8979 | 31264.96 | 31264.96 | 6% | 0.77 | 0.87 | 812 | 28292.96 | Not Found | Not Found
25.011. | 22 | 22.100. 1. | Civil Labor - Storm Drain Piping & Catch Basin Installation |  | 5928 | 6179.09 | 0 | 0 | 0 | 0 | 0 | 0 | 6179.09 | 6179.09 | 0% | 0 | 0 | 0 | 6179.09 | Not Found | Not Found
25.011. | 25 | 25.100. 1. | Civil - Foundations Concrete & Rebar Labor | PF CHECK | 4295 | 44684.04 | 300.65 | 3111 | 64.425 | 838 | 670.2606 | 3127.8828 | 44684.04 | 44684.04 | 7% | 0.8 | 1.01 | 836 | 40737.04 | Not Found | Not Found
25.011. | 25 | 25.200. 1. | Civil - Duct Banks Concrete & Rebar Labor | PF CHECK | 7465.6 | 18222.74 | 1119.84 | 3951 | 485.264 | 1501 | 1184.4781 | 2733.411 | 18222.74 | 18222.74 | 15% | 0.79 | 0.69 | 1504.5 | 12767.24 | Not Found | Not Found
25.011. | 25 | 25.300. 1. | Civil - Precast Manholes/Vaults Labor | PF CHECK BURN NO EARN | 150 | 5439.2 | 6 | 203.5 | 0 | 39 | 0 | 217.568 | 5439.2 | 5439.2 | 4% | 0 | 1.07 | 39 | 5196.7 | Not Found | Not Found
25.011. | 26 | 26.100. . | Grout Labor (per work package) | >100% OVERRUNNING PROJECTION CODE NOT PROGRESSABLE | 0.32 | 2.43 | 11.926 | 316 | 0 | 0 | 0 | 90.5631 | 2.43 | 8.479 | 3727% | 0 | 0.29 | 0 | -313.57 | Not Found | Not Found
25.011. | 26 | 26.100. PR. 3 | Grout Labor - H3 Pipe Racks |  | 195 | 2377.05 | 0 | 0 | 0 | 0 | 0 | 0 | 2377.05 | 2377.05 | 0% | 0 | 0 | 0 | 2377.05 | Not Found | Not Found
25.011. | 26 | 26.100. PR. 4 | Grout Labor - H4 Pipe Racks |  | 50 | 609.5 | 0 | 0 | 0 | 0 | 0 | 0 | 609.5 | 609.5 | 0% | 0 | 0 | 0 | 609.5 | Not Found | Not Found
25.011. | 26 | 26.100.SUP. 3 | Grout Labor - H3 Supp Steel | PF CHECK | 200 | 2438 | 40 | 514 | 40 | 131 | 487.6 | 487.6 | 2438 | 2438 | 20% | 3.72 | 0.95 | 130.5 | 1793.5 | Not Found | Not Found
25.011. | 26 | 26.100.SUP. 4 | Grout Labor - H4 Supp Steel |  | 151 | 1840.69 | 0 | 0 | 0 | 0 | 0 | 0 | 1840.69 | 1840.69 | 0% | 0 | 0 | 0 | 1840.69 | Not Found | Not Found
25.011. | 27 | 27.100. . | Anchor Bolts (per work package) |  | 5400 | 9450 | 27 | 47.5 | 0 | 0 | 0 | 47.25 | 9450 | 9450 | 1% | 0 | 0.99 | 0 | 9402.5 | Not Found | Not Found
25.011. | 27 | 27.100.SIT. 1 | H3 H4 Anchor Bolt Installation Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.011. | 30 | 30.100. . | Structural Steel Labor (per work package) |  | 1933.3 | 36302.37 | 0 | 0 | 0 | 0 | 0 | 0 | 36302.37 | 36302.37 | 0% | 0 | 0 | 0 | 36302.37 | Not Found | Not Found
25.011. | 30 | 30.100.SUP. 3 | H3 Data Halls - Supp Steel Labor | PF CHECK | 742 | 14840 | 667.8 | 6131 | 667.8 | 5975 | 13356 | 13356 | 14840 | 6812.2222 | 90% | 2.24 | 2.18 | 0 | 8709 | Not Found | Not Found
25.011. | 30 | 30.100.SUP. 4 | H4 Data Halls - Supp Steel Labor | PF CHECK BURN NO EARN | 567 | 11340 | 0 | 267.5 | 0 | 263 | 0 | 0 | 11340 | 11340 | 0% | 0 | 0 | 267.5 | 10805 | Not Found | Not Found
25.011. | 45 | 45.100. . | Mechanical Equipment Labor (per work package) |  | 1566 | 25112 | 0 | 0 | 0 | 0 | 0 | 0 | 25112 | 25112 | 0% | 0 | 0 | 0 | 25112 | Not Found | Not Found
25.011. | 45 | 45.200. . | Expanion Loops and Dog Legs Labor |  | 1052 | 10520 | 0 | 0 | 0 | 0 | 0 | 0 | 10520 | 10520 | 0% | 0 | 0 | 0 | 10520 | Not Found | Not Found
25.011. | 45 | 45.300. . | Set & Install MER Buildings and Generators |  | 96 | 17760 | 0 | 0 | 0 | 0 | 0 | 0 | 17760 | 17760 | 0% | 0 | 0 | 0 | 17760 | Not Found | Not Found
25.011. | 50 | 50.100. . | CS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | -0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | -0.31 | Not Found | Not Found
25.011. | 50 | 50.100.OSM. 1 | H3 CS Pipe Fabrication Labor - OSM | PF CHECK | 63983 | 50341.5 | 15995.75 | 12692.5 | 15995.75 | 1956 | 12585.375 | 12585.375 | 50341.5 | 50341.5 | 25% | 6.43 | 0.99 | 1955 | 35694 | Not Found | Not Found
25.011. | 50 | 50.100.SIT. 1 | H3 CS Pipe Installation Labor - SITE | PF CHECK BURN NO EARN | 63983 | 113392.9 | 0 | 13 | 0 | 13 | 0 | 0 | 113392.9 | 113392.9 | 0% | 0 | 0 | 13 | 113366.9 | Not Found | Not Found
25.011. | 50 | 50.100.OSM. 4 | H4 CS Pipe Fabrication Labor - OSM |  | 60267 | 47318.15 | 0 | 0 | 0 | 0 | 0 | 0 | 47318.15 | 47318.15 | 0% | 0 | 0 | 0 | 47318.15 | Not Found | Not Found
25.011. | 50 | 50.100.SIT. 4 | H4 CS Pipe Installation Labor - SITE |  | 60267 | 106753.7 | 0 | 0 | 0 | 0 | 0 | 0 | 106753.7 | 106753.7 | 0% | 0 | 0 | 0 | 106753.7 | Not Found | Not Found
25.011. | 51 | 51.100. . | SS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0% | 0 | 0 | 0 | 0.1 | Not Found | Not Found
25.011. | 51 | 51.100.SIT. 1 | H3 SS Pipe Installation Labor |  | 15409 | 56175.65 | 0 | 0 | 0 | 0 | 0 | 0 | 56175.65 | 56175.65 | 0% | 0 | 0 | 0 | 56175.65 | Not Found | Not Found
25.011. | 51 | 51.100.SIT. 4 | H4 SS Pipe Installation Labor |  | 15409 | 53553.39 | 0 | 0 | 0 | 0 | 0 | 0 | 53553.39 | 53553.39 | 0% | 0 | 0 | 0 | 53553.39 | Not Found | Not Found
25.011. | 52 | 52.100. . | MER Fire Water Risers Labor |  | 52 | 2444 | 0 | 0 | 0 | 0 | 0 | 0 | 2444 | 2444 | 0% | 0 | 0 | 0 | 2444 | Not Found | Not Found
25.011. | 55 | 55.100. . | Pipe Supports Labor (per work package) |  | 9715 | 36613.18 | 0 | 0 | 0 | 0 | 0 | 0 | 36613.18 | 36613.18 | 0% | 0 | 0 | 0 | 36613.18 | Not Found | Not Found
25.011. | 55 | 55.100.SIT. 1 | H3 H4 Pipe Support Installation Labor | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.011. | 58 | 58.100. . | Pipe Labels Labor (per work package) |  | 11491.8 | 9480.74 | 0 | 0 | 0 | 0 | 0 | 0 | 9480.74 | 9480.74 | 0% | 0 | 0 | 0 | 9480.74 | Not Found | Not Found
25.011. | 75 | 75.100. 1. 1. | Pressure Testing Labor | CODE NOT PROGRESSABLE | 0 | 31491.3 | 0 | 0 | 0 | 0 | 0 | 0 | 31491.3 | 31491.3 | 0% | 0 | 0 | 0 | 31491.3 | Not Found | Not Found
25.011. | 75 | 75.100. 1. 2. | Start-Up Support Labor | CODE NOT PROGRESSABLE | 0 | 6912 | 0 | 0 | 0 | 0 | 0 | 0 | 6912 | 6912 | 0% | 0 | 0 | 0 | 6912 | Not Found | Not Found
25.011. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 10097.68 | 0 | 520 | 0 | 260 | 0 | 0 | 10097.68 | 10097.68 | 0% | 0 | 0 | 0 | 9577.68 | Not Found | Not Found
25.011. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 36054 | 0 | 537 | 0 | 280 | 0 | 0 | 36054 | 36054 | 0% | 0 | 0 | 0 | 35517 | Not Found | Not Found
25.011. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | CODE NOT PROGRESSABLE | 0 | 15016 | 0 | 102 | 0 | 0 | 0 | 0 | 15016 | 15016 | 0% | 0 | 0 | 0 | 14914 | Not Found | Not Found
25.011. | 90 | 90.004. 1. | Site HSE & QA/QC | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 50688 | 0 | 2153 | 0 | 656 | 0 | 0 | 50688 | 50688 | 0% | 0 | 0 | 181.5 | 48353.5 | Not Found | Not Found
25.011. | 90 | 90.005. 1. | HR Staff | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4770 | 0 | 50 | 0 | 25 | 0 | 0 | 4770 | 4770 | 0% | 0 | 0 | 0 | 4720 | Not Found | Not Found
25.011. | 91 | 91.002. 1. | General Foreman | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 20340 | 0 | 682 | 0 | 221 | 0 | 0 | 20340 | 20340 | 0% | 0 | 0 | 221 | 19437 | Not Found | Not Found
25.011. | 91 | 91.002. 3. | Survey Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 8820 | 0 | 1111.5 | 0 | 428 | 0 | 0 | 8820 | 8820 | 0% | 0 | 0 | 425.5 | 7283 | Not Found | Not Found
25.011. | 91 | 91.002. 4. | Warehouse Crew | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 23520 | 0 | 4762.5 | 0 | 2276 | 0 | 0 | 23520 | 23520 | 0% | 0 | 0 | 2276.5 | 16481 | Not Found | Not Found
25.011. | 91 | 91.002. 5. | Operators | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 22080 | 0 | 2575 | 0 | 426 | 0 | 0 | 22080 | 22080 | 0% | 0 | 0 | 428 | 19077 | Not Found | Not Found
25.011. | 91 | 91.002. 6. | General Site Laborer (Fire Watch Ice/Water) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 4920 | 0 | 1293.5 | 0 | 41 | 0 | 0 | 4920 | 4920 | 0% | 0 | 0 | 42 | 3584.5 | Not Found | Not Found
25.011. | 91 | 91.003. 1. | Tool Room Attendant | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 5160 | 0 | 519.5 | 0 | 211 | 0 | 0 | 5160 | 5160 | 0% | 0 | 0 | 212 | 4428.5 | Not Found | Not Found
25.011. | 91 | 91.004. 1. | Orientation & Drug Testing | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 0 | 0 | 150 | 0 | 70 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 70 | -220 | Not Found | Not Found
25.011. | 91 | 91.005. 1. | Welder Testing Labor | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 350 | 0 | 50 | 0 | 10 | 0 | 0 | 350 | 350 | 0% | 0 | 0 | 10 | 290 | Not Found | Not Found
25.011. | 92 | 92.100. 1. | Job Set Up and Maintenance Labor | CODE NOT PROGRESSABLE | 0 | 9959.93 | 0 | 0 | 0 | 0 | 0 | 0 | 9959.93 | 9959.93 | 0% | 0 | 0 | 0 | 9959.93 | Not Found | Not Found
25.011. | 93 | 93.006. 1. | RIG Welder Pay | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.011. | 98 | 98.100. 2. | Night Shift Premium & Labor Escalation Allowance | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.011. | 98 | 98.200. 1. | OSM - Salary Staff | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
25.011. | 98 | 98.200. 6. | OSM Yard Mob/Demob & Maintenance Labor | CODE NOT PROGRESSABLE | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0% | 0 | 0 | 0 | 600 | Not Found | Not Found
25.011. | 98 | 98.H34. DB. 1. | H34 - LS - 35KV & Telecom DB - Labor | CODE NOT PROGRESSABLE | 0 | 59838.87 | 0 | 0 | 0 | 0 | 0 | 0 | 59838.87 | 59838.87 | 0% | 0 | 0 | 0 | 59838.87 | Not Found | Not Found
25.011. | 98 | 98.H34.CUP. 1. | H34 - LS - CUP FNDs - Labor | CODE NOT PROGRESSABLE | 0 | 14506.56 | 0 | 0 | 0 | 0 | 0 | 0 | 14506.56 | 14506.56 | 0% | 0 | 0 | 0 | 14506.56 | Not Found | Not Found
25.011. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
26.001. | 26 | 26.100. . | Grout Labor (per work package) | CODE NOT PROGRESSABLE | 118 | 1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1697 | 864.7 | 0
26.001. | 30 | 30.100. . | Structural Steel Labor (per work package) | CODE NOT PROGRESSABLE | 1368 | 33097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 33097 | 55204.4 | 0
26.001. | 45 | 45.100. . | Mechanical Equipment Labor (per work package) | CODE NOT PROGRESSABLE | 322 | 19992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 19992 | 23280 | 0
26.001. | 50 | 50.100. . | CS LB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 24190 | 83355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 83355 | 149916 | 0
26.001. | 50 | 50.150. . | CS SB Aboveground Labor (per work package) | CODE NOT PROGRESSABLE | 26208 | 49140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 49140 | 76988 | 0
26.001. | 52 | 52.100. . | Aboveground Hydrotest & Flush | CODE NOT PROGRESSABLE | 50398 | 23331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 23331 | Not Found | Not Found
26.001. | 75 | 75.100. 1. | Startup & Commissioning Support | CODE NOT PROGRESSABLE | 13258 | 13258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 13258 | Not Found | Not Found
26.001. | 90 | 90.001. 1. | Corporate Management (PM EM Corp Safety QC Proc Est.) | PF CHECK BURN NO EARN CODE NOT PROGRESSABLE | 0 | 8205 | 0 | 480 | 0 | 240 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 7725 | Not Found | Not Found
26.001. | 90 | 90.002. 1. | Site Management (CM Supt PE FE) | CODE NOT PROGRESSABLE | 0 | 29220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 29220 | Not Found | Not Found
26.001. | 90 | 90.003. 1. | Field Staff (Matl Manager Office Manager Clerical) | CODE NOT PROGRESSABLE | 0 | 8880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 8880 | Not Found | Not Found
26.001. | 90 | 90.004. 1. | Site HSE & QA/QC | CODE NOT PROGRESSABLE | 0 | 24480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 24480 | Not Found | Not Found
26.001. | 90 | 90.005. 1. | HR Staff | CODE NOT PROGRESSABLE | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2880 | Not Found | Not Found
26.001. | 91 | 91.002. 1. | General Foreman | CODE NOT PROGRESSABLE | 0 | 12480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 12480 | Not Found | Not Found
26.001. | 91 | 91.002. 3. | Survey Crew | CODE NOT PROGRESSABLE | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5460 | Not Found | Not Found
26.001. | 91 | 91.002. 4. | Warehouse Crew | CODE NOT PROGRESSABLE | 0 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 17700 | Not Found | Not Found
26.001. | 91 | 91.002. 5. | Operators | CODE NOT PROGRESSABLE | 0 | 8340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 8340 | Not Found | Not Found
26.001. | 91 | 91.002. 6. | General Site Laborer (Fire Watch Ice/Water etcï¿½) | CODE NOT PROGRESSABLE | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2880 | Not Found | Not Found
26.001. | 91 | 91.003. 1. | Tool Room Attendant | CODE NOT PROGRESSABLE | 0 | 2880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 2880 | Not Found | Not Found
26.001. | 91 | 91.004. 1. | Orientation & Drug Testing Labor | CODE NOT PROGRESSABLE | 0 | 1170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1170 | Not Found | Not Found
26.001. | 91 | 91.005. 1. | Welder Testing Labor | CODE NOT PROGRESSABLE | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 240 | Not Found | Not Found
26.001. | 92 | 92.100. 1. | Job Set Up Labor | CODE NOT PROGRESSABLE | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 1000 | Not Found | Not Found
26.001. | 93 | 93.006. 1. | Rig Welder Rig Rental | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
26.001. | 99 | 99.601. . | Accounting Accruals | CODE NOT PROGRESSABLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | Not Found | Not Found
Grand Total |  |  |  |  | 6184761.202 | 5928642.52 | 1286716.61 | 1805093.3 | 109751.822 | 96446 | 117299.058 | 1205774.5966 | 5795029.35 | 5653992.8235 | 20% | 1.22 | 0.67 | 83733 | 4039816.22 | Not Found | Not Found

## Phase Code Not Progressable
ERROR DESCRIPTION | CODE NOT PROGRESSABLE
masterPhase | (Multiple Items)

## Invisible Work
ERROR DESCRIPTION | (Multiple Items)
masterPhase | (Multiple Items)

## Magic Work
ERROR DESCRIPTION | EARN NO BURN
masterPhase | (Multiple Items)

## Overrrunning Projections
ERROR DESCRIPTION | (Multiple Items)
masterPhase | (Multiple Items)